Annex 1:

Logical Framework Matrix for Capacity Building of the Investigation Service of the Ministry of Finance of Georgia

| Capacity Building of the Investigation Service of the Ministry of Finance of Georgia |  | Programme name and number |  | ENPI 2013 Annual Action Plan |
| --- | --- | --- | --- | --- |
| INVESTIGATION SERVICE OF THE MINISTRY OF FINANCE |  | Contracting period expires: |  | Disbursement period expires: |
|  |  | Total budget: EUR 1 230 000 |  |  |
| Overall objective | Objectively Verifiable Indicators | Sources of Verification |  |  |
| Combating economical-financial crime in fiscal sphere and fostering healthy business environment in Georgia | - Positive EC opinion on the progress made. | - EC Regular Report on progress by Georgia in implementation of the ENP Action Plan priorities (and National Indicative Programmes beyond 2013). - Progress Reports delivered by the Partner Country in Twinning Project Evaluation reports |  |  |
| Project purpose | Objectively Verifiable Indicators | Sources of Verification |  | Assumptions |
| The purpose of this project is to strengthen the administrative capacity of the Investigation Service of the Ministry of Finance of Georgia in line with the European Union and international standards in the following fields: - Improvement of legal framework connected to Tax Crime, in particular, subordinate Articles and regulations of tax evasion e.g. VAT fraud; - Capacity development in: Human Resource management, modern methodology of investigation, statistical and analytical work, training of trainers; - Development of different guidelines (rules and procedures) to improve efficiency of the general management and operation of the IS; - Improvement of information processing, risk identification and management system (precise identification of companies, enterprises including risk factors or criminal points such as tax evasion, money laundering and fictitious financial transactions in order to initiate the right investigation); - Reinforcement of Intellectual Property Rights investigation, technologies and operation mechanisms. | - New and amended legal measures concerning investigation work - Instructions for improved Human Resource Management - Operational Guidelines for the IS are prepared - Improved techniques for development of the IS risk management - Recommendations for Intellectual Property Rights investigation are prepared | - EC Regular Reports on progress by Georgia in implementation of the ENP Action Plan priorities (and National Indicative Programmes beyond 2013) - Government reports - Project reports |  | - Commitment and support of the IS management. - Adequate resource allocation. - Sufficient capacity within the IS to absorb the assistance provided. - Trained staff is retained. - Timely availability of qualified and suitable STEs by Twinning partner. |
| 3.3. Results | Objectively Verifiable Indicators | Sources of Verification |  | Assumptions |
| 1. Draft of the revised legal framework and new instructions for the Investigation Service are in place. | 1.1 Assessment carried out regarding the structural and procedural differences between CC/CPC of Georgia and international criminal legislation 1.2 Drafted amendments to the CC of Georgia 1.3 Workshop conducted regarding revised legal framework 1.4 Changes referring to tax fraud legislation is drafted 1.5 Operational instructions for the IS is drafted 1.6 IS staff, Prosecutor’s office and RS staff trained in new investigation instructions | - Assessment Report (Indicator 1.1) - Draft legislation (Indicator 1.2, 1.4,1.5) - Workshop report (Indicator 1.3.) - Workshop Evaluation sheets (Indicator 1.3) - Training materials (Indicator 1.6) - Feedback evaluation sheets (training) (Indicator 1.6) - Project reports |  | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 2. Human Resources Division has implemented new methods of effective management of the staff of Investigation Service. | 2.1 Analytical report for Human Resources prepared 2.2 Report on recommendations for professional development of staff in the IS prepared 2.3 Recommendation regarding Training Needs Analysis prepared 2.4 IS management trained in new methods 2.5 Guideline concerning Training Needs Analysis prepared | - Analytical reports - STEs reports (Indicator2.1, 2.2, 2.3,2.5) - Training materials (Indicator 2.4) - Feedback evaluation sheets (training) (Indicator 2.4) - Project reports |  |  |
| 3. New rules and procedures are introduced to combat tax fraud and tax fraud related crimes in accordance with the EU standards. | 3.1 Analysis of the existing tax and criminal legislation with specific recommendations for the IS delivered 3.2 Guideline on combating VAT fraud is developed 3.3 IS staff trained in combating VAT fraud 3.4. Methodology of fighting against money laundering developed 3.5 IS staff trained in combating money laundering 3.4 IS staff trained in combating cyber crime 3.5 Instructions for Training of Trainers prepared 3.6 Study visit to MS carried out to improve experience regarding tax evasion, money laundering and cyber crime | - STE reports (All indicators) - Training materials (Indicator 3.2, 3.3, 3.4) - Feedback evaluation sheets (training) (Indicator 3.2, 3.3, 3.4) - Study visit report (Indicator 3.6) - Project reports |  |  |
| 4. The Investigation Service has developed and improved rules and procedures in the area of risk analysis and management. | 4.1 Assessment Report on the current risk analysis system delivered 4.2 Manual of risk assessment prepared 4.3 Recommendations regarding the improvement of methods for further information, cooperation and communication is drafted 4.4 IS staff trained in risk assessment and risk analysis 4.5 Study visit to MS carried out in risk management 4.6 Study visit to MS carried out in IT system related to investigation of financial and economic crimes | - STE reports (All indicators) - Training materials (Indicator 4.4) - Feedback evaluation sheets (training) (Indicator4.4.) - Study visit report (Indicator 4.5) - Project reports |  |  |
| 5. Rules and procedures of fighting against IPR related crimes are established based on the EU best practice. | 5.1 Assessment report on the current situation concerning IPR crime performed 5.2 Action plan drafted 5.3 IS staff trained in combating IPR crime 5.4. Study visit to MS carried out in investigating IPR crimes | - STE report (Indicator5.1) - Action plan (Indicator5.2) - Evaluation sheets (Training) (Indicator 5.3) - Training materials (Indicator 5.3) Feedback evaluation sheets (training) (Indicator 5.3) - Study visit report (Indicator 5.4) - Project reports |  |  |
| 3.4. Activities | Means (indicative) | Costs |  | Assumptions |
| General: | Twinning project: 21 months; STEs | EUR 1.300.000 |  |  |
| Organise Kickoff conference and Steering Committee |  | RTA + PL Interpretation Translation |  |  |
| Organise final “Closing conference” |  | RTA, PL, STEs Interpretation Translation |  |  |
| 3.4.1 Draft of the revised legal framework and new instructions for the Investigation Service are in place |  |  |  |  |
| 3.4.1.1 Assessment and analyze the existing Criminal Code and Criminal Procedure Code of Georgia based on the international standards in the field of criminal law | STE assesses structural and procedural differences between CC and CPC of Georgia and international criminal legislation. Prepares report on findings and recommendations for improvement | STE – 20 wd Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |  |
| 3.4.1.2 Drafted amendments to the Criminal Code of Georgia according EU standards to define special kind of crimes for performing procedures and regulations on modern standards according to Activity 1.1; translation completed. | STE together with the BA will analyses the findings of activity 1.1. Legislative changes are proposed based on these findings. STE holds workshop with IS staff from the Investigation Department and the Legal Division to review the proposed changes and amendments together with stakeholders. Report on results of the workshop to be prepared. Draft amendments to the Criminal Code of Georgia to be prepared by STE in cooperation with IS staff | STE – 20 wd Interpretation Translation |  |  |
| 3.4.1.3 Drafted changes and amendments to the relevant laws to achieve further alignment with EU Directives referring to tax fraud legislation; translation completed. | Working group will be created and together with the STE the WG will elaborate the relevant amendments to the laws. STE analyses the existing laws. Legislative changes are proposed based on these findings. STE holds workshop with BA to review the proposed changes and amendments together stakeholders. Report on results of the workshop to be prepared. Draft amendments to the relevant laws to be prepared by STE in cooperation with IS staff | STE – 20 wd Interpretation |  |  |
| 3.4.1.4 Draft operational instructions for investigators based on outcomes of the activities 1.2, and 1.3. . | STE will draft operational instructions for the IS concerning the relevant amendments in accordance with EU best practices. Draft operational instructions are discussed and agreed with the BA | STE – 25 wd Interpretation |  |  |
| 3.4.1.5 Training based on new instruction for the relevant IS staff, Prosecutor’s office and the Revenue Service | STE together with the BA will identify 25 trainees; STE will elaborate the training materials. STE will conduct the training in accordance with findings of activity 1.4 | STE – 20 wd Interpretation Translation |  |  |
| 3.4.3 Human Resources Division has implemented new methods of effective management of the staff of the Investigation Service |  |  |  |  |
| 3.4.2.1 Review of the present system and the structure of the IS | STE carries out analysis of the existing system and the structure of the IS; In coordination with the BA and relevant stakeholders, STE will draft the recommendations for the improvement of the IS structure for better operation | STE – 15 wd Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |  |
| 3.4.2.2 Draft action plan/roadmap of changes according to the findings of the activity 2.1 | STE and BA jointly draft action plan/road map of the procedures to be implemented for the improvement of the IS structure and system based on the recommendations elaborated in activity 2.1 | STE – 15 wd Interpretation Translation |  |  |
| 3.4.2.3 Perform gap and needs analysis of the Human Resource Management system of the IS | STE performs a Gap and Needs Analysis of current system and prepares report with proposals for possible improvement of the HRM system. Proposals to be reviewed by the relevant staff of the IS. | STE – 15 wd Interpretation |  |  |
| 3.4.2.4 Elaborate operational handbook for the IS inspectors and investigators | STE together with BA will prepare a handbook for IS inspectors and investigators. The handbook will be presented to the relevant IS staff | STE – 30 wd Interpretation Translation |  |  |
| 3.4.2.5 Development of the methodology of the conducting the training needs analysis for the inspectors and investigators of the fiscal and criminal crimes | STE develops methods and tools in Training need analysis specifically for the professionals working in the field of the economical and fiscal crimes. STE together with the BA conducts a workshop to present the elaborated methodology for the relevant staff of the IS. | STE – 20 wd Interpretation Translation |  |  |
| 3.4.2.6 Training of management staff of the IS in the effective Human Resources Management tools | STE develops the training program and materials. STE conducts the training for the heads and deputy heads of the departments and divisions (20 persons) in HRM tools and effective motivate tools for the IS employees | STE – 15 wd Interpretation Translation |  |  |
| 3.4.3 New rules and procedures are introduced to combat tax fraud and tax fraud related crimes in accordance with the EU standards |  |  |  |  |
| 3.4.3.1 Conduct a Gap and Needs analysis to establish divergences between Georgian Tax Code, Criminal Code and EU Directive, and to establish articles where assistance with interpretation is needed | STE performs a Gap and Needs Analysis (GNA) of exiting Georgian Tax Code, Criminal Code to establish divergences between Georgia Tax Code (articles related to the criminal cases) and other legislation and the EU directives. Establish articles which need further interpretation and clarification assistance by STE. The result of the GNA is presented in a report | STE – 15 wd Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |  |
| 3.4.3.2 Develop guideline on combating VAT fraud | STE analyses the existing regulations and situation in the country in the field of combating VAT fraud, based on the findings develops a guideline on combating VAT fraud in line with EU experience. | STE – 25 wd Interpretation Translation |  |  |
| 3.4.3.3 Conduct training courses with specialized staff of the IS regarding modern methodology of combating the VAT fraud | STE elaborates the training materials and conducts train for 60 persons in combating the VAT fraud with regards to the new guidelines | STE – 20 wd Interpretation Translation |  |  |
| 3.4.3.4 Develop effective methodology of fighting against money laundering | STE will analyze and asses the current money laundering legislation, drafts the recommendations for improvement and together with the BA develops methods of fighting against money laundering. Findings, recommendations and methodology is presented to the relevant authorities and BA staff | STE – 30 wd Interpretation Translation |  |  |
| 3.4.3.5 Training of the IS staff in combating money laundering . | STE elaborates training methods on money laundering and conducts training course for 60 persons. | STE – 20 wd Interpretation Translation |  |  |
| 3.4.3.6 Improve knowledge of IS staff through training course regarding combating cyber crime (or computer crime) | STE elaborates training materials and conducts trains for 30 persons in effective countermeasures to combat cyber crime | STE – 15 wd Interpretation Translation |  |  |
| 3.4.3.7 Developed instructions for internal training of trainers for IS staff (training for trainers scheme) to ensure that current investigation knowledge of VAT fraud including money laundering and cyber crime is available. | STE prepares training materials to hold interactive trainings with 20persons of the BA in investigation of VAT fraud including money laundering and cyber crime. Trainings to be given using ToT methodology | STE – 20 wd Interpretation Translation |  |  |
| 3.4.3.8 Conduct study visit to MS to improve experience and practical use of investigating tax evasion and cyber crime | MSA arranges study visit to a MS partner of the Twinning project, where 7 IS staff will have the possibility to gain operational experience in the investigating tax evasion and cyber crime during 5 working days. Study visit report to be prepared with experiences and conclusions made. | Study Visit 49 (7 persons x 7 days) per diems 7 flight tickets |  |  |
| 3.4.3.9 Conduct study visit to MS to improve experience and practical use of money laundering | MSA arranges study visit to a MS partner of the Twinning project, where 7 IS staff will have the possibility to gain operational experience in the investigating money laundering during 5 working days. Study visit report to be prepared with experiences and conclusions made. | Study Visit 49 (7 persons x 7 days) per diems 7 flight tickets |  |  |
| 3.4.4 The Investigation Service has developed and improved rules and procedures in the area of risk analysis and management. |  |  |  |  |
| 3.4.4.1 Analyze and assess the current risk analysis system, available information and criteria of risk assessment (Intelligence Standards). | STE will analyse and assess the current risk analysis system, available information and criteria. Need for further information from different sources such as third parties, will be assessed. Proposals for amendments to be implemented and development of criteria according to assessment prepared in report. If possible implement new criteria in risk analysis system to best EU practice. | STE –15 wd Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |  |
| 3.4.4.2 Prepare required manual of risk assessment (Intelligence Standards) | STE produces manual for Intelligence Standards together with IS staff based on the findings of the activity 4.1 and use of Law Enforcement Programme Standards documents. STE conducts a workshop of the BA to present and discuss the manual. | STE – 20 wd Interpretation Translation |  |  |
| 3.4.4.3 Draft the recommendations regarding the improvement of methods for further information, cooperation and communication.. | STE will assess the exiting information, cooperation and communication system of the IS. STE will draft the recommendations to support the IS to develop an efficient system of collecting and exchanging intelligence data in the IS with relevant international organization including open sources | STE – 20 wd Interpretation |  |  |
| 3.4.4.4 Training of the relevant IS staff members in new criteria of risk assessment and methods in risk analysis system according to Activity 4.1, 4.2 and 4.34.3 | STE prepares training materials to hold interactive trainings with 20 persons of the BA in risk management and risk analysis. | STE – 15 wd Interpretation Translation |  |  |
| 3.4.4.5 Conduct Study visit to MS to experience practical use of risk management | MSA arranges study visit to a MS partner of the Twinning project, where 8 IS staff will have the possibility to gain practical experience in risk management during 10 working days. Study visit report to be prepared with experiences and conclusions made | Study visit: 8 flights, 8x12 per diems |  |  |
| 3.4.4.6 Conduct Study visit to MS to experience practical use of IT system related to investigation of financial and economic crimes | MSA arranges study visit to a MS partner of the Twinning project, where 7 IS staff will have the possibility to gain practical experience in IT system 5 working days. Study visit report to be prepared with experiences and conclusions made. | Study visit: 7 flights, 7x7 per diems |  |  |
| 3.4.5 Rules and procedures of fighting against IPR related crimes are established based on the EU best practice |  |  |  |  |
| 3.4.5.1 Assess the current situation concerning the IPR crimes in Georgia | STE will conduct analysis and assessment of the Georgian situation in IRP crimes | STE – 15 wd Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |  |
| 3.4.5.2 Develop Action Plan for the investigators to effective combating IPR crimes in Georgia | MSA and BA create a working group (WG), the WG will consist with STE of the MSA, relevant IS staff and other stakeholders. The WG together with the STE will develop an Action Plan aiming combating IPR crimes in Georgia, Conduct workshop in order to present the developed Action Plan with participation of IS staff, National Intellectual Property Centre of Georgia (Sakpatenti) and Prosecutor’s office | STE – 25 wd Interpretation Translation |  |  |
| 3.4.5.3 Train officers in the field of Investigation of Intellectual Property Rights crimes. | STE will elaborate training materials and conducts 10 days train course for 15 IS officers specialized in identification and investigation of the IPR crimes in Georgia | STE – 10 wd Interpretation Translation |  |  |
| 3.4.5.4 Conduct Study visit to MS to experience practical use of investigating IPR crimes | MSA arranges study visit to a MS partner of the Twinning project, where 7 IS staff will have the possibility to gain practical experience in combating IPR crimes 5 working days. Study visit report to be prepared with experiences and conclusions made | Study visit: 7 flights, 7x7 per diems |  |  |