STANDARD TWINNING PROJECT FICHE

- Basic Information

  - Programme:	ENPI 2012 Annual Action Plan

  - Twinning Number:	GE/13/ENP/FI/17

  - Title:	Strengthening Administrative Capacity of the Georgia Revenue Service in Taxation

  - Sector:	Finance

  - Beneficiary country:	Georgia

- Objectives

  - Overall Objective(s):

The development of an efficient and effective tax administration system in harmony with the economic and financial interests and activities of businesses and citizens of Georgia.

  - Project purpose:

The purpose of this project is to strengthen the administrative capacity of the Georgia Revenue Service (GRS) in line with the European Union and international standards in the following fields:

- Tax control – to continue improving the risk analysis system and strengthen the control capacity of staff, and to introduce computer audit in the control work

- Enforcement of tax debts – to improve and implement measures that will increase tax collection

- Taxpayers’ services – improve the public trust and legal certainty

- Legislation – to provide analysis, recommendations and road maps in the fields of VAT and Excise to ensure implementation according to the EU Acquis and the Association Agreement

- Human resources – to improve and implement techniques that will provide professional development for Revenue Service staff

  - Contribution to Cooperation agreement/Association Agreement/Action Plan

In the last few years the Georgian Government has introduced several reforms which have ensured the overall macro-economic stability, fiscal consolidation and continuous growth. The reform efforts, particularly in economic liberalisation and to fight corruption, have been recognised internationally.

The present Twinning project is in line with the EU- Georgian Agenda:

The EU-Georgia Partnership and Cooperation Agreement (PCA)entered into force in July 2009 and although it does not specifically cover public financial management, it contains several articles that are relevant to the development strategy of the Ministry of Finance.

The EU-Georgia European Neighbourhood Policy (ENP) Action Plan came into force in November 2006, and it defines areas of cooperation relevant to the reform and development of state institution such as the Ministry of Finance. It further refers to specific areas for cooperation such as tax collection, public finance management and transparency, and e-government and e-learning. Priority area 2 of the ENP Action Plan concerns reforms in the area of tax administration, audit and investigation, and also refers to cooperation with taxpayers. Priority area 3 covers economic development and refers to specific reforms in public finance management, such as education and life-long learning opportunities to promote sustainable human resources development.

The National Indicative Programme  (NIP) 2011-2013, which is an ENP Instrument, has as Priority Area 1 the “Support for Democratic Development, Rule of Law and Governance”. The sub-priority 1.3 is defined as “public finance management and public administration reform” with the expected long term impact defined as “the development of a sound and transparent public finance management system and a stronger, stable, citizen-oriented public administration”

Georgia is currently in negotiation with the EU for the Association Agreement (AA) and Deep and Comprehensive Free Trade Area (DFCTA), expected to be finalised in May/June 2013. Under the Association Agreement Georgia will have to carry out approximation process with EU legislation in the field of VAT and Excise. The timeframe for implementation and the list of derogations are still under negotiation. The EU legislation needed to approximate for VAT includes:

- Council Directive 2006/112/EC of 28 November 2006 on the common system of value added tax

- Thirteenth Council Directive 86/560/EEC of 17 November 1986 on the harmonization of the laws of the Member States relating to turnover taxes – arrangements for the refund of value added tax to taxable persons not established in Community territory

For Excise, Georgia needs to approximate the following EU directives into the national legislation:

- Council Directive 2011/64/EU of 21 June 2011 on the structure and rates of excise duty applied on manufactured tobacco (codification)

- Council Directive 2007/74/EC of 20 December 2007 on travellers' allowances- section 3 on quantitative limits

- Council Directive 92/83/EEC of 19 October 1992 on the harmonisation of the structures of excise duties on alcohol and alcoholic beverages

- Council Directive 2003/96/EC of 27 October 2003 restructuring the Community framework for the taxation of energy products and electricity

- Council Directive 2008/118/EC of 16 December 2008 concerning the general arrangements for excise duty and repealing Directive 92/12/EEC - Article 1

- Description

  - Background and justification:

    - Background

It is of great importance for modern tax administrations to provide qualitative services to the taxpayers and citizens, and to have a strong and efficient tax control system in place, all to ensure a low burden on taxpayers and high tax compliance. To achieve this there must be constant focus on improving knowledge and skills of employees, upgrading technical infrastructure, improving work procedures and processes, and simplifying the obligations of the taxpayers.

To protect taxpayers’ rights and to carry out measures to ensure tax compliance are among the main priorities of the Georgia Revenue Service. It includes protection of the state’s and taxpayers’ interests, detection of non-compliance, simplification of administrative procedures, prevention of fraudulent activities, high quality audit and improved targeting of audit resources through case selection, and cooperation with foreign tax administrations.

The Georgia Revenue Service (GRS) is a relatively young administration, and a legal entity of public law of the Ministry of Finance of Georgia. In 2007 the two separate administrations Customs and Tax where joined into the Revenue Service. At the same time 80-95% of the staff was fired in effort to fight corruption and a new generation of staff was employed. This in turn has led to a young and educated, but in many cases inexperienced, work force. Since 2004 impressive progress has been made and many innovative components have been developed in the Revenue Service, and also many improvements made to the tax legislation.

The Revenue Service has introduced the following measures and services:

- Introduction of simplified tax regulations for micro and small businesses – micro business is exempted from income tax, small business is charged with 3% or 5% income tax; the taxpayers are authorized to carry out a simplified accounting.

- Advance Tax Ruling

- Modern Service centers

- District Tax Officer – who visits premises of micro and small taxpayers daily and provide MSMEs with all necessary information regarding amendments and updates to the tax legislation, or other developments in terms of tax administration, and other contemporary programs.; also answer all questions taxpayers raise daily, and clarify legislative provisions in a popular and understandable manner.

- Service PRIVÉ – an individual, exclusive fee based service of Personal Tax Advisor primarily to large and medium taxpayers, who wish to receive useful information in less time, individually and exclusively.

- Alternative Audit - low risk taxpayers can choose to be audited by private auditors. For this kind of audit the taxpayer has to pay a fee depending on the turnover. The fee is paid to the private auditor. In return, tax assessments and corrections made during the Alternative audit are not subject to penalties.

- Filing on a quarterly basis – the reporting period for taxable operations gradually transforms from a monthly into a quarterly filling.  This can also be considered as State investment in the private sector.

- Electronic filing – ensures simple, convenient and cost free method of tax return filing.

- Electronic VAT invoice – can eliminate the existence of non-commodity and fictional transactions as well as the mistakes in the filling process.

- Electronic Waybill – When delivering goods within the territory of Georgia for entrepreneurial activities a waybill has to be issued and submitted to GRS. The waybill is issued in electronic form from the e-page of the Taxpayer.

- GPRS system and Crypto module cash registers – New devices improve and simplify process of administration and risk management for Georgia Revenue Service. The cash registers are connected real time to Georgia Revenue Service database.

- Electronic Marking System – on-direct marking and highly secured paper-based labels with different security features on excise and non-excise goods with effective and modern track and trace system.

- www.rs.ge – web portal of the Revenue Service saves time, energy, financial and labor costs of the taxpayers. E-filing, submission of e-invoices and electronic waybills are all done through the web portal.

- Procedural manuals – elaborating procedural manuals for the consistent administration of the tax and customs’ unified practices and providing such manuals to every single employee to achieve  equal administrative performance.

- Mediation during the tax audit –just and effective system of dispute resolution with ability for taxpayer to discuss draft final protocol with Georgia Revenue Service in order to make decision acceptable for both sides.

- Taxpayer training – organizing trainings for the taxpayers in order to raise their awareness of different aspects of the Tax Code.

- Electronic administration system – serves as a tool for complete elimination of corrupted and subjective/biased decisions in the process of tax audit.

- www.hr.gov.ge – all available jobs within government services are advertised on the web portal of the Civil Service Bureau, including jobs in GRS.

From having 26 taxes in 2003 the number was reduced to only six different taxes in 2004, namely:

- profit tax (corporate income tax),

- personal income tax,

- VAT,

- property tax,

- import tax and

- excise tax.

A new Tax Code came into force on 1 January 2011, which covers all taxes and procedures administered by the GRS.

    - Justification

Even though the Revenue Service has come a long way in modernizing their services and controls, there are still areas that need developing and where international assistance is vital. The work force lacks experience and in-depth knowledge in areas such as audit and Human Resources Development.  Risk analysis systems and the criteria used need continued development and improvement to assist control efficiency and targeting of both audit and current controls. To further support efficient field audits, the use of computer audit technique should be implemented in the GRS. To enable specialization and segmenting, the project should continue building on the work already commenced by other donors with assistance in special taxation issues and business sectors.

As regards debt enforcement management, the GRS have a large amount of uncollected tax debts, which to a big part consists of uncollectible amounts, and it is important to get procedures and methods in place that will enable the GRS to concentrate their resources on the collection of new debts.

The GRS has furthermore very important requirements to fulfil in the areas of VAT and Excise legislation in respect of the Association Agreement expected to be signed later this year. Due to the differences in terminology and structure between the Georgian Tax Code and the EU Directives, it is of vital importance to get assistance from EU expertise at an early stage to ensure a smooth and successful approximation process.

The successful implementation of the project will create the proficient basis for the administrative capacity of Georgia Revenue Service by increasing the efficiency and effectiveness of all tax control functions of the Revenue Service, developing measures for improvement of the taxpayers’ services and increasing the justice principles and approach between the taxpayer and tax authorities.

The project moreover will assist in the fulfilment of the ENPI AP, AA and strategic plan of the Government. Willing to establish close relationship with the European Union, but also to occupy a full and whole place on the international market, Georgia wishes to improve its legislation and its internal procedures, and to fulfil commitment taken under the Association Agreement between the Government of Georgia and EU on implementation of the common system of value added tax and the arrangements for excise duty.

  - Linked activities (other international and national initiatives):

In the recent years, a number of projects financed by different donors have been contributing for development and strengthening of the Georgian Revenue Service. Below is a summary of the main interventions:

    - EU projects

There have been three main EU projects carried out in the field of taxation through Technical Assistance programmes, namely:

| Project title | Duration | Main activities |
| --- | --- | --- |
| Support to Tax Administration | 2005-2009 | The project was active in the following fields: - Taxpayer services, such as: - FAQ development - Public awareness publications - Development of Pocket Tax book - Development of Training programme and courses - Development of Training methodology manual - Market surveys - Risk based taxpayer profile audit system |
| Support to Tax Administration (continuation project) | Feb 2009-Nov 2009 | The project was active in the following fields: - Production of Fiscal Blueprints - Production of procedure manuals for audit - Seminars in tax collection and enforcement, audit management, strategic planning - Production of taxpayer leaflets |
| Georgian – European Policy and Legal Advice Center (GEPLAC) – Phase VII [Georgia] | June 2010- March 2012 | The overall objective of the project was to assist the Georgian Government in undertaking reforms to: i) deepen its democratic process; ii) further develop a market economy and iii) facilitate approximation to European values and integration into European Union markets as per the Partnership and Co-operation Agreement (PCA) commitments, and the European Neighbouring Policy Action Plan (ENP AP) priorities, endorsed in November 2006. |

There have been one Twinning project recently finalised with relation to the Ministry of Finance and The Revenue Service, and another is planned to take place shortly. The specific projects are:

| Project title | Duration | Main activities |
| --- | --- | --- |
| Revenue Service - Strengthening the National Customs and Sanitary and Phyto-sanitary Border Control System in Georgia (Partners: Denmark, Estonia, Italy); | 2011-April 2013 | The project was involved in e.g. the following customs activities: - Custom control procedures - Relation with traders - Risk management - Post-clearance control and audit - Prevention of smuggling - Rules of origin |
| Capacity Building of the Academy of the Ministry of Finance of Georgia | April 2013-January 2015 | To strengthen the capacity of the Academy in the fields of - strategic management, - training delivery, - professional development programmes, - quality management systems |

When planning the activities for this project full consideration has been given to the above projects in order not to duplicate efforts.

    - Other donors

There have been a few shorter projects delivered in the field of taxation by donors such as OECD, IOM and Ministry of Finance, the Netherlands. Currently there are several on-going projects that link to the proposed project in the field of tax auditing, debt enforcement and taxpayers’ services. These projects are conducted by USAID, US Treasury, IMF and IFC, World Bank. The table below lists all mentioned projects and the main activities in each.

| Donor | Project title | Duration | Main Activities |
| --- | --- | --- | --- |
| OECD | Transfer Pricing and Thin Capitali-sation Training | 2 weeks 2010+2011 | Training of 50 employees from Revenue Service and Financial Policy Department of the MoF |
| IOM | Cooperation with the International Organization for Migration | 2010-2011 | Training of trainers for employees of the Investigation Service, Revenue Service and the Financial-Analysis Service of the MoF |
| MoF, the Netherlands | Cooperation with the Ministry of Finance of the Netherlands | 1 week 2010 | Study tour to the Tax and Customs Administration in the Netherlands and workshop on taxation of small and medium enterprises to the Revenue Service and Chamber of Control of Georgia |
| USAID | Economic Prosperity Initiative | 2010-2014 | - Risk based audit - Assistance with risk analysis system - Return information - Audit manual - Transfer Pricing guidelines - Tax simplification process, e.g. tax payments - Training needs assessment (HR) - Job descriptions (HR) |
| U.S. Treasury Office of Technical Assistance (OTA) | Technical Assistance to the Revenue Service of Georgia | March 2012-March 2014 (with possibi-lity of pro-longing 1 year) | - Improve tax compliance by providing auditors with the expertise and tools necessary to conduct quality audits - Improve audit effectiveness through improved audit management processes including strategic planning and employee performance evaluation - Improve effectiveness in dispute resolution process - Build capacity in the analysis of technical tax issues |
| IMF | Technical assistance to tax administration | 2012-2014 | The project is active in the following fields: - Debt enforcement - Taxpayer registration - Tax return filing - Tax compliance approaches |
| IFC, World Bank | Helping Reform the Tax System in Georgia - Georgia Tax Simplification Project | 2010-2014 | The project aims to lower tax compliance costs for micro, small and medium enterprises (MSMEs) and has been/is active in the following tax fields: - Tax simplification for micro and small businesses - Training to improve taxpayers’ services for businesses - Assistance in drafting legislation for transfer pricing rules and procedures |

The Twinning partners shall take all necessary steps to ensure coordination with the above mentioned and other related activities in order to avoid any duplication or overlap, and to achieve possible synergies.

  - Results:

The Twinning project should have six mandatory results:

Result 1. Tax control measures promoting control efficiency and coverage are improved, developed and implemented.

Result 2. Amended and new instructions are in place to improve debt management systems

Result 3. The Revenue Service has developed and improved processes and procedures in their pursuit of activities that support taxpayers’ rights.

Result 4.  Recommendations for alignment of national VAT with EU Acquis in the field of EU VAT common system prepared in line with the Association Agreement.

Result 5.  Recommendations for alignment of national Excise legislation with the EU Acquis in the field of Excise directives prepared in line with the Association Agreement, and draft legislation prepared for Council Directive 2007/74/EC of 20 December 2007 on travellers’ allowances – section 3 on quantitative limits.

Result 6. The Human Resources Department has implemented new techniques to assist the provision of professional development to the Revenue Service staff.

  - Activities:

The activities set out in this section and the proposed method of implementation, are indicative and should, where appropriate, be revised during the preparation of the work plan and contract between the GRS and the MS administration. In developing their proposals, potential Twinning Partners are invited to propose their own solutions, based on their own experience.

    - General Activities

      - Kick-off Conference

Method:	The first month of the project will see the arrival of the Resident Twinning Advisor (RTA) in Georgia and her/his familiarisation with the local surroundings. The RTA will be located at the Georgia Revenue Service. During this time, she/he will be introduced to the Beneficiary Country stakeholders, the RTA counterpart, and key officials within the GRS. The RTA will hire two assistants (RTA Assistant and Translator) through an appropriate selection procedure (as foreseen in the Common Twinning Manual).

A one day ‘kick-off’ conference will be held in the first month aimed at launching and presenting the project to the stakeholders, the media, and the public at large. In order to inform the public about the start of the project and to conform to the EU visibility requirements, the meeting will be concluded with a press conference and a press release.

Also in the first month, the RTA will establish working relations with the leaders of other bilateral co-operations and form a formal co-ordinating committee, including GRS senior management, which will be tasked with ensuring that the different projects run smoothly and that there is no overlap with activities. The group will meet periodically as required.

Benchmark: Stakeholders, media and public informed about the start and content of the project.

Resources: RTA + PL + Interpretation + Translation.

      - Final Conference

Method:	During the last month of the project, a final ‘closing’ conference will be organised at which the results of the project will be presented. The conference should include presentations on the project’s achievements and the challenges still facing the GRS.

Benchmark: Stakeholders, media and the public informed about the project’s achievements and the remaining challenges for the GRS, in particular, and public accountability more generally.

Resources: RTA + PL + STE days + Interpretation + Translation

    - Activities for Result 1. Tax control measures promoting control efficiency and coverage are improved, developed and implemented.

Activity 1.1 Further development of the risk analysis system for audit selection

Methods: STE will analyse and assess the current risk analysis system, available information and criteria. Need for further information from different sources such as third parties, returns and audits system will be assessed. Proposals for amendments to be implemented and development of criteria according to assessment prepared in report. If possible implement new criteria in risk analysis system.

Benchmarks: Assessment carried out, report on proposals delivered

Resources: STE, interpretation.

Activity 1.2 Development and production of Business sector guide(s)

Methods: The MS Administration will together with BA and other involved donors to identify business sector(s) to be covered (e.g. super markets, restaurants). Sufficient number of audits will be conducted by GRS staff with support from STE(s). Results and experiences of the audits are analysed and reflected in the audit methodology outlined for the specific business sector in the business sector guide(s) that STE is to produce together with RS staff.

Benchmarks: Business sector(s) chosen, sufficient number of audits carried out and business sector guide(s) produced for continued use of audit staff.

Resources: MSA, STEs, interpretation.

Activity 1.3 Training of auditors in specific taxation issues

Method: The MS Administration will together with BA carry out an analysis of which specific taxation issues (e.g. large taxpayers, permanent establishments, tax haven issues) are to be included in the trainings. RTA and STE(s) will then design a training programme in accordance with the specific needs and level of knowledge of the participants in the trainings. STE(s) will produce training materials. STE(s) and RS to identify 15-20 staff to be trained according to Training of Trainers (ToT) methodology. Training sessions are combined with possibility to practical on-the-job support.

Benchmarks: Training programme and training materials produced. Training sessions carried out.

Resources: MS Administration, STE(s), interpretation, translation.

Activity 1.4 Develop software/programme for computer audit (audit technique to extract information from taxpayer’s accounting system) in tax control

Method: The STE together with GRS staff to analyse the most common accountings systems used in Georgia. GRS and STE to assess software requirements needed to develop the necessary software/programme and produce a technical specification. GRS IT staff to develop software under guidance of STE.

Benchmarks: Software for computer audit developed and in place.

Resources: STE, interpretation.

Activity 1.5 Draft necessary legislation for computer audit

Method: STE will together with GRS staff assess the legal conditions for implementing computer audit as an audit tool in GRS.  Legislative changes to be proposed. Draft legislation to be prepared by STE in cooperation with GRS staff.

Benchmarks: Legislation drafted.

Resources:  STE, interpretation.

Activity 1.6 Implement the use of computer audit in tax control

Method: STE together with GRS will select 5-10 auditors with good IT knowledge and skills to be trained as computer auditors using the new developed software. STE produces training materials and conduct training. GRS trainees perform sufficient number of computer audits under supervision by STE to ensure the capacity of the GRS trainees.

Benchmarks: Training materials prepared, training carried out, computer audits (on the job training) carried out.

Resources:  STE, interpretation, translation.

Activity 1.7 Internship for computer audit

Method: MS Administration (MSA) to arrange internship in MS for two GRS computer audit trainees to work alongside computer auditors in other EU country for 20 working days. The internship should also encompass the study of other electronic means and equipment that MS use in tax control/investigation, e.g. for analysis of cash registers, mirroring of hard disks, and the legal requirements for their use in MS. Internship  visit report to be prepared by trainees after visit.

Benchmarks: Internship carried out and report delivered.

Resources: MSA, cost for internship (flight tickets and per diems)

Activity 1.8 Produce guideline for computer audit

Method: STE produces guideline for computer audit together with GRS staff based on the developed software and the experiences made during trainings and audits carried out.

Benchmarks: Guideline prepared.

Resources:  STE, interpretation.

Activity 1.9 Prepare recommendations for the Current Control procedures: chronometric examination (recording goods/services produced/supplied by taxpayer), test purchase, observation, control of cash registers and inventory (stock-taking)

Method: STE will assess the current control procedures that the Monitoring Department of GRS carry out, and prepare report with proposals for possible amendments to procedures. Proposals to be reviewed by GRS and in coordination with STE identify the procedures to be implemented. STE will support in implementing procedures.

Benchmark: Assessment carried out, report prepared. Procedures implemented.

Resources: STE, interpretation.

Activity 1.10 Draft necessary legislation for Current Control procedures to be implemented

Method: STE will together with GRS staff assess the legal conditions for implementing current control procedures according to findings of activity 1.9.  Legislative changes are proposed. Draft legislation to be prepared by STE in cooperation with GRS staff.

Benchmarks: Legislation drafted.

Resources: STE, interpretation.

Activity 1.11 Conduct Study visit to MS to experience practical use of Current Control procedures

Method: MSA arranges 5 day study visit to a MS partner of the Twinning where the current control procedures according to activity 1.9 are currently in use. There will be 4 GRS staff, mainly managers, participating in the study visit and they will have the possibility to experience the practical use of the current control procedures, especially inventory (stock-taking). Study visit report to be prepared with experiences and conclusions made.

Benchmark: Study visit conducted, report delivered.

Resources: MSA, study visit costs (flight tickets, per diems).

Activity 1.12 Train staff in Current Control procedures

Method: STE will develop training materials and train 10 GRS staff in the current control procedures in accordance with findings of activity 1.9. Training is conducted with ToT approach.

Benchmark: Training material produced, training sessions conducted.

Resources: STE, interpretation, translation.

Activity 1.13 Produce guidelines for Current Control procedures

Method: STE to produce guidelines for current control measures together with GRS staff based on findings of assessment and the experiences made during study visit and trainings carried out.

Benchmarks: Guidelines prepared.

Resources:  STE, interpretation.

Activity 1.14 Develop and implement risk assessment measures for Current Controls

Methods: STE will analyse available information and propose risk assessment measures to be implemented. Proposals should include information and criteria to be used in the existing risk analysis system that GRS have. GRS reviews proposals and implements chosen measures under guidance of STE.

Benchmarks: Analysis carried out, report on proposals delivered. Measures implemented.

Resources: STE(s), interpretation.

Activity 1.15 Study visit for risk assessment for Audit and Current Control selection

Method: MSA arranges study visit to MS partner of the Twinning to study risk analysis systems and criteria used for both audit and current controls for 5 GRS staff for 5 working days. Study visit report to be prepared by participants after visit stating findings and conclusions made.

Benchmarks: Study visit carried out and report delivered.

Resources: MSA, cost for study visit (flight tickets and per diems)

Activity 1.16 Train staff in risk assessment measures

Method: STE will develop training materials and train 5 GRS staff in risk assessment measures according to ToT approach.

Benchmark: Training material produced, training sessions conducted.

Resources: STE, interpretation, translation.

    - Activities for Result 2. Amended and new instructions are in place to improve debt management systems

Activity 2.1 Assess current situation for debt enforcement and establish new and/or amended measures identified during assessment to be implemented (such as postponement of debt-payment, debt relief, instalment plans and write-off)

Method: STE will assess current situation and prepare report with proposals for possible debt enforcement measures to be implemented and amended. Proposals to be reviewed by GRS, and in coordination with STE identify the measures to be implemented. STE will support in implementing measures.

Benchmark: Assessment carried out, report prepared. Measures implemented.

Resources: STE, interpretation.

Activity 2.2 Establish evaluation methods for measuring effectiveness of enforcement procedures

Method: STE assesses current situation regarding measuring the effectiveness of enforcement and prepares a report with recommendations on evaluation methods to be implemented.

Benchmark: Evaluation methods assessed and report with recommendations delivered.

Resources: STE, interpretation.

Activity 2.3 Draft necessary legislation for debt enforcement measures to be implemented

Method: STE will together with GRS staff assess the legal conditions for implementing debt enforcement measures according to activity 2.1.  Legislative changes are proposed. Draft legislation to be prepared by STE in cooperation with GRS staff.

Benchmarks: Legislation drafted.

Resources: STE, interpretation.

Activity 2.4 Conduct Study visit to MS to experience practical use of debt enforcement measures to be implemented by GRS

Method: MSA to arrange 5 day study visit to a MS partner of the Twinning where the debt enforcement measures according to activity 2.1 are currently in use. There will  be  4  GRS staff, mainly managers,  participating  in the study visit and they will have the possibility to experience the practical use of debt enforcements measures to be implemented by GRS and to gain knowledge how tackle problems that can arise. Study visit report to be prepared with experiences and conclusions made.

Benchmark: Study visit conducted, report delivered.

Resources: MSA, study visit costs (flight tickets, per diems).

Activity 2.5 Train staff in debt enforcement measures to be implemented

Method: STE will develop training materials and train 5 GRS staff in the debt enforcement measures that are chosen by GRS to be implemented. Training is conducted with ToT approach.

Benchmark: Training material produced, training sessions conducted.

Resources: STE, interpretation, translation.

Activity 2.6  Prepare guidelines for debt enforcement measures to be implemented

Method: STE together with GRS staff to prepare guidelines for debt enforcement measures to be implemented.

Benchmark: Guidelines delivered.

Resources: STE, interpretation,

Activity 2.7 Train staff and draft recommendations for co-operation and exchange of information for recovery purposes

Method: STE will develop training materials and conduct training of 5 GRS staff in how cooperation and exchange of information is used for recovery purposes. Training is conducted with ToT approach. A report is drafted with recommendations for GRS based on EU practices.

Benchmark: Training material is produced, training is carried out. Report with recommendations for GRS practices is delivered.

Resources: STE, interpretation, translation.

    - Activities for Result 3. The Revenue Service has developed and improved processes and procedures in their pursuit of activities that support taxpayers’ rights.

Activity 3.1 Assess current taxpayers’ services and prepare recommendations in accordance with EU best practices for measures to be taken for improvement, (e.g. establish quality indicators, how to receive and analyse public feedback, special measures and tools for vulnerable groups)

Methods: STE assesses current taxpayers’ services and draft a report with recommendations for improvement in accordance with EU best practices.

Benchmark: Assessment carried out and report delivered.

Resources: STE, interpretation.

Activity 3.2. Assess the taxpayers’ call centre and prepare recommendations for improvement.

Methods: STE assesses the taxpayers’ call centre and draft a report with recommendations for improvement in accordance with the EU best practices.

Benchmark: Assessment carried out and report delivered.

Resources: STE, interpretation.

Activity 3.3 Prepare recommendations regarding the refund scheme for income tax allowance for individuals

Method: A new scheme for refund of tax for income tax allowance for individuals is introduced from income year 2013, with refunds first being administered in 2014. STE assesses efficiency and effectiveness of legislation and working procedures. Report on findings and recommendations to be prepared.

Benchmark: Report on findings and recommendations delivered.

Resources: STE, interpretation.

Activity 3.4 Prepare recommendations for work procedures regarding elimination of double taxation.

Method: STE assesses current work procedures and knowledge level in GRS. Prepares report with analysis of EU practices and recommendations for amendments in work procedures.

Benchmarks: Assessment of work procedures in GRS and analysis of EU practices conducted. Report with recommendations delivered.

Resources: STE, interpretation.

Activity 3.5 Train staff in work procedures for elimination of double taxation according to double taxation agreements

Method: Produce training materials and train 10 GRS staff in work procedures for elimination of double taxation according to ToT methodology.

Benchmarks: Training material produced and training conducted.

Resources: STE, interpretation, translation.

Activity 3.6 Draft guideline for elimination of double taxation according to double taxation agreements

Method: In accordance with findings during activity 3.4 and 3.5 the STE together with GRS staff will produce guideline for work procedures for elimination of double taxation.

Benchmarks: Guideline produced.

Resources: STE, interpretation.

Activity 3.7 Prepare recommendations for GRS regarding Advance Tax Rulings, Public Rulings/recommendations and involvement of private sector in law-making

Method: STE assesses the current situation in GRS regarding Advance Tax Ruling, Public Rulings/Recommendations, and Involving private sector in law making. STE during assessment holds discussion workshops with 5 GRS staff to share experiences. Report to be prepared regarding findings and with recommendations for possible implementations by GRS based on EU practices.

Benchmark: Analysis and assessment performed, including discussion workshops. Report with findings and recommendations delivered.

Resources: STE, interpretation.

Activity 3.8 Prepare recommendations regarding production losses/inventory shrinkage for different business sectors

Method: STE analyses EU practices regarding production losses/inventory shrinkage in different business sectors. STE assesses practices within GRS and recommends possible amendments. Prepare report on findings of analysis and assessment, with recommendations on measures for GRS to implement.

Benchmarks: Analysis of EU practices conducted and assessment of work procedures within GRS carried out. Report on findings and recommendations delivered.

Resources: STE, interpretation.

Activity 3.9 Conduct study visit to MS for GRS to gain experience in operation of call centres, service centres, refund schemes for tax allowances, single tax account.

Method: MSA arranges study visit to a MS partner of the Twinning where 3 GRS staff will have the possibility to gain operational experience in the different fields during 5 working days. Study visit report to be prepared with experiences and conclusions made.

Benchmarks: Study visit carried out. Report delivered.

Resources: MSA, study visit costs (flight tickets, per diems).

Activity 3.10 Prepare recommendations regarding appeal process in GRS

Method: During the work plan preparation MSA and GRS will identify all stakeholders (e.g. Ministry of Finance, U.S. Treasury (OTA) project, Business Ombudsman) in the activity, and also have close coordination with the U.S. Treasury (OTA) project to ensure that duplication and overlap do not occur. STE analyses and assesses GRS practices regarding appeal process in tax administration and court, covering both legal and formal basis and requirements for appeals, and the procedures regulating the appeal process. STE prepares report with findings and recommendations for measures to be implemented based on EU practices. Stakeholders will be involved and informed at all stages of the activity.

Benchmarks: Analysis and assessment of procedures within GRS carried out. Report on findings and recommendations delivered.

Resources: STE, interpretation.

Activity 3.11 Conduct trainings regarding appeal process in GRS

Method: STE prepares training materials and to hold interactive trainings with 15-20 persons from Dispute Resolution Department, based on findings of activity 3.10. Trainings to be given using ToT methodology.

Benchmarks: Training material prepared. Trainings carried out.

Resources: STE, interpretation, translation.

    - Activities for Result 4. Recommendations for alignment of national VAT legislation with EU Acquis in the field of EU VAT common system prepared in line with Association Agreement

Activity 4.1 Conduct a Gap and Needs Analysis to establish divergences between Georgia Tax Code and EU VAT Directive, and to establish articles where assistance with interpretation is needed

Method: STE performs a Gap and Needs Analysis (GNA) of current VAT legislation in Georgia to establish divergences between Georgia Tax Code and its secondary legislation, and the EU VAT directives to be approximated according to the Association Agreement, and also to establish articles which need further interpretation and clarification assistance by STE. The result of the GNA is presented in a report.

Benchmarks: Analysis performed, and GNA report delivered.

Resources: STE, interpretation.

Activity 4.2 Conduct workshops with specialised staff in established areas according to Gap and Needs Analysis

Method: STE conducts workshops with maximum 10 VAT specialists from Tax Policy Department, MoF, and Legal Department, GRS, regarding the established areas where weaknesses exist to interpret and clarify EU legislation. Duration of workshops maximum 15 working days. Report on findings and conclusions made during workshops prepared.

Benchmark: Workshops conducted. Report delivered.

Resources: STE, interpretation.

Activity 4.3 Draft an action plan/roadmap for legislative and procedural changes to be implemented in accordance with VAT directives.

Method: STE, Tax Policy Department, MoF, and Legal Department, GRS, jointly draft action plan/road map of the legislation and procedures to be implemented in accordance with VAT directives, also including recommendations for transitional provisions. STE will also during the course of activity 4.2 and 4.3 give lecture regarding experienced issues with implementation of VAT Directives in other country/ies for interested parties within GRS, MoF and other stakeholders that will be identified during the work plan preparation.

Benchmark: Action plan/road map delivered. Lecture material prepared and lecture conducted.

Resources: STE, interpretation, translation.

    - Activities for Result 5. Recommendations for alignment of national Excise legislation with EU Acquis in the field of Excise directives prepared in line with Association Agreement and draft legislation prepared for Council Directive 2007/74/EC of 20 December 2007 on travellers’ allowances – section 3 on quantitative limits

Activity 5.1 Prepare recommendations for structural and procedural changes needed in excise legislation and procedures

Method: STE assesses structural and procedural differences between Georgia Tax Code and EU directives. Prepares report on findings and recommend changes to implement.

Benchmark: Assessment carried out and report delivered.

Resources: STE, interpretation.

Activity 5.2 Draft action plan/roadmap of necessary changes to be implemented

Method: STE and staff of Tax Policy Department, MoF and Legal Department, GRS, jointly draft action plan/road map of the legislation and procedures to be implemented in accordance with Excise directives.

Benchmark: Action plan/road map delivered.

Resources: STE, interpretation.

Activity 5.3 Draft national legislation to be implemented in accordance with Council Directive 2007/74/EC of 20 December 2007 on travellers’ allowances – section 3 on quantitative limits

Method: STE and staff of Tax Policy Department, MoF and Legal Department, GRS, jointly draft legislation to be implemented.

Benchmark: Draft legislation prepared.

Resources: STE, interpretation.

    - Activities for Result 6. The Human Resources Department have implemented new techniques to assist the provision of professional development to the Revenue Service staff.,

Activity 6.1 Prepare recommendations for professional development of staff in the Revenue Service.

Method: STE carries out analysis of EU practices for professional development in tax administrations and performs a gap analysis to establish weaknesses in GRS.  Prepare report on findings and recommendations.

Benchmark: Analysis of EU practices carried out. Gap analysis performed.  Report with findings and recommendations delivered.

Resources: STE, interpretation.

Activity 6.2 Assessment of techniques and skills in Training Needs Analysis of the HR Department, GRS

Method: STE assesses current techniques and skills in practice in HR Department, GRS. Prepares report on findings.

Benchmark: Assessment carried out. Report prepared.

Resources: STE, interpretation.

Activity 6.3 Conduct workshops in techniques and skills in Training Needs Analysis with the HR Department, GRS

Method: STE holds in-depth workshops with 5-6 HR staff covering issues in accordance with assessment findings in activity 6.2. Report to be prepared on results of workshops.

Benchmark: Workshops conducted.

Resources: STE, interpretation.

Activity 6.4 Prepare guideline in Training Needs Analysis

Method: STE together with HR staff prepare guideline for Training Needs Analysis.

Benchmark: Guideline prepared.

Resources: STE, interpretation.

Activity 6.5 Assessment of techniques and skill in Job Task Analysis of HR Department, GRS

Method: STE assesses current techniques and skills in practice in HR department, GRS. Prepares report on findings.

Benchmark: Assessment carried out. Report prepared.

Resources: STE, interpretation.

Activity 6.6 Conduct workshops on techniques and skill in Job Task Analysis

Method: STE holds in-depth workshops with 5-6 HR staff in accordance with assessment findings. Special attention to be given to how to determine knowledge and competences needed for specific job positions. Report on results of workshops to be prepared.

Benchmark: Workshops conducted. Report prepared.

Resources: STE, interpretation

Activity 6.7 Prepare guideline for Job Task Analysis

Method: STE together with HR staff prepares guideline for Job Task Analysis.

Benchmark: Guideline delivered.

Resources: STE, interpretation,

Activity 6.8 Further development of e-learning concept within GRS

Method: STE assesses current situation of e-learning practices within GRS. Report on findings to be prepared with recommendations for how to make e-learning concept more utilized and functional within GRS. GRS implements measures according to recommendations under guidance of STE.

Benchmark: Assessment carried out. Report with findings and recommendations prepared. Measures implemented.

Resources: STE, interpretation.

Activity 6.9 Development of performance evaluation methods and performance indicators within GRS

Method: STE assesses current situation of performance evaluation and performance indicators in HR Department. Report on findings and recommendations prepared. GRS implements evaluation methods and performance indicators according to recommendations under guidance of STE.

Benchmark: Assessment carried out. Report with findings and recommendations prepared. Measures implemented.

Resources: STE, interpretation.

  - Means/ Input from the MS Partner Administration:

    - Profile and tasks of the Project Leader

Role and tasks

- The Project Leader will direct, co-ordinate, and control the overall thrust of the project. He/she will lead the activities of the project, ensure the achievement of the results, be responsible for the implementation of the activities and, with the support of the RTA, produce progress reports.

- The Project Leader is expected to devote a minimum of three days per month to the project in his home administration, not in Georgia. In addition, as Co-Chairman, he/she should co-ordinate, from the Member State side, the Project Steering Committee (PSC), which will meet in Georgia at least every three months.

# Profile

Qualification and skills:

- Good English language skills, both spoken and written;

- Good inter-personal skills;

- Command of the Georgian language would be a strong asset.

General professional experience:

- Long term civil servant from the MS administration;

- Minimum 8 years of professional experience;

- Experienced project manager, demonstrating good record in organisational leadership, staff motivation, and communication.

Specific professional experience:

- Knowledge and experience of tax control and EU legislation.

- Currently belonging to a Member State finance administration.

    - Profile and tasks of the RTA

Role and tasks

The RTA will be responsible for the day-to-day management and implementation of the project. He/she will be responsible for co-ordinating all the different activities and inputs and for liaising with the RTA Counterpart in the Revenue Service of Georgia. Specifically, the RTA will be responsible for:

- Overall supervision of the project implementation and co-ordination of all activities, as well as managing the project administration;

- Co-ordinating the activities of team members in line with agreed work programs to enable timely completion of project outputs;

- Providing technical input to the project whenever needed and providing advice in their field of expertise;

- Liaising with MS and BC Project Leaders and ensuring on-going regular contact with the RTA Counterpart;

- Liaising with the EU Project Manager;

- Liaising with key stakeholders (e.g. other relevant projects and Georgian institutions).

The RTA will provide 18 months input on site (including leave) and will be based in an office in the GRS.

# Profile

Qualification and skills:

- University level education, or professional qualification, preferably in accounting, business studies, or related discipline;

- Excellent English language skills, both spoken and written, and command of the Georgian language would be a strong asset;

- PC Computer literacy;

- Good inter-personal skills.

General professional experience:

- Civil Servant from an EU MS Administration;

- Minimum 7 years of professional experience;

- Experienced project manager, demonstrating good record in organisational leadership, staff motivation and communication;

- Excellent team-working skills;

- Strong analytical skills;

Specific professional experience:

- At least 5 years’ experience in taxation, preferably in a management role;

- Relevant working experience in transition economies of the CIS would be an asset.

    - Profile and tasks of the short-term experts

Tasks of short term expertise

Terms of Reference for short-term experts will be elaborated by Project Leader/RTA at the work plan preparation stage.

Profile of short term expertise

To cover all the 49 activities described in 3.4 there must be a pool of short term experts with a set of different skills and qualifications. The actual duration of the assignments of each of the short-term experts will be defined during the drafting of the twinning agreement. The short term experts will work in close co-operation with the Project Leader/ RTA and the Beneficiary in order to meet the specific objectives as set out above.

The exact number of short term experts and their required qualifications should be identified by the Project Leader/RTA in the course of designing the delivery of the project. But in order to cover the activities to be performed in the project the short term experts are expected to have following qualifications and skills:

General:

- University degree or relevant professional background in tax administration of minimum 7 years.

- At least 5 years working experience in their respective field of expertise

- Sound knowledge of relevant EU legislative and institutional requirements related to the various components of this project

- Very good command of English (oral and written)

- Good writing and presentation skills

- Good training and facilitation skills

- Excellent computer skills (Word, Excel, Power Point);

Specific:

STE on Tax control

- Expertise in development of risk analysis system and risk criteria

- Expertise in field audit and preparation of Business sector guides

- Expertise in specific taxation issues

- Expertise in drafting legislation

- Expertise in developing software for computer audit

- Expertise in computer audit

- Expertise in Current control procedures as defined in Tax Code of Georgia

STE on Debt management

- Expertise in debt management procedures

- Expertise in drafting legislation

- Experience in developing and managing IT systems for debt management

STE on taxpayers’ rights

- Expertise in management, monitoring and evaluation of taxpayer services

- Expertise in call centre development and management

- Expertise in tax refund systems

- Expertise in elimination of double taxation

- Expertise in Advance Tax Rulings

- Expertise in Public Rulings/recommendations

- Expertise in involving public sector in law-making

- Experience in tax treatment of production losses/inventory shrinkage

- Expertise in appeal process

STE on VAT

- Expertise in VAT legislation and practical working experience in interpreting VAT legislation

- Expertise in implementation of EU VAT Directives in national legislation

STE on Excise

- Expertise in Excise legislation and practical working experience in interpreting Excise legislation

- Expertise in drafting legislation

- Expertise in implementation of EU Excise Directives in national legislation

STE on Human resources management

- Expertise in Career development methods

- Expertise in Recruitment and selection

- Expertise in Motivation and promotion

- Expertise in Training needs analysis

- Expertise in Job Task Analysis

- Expertise in promoting E-learning, distance learning

- Expertise in Performance evaluation and performance indicators

Additional assets for all STEs would be:

- Relevant working experience in transition countries.

- Knowledge of Georgian and/or Russian language

- Institutional Framework

The main Beneficiary Institution (BI) of the project is the Georgia Revenue Service (GRS) of the Ministry of Finance (MoF) of Georgia. For the VAT and Excise activities of the project the Tax Policy Department, MoF, will also be Beneficiary Institution together with the GRS.

In 2007 the two separate administrations Customs and Tax where joined into the Georgia Revenue Service. In March 2013, the number of staff of the whole GRS was 3 025, whereof approximately 1 290 were working in the three main Tax departments: Service, Audit and Monitoring. The organisational chart of Georgia Revenue Service is attached in Annex 3. The divisions and number of staff of each department, excluding the customs departments, can be found in Annex 4.

The GRS has 16 Service centres established in Georgia, whereof 4 are located in Tbilisi. There are also in total 17 Revenue employees located in local government or town halls in smaller towns that do not require a full Service centre. There are seven Monitoring offices in the country, which are responsible for Current controls and debt enforcement. The Audit Department is only located centrally in Tbilisi.

The number of taxpayers submitting returns in 2012 where as follows:

- Profit tax: 61 237

- Income tax for individuals: 121 432

- Property tax: 55 085

- VAT: 57 875

- Excise duties: 270

The legal framework for GRS is the Constitution of Georgia, the Tax Code of Georgia, international tax agreements and treaties, and also the secondary legislation in form of decrees (issued by the Georgian government) and orders (issued by MoF). The MoF also issues instructions regarding the application of certain chapters and articles of the Tax Code of Georgia. The Director General of the GRS issues internal guidelines for the staff to follow.

- Budget

Euro 1.3 million.

- Implementation Arrangements

  - Implementing Agency responsible for tendering, contracting and accounting (AO/CFCU/PAO/Commission).

The European Union Delegation in Tbilisi, Georgia, will be responsible for the tendering, contracting, payments and financial reporting, and will work in close co-operation with the Beneficiary. The person in charge of this project at the Delegation of the European Union to Georgia is:

Mr.Irakli Khmaladze

Project Manager, Economics and Public Finance

Delegation of the European Union to Georgia

38 Nino Chkheidze St, 0102 Tbilisi, Georgia

Tel: +995 32 2943 763

# E-mail: irakli.khmaladze@eeas.europa.eu

- The Project Administration Office (PAO) of the Office of the State Minister of Georgia on European and Euro-Atlantic Integration will support the Twinning Project implementation process together with the EU Delegation. The person in charge of this project is:

- Mr Roman Kakulia

- Head of Project Administration Office (PAO) in Georgia,

- Office of the State Minister of Georgia on European and Euro-Atlantic Integration

- 7, Ingorokva Street, Tbilisi 0134, Georgia

- Tel: +995 32 299 89 14

- e-mail: pao@eu-nato-gov.ge

  - Main counterpart in the BC

Project Leader:

- Mr. Samson Uridia

- Head of Department for International Relations

- Georgia Revenue Service

- 68a, Kostava St., 0179 Tbilisi, Georgia

- Phone: + 995 (32) 226 29 01

- Mobile: +995 (577) 05 44 34

- E-mail: s.uridia@rs.ge

Web: www.rs.ge

www.mof.ge

RTA Counterpart:

# Mr. Dachi Kinkladze

Deputy Head

Department for International Relations

Georgia Revenue Service (Tax and Customs Administration)

68a, Kostava St., 0179 Tbilisi, Georgia

Phone: +995 (32) 226 29 19

Mobile: +995 (599) 04 13 01

E-mail: dachi.kinkladze@rs.ge

Web: www.rs.ge

www.mof.ge

  - Contracts

The Project will be implemented in the form of a twinning contract between Georgia and an EU Member State.

- Implementation Schedule (indicative)

  - Launching of the call for proposals (Date):	July 2013

  - Start of project activities (Date):			April 2014

  - Project completion (Date):			September 2015

  - Duration of the execution period (number of months): The implementation period will be 18 months. Legal duration of the Twinning contract, including periods for start-up and completion of activities, is 21 months in accordance with the Twinning Manual 2012.

- Sustainability

The achievements of the Twinning project (mandatory results) will be maintained as a permanent asset to the Beneficiary Institution both on central and local level even after the end of the Twinning implementation. The prerequisite for this is, inter alia, that effective mechanisms are put in place by the Beneficiary Institution to disseminate and consolidate the results of the project.

The Beneficiary Institution is fully committed to ensure the long term impact of the Twinning project. During the project implementation, the twinning partners should develop documents/handouts, guidelines that will be easily accessible for later use by the beneficiary administration. Staff benefiting from trainings/study visits shall transfer knowledge through subsequent training to their colleagues at all levels.

- Crosscutting issues

Equal Opportunities and non-discrimination

The principles and practice of equal opportunity will be guaranteed so as to ensure equitable gender participation in the project. The principle of equal opportunity shall apply both to the GRS staff involved in the project and project members participating from contracting authority/ies. Every effort will be made to ensure broad gender representation among all participants.

Environment and climate change

Not applicable

Minorities and vulnerable groups

Minority and vulnerable groups' concerns will be reflected in all activities of the project.Participation in the project activities will be guaranteed on the basis of equal access regardless of racial or ethnic origin, religion or belief, disability, sex or sexual orientation.

- Conditionality and sequencing

This Twinning Project Fiche has been drafted in close cooperation with the Georgian counterpart, which commits itself to provide the contributions stated in the Fiche. They include such as:

- Strong commitment and support of GRS management to the Project implementation

- Strong involvement and commitment of GRS staff at all levels

- Assigning dedicated staff to activities connected with the Project

- Ensuring coordination between departments and institutions connected with the Project

- Ensuring access to indispensable information and documents

- Supply of office room for the RTA for the entire duration of the Project, including access to computer, telephone, internet, printer, photocopier

- Adequate conditions for the STEs to perform their work while on mission to the BI

- Providing suitable venues and equipment for the training sessions and meetings that will be held under the Project

- Designating a GRS counterpart for each MS expert

Significant changes in the GRS staff could be of a significant risk for the successful implementation of the Project. This primarily refers to professional staff having participated in the project design and those having knowledge of the English language.

Support of the Project from the GRS side requires significant labour costs not yet envisioned. In order to successfully implement the Twinning Project it is regarded as important that the GRS management take measures to ensure appropriate staffing – both in volume and quality - and motivation for participation in the TWG Project and achieving the mandatory results jointly with the EU Partners.

The ‘language barrier’ may become a critical issue of project implementation: most probably practically every meeting, discussion and workshop will require interpretation services and all presentations and technical material must be translated beforehand. This will pose serious strain on the Project’s and GRS’ capacities but also may double and sometimes even triple the time required and planned for each activity. GRS management is advised to take steps to improve the situation as possible yet before the Project start.

| Glossary: | Abbreviation Meaning |
| --- | --- |
| BI | Beneficiary Institution |
| CA | Competent Authority |
| CIS | Commonwealth of Independent States |
| DG | Directorate General |
| DG TAXUD | Directorate General Taxation and Customs Union |
| DCFTA | Deep and Comprehensive Free Trade Agreement |
| EC | European Commission |
| EEC | European Economic Community |
| ENP (AP) | European Neighbourhood Plan (Action Plan) |
| ENPI | European Neighbourhood Plan Instrument |
| EU | European Union |
| EUR | The European Union Currency ‘Euro’ |
| GEPLAC | Georgian European Policy and Legal Advice Centre |
| GRS | Georgia Revenue Service |
| IFC | International Finance Corporation |
| IMF | International Monetary Fund |
| MOF | Ministry of Finance |
| MOU | Memorandum of Understanding |
| MS | Member State |
| MSA | Member State Administration |
| MSME | Micro, Small, Medium sized Enterprises |
| OTA | Office of Technical Assistance (U.S. Treasury) |
| PAO | Programme Administration Office |
| PCA | Partnership and Cooperation Agreement |
| PL | Project Leader |
| PSC | Project Steering Committee |
| RS | Revenue Service |
| RTA | Resident Twinning Adviser |
| STE | Short Term Expert |
| TA | Technical Assistance |
| ToT | Training of Trainers |
| TAIEX | Technical Assistance Information Exchange Unit |
| USAID | United States Agency for International Development |
| VAT | Value Added Tax |

ANNEXES TO PROJECT FICHE

- Logical framework matrix in standard format

- Implementation chart

- Organisational chart of the Revenue Service of Georgia

- List of departments and divisions within the tax side of the Georgia Revenue Service

Annex 1.	Logical Framework Matrix for Strengthening Administrative Capacity of the Georgia Revenue Service in Taxation

| Strengthening Administrative Capacity of the Georgia Revenue Service in Taxation |  | Programme name and number | ENPI 2012 Annual Action Plan |
| --- | --- | --- | --- |
| Ministry of Finance |  | Contracting period expires: | Disbursement period expires: |
|  |  | Total budget: EUR 1 300 000 |  |
| Overall objective | Objectively Verifiable Indicators | Sources of Verification |  |
| The development of an efficient and effective tax administration system in harmony with the economic and financial interests and activities of businesses and citizens of Georgia. | - Positive EC opinion on the progress made. - Positive public opinion. | - EC Regular Report on progress by Georgia in implementation of the ENP Action Plan priorities (and National Indicative Programmes beyond 2013). - Evaluation of statements/polls from public/private sector. |  |
| Project purpose | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| The purpose of this project is to strengthen the administrative capacity of the Revenue Service of Georgia in line with the European Union and international standards in the following fields: - Tax control – to continue improving the risk analysis system and strengthen the control capacity of staff, and to introduce computer audit in the control work - Enforcement of tax debts – to improve and implement instructions that will increase tax collection - Taxpayers’ services – improve the public trust and legal certainty - Legislation – to provide analysis, recommendations and road maps in the fields of VAT and Excise to ensure implementation according to EU Acquis and Association Agreement - Human resources – to improve and implement techniques that will provide professional development for Revenue Service staff | - New and amended tax control measures are implemented. - Instructions for improved debt management are in place. - Procedures to promote public trust and legal certainty in Revenue Service are in place. - Recommendations and road maps for alignment of national VAT and Excise legislation with EU legislation are prepared. - Legislation for Council Directive 2007/74/EC is drafted. - Improved and new techniques for professional development of staff are in place. | - EC Regular Reports on progress by Georgia in implementation of the ENP Action Plan priorities (and National Indicative Programmes beyond 2013) - Government reports - Project reports | - Commitment and support of GRS management. - Adequate resource allocation. - Sufficient capacity within GRS to absorb the assistance provided. - Trained staff is retained. - Timely availability of qualified and suitable STEs by Twinning partner. |
| 3.3 Results | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| 1.Tax control measures promoting control efficiency and coverage are improved, developed and implemented. | 1.1 Report prepared with proposals for amendments and development of criteria for risk analysis system for audit selection. 1.2 Business sector guide(s) produced for future use of control staff. 1.3 Control staff trained in: a) specific taxation issues such as e.g. large taxpayers, tax haven issues, permanent establishments), b) computer audit, c) current control procedures and d) risk assessment 1.4 Software for computer audit is developed and in use. 1.5 Report on recommendations for the current control procedures prepared. 1.6.Guidelines produced for: a) computer audit, and b) current control procedures 1.7 Internship and Study visits carried out for: a) computer audit, b) current control procedures, and d) risk assessment for audit and current control selection. 1.8 Legislation drafted for: a) computer audit, and b) current control procedures. 1.9 Risk criteria to assist in selection of taxpayers to be subject to current control in place. | - Reports on risk analysis system for audit, current control procedures, and risk assessment measures for current control. (Indicator 1.1, 1.5) - Business sector guide(s) (Indicator 1.2) - Training materials (Indicator 1.3) - Feedback evaluation sheets (training) (Indicator 1.3) - Software for computer audit (Indicator 1.4) - Guidelines (Indicator 1.6) - Internship and Study visit reports (Indicator 1.7) - Draft legislation (Indicator 1.8) - STEs reports (All indicators) - Project Interim reports (All indicators) - Project Steering Committee (PSC) Meeting minutes (All indicators) - Project Final report (All indicators) | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 2. Amended and new instructions are in place to improve debt management systems. | 2.1 Report prepared with proposals of new measures to be implemented and possible amendments to existing measures. 2.2 Legislation is drafted for debt enforcement measures. 2.3 Measures for debt enforcement are implemented. 2.4 Study visit to an MS is carried out to experience practical use of debt enforcement procedures to be implemented by GRS. 2.5 Staff is trained in debt enforcement procedures implemented by GRS. 2.6 Staff is trained in cooperation and exchange of information between tax administrations for recovery purposes. 2.7 Report is prepared on recommendations for GRS practices in cooperation and information exchange for recovery services. | - Report on debt enforcement measures (Indicator 2.1) - Draft legislation (Indicator 2.2) - Study visit report (Indicator 2.4) - Training materials (Indicator 2.5, 2.6) - Feedback evaluation sheets (training) (Indicator 2.5, 2.6) - Report on recommendations for cooperation and information exchange for recovery purposes (Indicator 2.7) - STEs reports (All indicators) - Project Interim reports (All indicators) - PSC Meeting minutes (All indicators) - Project Final report (All indicators) | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 3. The Revenue Service has developed and improved processes and procedures in their tax related services | 3.1 Reports delivered on: a) recommendations for improvements of taxpayers’ services in accordance with EU best practices delivered. b) recommendations for call centre delivered. c) findings and recommendations on refund scheme for income tax for individual prepared. d) recommendations for amended work procedures for elimination of double taxation e) recommendations on Advance Tax rulings, Public rulings and involving private sector in law-making f) recommendations regarding production losses/inventory shrinkage g) appeal process in GRS 3.2 Staff is trained in: a) work procedures for elimination of double taxation in accordance with double taxation agreements b) appeal process. 3.3 Guideline produced for elimination of double taxation according to double taxation agreements. 3.4 Study visit to MS carried out to gain experience regarding call centres, service centres, refund schemes for tax allowances, single tax account | - Reports on: a) improvement of taxpayer services in accordance with EU best practices b) call centre c) refund scheme for income tax for individuals d) elimination of double taxation e) Advance Tax Rulings, Public rulings, and private sector involvement in law-making f) production losses and inventory shrinkage g) appeal process (Indicator 3.1) - Training materials (Indicator 3.2) - Feedback evaluation sheets (training) (Indicator 3.2) - Guideline (Indicator 3.3) - Study visit report (Indicator 3.4) - STEs reports (All indicators) - Project Interim reports (All indicators) - PSC Meeting minutes (All indicators) - Project Final report (All indicators) | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 4. Recommendations for alignment of national VAT with EU Acquis in the field of EU VAT common system prepared in line with Association Agreement. | - Report delivered on result of gap and needs analysis (GNA) to establish divergences between Georgian Tax Code and EU VAT Directives and to establish articles where assistance with interpretations is needed. 4.2 Workshops conducted for specialised staff in established areas according to GNA. 4.3 Action plan/road map for legislative and procedural changes to be implemented in accordance with EU VAT Directives delivered. | - Gap and Needs Analysis report on divergences between Georgian Tax Code and EU VAT Directives (Indicator 4.1) - Workshop reports (Indicator 4.2) - Evaluation sheets (workshops) (Indicator 4.2) - Action plan/road map (Indicator 4.3) - STE reports (All indicators) - Project Interim reports (All indicators) - PSC Meeting minutes (All indicators) - Project Final report (All indicators) | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 5. Recommendations for alignment of national Excise legislation with EU Acquis in the field of Excise directives prepared in line with Association Agreement and draft legislation prepared for implementation of Council Directive 2007/74/EC of 20 December 2007 on travellers’ allowances – section 3 on quantitative limits. | 5.1 Report delivered on structural and procedural changes needed in excise legislation and procedures to harmonise with and fulfil obligations according to EU legislation. 5.2 Action plan/road map for legislation and procedures to be implemented in accordance with EU Excise Directives delivered. 5.3 Legislation to be implemented in accordance with Council Directive 2007/74/EC drafted. | - Report on structural and procedural changes needed according to EU Excise legislation. (Indicator 5.1) - Action plan/road map. (Indicator 5.2) - Draft legislation. (Indicator 5.3) - STE reports (All indicators) - Project Interim reports (All indicators) - PSC Meeting minutes (All indicators) - Project Final report (All indicators) | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 6. The Human Resources Department has implemented new techniques to assist the provision of professional development to the Revenue Service staff. | 6.1 Report on findings of analysis and recommendations for professional development in GRS delivered. 6.2 Analysis of current skills and techniques in Training Needs Analysis (TNA) in HR department carried out and report on findings delivered. 6.3 Analysis of current techniques and skills in Job Task Analysis (JTA) in HR department carried out and report on findings delivered. 6.4 HR staff trained in: a) TNA, b) JTA 6.5 Guidelines prepared for: a) TNA, and b) JTA. 6.6 Report delivered with recommendations for measures to be implemented to further develop e-learning concept. 6.7 Measures implemented to that will make e-learning concept more utilized and functional within GRS. 6.8 Report delivered with recommendations for performance evaluation and performance indicators. 6.9 Performance evaluation methods and performance indicators implemented in GRS. | - Reports on: A) for professional development in GRS. (Indicator 6.1) B) on GRS staffs ‘current techniques and skills in TNA, (Indicator 6.2) C) GRS staffs ‘current techniques and skills in JTA (Indicator 6.3) - Training materials. (Indicator 6.4) - Feedback evaluation sheets (trainings) (Indicator 6.4) - Guidelines (Indicator 6.5) - Reports on: A) recommendations for further development of e-learning concept (Indicator 6.6) B) recommendations for performance evaluation and performance indicators (Indicator 6.8) - STEs reports (All indicators) - Project Interim reports (All indicators) - PSC Meeting minutes (All indicators) - Project Final report (All indicators) | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 3.4 Activities | Means (indicative) | Costs | Assumptions |
| General: | Twinning project: 18 months; STEs 625 week days (wd) | EUR 1.300.000 |  |
| # Organise Kick-off Conference and Steering Committee |  | RTA + PL Interpretation Translation |  |
| Organise final “Closing conference” |  | RTA, PL, STEs Interpretation Translation |  |
| 3.4.1. Tax control measures promoting control efficiency and coveage are improved, developed and implemented. |  |  |  |
| 3.4.1.1 Further development of the risk analysis system | STE will analyse and assess the current risk analysis system, available information and criteria. Need for further information from different sources such as third parties, returns and audits system will be assessed. Proposals for amendments to be implemented and development of criteria according to assessment prepared in report. If possible implement new criteria in risk analysis system. | STE – 15 wd Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 3.4.1.2 Development and production of Business sector guide(s) | The RTA will together with BA and other involved donors decide on business sector(s) to be covered. Sufficient number of audits will be conducted with support from STE(s). Results and experiences of audits are analysed and reported in business sector guide(s). | RTA, STE(s) – 75 wd Interpretation |  |
| 3.4.1.3 Training of auditors in specific taxation issues | The RTA will together with BA carry out an analysis of which specific taxation issues (e.g. large taxpayers, permanent establish-ments, tax haven issues) are to be included in the trainings. RTA and STE(s) will then design a training programme in accordance with the specific needs and level of know-ledge of the participants in the trainings. STE(s) will produce training materials. STE(s) and RS to identify 15-20 staff to be trained according to Training of Trainers (ToT) methodology. Training sessions are combined with possibility to practical on-the-job support. | RTA, STEs – 25 wd Translation Interpretation |  |
| 3.4.1.4 Develop software/programme for computer audit (audit technique to extract information from taxpayer’s accounting system) in tax control | STE and GRS to analyse the most common accountings systems used in Georgia. GRS and STE to assess requirements needed to develop the software and produce technical spe-cification. GRS IT staff to develop software under guidance of STE. | STE – 25 wd Interpretation |  |
| 3.4.1.5 Draft necessary legislation for computer audit | STE will together with GRS staff assess the legal conditions for implementing computer audit as an audit tool in GRS. Legislative changes to be proposed. Draft legislation to be prepared by STE in cooperation with GRS staff. | STE – 5 wd Interpretation |  |
| 3.4.1.6 Implement the use of computer audit in tax control | STE together with GRS will select 5-10 auditors with good IT knowledge and skills to be trained as computer auditors using the new developed software. STE to produce training materials and conduct training. GRS trainees to perform sufficient number of computer audits under supervision by STE to ensure the capacity of the GRS trainees. | STE – 60 wd, Interpretation, Translation |  |
| 3.4.1.7 Internship for computer audit | MS Administration (MSA) to arrange internship in MS for two GRS computer audit trainees to work alongside computer auditors in other EU country for 20 working days. The internship should also encompass the study of other electronic means and equipment that MS use in tax control/investigation, e.g. for analysis of cash registers, mirroring of hard disks, and the legal requirements for their use in MS. Study visit report to be prepared by trainees after visit. | Internship: 2 flights, 2x27 per diems |  |
| 3.4.1.8 Produce guideline for computer audit | STE produces guideline for computer audit together with GRS staff based on the developed software and the experiences made during trainings and audits carried out. | STE – 10 wd Interpretation |  |
| 3.4.1.9 Prepare recommendations for the Current Control procedures: chronometric examination (recordings of goods/services produced/supplied by taxpayer), test purchase, observation, control of cash registers and inventory (stock-taking) | STE will assess the current control procedures that the Monitoring Department of GRS carry out as specified in the Tax Code of Georgia, and prepare report with proposals for possible amendments to procedures. Proposals to be reviewed by GRS and in coordination with STE identify the amended procedures to be implemented. STE will support in implementing procedures. | STE – 10 wd Interpretation |  |
| 3.4.1.10 Draft necessary legislation for amended Current Control procedures to be implemented | STE will together with GRS staff assess the legal conditions for implementing current control procedures according to findings of activity 3.4.1.9. Legislative changes are proposed. Draft legislation to be prepared by STE in cooperation with GRS staff. | STE – 5 wd Interpretation |  |
| 3.4.1.11 Conduct Study visit to MS to experience practical use of Current Control procedures | MSA arranges 5 day study visit to a MS partner of the Twinning where the current control procedures according to activity 3.4.1.9 are currently in use. There will be 4 GRS staff, mainly managers, participating in the study visit and they will have the possibility to experience the practical use of the current control procedures, especially inventory (stock-taking). Study visit report to be prepared with experiences and conclusions made. | Study visit: 4 flights, 4x7 per diems |  |
| 3.4.1.12 Train staff in Current Control procedures | STE will develop training materials and train 10 GRS staff in the current control procedures in accordance with findings of activity 3.4.1.9. Training is conducted with ToT approach. | STE – 10 wd Interpretation Translation |  |
| 3.4.1.13 Produce guidelines for current control procedures | STE to produce guidelines for current control measures together with GRS staff based on findings of assessment and the experiences made during study visit and trainings carried out. | STE – 10 wd Interpretation |  |
| 3.4.1.14 Develop and implement risk assessment measures for Current Controls | STE will analyse available information and propose risk assessment measures to be implemented. Proposals should include information and criteria to be used in the existing risk analysis system that GRS have. GRS reviews proposals and implements chosen measures under guidance of STE. | STE – 20 wd Interpretation |  |
| 3.4.1.15 Study visit for risk assessment for Audit and Current Control selection | MSA arranges study visit to MS to study risk analysis systems and criteria used for both audit and current controls for 5 GRS staff for 5 working days. Study visit report to be prepared by participants after visit stating findings and conclusions made | Study visit: 5 flights, 5 x7 per diems |  |
| 3.4.1.16 Train staff in risk assessment measures | STE will develop training materials and train 5 GRS staff in risk assessment measures according to ToT approach. | STE – 5 wd Interpretation Translation |  |
| 3.4.2 Amended and new instructions are in place to improve debt management systems |  |  |  |
| 3.4.2.1 Assess current situation for debt enforcement and establish new and/or amended measures identified during assessment to be implemented (such as postpone of debt payment, debt relief, instalment plans and write-off) | STE will assess current situation and prepare report with proposals for possible debt enforcement measures to be implemented and amended. Proposals to be reviewed by GRS, and in coordination with STE identify the measures to be implemented. STE will support in implementing measures. | STE – 15 wd Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 3.4.2.2 Establish evaluation methods for measuring effectiveness of enforcement procedures | STE assesses current situation regarding measuring the effectiveness of enforcement and prepares a report with recommendations on evaluation methods to be implemented. | STE – 10 wd Interpretation |  |
| 3.4.2.3 Draft necessary legislation for debt enforcement measures to be implemented | STE will together with GRS staff assess the legal conditions for implementing debt enforcement measures according to activity 3.4.2.1. Legislative changes are proposed. Draft legislation to be prepared by STE in cooperation with GRS staff. | STE – 5 wd Interpretation |  |
| 3.4.2.4 Conduct Study visit to MS to experience practical use of debt enforcement measures to be implemented by RS | MSA to arrange 5 day study visit to a MS Partner of the Twinning where the debt enforcement measures according to activity 3.4.2.1 are currently in use. There will be 4 GRS staff, mainly managers, participating in the study visit and they will have the possibility to experience the practical use of debt enforcements measures to be implemented by GRS and to gain knowledge how tackle problems that can arise. Study visit report to be prepared with experiences and conclusions made. | Study visit: 4 flights, 4x7 per diems |  |
| 3.4.2.5 Train staff in debt enforcement measures to be implemented | STE will develop training materials and train 5 GRS staff in the debt enforcement measures that are chosen by GRS to be implemented. Training is conducted with ToT approach. | STE – 5 wd Interpretation Translation |  |
| 3.4.2.6 Prepare guidelines for debt enforcement measures to be implemented | STE together with GRS staff to prepare guidelines for debt enforcement measures to be implemented. | STE –10 wd Interpretation |  |
| 3.4.2.7 Train staff and draft recommendations for co-operation and exchange of information for recovery purposes | STE will develop training materials and conduct training of 5 GRS staff in how cooperation and exchange of information is used for recovery purposes. Training conducted with ToT approach. A report is drafted with recommendations for GRS based on EU practices. | STE – 10 wd Interpretation Translation |  |
| 3.4.3 The Revenue Service has developed and improved processes and procedures in their pursuit of activities that support taxpayers’ rights. |  |  |  |
| 3.4.3.1 Assess current taxpayers’ services and prepare recommend-dations in accordance with EU best practices for measures to be taken for improvement, (e.g. establish quality indicators, how to receive and analyse public feedback, special measures and tools for vulnerable groups). | STE assesses current taxpayers’ services and drafts a report with recommendations for improvement in accordance with EU best practices. | STE – 20 wd Interpretation | - Full commitment of all involved parties. - Availability of staff that will participate in project activities from the beginning to project completion |
| 3.4.3.2. Assess the taxpayers’ call centre and prepare recommendations for improvement. | STE assesses the taxpayers’ call centre and drafts a report with recommendations for improvement in accordance with the EU best practices. | STE – 5 wd Interpretation |  |
| 3.4.3.3 Prepare recommendations regarding the refund scheme for income tax allowance for individuals | A new scheme for refund of tax for income tax allowance for individuals is introduced from income year 2013, with refunds first being administered in 2014. STE assesses efficiency and effectiveness of legislation and working procedures. Report on findings and recommendations to be prepared. | STE – 5 wd Interpretation |  |
| 3.4.3.4 Prepare recommendations for work procedures regarding elimination of double taxation. | STE assesses current work procedures and knowledge level in GRS. Prepares report with analysis of EU practices and recommendations for amendments in work procedures. | STE – 10 wd Interpretation |  |
| 3.4.3.5 Train staff in work procedures for elimination of double taxation according to double taxation agreements | STE produces training materials and trains 10 GRS staff in work procedures according to ToT methodology. | STE – 5 wd Interpretation Translation |  |
| 3.4.3.6 Draft guideline for elimination of double taxation according to double taxation agreements | In accordance with findings during activity 3.4.3.4 and 3.4.3.5 the STE together with GRS staff will produce guideline for work procedures for elimination of double taxation | STE – 5 wd Interpretation |  |
| 3.4.3.7 Prepare recommendations for GRS regarding Advance Tax Rulings, Public Rulings/recommendations and involvement of private sector in law-making | STE assesses the current situation in GRS regarding Advance Tax Ruling, Public Rulings/Recommendations, and Involving private sector in law making. STE during assessment holds discussion workshops with 5 GRS staff to share experiences. Report to be prepared regarding findings and with recommendations for possible implementations by GRS based on EU practices. | STE – 15 wd Interpretation |  |
| 3.4.3.8 Prepare recommendations regarding production losses/inventory shrinkage for different business sectors | STE analyses EU practices regarding production losses/inventory shrinkage in different business sectors. STE assesses practices within GRS and recommends possible amendments. Prepare report on findings of analysis and assessment, with recommendations on measures for GRS to implement. | STE – 5 wd Interpretation |  |
| 3.4.3.9 Conduct study visit to MS for GRS gain experience in operation of service centres, call centres, refund schemes for tax allowances, single tax account | MSA arranges study visit to a MS Partner of the Twinning where 3 GRS staff will have the possibility to gain operational experience in the different fields during 5 working days. Study visit report to be prepared with experiences and conclusions made. | Study visit: 3 flights, 3 x 7 per diems |  |
| 3.4.3.10 Prepare recommendations regarding appeal process in GRS | During the work plan preparation MSA and GRS will identify all stakeholders (e.g. Ministry of Finance, U.S. Treasury (OTA) project, Business Ombudsman) in the activity, and also have close coordination with the U.S. Treasury (OTA) project to ensure that duplication and overlap do not occur. STE analyses and assesses GRS practices regarding appeal process in tax administration and court, covering both legal and formal basis and requirements for appeals, and the procedures regulating the appeal process. STE prepares report with findings and recommendations for measures to be implemented based on EU practices. Stakeholders will be involved and informed at all stages of the activity. | STE – 10 wd Interpretation |  |
| 3.4.3.11 Conduct trainings regarding amended appeal process in GRS | STE prepares training materials and to hold interactive trainings with 15-20 persons from Dispute Resolution Department, based on findings of activity 3.4.3.10. Trainings to be given using ToT methodology. | STE – 5 wd Interpretation Translation |  |
| 3.4.4 Recommendations for alignment of national VAT legislation with EU Acquis in the field of EU VAT common system prepared in line with Association Agreement |  |  |  |
| 3.4.4.1 Conduct a gap and needs analysis to establish divergences between Georgia Tax Code and EU VAT Directive, and to establish articles where assistance with interpretation is needed . | STE performs a Gap and Needs Analysis (GNA) of current VAT legislation in Georgia to establish divergences between Georgia Tax Code and its secondary legislation, and the EU VAT directives to be approximated according to the Association Agreement, and also to establish articles which need further interpretation and clarification assistance by STE. The result of the GNA is presented in a report. | STE – 55 wd Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 3.4.4.2 Conduct workshops with specialised staff in established areas according to Gap and Needs Analysis | STE conducts workshops with maximum 10 VAT specialists from Tax Policy Department, MoF, and Legal Department, Revenue Service, regarding the established areas where weaknesses exist to interpret and clarify EU legislation. Duration of workshops maximum 15 working days. Report on findings and conclusions made during workshops prepared. | STE -15 wd Interpretation |  |
| 3.4.4.3 Draft an action plan/roadmap for legislative and procedural changes to be implemented in accordance with VAT directives. | STE, Tax Policy Department, MoF, and Legal Department, GRS, jointly draft action plan/road map of the legislation and procedures to be implemented in accordance with VAT directives, also including recommendations for transitional provisions. STE will also during the course of activity 3.4.4.2 and 3.4.4.3 give lecture regarding experienced issues with implementation of VAT Directives in other country/ies for interested parties within GRS, MoF and other stakeholders that will be identified during the work plan preparation. | STE – 20 wd Interpretation |  |
| 3.4.5 Recommendations for alignment of national VAT legislation with EU Acquis in the field of EU VAT common system prepared in line with Association Agreement |  |  |  |
| 3.4.5.1 Prepare recommendations for structural and procedural changes needed in excise legislation and procedures | STE assesses structural and procedural differences between Georgia Tax Code and EU directives. Prepares report on findings and recommend changes to implement. | STE – 20 Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 3.4.5.2 Draft action plan/roadmap of necessary changes to be implemented | STE and staff of Tax Policy Department, MoF and Legal Department, GRS, jointly draft action plan/road map of the legislation and procedures to be implemented in accordance with Excise directives. | STE – 5 wd Interpretation |  |
| 3.4.5.3 Draft national legislation to be implemented in accordance with Council Directive Council Directive 2007/74/EC of 20 December 2007 on travellers’ allowances – section 3 on quantitative limits | STE and staff of Tax Policy Department, MoF and Legal Department, GRS, jointly draft legislation to be implemented. | STE – 10 wd Interpretation |  |
| 3.4.6 The Human Resources Department have implemented new techniques to assist the provision of professional development to the Revenue Service staff. |  |  |  |
| 3.4.6.1 Prepare recommendations for professional development of staff in the Revenue Service. | STE carries out analysis of EU practices for professional development in tax administrations and performs a gap analysis to establish weaknesses in GRS. Prepare report on findings and recommendations. | STE – 10 wd Interpretation | - Full commitment of all involved parties - Availability of staff that will participate in project activities from the beginning to project completion |
| 3.4.6.2 Assessment of techniques and skills in Training Needs Analysis of the HR Department, GRS | STE assesses current techniques and skills in practice in HR Department. Prepare report on findings. | STE – 5 wd Interpretation |  |
| 3.4.6.3 Conduct workshops in techniques and skills in Training Needs Analysis with the HR Department, GRS | STE holds in-depth workshops with 5-6 HR staff covering issues in accordance with assessment findings in activity 3.4.6.2. Report to be prepared on results of workshops. | STE – 5 wd Interpretation Translation |  |
| 3.4.6.4 Prepare guideline in Training Needs Analysis | STE together with HR staff prepare guideline for Training Needs Analysis. | STE – 5 wd Interpretation |  |
| 3.4.6.5 Assessment of techniques and skill in Job Task Analysis of HR Department, GRS | STE assesses current techniques and skills in practice in HR department. Prepare report on findings. | STE – 5 wd Interpretation |  |
| 3.4.6.6 Conduct workshops on techniques and skill in Job Task Analysis | STE holds in-depth workshops with 5-6 HR staff in accordance with assessment findings. Special attention to be given to how to determine knowledge and competences needed for specific job positions. Report on results of workshops to be prepared. | STE – 5 wd Interpretation Translation |  |
| 3.4.6.7 Prepare guideline for Job Task Analysis | STE together with HR staff prepares guideline for Job Task Analysis. | STE – 5 wd Interpretation |  |
| 3.4.6.8 Further development of e-learning concept within GRS | STE assesses current situation of e-learning practices within GRS. Report on findings to be prepared with recommendations for how to make e-learning concept more utilized and functional within GRS. GRS implements measures according to recommendations under guidance of STE. | STE – 20 wd Interpretation |  |
| 3.4.6.9 Development of performance evaluation methods and performance indicators within GRS | STE assesses current situation of performance evaluation and performance indicators in HR department. Report on findings and recommendations prepared. GRS implements evaluation methods and performance indicators according to recommendations under guidance of STE. | STE – 20 wd Interpretation |  |
|  |  |  | Preconditions |
|  |  |  | None |

Annex 3 Organizational chart of the Georgia Revenue Service

Administrative Department

Service Department

Tax Monitoring Department

Information Technology Center

PR and Marketing Department

Human Resources Department

Dispute Resolution Department

Audit Department

Customs Department

Department for International Relations

Legal Department

Deputy Director General

Deputy Director General

Deputy Director General

Deputy Director General

Director General

Annex 3 Organizational chart of the Georgia Revenue Service

| Name | Number of employees |
| --- | --- |
| Service Department | 503 |
| Information-Consultation Division | 48 |
| Call Center | 10 |
| Service Centers (16) | 209 |
| Prive | 30 |
| Information Processing Division | 91 |
| District Officers Division | 110 |
| Audit Department | 410 |
| Main Division of Audits | 310 |
| IT Division | 24 |
| Mediation Division | 8 |
| Audit Monitoring Division | 19 |
| Quality Control Division | 18 |
| Risk Management Division | 18 |
| Methodology Division | 6 |
| Monitoring Department | 377 |
| Monitoring Division | 46 |
| Analysis Division | 11 |
| Legal IssuesDivision | 20 |
| Current Control Division | 69 |
| Enforcement Measure Division | 35 |
| Expertise Division | 4 |
| Regional Divisions (7) | 145 |
| Division for Tax Offence Detection | 43 |
| Dispute Resolution Department | 65 |
| Court Litigation Division | 20 |
| Division of Appeals | 30 |
| Tax Agreement Division | 10 |
| Human Resources Department | 20 |
| Human Resources Management Division | 8 |
| Human Resources Development Division | 8 |
| Department for International Relations | 23 |
| Legal Department | 26 |

All official documents mentioned in section 2.3 can be obtained here http://www.eeas.europa.eu/georgia/

Organisational chart of the GRS is found in Annex 3.

There is a HR strategy being developed with assistance of the U.S. Treasury (OTA) project.

Activities under Result 6 will be coordinated with both the Twinning project for the Academy of MoF, and the U.S. Treasury (OTA) project, in order to avoid any duplication.