Twinning Project Fiche

- Basic Information

  - Programme: 		European Neighbourhood and Partnership Instrument – National Action Programme 2010 (CRIS no.ENPI/2010/22136)

  - Twinning Number:	EuropeAid/134492/L/ACT/MD - MD/13/ENP/FI/12

  - Title:	Consolidation and Strengthening the External Public Audit in

the Republic of Moldova

  - Sector:	Finance

  - Beneficiary country:	Republic of Moldova

- Objectives

  - Overall Objective:

To improve accountability and management of public funds in the RM through enhanced external audit capacity in conformity with recognized international audit standards and in line with European best practice.

  - Project purpose:

To support the Court of Accounts of the Republic of Moldova in improving its function, performance and impact.

  - Contribution to the EU-Republic of Moldova Partnership and Co-operation Agreement, the European Neighbourhood Policy Action Plan, and the ENP National Indicative Programme for Moldova

The project will contribute to the fulfilment of RM’s obligations stipulated in the Partnership and Cooperation Agreement (hereafter “the PCA”) between the European Union and the Republic of Moldova, which was signed on 28th November 1994 and entered into force in 1998. According the EU /Moldova European Neighbourhood Policy (ENP) - Action Plan adopted in February 2005, “Financial Control and related matters” are seen and figure under key areas to be addressed.

According to Article 42 of the Action Plan - “Sound management and control of public finances” encompasses improved “public finance management and transparency”, the “appropriate audit of budget revenue and expenditures” and last not least:

“External Audit” by ensuring “the establishment and adequate functioning of an independent Supreme Audit Institution in line with the internationally accepted and EU best practice external audit standards (INTOSAI standards – International Organization of Supreme Audit Institutions)”.

Much of other items falling under the aforementioned article 42 of the Action Plan have been addressed in the meantime. Some of them should be recalled here in summary and abbreviated form to situate the financial control and external audit aspects in the “starting” context of the PCA. They are relevant for the twinning project as developed in the section on “situation and background”, as concerning the promotion “of the development of appropriate administrative capacity to prevent and fight effectively against fraud and other irregularities affecting national and international funds. This aspect includes the establishment of well-functioning co-operation structures involving all relevant national entities”. As regards the “management and control of EU funds”, - “effective cooperation with the relevant EU Institutions and bodies in the case of on-the-spot checks and related inspections shall be ensured. A most important objective has been the “development of a strategy and policy paper for the public internal financial control system (managerial accountability and internal audit)” and the following establishment of a “legislative framework for public internal financial control”. A “gradual harmonization of control systems and practice with internationally agreed standards (IFAC, IIA, INTOSAI) and methodologies” has been aimed for, as well as an orientation and alignment “with EU best practices for the control and audit of public income, expenditure, assets and liabilities”.

The ENPI Country Strategy Paper 2007-2013 for Moldova mentions in general terms, that EC assistance is supporting the process of reform in Moldova, as envisaged in the PCA and the ENP Action Plan.

Twinning is seen as one of the tools for Comprehensive Institution Building (CIB) implementation as confirmed in the NIP and the CIB Programme 2010 agreements.

The Twinning project will assist the Court of Accounts (CoA) (i) to consolidate its achievements following its first Strategic Development Plan (SDP) 2006 – 2010 established in the context of Public Administrative Reform efforts for Central Public Authorities (CPA) and (ii) contribute to further enhance its function, performance and impact as set out in the goals and objectives of its second SDP covering the years 2011-2015.

- Description

  - Background and justification

In the context of the Partnership and Cooperation Agreement (PCA) between the European Union and the Republic of Moldova and based on Article 42 referred to above of the EU/Moldova ENP Action Plan, the Twinning project provides the opportunity to bring definitely in line the Courts activities and outcome with the internationally accepted external audit standards and EU best practice. It also offers the opportunity to make the Courts voice heard on the legal approximation of the country’s legislation with the EU Acquis in all domains of the audit of the management of public funds: regardless if they are from domestic or external sources or related to EU fund flows.

This twinning project is designed at a time when the country is preparing and negotiating its association and way forward, intending a systematic approximation of its legal and regulatory framework towards the EU Acquis. In this perspective, the CoA twinning project offers the opportunity for an enhanced cooperation between the Republic of Moldova and the European Union.

The country’s adherence to the concept of Public Internal Financial Control (PIFC) promoted and supported by the EU is demonstrated through a Twinning project having started in November 2011 for a twenty months period. Its aim is to strengthen Public Financial Management in the Republic of Moldova with an overall objective to improve the management of public financial control in the RM in line with internationally recognized standards and European best practices. Its special purpose is to support the Ministry of Finance to improve the Public Internal Financial Control. Considering these developments, it seems only logical to address and support efforts for a strengthened public external audit function as a subject  for a further twinning project and as requested by the country.

As a matter of fact the ongoing reform of the Governments internal control systems and practices has and will deeply change the control environment of Government, of Parliament and also for the Court of Accounts. Through the reform best internal audit- and Financial Management and Control (FMC) practices are introduced, based on previous strategies and the adoption of a Law on PIFC. The roll out of the reform assisted by the PIFC Twinning project reaches all levels of Governance. It is a decisive step for the RM’s aim to end with the “system of vertically organized executive power, that has prevailed so far” - also in the domain of control of public funds management. It is a step away from the former set up of controls and respective institutions empowered. As it has been formulated for the desirable decentralization approach in general and the objective to rely on “a coordinated system of decentralized, transparent and flexible entities” with an “adequate and properly managed resource base”, the reform of Government internal control of public funds is under way in this perspective. Decentralising of power and ensuring local autonomy as a central requirement of the EU/RM partnership has started in the domain of control in recent years. It will however take a certain time and require new political decisions for further decentralized governance in this area.

The former programme of external control as “financial revision” as carried out by the Financial Control and Revision Service (FCRS), as well as the “external control” through controllers at the Court of Accounts are all being replaced at respective levels of Government. They are replaced first of all by decentralized and ”internalized” control practices as described earlier. Public managers will be hold accountable for sound financial management, in terms of economy, efficiency and effectiveness, following “FMC” practices and the establishment of independent internal audit units. A future “Financial Inspection” service of the Ministry of Finance will act for Government to protect its financial interests as well as those of the European Union. Its role and tasks will be mainly geared at the prevention, mitigation and follow up of irregularities and fraud observed. A Government regulation is under preparation and yet pending. The “Centre for Combating Economic Crime and Corruption” will undergo a reorganization as national centre and according to a related proposal under actual Parliaments examination, will (i) concentrate its activities on fighting against corruption and (ii) will be subordinated in the future to Parliament will continue its activities. Finally the Court of Accounts of the Republic of Moldova is acting as a Supreme Audit Institution and is ensuring the public external audit function in line with international standards.

The Court is aiming at an increased interaction with Parliament and Government and generally stronger responsiveness of audited entities. The increased impact of its activities and follow up of its recommendations shall ultimately contribute to an improved management of public funds in the RM and awareness of civil society on the Court’s role.

Substantial assistance of the CoA since 2005 through the Swedish National Audit Office (SNAO) and through the World Bank (WB) 2007 -2011have allowed the Court to meet increasingly the prerogatives of a Supreme Audit Institution. The WBs’ assistance ended in 2011 and the Swedish bilateral assistance will end 2012.It is hoped by the Court that both assistances will continue after 2012: through a World Bank/Russia Trust Fund financed project actually proposed and through further assistance through Sweden.

The Twinning design suggested in this draft twinning project fiche takes into account this eventuality. It considers and relies on the Courts’ strong commitment and ambition for further development of its competence and performance. It reflects the Court’s vision, goals and objectives as laid down in its SDP 2011-2015.

The Twinning project can make an important and decisive contribution to further implement the SDP 2011-2015 of the CoA in the intended 21 months period falling into 2013-2015. Though substantial in its planned resource endowment it cannot cover entirely all the activities suggested by the SDP and in all its aspects. The Court has proven successfully its capacity to absorb important external assistance and is confident to accommodate continued and strongly reinforced assistance particularly with a view to the strong challenges it faces.

    - Legal basis

The Law on the Court of Accounts - adopted as of the 5th of December 2008 (No. 261) and coming into force from the 1st of January 2009, guarantees its independence – as based on and stipulated in the Constitution, Article 2 of the Law in principle and through its Article 6 addressing its organisational, functional, operational and financial independence.

The Court of Accounts is assigned as responsible institution for the external audit of the management of public funds in article 13 of the “The Law on Budgetary System and Budgetary Process”.

The Law on the CoA, as inspired by EU standards and developed with support of the Swedish National Audit Office (SNAO), forms the basis for the Courts gradual transformation from an external control institution into a Supreme Audit Institution. It reflects (i) the Lima Declaration of Guidelines on Auditing precepts’ key principles as those of the Mexico Declaration on SAI Independence and allows (ii) SAI to progress in its performance of the external audit function in line with INTOSAI standards.

A first example of the new Laws’ key changes and move away from types of external financial control to regularity audit is given through the audits performed by the CoA on Government reports regarding the execution of the State budget, the National Social Insurance Fund/Budget (BASS) and the Mandatory Health Insurance Fund/Budget (FAOAM) for the past budget exercise 2009 (all budgets under the National Public Budget together with Administrative Territorial Units Budget (BUAT).The CoA has successfully performed a number of audits in recent years set out as Policy Matrix conditions for EU budget support programmes.

  - Linked activities

EU Twinning Project PIFC

Following support of the Ministry of Finance for the implementation of PIFC by a technical assistance project Public Financial Management Project through a World Bank Trust Fund launched in January 2006, the PIFC Twinning project started in November 2011 through institutions of Sweden (Financial Management Authority) and the Netherlands (The National Academy for Economy and Finance). It offers a number of potential synergies for internal as well as external auditors. It operates on the basis of four components, aiming at: (1) an enhanced capacity of the Central Harmonisation Unit in the MF to oversee the implementation of PIFC in Moldova, (2) an updated legislative and normative framework for PIFC,(3) a strengthened - Financial and Managerial (FMC) control and (4) a strengthened Internal Audit Capacity.

Of either direct or indirect interests of the CoA and apart from its general interest in the outcome of the twinning for the Government internal new control environment, are activities of the PIFC twinning project such as especially the results of a review of the operational manual for Internal Audit, as the development of  a new methodological norm (guide) for IT systems audit, as the development of a new methodological norm (guide) on sampling techniques, as the development of  a new methodological norm (Guide) about the role of the auditor in relation to fraud and corruption, as for instance developed  options for certification of internal auditors.

The project will be in an advanced and almost final stage when the CoA twinning is likely to start in the second quarter of 2013.

Similarly the CoA Twinning project will create potential opportunities for enhancing the knowledge and performance of internal controllers/auditors of Government.

Swedish Bilateral Assistance to the Court of Auditors through the Swedish National Audit Office (SNAO) (2006-2012) and eventually beyond

The SNAO had and has an outstanding role in accompanying the CoA since 2007 in its transition to a Supreme Audit Institution. Supporting the goals and objectives of the first and second Courts SDP for major elements - within phase 1 of the cooperation 2007 - 2009 and the current phase 2010-2012, the Swedish bilateral cooperation has been concentrated on developments in the following areas:

First of all and following a new concept of external audit introduced by the Law on the CoA in 2008, the SNAO supported the development of the internal normative framework to conduct regularity, performance and other types of audits and the related capacity building of the methodology department. Auditor profession building assistance has focussed on regularity/financial audits and the quality framework system; Modern management practice has been supported regarding human resource development, internal information and communication. Assistance for institutional strengthening helped to set up the internal audit function at the Court and its consolidation, as well as to develop its internal public financial control system; assistance to introduce a time-recording system will enhance costing and strategic planning of activities. In support of securing a greater impact of the Courts activities’ the external communication has been enhanced with respect to the communication with Parliament on the annual report in first instance and the management of the cooperation project and of international relations.

Training has been a privileged instrument for capacity building.

Financial support provided by the SNAO allowed the CoA amongst others (i) to edit the Annual Report in a standard format and ensure a larger dissemination to the Parliament, Government, CPA’s, civil society, superior education institutions and others,(ii) to allow public auditors to actively participate at conferences and workshops, organized by EUROSAI and INTOSAI, and (iii) employees of the CoA to continue learning English.

It is yet unknown if the SNAO assistance will be granted beyond 2012, but activities of the twinning project can be adjusted later and at the start of the project to avoid overlaps and ensure synergies as well as considering the absorptive capacity of the Court.

World Bank support to the CoA through a Single Purpose Trust Fund

The Support Project of technical assistance for strategic development of the CoA, managed by the WB  through the Multi Donor/Single Purpose Trust Fund (UK/DFID) and Dutch Government (with a grant volume of 2.79 Million USD) approved in March 2007 and ending December 25th 2011 aimed at (i)-maintaining and developing the capacity and skills to conduct regularity, performance, and IT audits,(ii) improving the quality of audit work, (iii) implementing an improved IT capacity and (iv) improving human resources management.

To develop the audit capacity, with a view to ensure performance audits and IT audits to have a prominent place in the Court of Accounts activity, the TA received by the CoA included amongst others support for conducting 5 performance pilot audits and 3 IT pilot audits, for developing performance audit standards and a performance audit manual. Training for the teams of auditors engaged in pilot audits was provided to enhance new knowledge of the CoA about the IT audit processes, models and types of controls to be used during audit missions. Support to improving human resources management has been focussing on (i) designing a new HR management system; (ii) developing a detailed training plan and training trainers; (iii) training personnel in new HRM practices; (iv) establishing effective human resource planning systems.

Upcoming World Bank/Russia Trust Fund financed Project

Further assistance to the CoA is currently under planning and proposed with a financial volume of 1.2 Million USD and to be implemented starting at the same period as the twinning, mainly oriented to the same areas as the previous assistance as described above.

Sigma/OECD - Support to the Financial Control and Revision Service (FCRS)

Sigma consulting services in the period of 11/2011 to 9/2012 shall contribute to the Ministry of Finances’ efforts to develop a robust EU proof financial control framework. Improving interrelated issues between PIFC and Financial Inspection shall be clarified and improvements facilitated by drafting a development plan for the FCRS. A number of seminars shall raise awareness about the functioning of a financial inspection in a PIFC environment. The MFs’ Financial Control and Revision Service (FCRS) shall be assisted in harmonizing its activity within a financial inspection function according to good European practices. The assistance includes support to the ongoing process of drafting a Regulation in this respect.

  - Results

The mandatory results to be achieved by the project and their related measurable indicators are the following:

Component 1 Strengthen the Audit Capacities of the CoA

Mandatory result 1:

Built/strengthened capacities of the CoA in the area of performance audits, systems audits and EU funds audits

Indicators:

- Training Needs Assessment carried out;

- Training Plan developed, discussed and agreed;

- Training materials including at least 6 case studies  necessary for performance auditing, systems auditing and EU Funds auditing are developed and agreed;

- Two teams of auditors (max. 16 people) established and trained in system audit;

- One team of auditors (max. 8 people) established and trained in performance audit;

- One team of auditors (max. 8 people) established and trained in EU funds audit;

- Four study visits for 4 audit teams (max. 32 people) involved in the planned Pilot audits organised;

- Two system audits, one performance audit and one EU funds audit carried out by the 4 selected and trained groups;

- Two cold evaluations planned and carried out, including preparation of the check lists;

- An institutionalized team of trainers involved in the planned 4 Pilot audits (max. 8 CoA auditors) able to share accumulated knowledge to other auditors involved in EU funds auditing has been trained;

- New methodological and regulatory norms, especially the ones related to system audits and EU funds audits developed and approved.

Component 2 - Legal Reform

Mandatory result 2:

Revised and updated Legal Framework of the CoA

Indicators:

- The Draft Law on the CoA is revised,  updated and submitted for adoption to the Parliament;

- The internal regulations are revised and approved by the CoA according to the revised Law on the CoA;

Component 3 - Human Resources Management of the CoA

Mandatory result 3:

Revised and updated Human Resources Management of the CoA

Indicators:

- An improved Staff Appraisal System

- Training Needs Assessment procedure is established and operational

- Training Plan drafted and approved

- HR Management Policies revised in line with the EU standards and best practices.

- Job descriptions and competences statements for all levels of the CoA staff are established in accordance with the changes in the legal framework, the new audit procedures, the training programmes and the management policies.

Component 4  - Strengthen the interaction with the authorities of the Republic of Moldova and increase the impact of the Court of Accounts activities

Mandatory result 4:

Improved external and internal communication with the Parliament, the Government, civil society, media and other authorities leading to increased impact and enhanced visibility of the CoA with the above mentioned stakeholders.

Indicators:

- Benchmark Analysis on openness, transparency and visibility of the CoA with all stakeholders, developed and submitted to CoA management for consideration;

- Communication guidelines developed and operational;

- Regulation on the procedures regarding the relations between the CoA and the Parliament, drafted and submitted to the Parliament for adoption;

- At least three workshops to improve the communication between the CoA and  the Parliament, the Government (State Chancellery and Ministry of Finance) and other authorities are organised;

- Two study visits for CoA and Parliament members organised;

- At least three awareness raising events organised for the media and the civil society.

  - Activities

The activities mentioned in this Twinning fiche and the number of allocated working days per activity are only of indicative nature and can be later adjusted by agreement between the partner administrations.

3.4.1	General Activities

In addition to the activities related to the three core components of the twinning assignment, the project will also organize two general activities in order to ensure visibility at project start and present the project’s impact at the stage of completion. Furthermore, in order to ensure an effective management and monitoring mechanism, regular meetings of the Steering Committee will be organized.

Activity 0.1:	Project Inception and Kick-off Workshop

The first month of the project will be used for kick-off activities as well as establishment of the Project Office by the Resident Twinning Adviser (RTA) in the premises of the Court of Accounts. The RTA will also hire an Assistant (RTA Assistant) and a permanent interpreter/ translator, both to be recruited through an appropriate selection procedure.

During the inception period, the RTA will organise a kick-off meeting, with the purpose of providing a first official contact to all stakeholders involved in the project and presenting the project to the media and the public at large. In order to guarantee large public information about the start of the project, the meeting will be concluded with a press conference and a press release. The nature of this meeting will be operational, and will be attended by the EU Delegation to the Republic of Moldova, the PAO representative, the President and Members of the Court of Accounts, the Project Leader, the RTA and representatives of key stakeholders interested in and concerned by external audit, as well as representatives from the MS Embassies in Moldova. The Kick-off Meeting will give the participants the opportunity to receive detailed information about the project objectives, purposes and implementation plan.

Indicative number of allocated expert working days:

| MS: | RTA, Project Leader (PL) |
| --- | --- |
| MS Expertise (w/d): | 3 w/d (1 PL mission x 3 days) |

Activity 0.2: Project Completion Conference

During the last two months of the project, a closing conference will be organised at which the results of the project will be presented. Aim of this activity is to disseminate the project results and create public awareness. The roundtable will take place in Chisinau and all project stakeholders as well as key stakeholders interested in external audit will be invited to participate. The roundtable will be concluded with recommendations for follow-up actions and lessons learned for similar projects.

Indicative number of allocated expert working days:

| MS: | RTA, Project Leader (PL) |
| --- | --- |
| MS Expertise (w/d): | 3 w/d (1 PL mission x 3 days) |

3.4.2	Component 1: Strengthen audit capacities of the CoA

Mandatory Result 1 - Built/strengthened capacities of the CoA in the area of performance audits, systems audits and EU funds audits.

Activity 1.1: Training related to performance, system and EU funds audits and preparation of the necessary baseline assessments; study visits for audit teams organised:

- Identifying and institutionalising a team of auditors who will be involved in performance, system and EU funds audits;

- Prepare training needs analysis;

- Prepare training programme and modules for performance, system and EU funds audits;

- Identify actions for training on the job;

- Training on drafting audit reports and recommendations;

- Evaluation of obtained audit skills as a result of training program implementation;

- Providing of 4 study visits to EU MS for 4 audit teams (each 5 persons) involved in pilot audits.

Indicative number of allocated expert working days:

| MS Expertise (w/d): Details about the study visits: | 220 w/d (20 STE missions x 10 w/d; 20 w/d – Duration of the study visits will be 5 days in every EU country) |
| --- | --- |

Activity 1.2:	Creation and training of group of trainers specialized in performance/system and EU funds audits:

- Preparing of training cycles for trainers;

- Institutionalization of groups of specialized trainers;

- Training of trainers group.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 60 w/d (6 STE missions x 10 w/d) |
| --- | --- |

Activity 1.3:	Development and consolidation of CoA capacities to perform performance/system audits and audit of EU funds with the support of experts and their participation in audit missions, according to the new developed methodological and regulatory norms:

- Identification of general actions in view of preparing the 4 pilot audits and follow up audit actions;

- Practical exercises with the participation of experts with respect to audit activities;

- Identification/selection and preparing of pilot audits with the participation of experts;

- Immediate settlement of impediments appeared during audit process;

- Drafting manuals/guides (especially for system audit), as a result and on the base of performed pilot audits.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 160 w/d (16 STE missions x 10 w/d) |
| --- | --- |

Activity 1.4:	Joint cold evaluation of the quality of audits performed and elaboration of checklists for quality cold reviews:

- Training regarding cold evaluation of performance/system and EU funds audits;

- Evaluation at cold of two performance audits;

- Identification and document of check lists;

- Extension of learned practice regarding cold review of performance audits through training.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 60 w/d (6 STE missions x 10 w/d) |
| --- | --- |

3.4.3	 Component 2: Legal reform

Mandatory Result 2 - Revised and updated Legal framework of the CoA

Activity 2.1:	Reviewing the current Law of the CoA in line with the EU best practices and the regulations of international organizations in the field. Adjusting the Law in accordance with the new requirements and procedures. Assistance on passing the project through the legislative process:

- Analysis of national legal framework relevant to the activity of CoA;

- Reviewing and submitting proposals for the review of the national normative control framework aligned and harmonized with the EU best practices and the regulations of international organizations in the field;

- Assistance on passing the project through the legislative process.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 80 w/d (8 STE missions x 10 w/d) |
| --- | --- |

Activity 2.2:	Adjusting and revising internal regulations in accordance with changes in the legal framework:

- Analysing the international regulatory framework in the external audit field (the international audit standards) in comparison with the CoA’s regulatory framework;

- Updating and revising of the CoA’s regulatory framework in auditing in order to bring it in line with the international legal and regulatory framework;

- Create conditions for setting up and implementation of a meaningful significant knowledge base in the area of EU Acquis and especially regarding electronic library and thesaurus support.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 70 w/d (7 STE missions x 10 w/d) |
| --- | --- |

3.4.4 Component 3 - Human Resources Management of the CoA

Mandatory Result 3 - Revised and improved Human Resources Management of the CoA

Activity 3.1:	Establishing of Training Needs Assessment procedure, drafting and implementing the Stuff Appraisal System procedures:

- Gap analysis of current CoA practice referring to management and development of human resources (examination of norm regarding the status of civil servant and related constraints);Practical assistance to the HR Department to achieve a comprehensive training needs analysis based on information from individuals’ personal development plans and using information from Senior Managements’ view of the CoA’s outputs and effectiveness, and from the audit Methodology unit’s ongoing assessments against international standards and the quality control reviews.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 40 w/d (4 STE missions x 10 w/d) |
| --- | --- |

Activity 3.2:	Implementation of modern procedures of human resources management in line with the EU standards; revising job description and competences statements, in accordance with the changes in the legal framework:

- Assistance to the HR Department in setting criteria for assessing the benefits of possible qualification schemes for suitable auditors, to attract and act as a motivator for quality stuff;

- Practical assistance to the HR Department in developing a skills and regulatory framework for all grades, against which staff performance can be assessed in a more objective and consistent way;

- Seminars for all stuff and managers in setting clear and quantifiable work objectives;

- Seminars for all managers on how to undertake stuff appraisals;

- Practical assistance to the HR Department in assessing the results of a performance appraisal system, with the aim of ensuring fairness and consistency, this would cover training in project management and development of management skills in general;

- Provision of ongoing advice to the management of CoA.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 60 w/d (6 STE missions x 10 w/d) |
| --- | --- |

3.4.5 Component 4: Strengthen the interaction with the authorities of the Republic of Moldova and increase the impact of the Court of Accounts activities

Mandatory Result 4 - Improved external and internal communication with the Parliament, the Government, civil society, media, other authorities and the public at large leading to increased impact and enhanced visibility of the CoA with the above mentioned stakeholders

Activity 4.1:	Implement measures to stabilize, maintain and intensify efficient relations with Parliament, Government and public authorities; organising workshops to improve the communication between the CoA and other authorities:

- Gap analysis of current relations between CoA and Parliament/Government;

- Identify measures for intensified relations through a developed innovative concept to be agreed with partners;

- Measures to enhance routine practice based on the new concept;

- Implement pilot activities to promote new forms of cooperation.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 30 w/d (3 STE missions x 10 w/d) |
| --- | --- |

Activity 4.2:	Implement measures to stabilize, maintain and intensify efficient relations with media and civil society; organising awareness raising events for the media, the civil society and public at large:

- Preparing a model of adequate communication;

- Training of staff in view of improving the level of communication with audited entities;

- Sharing of CoA knowledge in view of increasing the confidence of audited entities and of civil society in the activities of the CoA by organizing round tables and workshops;

- Measures to improve the communication process with audited entities.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 30 w/d (3 STE missions x 10 w/d) |
| --- | --- |

Activity 4.3:	Promoting new efficient mechanism and measures enforcing stronger accountability of audited entities to follow CoA's recommendations and to intensify relations between CoA and audited entities:

- Analysis of current work process of implementation of CoA's recommendations as compared with best practices;

- Development of audit staff capacities to draft and consolidate the audit statements and recommendations;

- Elaborate necessary proposals to review the legislative and normative framework, as well as the institutional regulatory framework regarding accountability of audited entities in view of audit recommendations implementation;

- Establishing relevant instruments with respect to a fundamental and continuous approach to implementation of audit recommendations based on existing processes of risks’ appreciation.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 40 w/d (4 STE missions x 10 w/d) |
| --- | --- |

Activity 4.4:	Coaching of CoA's members for measures to increase the Courts impact on improved public funds management:

- Identify gaps and actions to increase the Court of Accounts impact and agree with CoA members on areas for coaching based on gap analysis;

- Identify and implement actions to promote the role and performance of Court members;

- Strengthen the Courts’ collegial action.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 40w/d (4 STE missions x 10 w/d) |
| --- | --- |

Activity 4.5:	Developing Benchmark Analysis on openness, transparency and visibility of the CoA with all stakeholders; developing guidelines for communication with all stakeholders (including a procedure guidence for Parliament and Government on follow-up of CoA's reports):

- Develop, issue and presentation of the Benchmark Analysis on openness, transparency and visibility of the CoA with all stakeholders;

- Establish joint working group and coordination mechanisms;

- Identify objective and content of procedural guide;

- Elaborate draft of procedural guides and its preparation for consultation;

- Assistance to bring the project through the legislative process.

Indicative number of allocated expert working days:

| MS Expertise (w/d): | 60 w/d (6 STE missions x 10 w/d) |
| --- | --- |

Activity 4.6:	Study visits for Court members and senior managers together with the involved Members of the Parliament in MS good practices of collaboration with European Court of Accounts and European Parliament to learn about the modalities of their interaction:

- Prepare the study missions to MS with good practices of collaboration with EU Court of Auditors and EU Parliament;

- Prepare and organize sessions (both within study visits and local working meetings) for the members of institutions involved in collaboration, as well as sharing of information and practices relevant to main areas of interaction between the Court and Parliament on issues to be discussed;

- Performing 3 study missions;

- Conclusions and analyses activities of lessons learnt, eventual actions to be identified for the future.

Indicative number of allocated expert working days:

| MS: | RTA |
| --- | --- |
| MS Expertise (w/d): | 20 w/d (2 STE missions x 7 w/d and 6 w/d for preparatory activities) Details regarding 2 study missions: 7 participants (Court of Accounts and Parliament) for a duration of 5 days for each study mission to 3 EU Member States’ institutions (SAI’s and respective Parliament bodies) |

3.5 Means/ Input from MS Partner Administration

3.5.1	Profile and tasks of the Project Leader (PL)

The Project Leader is supposed to coordinate the activities, disseminate project information among stakeholders, take part in discussions with the high level officials, present and defend project input and expected outputs, manage the project team, prepare project management reports, help overcome project related problems, and assist the RTA for continuous development of project initiatives. The PL will be expected to devote a minimum of 3 days per month to the project in his/her home administration. In addition, he/she will coordinate, from the MS side, the Project Steering Committee (PSC), which will meet in Moldova every three months.

Project Leader Profile:

- The Project Leader must be a civil servant with personal experience of minimum 7 years in the implementation of financial management and control;

- Senior civil servant or equivalent staff of a MS institution in a position that could let him/her fulfill the tasks associated to the Project Leader role;

- Specific experience in project management with focus on EU funded projects and in particular twinning would be an advantage;

- Very good command of written and spoken English;

- Strong leadership and problem solving skills.

Project Leader Tasks:

- Overall coordination, guidance and monitoring of the project;

- Preparation of project progress reports with support of RTA;

- Timely achievement of the project results;

- Co-chairing of project steering committees;

- Provision of legal and technical advice and analysis whenever needed.

3.5.2 Profile and tasks of the Resident Twinning Advisor (RTA)

The Resident Twinning Advisor (RTA) will be based in Moldova to provide full-time input to the project for the entire duration of the project.

RTA Profile:

- University degree/education in  economics, finance, law, audit or related field;

- At least 5 years experience in public sector auditing and control (external/internal audit , Financial management and control);

- Specific professional experience in external audit ;

- Recent experience in a senior position in an institution responsible for External audit in an EU MS;

- Experience in project management ;

- Strong initiative, analytical and team working skills;

- Excellent communication skills, with fluency in written and spoken English language;

- Knowledge of Romanian/Russian language would be an asset.

RTA Tasks:

- To manage the day-to-day coordination and progress of activities of the project in Moldova;

- To provide technical inputs in areas of project implementation, including the EU Acquis;

- To liaise with the BC Project Leader and RTA counterpart;

- To report to the MS Project Leader.

The proposed RTA must be a public servant of a Member State administration who should have worked for such organization for at least 1 year before the date of launching of the call for proposal of this Twinning project. In his/her daily work in Moldova, the RTA will be supported by an RTA Assistant as well as by a permanent interpreter / translator in case that possibility is seen as cost-effective efficient in the light of the volume of translation. Both, RTA Assistant and potentially RTA Language Assistant are to be recruited and funded by the project.

3.5.3	Profile and tasks of the short-term experts (STE)

The RTA will be assisted by short-term experts so as to cover the full range of expertise required. These will be suitably qualified and capable to provide the necessary skills according to the activities mentioned above.

STE Profiles - general experience:

- A university degree in a relevant subject;

- A minimum of five years experience in their respective field;

- An excellent command of written and spoken English;

- Experience in ENP countries as well in other projects would be an advantage;

- Knowledge of Romanian/Russian language would be an asset.

STE Profiles - specific experience (indicative list) in areas of

- Public external audit;

- Performance- and system audits;

- EU Acquis and MS practices of public audit, financial management and control for EU fund flows;

- Legal expertise in audit domains and regulatory and procedural frameworks;

- Experience and skills in Parliamentary budget controls procedures;

- Human Resource Management;

- Strategic Planning;

- Training and curriculum development; coaching of senior management in decision taking process;

- Financial Management and Control systems, including internal Audit;

- IT audit;

- Internal and external communication.

STE Tasks:

- To provide technical inputs in specific areas of project implementation of the activities listed in the twinning fiche, including organization of workshops, training, coaching, drafting of methodological and handout materials as per the terms of reference provided by the RTA prior to each mission;

- To liaise with the RTA, the RTA counterpart and beneficiary component leader;

- To report to the RTA.

- Institutional Framework

Beneficiary institution for the twinning project is the Court of Accounts (CoA) of the Republic of Moldova, who is a member INTOSAI (takes part in INTOSAI working groups) and EUROSAI, and responsible for the external public audit of public funds management in Moldova. According to Article 133 of the Constitution, the President of the CoA is appointed by Parliament for a 5-year term on proposal of the President of the Parliament. The Court of Audit is composed of 7 members, who are appointed by the Parliament, also for a 5 years term, at the proposal of the President of the Court of Accounts.

The CoA is a Public Central Authority and its budget is part of the State Budget as approved by Parliament. Its activities are financed by an allocation from the State Budget of the Republic of Moldova and respective funds are disposed of independently from other authorities and commercial structures.

The CoA has currently around 160 employees and is organised by general audit directorates, audit directorates and support sections and services (The CoA’s organizational chart is provided in Annex 3).

The main roles and responsibilities for the external audit of the CoA as “the only state public authority that controls the formation, management and use of public financial resources” (Article 2 Law on CoA) in accordance with its mandate is to audit the state budget, the national social insurance budget, the mandatory Health Insurance budget and the administrative territorial units budgets (National Public Budget) - economic agents with state capital holdings of 50% or more.

Audits performed by the CoA in the years 2010 and 2011 are summarized hereafter for their main audit types and categories of audited entities.

In 2010, the Court of Accounts performed 42 audit missions, including regularity audits, performance audits and IT audits (starting in 2009); it adopted 42 decisions on approval of 49 audit reports. The total number of approved audit reports: 18 are regularity audit reports, 5 – performance audit reports, 2 – IT audit reports and 24 – other types of audits.

157 entities were audited, of which:

- 29 central public authorities;

- 37 local public authorities;

- 73 subordinated institutions;

- 18 economic agents (state enterprises, joint stock companies).

In 2011, 57 audit missions have been performed and 65 audit reports were approved, including: 57 regularity audit reports (audits regarding national public budget execution according to policies and audits templates of some projects/programs), 6 – performance audit reports, 2 – IT audit reports.

323 entities were audited, of which:

- 30central public authorities;

- 162 local public authorities;

- 64 subordinated institutions;

- 34 economic agents (state enterprises, joint stock companies);

- 33 other institutions.

- Budget

The indicative total budget available of the action is € 1,600,000.

The beneficiary will provide its logistic support in the form foreseen in the “twinning” manual.

- Implementation Arrangements

A new Financial Regulation applicable to the general budget of the European Union entered into force on 1st January 2013. This implies several changes to the Twinning contract templates. An updated version of the Twinning Manual and of its Annexes, incorporating these changes, is in preparation and shall be published soon on EuropeAid website. The Twinning contract that shall be signed as a result of the present procedure shall follow the templates of the updated Twinning Manual and Annexes.

  - Contracting Authority responsible for tendering, contracting and accounting

The Contracting Authority responsible for tendering, contracting and accounting is the Delegation of the European Union to Moldova. The person in charge of this project is:

Mr. Oleg Hirbu, Operations Section

Delegation of the European Union to Moldova

Office Address:

12 Kogalniceanu Str., MD 2001, Chisinau, Moldova

Tel.: +373-22-505210

Fax: +373-22-545421

E-mail: Oleg.Hirbu@eeas.europa.eu

The PAO will support the twinning project implementation process with the EU Delegation.  The person in charge of this project in the PAO is:

Mr. Ion Gumene, State Chancellery

Office Address: House of the Government,

1, Piata Marii Adunari Nationale

MD-2033, Chisinau, Republic of Moldova

Tel: +373-22-250215

Fax:+373-22-250259

E-Mail: ion.gumene@gov.md

  - Main counterpart in the BC

The counterpart in Moldova will be the Court of Accounts (CoA) of the Republic of Moldova. The Moldovan Project Leader will be Mrs. Angela Pascaru, Member of the Court of Accounts. The PL will hold the responsibility for all project components implemented in the CoA including activities dealing with the EU Acquis. The Moldovan Project Leader is committed – together with the MS Project Leader – to achieve the mandatory results. This commitment includes ensuring a high level of political commitment and a more practical commitment at the level of the CoA.

The RTA counterpart will be Mrs. Viorica Verdes, Head of the Division of Methodology, Assistance and Quality Evaluation. The RTA counterpart will be in charge of co-ordinating smooth and efficient implementation of project activities – together with the RTA – in the three components. She will ensure, on a daily basis, that CoA Departments and staff are ready to carry out together with MS experts all the planned activities, including workshops, preparation of legislative and methodological documents, study visits, internships, Final Conference. She will make sure that a proper level of ownership on project outputs and mandatory results is achieved by the beneficiary institution. She will be responsible – together with the Moldovan Project Leader – for enabling a high level of sustainability of achieved results after project completion.

The Component Leaders for Component 1 will be the Heads of the General Audit Divisions: Mrs. Natalia Trofim, Mrs. Valentina Madan, Mrs. Sofia Ciuvalschi and Mr. Vladimir Potlog.

The Component Leaders for Component 2 will be Lilia Ivasco, Head of the Human Resources Section and Ana Saichin, Head of the Legal Division.

The Component Leaders for Component 3 and 4 will be Angela Frunze, Head of the General Division of Methodology, Planning and Analysis and Violeta Balan, Head of the Public Relations and Image Service.

Responsible for organizational issues are the following persons: Gheorghe Mihai, Head of Staff of the CoA and Victoria Caldarii, Head of the External Relations Service.

The tasks of the CoA’s Component Leaders are to (a) ensure smooth collaboration with the twinning experts in their respective field, (b) availability of CoA personnel according to the work plan agreed in the twinning contract, (c) well targeted component activities and that (d) the outputs and results of the twinning project are timely introduced and applied.

A Project Steering Committee (PSC), consisting of the CoA, the PAO representatives and representatives of the Delegation of the EU to the Republic of Moldova will be established upon project start.

    - Moldovan Project Leader

The Moldovan Project Leader will be:

Mrs. Angela Pascaru, Member of the CoA,

Tel: +373 22 266 005

E-Mail: a_pascaru@ccrm.md

CoA address:

69, Stefan cel Mare Ave, Chisinau,

Republic of Moldova

    - Counterpart to the Resident Twinning Advisor

The counterpart to the Resident Twinning Advisor will be:

Mrs. Viorica Verdes, Superior State controller/Public Auditor – Directorate for Methodology, planning and analysis

Tel: + 373 22 266 060

E-Mail: v_verdes@ccrm.md

69, Stefan cel Mare Ave, Chisinau,

Republic of Moldova

    - Steering Committee

A Project Steering Committee (PSC) will be established upon project start. The PSC will encompass the Project Leader, RTA as well as their respective BC counterparts and the PAO, as well as representatives of Parliament, the Ministry of Finance and representative of the Delegation of the EU to Moldova. Representatives of other donors and relevant projects may be invited to participate as observers in the Steering Committee meetings.

The PSC will be established for the control and supervision of the project activities and the mandatory results. The Steering Committee will meet at regular intervals and will assess the progress of the project, verify the achievements of the outputs and mandatory results and discuss any other issues which might affect a smooth implementation of the project. The PSC will submit by the end of the meeting (as recorded in the minutes of meeting) an approval/not approval of the project reports. Official minutes of the PSC meetings will be kept in English and distributed to all parties within 15 days after the PSC meeting.

6.3 Contracts

Only one twinning contract is foreseen for this project.

- Implementation Schedule (indicative)

| Project duration: | 24 months |
| --- | --- |
| Launch of the call for MS Twinning proposals: | May 2013 |
| Reception of the proposals: | July 2013 |
| Notification to MS: | July 2013 |
| Signature of the contract: | November 2013 |
| Start of Twinning Project Activities: | December 2013 (implementation) |
| Project Completion: | End of December 2015 |

- Sustainability

The achievements of the Twinning Project (mandatory results) should be maintained as a permanent asset to the Beneficiary administration even after the end of the Twinning project implementation. This assumes inter alia that effective mechanisms are put in place by the Beneficiary administration to disseminate and consolidate the results of the project.

A long term effect of the Twinning Project will be a Court of Accounts acting upon completion of its transition to a Supreme National Audit Institution likewise the institutions for external audit in the EU MS. Through the consolidation of the past institution - and capacity building efforts and through improving its function, performance and impact, the CoA will irreversibly be established as a national and internationally highly respected and reputable institution as oriented at international standards and European best practice. It will therefore as an ultimate goal of its enhanced external audit capacity contribute to an ever increasing accountability and sound financial management of public funds in the RM.

The sustainability of project achievements can be regarded and anticipated in a very positive perspective, as the twinning design supports capacity building and institutional development of the CoA already on a good way. It assumes that changes of the institutional framework and practice of the CoA are suggested and implemented. These changes are supposed to reflect and be oriented at international standards, EU best practice and a changing control environment in the RM as further harmonized with the EU Acquis. Measures intended reach out to most departments of the CoA and will reinforce human resource management and development capacities and a larger part of the CoAs staff. Larger training programmes and sustained joint audit preparations and missions with twinning partners’ experts are expected to consolidate capacities and enhance the efficiency of operations. Much attention is given and a number of activities are geared at the interaction of the CoA on the national and international level, including Parliament – Government authorities - Civil Society and EU MS – SAI relations. A reasonable sustainability impact can therefore be expected for the visibility and credibility of the CoAs role and positive influence on improved public funds management and control in the RM.

- Crosscutting issues (equal opportunity, environment, etc.)

Each Twinning partner is required to comply with the equal opportunities requirements of the European Union. The principal of equal opportunity will be integrated into all stages of the project implementation.

- Conditionality and Sequencing

The contracting deadline for this project will be the 25/11/2013, so the first draft of the contract will have to be sent no later than 16/09/2013.

Nevertheless, full commitment and support is required from the CoA and the Government, including their readiness to establish and take active part in a Steering Committee that will coordinate the implementation of the twinning project. The CoA should in particular: nominate the counterpart personnel; nominate the relevant staff to participate in regulatory drafting, capacity building and training activities in accordance with the approved twinning programme; provide appropriate premises, facilities and work space.

ANNEXES TO PROJECT FICHE

Annex 1 – Logical Framework Matrix

Annex 2 – Indicative Work Plan

Annex 3 – Organisational Chart of the CoA

Annex 4 – List of Acronyms

Annex 1 – Logical Framework Matrix

| “Consolidation and Strengthening of External Public Audit” |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Contracting period expires: |  |  | Disbursement period expires: |
|  | Total maximum budget: € 1,600 000 |  |  | Budget year: |
| Overall Objective | Objectively verifiable Indicators |  | Sources of Verification | Assumptions |
| To improve accountability and management of public funds in the RM through enhanced external audit capacity in conformity with recognized international audit standards and in line with European best practice | - Proper and efficient utilization of public funds; - Increased audit transparency and public confidence in the quality of external audit in Moldova have increased; - INTOSAI standards and EU auditing best practices are widely applied in practice; - Increased collaboration with EU MS SAIs and enhanced interest for cooperation. |  | - Parliamentary and Governmental Reports about the execution of the National Budget; - European Commission Country Progress Reports on Moldova; - Statistics and Reports of key international financial institutions (IMF, WB, EBRD on public finance in the RM; - CoA Annual Reports; - Transparency International and other similar organisations’ assessments about status and progress of management of public funds in Moldova; - Civil society assessment about transparency and confidence in public finance in the RM; - Cooperation Agreements between the CoA and other EU MS SAIs. | None |
| Project Purpose | Objectively verifiable Indicators |  | Sources of Verification | Assumptions |
| To support the Court of Accounts in improving its function, performance and impact | - Institutional capacity of CoA has been strengthened and the skills base enhanced; - The normative and regulatory framework regulating the CoA has been improved; - Human Resources Management of the CoA has been revised and improved; - Interactions between CoA and other authorities of the RM have been significantly improved; - Based on improved communication between the CoA and the Parliament/Government as well as an enhanced public awareness raising activity the overall impact of CoA activities has been enhanced . |  | - Comparative assessments of institutional capacity, performance and impact of the CoA at the start and at the end of the project; - Parliamentary discussions and Reports issued by the Parliament regarding performance of the Court of Accounts; - Reports of the Project Steering Committee; - Several internal CoA publications and external articles and reports assessing the extent to which the newly introduced best practices have been implemented. - Articles published in newspapers, internet and other media; - Opinions of civil society organisations. | - Government and the Parliament support measures to improve the functioning, performance and impact of the Court of Account of Moldova. - Parliament and Government commitment to discuss and approve the necessary measures proposed by the CoA; - The CoA receives the necessary resources to implement the TWG project as planned. - Resignations of trained staff can be kept within a reasonable limit, i.e. not more than 10% a year. |
| Results | Objectively verifiable Indicators |  | Sources of Verification | - Assumptions |
| Mandatory result 1: Built/strengthened capacities of the CoA in the area of performance audits, systems audits and EU funds audits. | - Training Needs Assessment carried out; - Training Plan developed and approved; - Training materials developed and agreed; - Two teams of auditors (max. 16 people) established and trained in system audit; - One team of auditors (max. 8 people) established and trained in performance audit ; - One team of auditors (max. 8 people) established and trained in EU funds audit; - Four study visits for 4 audit teams (max. 20 people) organised; - Two system audits, one performance audit and one EU funds audit carried out by the 4 selected and trained groups; - Two cold evaluations carried out, including preparation of the check lists; - An institutionalized team of trainers involved in the planned 4 Pilot audits trained(max. 8 auditors); - New methodological and regulatory norms developed and approved. |  | - Training Needs Assessment Report; - Training Plan; - Training materials; - Establishment documents of the respective teams and evaluation sheets of each training; - List of attendants to each training; - Four reports on benefits and impact of the study visits; - Four audit reports; - Checklists for quality cold reviews of performance audits; - Completed reports of two cold evaluations; - Report on the respective training; - New methodological and regulatory norms on system audits and EU funds audits. | - CoA management staff is committed and willing to facilitate the participation of the relevant staff in the activities foreseen. |
| Mandatory result 2 : Revised and updated Legal framework of the CoA | - The Draft Law on the CoA has been revised, updated and submitted for adoption to the Parliament; - The internal regulations has been revised and approved according to the revised Law on CoA. |  | - Revised draft Law on the CoA submitted to the Parliament; - Revised, finalised and approved internal regulations. | - Government and Parliament political support for Law on CoA revision |
| Mandatory result 3 : Revised and updated Human Resources Management of the CoA | - An improved Staff Appraisal System; - Training Needs Assessment procedure has been established and operational; - Training Plan drafted and approved; - HR Management Policies has been revised in line with the EU standards and best practices ; - Job descriptions and competences statements for all levels of the CoA staff are established in accordance with the changes in the legal framework, the new audit procedures, the training programmes and the management policies. |  | - Report on Staff Appraisal System; - Report on Training Needs Assessment procedure; - Training Plan; - HR Management policies documentation; - Job descriptions and competences. |  |
| Mandatory result 4: Improved external and internal communication with the Parliament, the Government, civil society, media and other authorities leading to increased impact and enhanced visibility of the CoA with the above mentioned stakeholders | - Benchmark Analysis on openness, transparency and visibility of the CoA with all stakeholders, developed and submitted to CoA management for consideration; - Communication guidelines developed and operational; - Regulation on the procedures regarding the relations between the CoA and the Parliament and Government, including guidence on follow-up of CoA's reports, drafted and submitted to Parliament for adoption; - At least three workshops to improve the communication between the CoA and the Parliament, the Government and other authorities have been organised; - Three study visits for CoA and Parliament members have been organised; - Three awareness raising events have been organised for the media and the civil society. |  | - Benchmark Analysis; - Communication guidelines; - Approved Regulations; - Agenda, distribution materials and reports on the workshops; - Reports on the study tours; - Reports on the awareness events; - Reflections of the events in the media (articles, news, interviews, others); - Impact analysis discussed by the CoA management and available to all stakeholders. | - Availability of sufficient national financial resources for co-financing of the project activities; - Active involvement of audited entities; - Negative impact (instability) after Parliament election 2014 avoided; - Consensual views with MPs on procedures. |
| Activities | Means (indicative) |  |  | Assumptions |
| Activity 0.1: Kick-off meeting | PL 1x3 w/d. |  |  |  |
| Activity 0.2 Final Closing Conference | PL 1x3 w/d. |  |  |  |
| Component 1: Strengthen audit capacities |  |  |  |  |
| Activity 1.1: Training related to performance, system audits and EU funds and preparation of the necessary baseline assessments; study visits for audit teams organised. |  | 20 STEs mission x 10 w/d; 20 w/d – 4 x 5 days in study visits |  |  |
| Activity 1.2: Creation of groups of trainers specialized in performance/system audits and EU funds. |  | 6 STEs mission x 10 w/d. |  |  |
| Activity 1.3: Development and consolidation of CoA capacities to perform performance/system audits and audit of EU funds with the support of experts and their participation in audit missions, according to the new developed methodological and regulatory norms. |  | 16 STEs mission x 10 w/d. |  |  |
| Activity 1.4: Joint cold evaluation with experts of the quality of performed audits, elaborating of checklists for quality cold reviews. |  | 6 STEs mission x 10 w/d. |  |  |
| #### Component 2: Legal reform |  |  |  |  |
| Activity 2.1. Reviewing the current Law of the CoA in line with the EU best practices and the regulations of international organizations in the field. Adjusting the Law in accordance with the new requirements and procedures. Assistance on passing the project through the legislative process. |  | 8 STEs mission x 10 w/d. |  |  |
| Activity 2.2: Adjusting and revising internal regulations in accordance with changes in the legal framework. |  | 7 STEs mission x 10 w/d. |  |  |
| Component 3 Human Resources Management of the CoA |  |  |  |  |
| Activity 3.1 Establishing of Training Needs Assessment procedure, drafting and implementing the Stuff Appraisal System procedures. |  | 4 STEs mission x 10 w/d. |  |  |
| Activity 3.2: Implementation of modern procedures of human resources management (HRM) in line with the EU standards; revising job description and competences statements, in accordance with the changes in the legal framework.) |  | 6 STEs mission x 10 w/d. |  |  |
| Component 4: Strengthen Interaction and Impact of the Court |  |  |  |  |
| Activity 4.1: Implement measures to stabilize, maintain and intensify efficient relations with Parliament, Government and other authorities; organising workshops to improve the communication between the CoA and the specified authorities. |  | 3 STEs mission x 10 w/d. |  |  |
| Activity 4.2: Implement measures to stabilize, maintain and intensify efficient relations with media and civil society; organising awareness raising events for the media and the civil society and public at large. |  | 3 STEs missions x 10 w/d. |  |  |
| Activity 4.3: Promoting new efficient mechanism and measures enforcing stronger accountability of audited entities to follow CoA's recommendations and to intensify relations between CoA and audited entities. |  | 4 STEs mission x 10 w/d. |  |  |
| Activity 4.4: Coaching of CoA's members for measures to increase the Court's impact on improved public funds management |  | 4 STEs mission x 10 w/d. |  |  |
| Activity 4.5: Developing Benchmark Analysis on openness, transparency and visibility of the CoA with all stakeholders; developing guidelines for communication with all stakeholders (inclusive the procedure guides for Parliament and Government on follow-up of CoA's reports to deal with Court’s reports) |  | 6 STEs mission x 10 w/d. |  |  |
| Activity 4.6: Study visits for Court members and senior managers together with the involved Members of the Parliament in MS good practices of collaboration with European Court of Accounts and European Parliament to learn about the modalities of their interaction |  | 20 w/d (3 STE missions x 5 w/d and 5 w/d for preparatory activities) |  |  |

Annex 2 – Indicative Work Plan

The following work plan is indicative and gives only an orientation how the Twinning Project may be structured to ensure a

smooth implementation process.

| Activity | Project Month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| General Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 0.1: Kick-off meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Final Conference |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.1: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.3: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 1.4: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.1: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.3: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 2.4: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.1: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 3.2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Component 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.1: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.2: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.3: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.4: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.5: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity 4.6: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Annex 3 – Organisational Chart of the CoA

Plenum of the CoA (6)

The President of the CoA

Head of Staff of the CoA  (1)

Internal Auditor

(1)

Auditor intern

(1)

General Division I: Audit of State Budget and State Property

(27)

Chief accountant

(1)

General Services Section

(9)

Legal division

(5)

Administrative and Logistics Division

(11)

General Division II: Audit of Finances of Social Sector and National Economy (19)

Human Resources Section

(4)

Secția  resurse umane

(4)

External Relations Service

(3)

General Division III: Audit of Local Public Authorities (35)

Public Relations and Image Service

(3)

General Division of Methodology, Planning and Analysis

(18)

Finance and Budget Service

(2)

Performance Audit Division

(9)

IT Audit Division

(5)

Source : Court of Accounts  – Status : 10.08.2012

Annex 4 – List of Acronyms

| CHU | Central Harmonization Unit |
| --- | --- |
| CIB | Comprehensive Institution Building |
| CIFMA | Compulsory Insurance Fund for medical Assistance |
| CoA | Court of Accounts |
| CPA | Central Public Authority |
| CSP | Country Strategy Paper |
| ENPI | European Neighbourhood and Partnership Instrument |
| EU | European Union |
| EUR | Euro |
| EUROSAI | European Organisation of Supreme Audit Institutions |
| FMC | Financial Management and Control |
| FCRS | Financial Control and Revision Service |
| IA | Internal Audit |
| INTOSAI | International Organization of Supreme Audit Institutions |
| IFAC | International Federation of Accountants |
| IT | Information Technology |
| LPA | Local Public Authority |
| MTBF | Medium Term Budget Framework |
| MS | Member State of EU |
| NIP | National Indicative programme |
| OECD | Organisation for Economic Cooperation and Development |
| PCA | Partnership and Cooperation Agreement |
| PCS | Project Steering Committee |
| PIFC | Public Internal Financial Control |
| PL | Project Leader |
| RTA | Resident Twinning Advisor |
| SAI | Supreme Audit Institution |
| SDP | Strategic Development Plan |
| SNAO | Swedish National Audit Office |
| SSIF | State Social Insurance Fund |
| STE | Short-term Experts |
| WB | World Bank |

Financial Regulation: Regulation (EC, Euratom) No 966/2012 of the European Parliament and of the Council of 25 October 2012 on the financial rules applicable to the general budget of the Union and repealing Council Regulation (EC, Euratom) No 1605/2002.

http://eur-lex.europa.eu/LexUriServ/LexUriServ.do?uri=OJ:L:2012:298:0001:0096:EN:PDF

Rules of Application: Commission Delegated Regulation (EU) No 1268/2012 of 29 October 2012 on the rules of application of Regulation (EU, Euratom) No 966/2012 of the European Parliament and of the Council on the financial rules applicable to the general budget of the Union.

http://eur-lex.europa.eu/LexUriServ/LexUriServ.do?uri=OJ:L:2012:362:FULL:EN:PDF

http://ec.europa.eu/europeaid/where/neighbourhood/overview/twinning_en.htm