# ANNEX 1: Logical framework matrix in standard format

| LOGFRAME PLANNING MATRIX FOR Project Fiche |  | Programme name: IPA 2011 “Strengthening technical and operational capacities of Albanian Customs Administration" |  |  |
| --- | --- | --- | --- | --- |
|  |  | Contracting period expires: Two years following the date of the conclusion of the Financing Agreement |  | Disbursement period expires: One year following the end date for the execution of contracts |
| CRIS Number: |  | Total budget : | IPA budget: 1 500 000 EUR |  |
| Overall objective | Objectively verifiable indicators | Sources of Verification |  |  |
| Compliance with the requirements of the EU acquis in the field of Customs. | Positive evaluation of progress in the field of Customs. Internal technical reports. | Commission Opinion on Albania’s application to EU Membership |  |  |
| Project purpose | Objectively verifiable indicators | Sources of Verification |  | Assumptions |
| Improve the performance of the Albanian Customs Administration according to European standards. | - The number of laboratory analyses performed using ISO standards and according to the EU best practice increased by 60% by end of 2014; - Identification of multi-level risk and risk areas on all levels increased by 20% , by mid of 2014; - At least 25 Effective Post Clearance Controls performed by mid 2014; - Increased number of Applications for Action for protection of Intellectual Property Rights at borders, by 50% by mid 2014. | Annual Report of Customs General Directorate to the Ministry of Finance and Ministry of Integration |  | Continuous review and alignment of implementation methods and understanding throughout organisation of requirements for the acquis |
| Results | Objectively verifiable indicators | Sources of Verification |  | Assumptions |
| Result 1: Capacities on Risk Analysis and Risk Management enhanced. Result 2: Capacities for efficient enforcement of Post Clearance Controls enhanced. Result 3: Capacities for efficient enforcement of the compliance to Intellectual Property Rights enhanced. Result 4: Customs Laboratory fully aligned to EU best practices and standards. | - Gaps and needs analysis and SWOT analysis of the customs existing risk management system with specific recommendations for improvements conducted; - Guidelines on working methodology of risk management system developed; - Analytical and intelligence techniques for risk treatment prepared by the end of 2013; - Analytical and monitoring mechanisms in place and recommendations adopted on all organizational levels of Albanian Customs Administration by the end of 2013; National risk assessment reports are produced; - Data exchange procedures prepared and internal and external contact points for cooperation appointed by the end of 2013; Agreements with trade on receipt of electronic business information are signed; - Intelligence-led risk analysis for all customs procedures and for Intellectual Property Rights and protection of society issues are introduced in the risk analysis system; - New training modules within the Albanian Customs Administration established by the end of 2013 and at least 30 staff trained; - Relevant Training of Trainers conducted by the end of 2013, to perform in-house training of staff. - Necessary legal acts and instructions drafted by the end of 2013; - Post clearance control strategy prepared; - All necessary improvements of IT system proposed and implemented according to capacities available, by the end of 2013; - An audit policy in place; - Long and short term plans for Post Clearance Controls prepared and implemented by the end of 2013; - Protocols for horizontal and vertical collaboration in place by the end of 2013; - Long-term and medium-term training programmes prepared and 26 Post Clearance Control inspectors and 3 heads of sectors (including Director) trained in specific Post Clearance Control areas. - An action plan introduced; - Improved legislation on enforcement of Intellectual Property Rights drafted; - Number of new and improved procedures and working methods (related to applications for action and/or ex officio, destruction of goods, etc) in relation to the EU acquis and EU best practices, supported by the appropriate control mechanisms, by 2013; - Risk analysis and risk management system for identification of goods violating Intellectual Property Rights in accordance with the EU standards established and operational by end of 2013; - Statistics on Intellectual Property Rights detentions similar to the EU template on data collection are introduced; - At last 25 staff members trained on investigation and counterfeit and pirated goods and capable of applying new enforcement techniques; - Elaboration and implementation of public awareness campaigns, at least 3 per year; - Memoranda of Understanding (MoUs) with major trade representatives, airlines, shipping companies, express carriers are signed; - Number of workshops/seminars organized to promote cooperation between customs and stakeholders. - Procedures for the management of samples for analysis between Customs offices and Laboratories established ; - Procedures for sending samples to the laboratory and for producing the laboratory technical reports established, monitoring of the implementation of procedures in the first months assured; - Laboratory analysis reports are obligatory and are available to customs staff and traders; - At least 20 instructions (on sampling procedures, sample handling, sample storage in Custom houses, sample labeling, sample analyzing procedures, running the quality system handbook, etc) in place and disseminated by the end of 2013; - All members of laboratory staff trained on laboratory safety rules, security and hygiene procedures and at least 20 trainings delivered to laboratory personnel and customs staff according to the specific needs of the work with laboratory appliances by the end of 2013; - At least 100 customs officers involved in taking samples trained on correct sampling, labeling, packing and transportation of samples, and in the relevant health and safety requirements by the end of 2013; - At least 10 formal partnerships with other customs laboratories and/or with other qualified analytical institutions, inside and outside the country, developed within 2013; - Full accreditation of laboratory (certification according to EN/ISO 17025 and accreditation of the system according to EN/ISO 9001), by the end of 2013. | - Document of reviews and risk profiles - Regular Project implementation Reports - Interviews with the staff - Cooperation protocols - Decisions on appointment of contact point - Monthly and periodic reports to Albanian Custom Administration Director General - Training materials and training evaluation sheets - Copies of drafted documents; - Periodic Project Implementation reports to Director General of Albanian Custom Administration; - Training reports and evaluations; - Interviews with participants of internship and study tours; - EC reports - Statistics and other data - Evaluations forms of study visits and trainings - Periodic Project Implementation reports to Director General of Albanian Custom Administration - Cooperation and data exchange Procedures in place - Project Progress/Monitoring Reports - Regular project reports - Regular reports of the Commission’ services - Custom’s Laboratory Annual Reports; - Certificate of accreditation |  | - Annual review of working methods, procedures and capacity and follow-up. - Sufficient number of trainees available within Albanian Custom Administration - full commitment of the trainees and support of the top ACA management - Annual review of working methods, procedures and capacity and follow-up - Annual review of working methods, procedures and capacity and follow-up - Sufficient number of qualified staff to perform all types of analysis - availability of trainees - Support of the top management - Annual review of working methods, procedures and capacity and follow-up. |
| Activities | Means | Costs |  | Assumptions |
| Activities related to the Result 1: Activity 1.1: Conducting Gap and Needs analyses and SWOT analysis of existing customs risk management system resulting in recommendations for improvements Activity 1.2: Establishing within Albanian Customs Administration a harmonized Model of Risk Management in accordance with international standards and EU best practice; Activity1.3: Establishing working groups and preparing draft guidelines for working methods, covering risk management issues in the different customs areas. Activity 1.4: Enhancing communication and coordination between the Directorates/Units dealing with risk analyses information within Albanian Customs Administration and with relevant national/international agencies. Activity 1.5: Strengthening the operational capacity of the Albanian Customs Administration on Risk Analyses and Risk Management. Activities related to Result 2: Activity 2.1: Improving Albanian customs legislative and organizational framework of Post Clearance Control, in accordance with EU acquis and best practice. Improvement on the basis of existing gap analysis of the EU Blueprints and audit; Activity 2.2: Creating a post clearance control strategy; Activity 2.3: Strengthening the operational capacity of the Albanian Customs Administration on Post Clearance Control and providing practical assistance in performing post clearance controls; Activity 2.4: Preparing the “Audit Manual” for auditors; this manual should be based on EU standards taking into account national requirements; it should be a guideline for an auditor during his work; Activity 2.5: Enhancing knowledge, skills and experiences of Albanian Customs officers on Post Clearance Control. Activities related to the Result 3: Activity 3.1: Improving Albanian customs legislative and organizational framework of Intellectual property rights, in accordance with EU acquis and best practice. Activity 3.2: Strengthening the operational capacity of the Albanian Customs Administration in enforcement of Intellectual Property Rights. Activity 3.3: Enhancing knowledge, skills and experiences of Albanian Customs officers on enforcement of Intellectual Property rights Activity 3.4: Rising of public awareness for better understanding of the legal aspects of Intellectual Property Rights and the benefits of protection of the industrial property rights and promoting cooperation with stakeholders. Activities related to the Result 4: Activity 4.1: Develop and disseminate written procedures and guidelines for customs laboratory on: - correct sampling, labeling, packing and dispatching of the samples, and in relevant health and safety requirements, - sending samples for analysis from the customs offices to the customs laboratory, - putting into operation the management of samples in the customs laboratory; - laboratory safety, security and hygiene requirements; Activity 4.2: Development of co-operation with Member States customs laboratories and/or with other analytical institution inside and outside the country; Activity 4.3: Enhancing knowledge, skills and experience of Albanian customs staff in management and sending of samples; Activity 4.4: Enhancing knowledge, skills and experiences of Albanian customs laboratory staff in practices of the Customs Laboratory, such as on the use of equipment for analyzing goods, on the use of analytical methods for the control of goods with customs controls purposes and on tariff classification; Activity 4.5: Preparation of the implementation of international quality guidelines (Is) to facilitate accreditation process to give proof of the competence and quality of the customs laboratory. | One Twinning contract : Support to the Albanian Customs Administration - One Member State Project Leader, - One Member State Resident Twinning Adviser, - Medium/Short-term experts. | Twinning contract: 1500000 EUR |  | Both parties (twinned and operating structure) mobilise appropriate human and financial resources. Limited staff turnover within Albanian Customs Administration Full support of ACA management |
| Preconditions: Conclusion in due time of the financial and twinning contracts. |  |  |  |  |