TWINNING PROJECT FICHE

Modernisation of the Real Estate

Tax Administration in Egypt –

Developing Capacities of the Real Estate Taxation Authority

Prepared on behalf of the

EUROPEAN COMMISSION

Under the

Support to the EU-Egypt Association Agreement Programme (SAAP)
Contents

List of useful abbreviations	4

1.	BASIC INFORMATION	5

2.	OBJECTIVES	5

2.1.	Overall Objective	5

2.2.	Project Purpose	5

2.3.	Contribution to National Development Plan/Cooperation Agreement/ Association Agreement/Action Plan	6

3.	DESCRIPTION	7

3.1.	Background and Justification	7

A. The Real Estate tax system in Egypt and Inbound Logistics of the Value Chain	7

B. The Egyptian Real Estate Tax Authority -  (Core Functions and Operations)	8

C. Taxpayers Services and Public Relations (System outputs/Outbound Logistics of the Real Estate Tax Value Chain)	9

3.2.	Linked Activities (other international and national initiatives)	9

3.3.	Expected Results	10

3.4.	Activities	10

Component I: Property Tax Administration	10

3.4.1.	Activities Linked to Property Tax Administration (Component I)	10

3.4.2.	Activities Linked to Property Valuation and Assessment Techniques	11

3.4.3.	Activities Linked to Tax Roll Processing and Billing Systems	11

3.4.4.	Activities Linked to Appeals System and Procedures	11

3.4.5.	Activities Linked to Tax Collection System	11

3.4.6.	Activities Linked to Compliance Systems, Processes, and Procedures and Enforcement	11

Component II: Regulatory and Legal Framework for Effective Administration	12

3.4.7.	Activities Linked to the Regulatory and Legal Framework for Effective Administration (Component II)	12

Component III: ERETA’s Communication function and Taxpayer Services	12

3.4.8.	Activities Linked to ERETA’s Communication Function and Taxpayer Services (Component III)	12

Component IV:  Supporting Functions Development (Horizontal Operations)	12

3.4.9.	Activities Linked to Upgrading the Supporting Functions (Component IV)	13

3.4.9.1.	Activities Linked to Planning and Policy Support	13

3.4.9.2.	Activities Linked to Information Management	13

3.4.9.3.	Activities Linked to Quality Assurance	13

3.4.9.4.	Activities Linked to Information Technology	13

3.4.9.5.	Activities Linked to Developing a Sustainable Training Capacity at ERETA	14

3.5.	Means	14

3.5.1.	Profile and tasks of the Project Leader (PL)	14

3.5.2.	Profile and tasks of the Resident Twinning Advisor (RTA)	14

3.5.3.	Profile and Tasks of the RTA Assistant	15

3.5.4.	Profile and Tasks of the Short-term and Medium-term Experts	17

4.	INSTITUTIONAL FRAMEWORK OF THE TWINNING PROJECT	23

4.1.	Egyptian Project Leader	23

4.2.	RTA Counterpart	23

5.	BUDGET	23

6.	IMPLEMENTATION ARRANGEMENTS	24

6.1.	Implementing Agency Responsible for Tendering, Contracting and Accounting	24

6.2.	Main counterpart in the Beneficiary Country	24

6.3.	Contracts	24

7.	INDICATIVE IMPLEMENTATION SCHEDULE	25

8.	SUSTAINABILTY	25

9.	CROSSCUTTING ISSUES	25

10.	CONDITIONALITY AND SEQUENCING	25

11.	ANNEXES	26

ANNEX I: The Consulting Company scope of work	26

ANNEX II: Log-frame planning matrix	27

ANNEX III: Indicative Implementation Timetable for the Project	40

| # List of useful abbreviations |  |
| --- | --- |
| AA | Egypt-EU Association Agreement |
| AP | Action Plan |
| BC | Beneficiary Country |
| EC | European Commission |
| ENP | European Neighbourhood Policy |
| ENPI | European Neighbourhood Policy Instrument |
| ERETA | Egyptian Real-Estate Taxation Authority |
| ICT | Information and Communications Technology |
| IS | Information Systems |
| IT | Information Technology |
| MIS | Management Information Systems |
| MOF | Ministry of Finance |
| MOU | Memorandum of Understanding |
| MS | Member State of the European Union |
| MTE | Mid-Term Expert |
| PAO | Programme Administration Office in Egypt |
| PL | Project Leader |
| PSC | Project Steering Committee |
| QA | Quality Assurance |
| RTA | Resident Twinning Advisor |
| SAAP | Support Association Agreement Programme between EU and Egypt |
| SAAP II | Support to the Implementation of the Action Plan and Association Agreement |
| SERVQUAL | Service Quality model identified |
| STEs | Short Term Experts |
| TA | Technical Assistance |
| ToT | Training of Trainers |
| USAID | United States Agency for International Development |

STANDARD TWINNING PROJECT FICHE

# BASIC INFORMATION

| - Programme: | Support to the Implementation of the Action Plan and Association Agreement (SAAP II) |  |
| --- | --- | --- |
| - Twinning Number: | EG10/ENP-AP/FI/14 |
| - Title: | Modernisation of the Real Estate Tax Administration in Egypt- Developing Capacities of the Real Estate Taxation Authority |
| - Sector: | Finance |  |
| - Beneficiary Country: | Egypt |  |

# OBJECTIVES

## Overall Objective

To improve the Real Estate Tax system in Egypt within the context of the national reform priorities and in line with the EU and international best practices.

## Project Purpose

The project purpose is to support the Egyptian Real-Estate Taxes Authority ERETA in undertaking the relevant measures to develop its core functions and reinforce an effective real estate tax system, in line with the EU and international best practices, and taking into consideration the socioeconomic context and national priorities.  In particular, the project will focus on the following:

- Reinforcing the effectiveness and efficiency of the Real Estate Tax administration, with focus on creating leverages within the Property Tax Value Chain/System.

- Supporting the enforcement of the national legal and regulatory framework of the Real Estate Tax system, in line with the EU and international best practices, and in accordance with the pertinent national priorities, context, and capacity.

- Supporting ERETA in developing sustainable capacities to contribute to continuous improvement and modernisation of the Property Tax Administration in Egypt.

- Improving the quality of, and access to, Taxpayers Services, to raise public awareness and develop advocacy for the Property Tax reform efforts in general.

## Contribution to National Development Plan/Cooperation Agreement/ Association Agreement/Action Plan

Through its demand-driven feature, the twinning instrument responds to national needs and priorities.  The Egyptian Government has embarked on an economic reform and structural adjustment programme since 1991. The reform process encompasses a complete overhaul of the Egyptian Tax System and the introduction of extensive legislative and institutional measures as regards to fiscal reform, in particular, tax administration and legal enforcement.

In recent years, significant legislative and institutional measures have been undertaken with regard to the country’s fiscal system. Several fiscal reform areas are being addressed, such as income and real estate taxes, customs and pensions. The government has shown commitment to reinforce a culture of openness and mutual trust with the Egyptian citizens as well as to improve taxpayers’ services.

National reform efforts have been focused on the best suited fiscal structure and practices that would contribute to the modernisation and efficiency of the Egyptian economy, while taking into consideration social equity and mitigating the negative repercussions of the liberalisation strategies. The structural and legislative reforms being implemented would improve the government's overall capacity to reinforce economic performance.

Furthermore, it is noticeable that the Egyptian government has considered improving its regulatory and supervisory role, particularly as regards to fiscal administration, this is reflected in different policies and strategies to improve the efficiency and transparency of fiscal system, for instance, the state budget’s accounting methodology was overhauled.  The government also submitted a 5-year fiscal consolidation plan to bring down the deficit by 1% per annum till 2010/2011. There is also keenness to realise complementarities among different areas/sectors; reform in the performance of the Real Estate Tax system would contribute to other development in other areas such as mortgage finance and real estate investments.

From an EU-Egypt's cooperation perspective, the twinning project is in line with the basic underpinnings of the Egypt-EU Association Agreement AA signed in 2004 and the Action Plan signed in 2007.  Specifically, the AA aims to contribute to the economic and social development of Egypt (Articles 1, 39), and to promote reforms designed to promote the economy (Article 72).

While the AA serves as the legal basis for cooperation with Egypt, the ENP Action Plan AP provides a comprehensive policy framework with specific and detailed mechanisms to support Egypt's economic, political, and social development. Within the context of the AP, a particular emphasis is made on reforming the tax system, improving public finance management, and upgrading public institutions.

Furthermore, Institutional Twinning is a viable instrument to align to the EU standards and best practices. In particular, the AP foresees further integration into the European Union economic, social and technological structures and a possibility to advance the approximation of the Egyptian legislation, norms and standards to those of the European Union, thereby enhancing prospects for trade, investment and growth.

# DESCRIPTION

## Background and Justification

Reform of the Real Estate Tax system is an integral part of national efforts to develop the overall fiscal performance and to contribute effectively to the overall reform process and to ensuring social equity.  There is a considerable political commitment towards developing the Real Estate Tax system in Egypt; to make it transparent, fairer, easier for the taxpayer to understand, and simpler for the central and local government to administer. Several interventions have already been undertaken, particularly, a new Legislative act was ratified (Real Estate Tax Law No. 196/2008). The new Law covers real estate and focuses on mitigating enforcement challenges of the previously enacted laws (e.g. duplication and redundancies), as well as other challenges such as the evolving changes of rental values, tax exemption rules, tax evasion, and very low percentages of property registration. The executive regulations for the new act were issued in 2009.

# A. The Real Estate tax system in Egypt and Inbound Logistics of the Value Chain

A comprehensive reform of the real estate tax system in Egypt is dependent on several and interdependent elements directly linked to the Real Estate Tax value chain (Annex 1)

In order to identify, register and appraise property, sufficient coordination as well as relevant information flow should be improved among the Official Cadastre, the Public Register, and ERETA as well as with other relevant stakeholders. Deficiencies in regulatory, institutional, and operational frameworks result in waste of resources, redundancies of data, lack of clarity on the legal ownership and identification of the real estate parcels- which all affect the efficiency and effectiveness of the Real Estate Tax system as a whole. Therefore, it is crucial to ensure that the roles and responsibilities of stakeholders are articulated and well defined.

There are some national efforts to upgrade operations of the Egyptian cadastre and the Buildings' Register by using IT technologies, on a pilot basis; nevertheless, it is rather indispensable to consider the coherence and functioning of the overall system for sustainable results.

The twining project will contribute to improving the overall framework of the Real Estate Tax in Egypt, with emphasis on developing national sustainable capacities to ensure that such framework is conducive to further reforms in the future.

It is noteworthy that the magnitude of comprehensive reform and resources needed are quite significant and would require considerable political and institutional commitment by all concerned stakeholders.

The following is a summary of legislations pertinent to the Property Tax administration in Egypt:

- The Real Estate Taxation Law No. 196/2008 and its executive regulations.

- Law No.91/2005 for the income tax law and its executive regulations

- Law No. 113/1939 for the regulation of taxes imposed on agricultural land.

- Law No. 66/ 1955 for the decentralization of tax collection

- Law No. 46/1968 on the collection of the Real Estate Tax law.

- Law No. 49/ 1977 for regulating the sales and renting of Property and the Tenant - Owner Relationship ,

- Law No. 136/1981 for dealing with special provisions of regulating the sales and renting of Property and the Tenant - Owner Relationship.

# B. The Egyptian Real Estate Tax Authority -  (Core Functions and Operations)

The Real Estate Taxation Authority (ERETA) is in charge of real estate tax administration and collection. ERETA is an independent subdivision of the Ministry of Finance (MOF) - that was established in 1883 as one of the oldest public authorities in the country.

As regards the Real Estate Tax, ERETA’s core function is to enforce the Real Estate Tax Law through effective administration and collection of property taxes, as well as through proposing and executing secondary legislations and executive regulations. In particular, ERETA is mandated to perform the following tasks:

- Developing and coordinating Real Estate Taxes’ related information and fiscal cadastre.

- Assessing and collecting of the Real Estate Tax, administration of exemptions, seizures, sanctions, complaints and annual inspections.

- Supervising the Collection and Tellers Institute and the activities performed by collectors, surveyors and tellers.

- Supervising and monitoring the collection of tax payments

- Responding to taxpayers’ complaints.

- Performing technical inspections, planning, monitoring and producing statistics.

- Carrying out technical research.

- Training activities.

- Providing information and other services to taxpayers.

It is noteworthy that until the enactment of Law 196/2008, regional directorates for real estate tax were administratively linked to the Governorates, at present; they are directly linked under the supervision of ERETA. (As stipulated by the new law).

There are some challenges that relate to institutional, operational, and procedural deficiencies within ERETA’s internal system to process/administer/collect property taxes:

- An outdated organisational structure and operational practices- reflected in overlapping functions and resulting in excessive red tape and inefficiencies.

- Insufficient technical expertise in general, particularly in valuation and assessment (e.g. the use of massive and specialised appraisal systems).

- Limited resources to apply wide scale reforms using information technology.

- Deficiency in formal training hinders ERETA’s capacity to interpret and implement the Real Estate Tax Law.

- As Law No. 196 was recently enacted, ERETA needs to assess the applicability of the law (within the framework of the recently issued executive regulations) and develop its capacity for better law enforcement.

# C. Taxpayers Services and Public Relations (System outputs/Outbound Logistics of the Real Estate Tax Value Chain)

Advocacy for the new legislation and other reforms in the Real Estate Tax system is crucial to proper enforcement. ERETA needs to develop its capacity to improve public awareness, to provide access to relevant information and other taxpayers’ services, generally to create direct and effective channels of communication with the public. Without such efforts, pubic resistance that results partially from unawareness would impede the efficiency and effectiveness of the Tax Administration.

User friendliness should be an important consideration in the re-design/upgrading of that function. A single communication point could be considered for different regional areas (communication points interface); this function would include logging calls, answering basic inquiries, and dispatching and follow up on more complex inquiries. It is crucial to create the know-how for "Triage"- a customer service activity designed to prioritise incoming requests and distribute them to the unit/person that can best respond to the inquiry. The triage function enables prioritisation of information requests, capturing of process performance data, provides an avenue for an  increased usage of e-mail inquiries and customer self-service on the web, provides a simpler interface to customers on how to interact with the tax administration, and allows staff to handle requests more efficiently on a batch manner.

## Linked Activities (other international and national initiatives)

The Management Consulting firm has already undertaken significant assignment concerning the future organisational structure and strategic planning of ERETA.  Specifically, the management consultancy proposed a three-phase development programme, including organisational strategy, pilot set-up and design of a national roll-out plan, and implementation (Annex II).

A contract has been awarded by a government contractor to assist ERETA in installing an IT network and relevant workstations and GIS system.

On the other hand, the United States Agency for International Development (USAID) has been developing during the last years in Egypt different activities concerning the Egyptian Fiscal Reform and the program of modernization.

Moreover, European Member States, including the Netherlands, Denmark and Spain have provided technical assistance on tax reform issues at the Central Tax Authority Training Center in Cairo.

## Expected Results

- The capacity to improve the property tax administration has been developed and reinforced to ensure an effective implementation of ERETA's mandate.

- The legal and regulatory framework to effectuate a developed real estate tax system has been proposed and reform has been initiated.

- ERETA's Communication and Taxpayers Services' function has been reinforced; with focus on creating a sustainable mechanism for external communication.

- ERETA's sustained capacity for modernising and maintaining an efficient tax administration has been upgraded (training capacity at ERETA has been enhanced and sustained).

## Activities

- Conducting a kick-off meeting at the beginning of the project that invites the stakeholders of the project to provide them with a background of on the project components.

- Holding a final meeting owing to ensure that the results achieved by the Project are made available to all stakeholders.

# Component I: Property Tax Administration

This component aims at upgrading the efficiency and effectiveness of the property tax administration in Egypt through creating leverages across the Property Tax Value Chain. Focus will be made on developing ERETA's core functions (upgrading related technical and human capacities) and developing workflow systems with other direct stakeholders.

Twinning actions under this component will address the following core operations/functions:

- 1.1 System and process of taxable property identification and registration

- 1.2 Property tax valuation and  assessment techniques

- 1.3 Property tax roll processing and billing system

- 1.4 Property Tax Appeal system

- 1.5 Property tax collection system

- 1.6 Property tax compliance and enforcement

### Activities Linked to Property Tax Administration (Component I)

System and Process of Taxable Property Identification and Registration

- Assessing and analysing current System and Procedures in comparison to selected experiences at the EU MS.

- Developing a Strategy for improving the framework and system of cadastre information for taxable property and Action Plan for alternative reform measures.

- Implementing proposed reforms on selected pilot/s including building the capacities of related ERETA staff.

### Activities Linked to Property Valuation and Assessment Techniques

- Reviewing current system, periodicity, and procedures of the valuation and assessment techniques at the central and local levels.

- Proposing detailed recommendations for developing techniques, methodologies, and applications of valuation and assessment techniques.

- Assisting ERETA in upgrading the institutional set-up/workflow of the Valuation and Assessment and the related internal functions, including building the capacities of related ERETA staff.

### Activities Linked to Tax Roll Processing and Billing Systems

- Reviewing current system and capacity of tax roll processing; and defining systems gaps in light of European and international best practices/standards.

- Developing a Road Map for tax roll processing and billing system, and gradual automation system based on identified set of priorities.

- Implementing the Road Map on a pilot basis and build the capacities of related ERETA staff.

### Activities Linked to Appeals System and Procedures

- Conducting a gap analysis of current systems and procedures of appeals in line with European and international best practices.

- Developing recommendations and Road Map for developing the appeals system and procedures.

- Implementing reforms of activities linked to Appeals System and Procedures and build the capacities of related ERETA staff.

### Activities Linked to Tax Collection System

- Reviewing current system, methodology, standards, and capacities of property tax collection, in light of European and international best practices.

- Develop a Road Map for upgrading the system of property tax collection in Egypt, the Road Map should address the roles and responsibilities of the central and local levels and their interrelations (in coordination with the legal component).

- Initiating the implementation of the Road Map on a selected pilot/s including assisting in developing the institutional, human, and technical capacities within ERETA (at central level).

### Activities Linked to Compliance Systems, Processes, and Procedures and Enforcement

- Assessing current system and methods as well as inherent capacities for property tax compliance in light of European and international best practices.

- Developing a strategy for upgrading the system and innovative methods of compliance and enforcement.

- Implementing the proposed reforms including building the capacities of related ERETA staff.

# Component II: Regulatory and Legal Framework for Effective Administration

This component should contribute to developing the regulatory framework and law enforcement mechanisms necessary for the proper and efficient functioning of the property tax administration system.  All expected results must complement national efforts and priorities, particularly recent reform efforts which resulted in ratifying Law No. 196/2008.  Interventions through this component will reinforce the executive legal ground for implementing different reforms (operational and technical reform measures proposed through other components of the twinning project).

### Activities Linked to the Regulatory and Legal Framework for Effective Administration (Component II)

- Conducting a gap analysis of the regulatory and Legal Framework, in line with the European best practices and proposing a refined Legal Framework in line with selected EU and international best practices.

- Designing training modules to improve the capacity of the Legal Division of ERETA staff and others in charge of appeals on the proposed legal measures and executive regulations.

# Component III: ERETA’s Communication function and Taxpayer Services

This component aims at developing an effective and sustainable communication mechanism between ERETA and taxpayers and improving taxpayers' services. The external communication mechanism at ERETA should act as a customer-oriented focal point and liaison that links different stages/functions of the property tax value chain with the end users (i.e. taxpayers).  Taxpayer services and external communication mechanism should be dual effective, disseminating relevant information and improving awareness on a periodic basis as well as responding to taxpayers’ inquiries and providing other relevant services.  Different responsibilities may include: Property Tax Web management (in coordination with content management and IT), Information Assistance, Education/Awareness, and handling customers' complaints.

### Activities Linked to ERETA’s Communication Function and Taxpayer Services (Component III)

- Assessing ERETA’s capacities to perform outreach and taxpayers services and conducting a gap analysis in relation to selected best practices in the EU Member States and other international experiences.

- Putting the framework for developing the Division for Taxpayers Services and External Communication; to build on existing capacities.

- Specifying the needed equipment and software for the Division of Taxpayers Services centre/contact point.

- Implementing a pilot project for taxpayers’ services centre/contact point.

- Assisting ERETA in designing and implementing an awareness/outreach campaign to foster public support for property tax reform and tax compliance.

# Component IV:  Supporting Functions Development (Horizontal Operations)

This component aims at developing a selected number of supporting functions/horizontal operations which are crucial to maintain and monitor development/performance in the core/primary functions.  In particular, the use of specialised techniques/methods across different stages of the value chain (e.g. mass appraisal) would necessitate certain capacities to be built at to implement and sustain reform (e.g. quality assurance techniques). In summary, the Supporting Functions ensure the coherence, sustainability, and governance of the overall real estate tax system.

Twinning actions under this component will address the following core operations/functions:

- Planning and Policy Support

- Information Management

- Quality Assurance and Audit

- Information Technology Related Functions

- ERETA’s Training Capacity

### Activities Linked to Upgrading the Supporting Functions (Component IV)

### Activities Linked to Planning and Policy Support

- Assisting ERETA in developing an integrated model (Strategic Outlook) for ERETA within the overall Real Estate Tax context. The proposed model will ensure the integration of ERETA's value chain and will define means to direct the organisation towards defined/targeted core competencies. The outputs of this activity may serve as inputs for developing a sustainable policy support system.

- Setting the ground for the planning and policy support role (objectives, scope, workflow, outputs, and resources).

- Assisting ERETA in drafting the related manuals of operations as a reference for the planning and policy support functions.

### Activities Linked to Information Management

- Conducting an assessment of the ERETA’s information layout;  to evaluate interrelation and accessibility of information sources, platforms/formats, processing, flows and outputs  at  various organisational levels.

- Assisting ERETA in developing a Strategic Plan for developing its information system with a focus on internal and external information resources with other/stakeholders. This activity will be very much linked to different other components (e.g. IT). The Road Map should include the breakdown and types of data, classification, formats, and purposes. A proposed information flow within the whole organisation should be also articulated.

### Activities Linked to Quality Assurance

- Analysing current principles and methods for quality assurance.

- Assisting ERETA in defining and developing an approach and methodology for quality assurance system in ERETA.

- Supporting ERETA to set-up the groundwork and institutional framework for the QA and Audit function/unit/mechanisms.

- Implementing the proposed measures on a selected pilot.

### Activities Linked to Information Technology

- Conducting an assessment of current IT capacities, needs and existing plans.

- Assisting ERETA in developing an update of the current ERETA's IT plan.

- Drafting tender dossier/s for the needed equipment/software for the different components of the twinning project and providing training for related staff.

- Designing a dynamic web-portal which would upgrade existing ERETA’s website.

### Activities Linked to Developing a Sustainable Training Capacity at ERETA

- Assisting ERETA in setting up/upgrading its Training Division organisationally and institutionally.

- Enhancing the capacities of the staff at the Training Division in the different related functions.

## Means

### Profile and tasks of the Project Leader (PL)

The Project Leader will be responsible for the overall conception and direction of the MS involvement in the twinning project. The PL will be expected to devote a minimum of 3 days per month to the project in his home administration. In addition, he/she will be responsible for the organisation, from the Member State side and in coordination with the BC Project Leader, the Project Steering Committee (PSC), which will meet in Egypt at least every three months.

Tasks

The main tasks of the Member State (MS) Project Leader are to ensure:

- The overall coordination of the Project;

- The achievement of the mandatory results.

Profile

- Long-term civil servant from a Member State administration with at least 10 years experience in real estate taxation or finance/tax administration related filed;

- Excellent inter-personal and leadership skills;

- Have relevant education or experience in the field of project management, institutional development and supervision of finance and/or real estate tax reform projects;

- Excellent command of written and spoken English;

- Experience or relevant knowledge of ENPI context/reforms is advantageous;

- University degree or higher in a relevant field;

- Experience/knowledge of reforms in ENP/Eastern European countries is an asset.

### Profile and tasks of the Resident Twinning Advisor (RTA)

The Resident Twinning Advisor (RTA) will provide at least 30 months input on site. He/she will lead all aspects of the work of the MS team and will work directly with the BC project leader and RTA counterpart on a daily basis to support and coordinate the activities being implemented in the BC. His/her role is not purely administrative as the RTA is expected to provide high level advice and direction on all project activities.

Tasks

- Manage the day-to-day coordination and progress of the project's activities (necessary office accommodation will be provided by ERETA);

- Liaise with the Beneficiary Country (BC) Project Leader and RTA counterpart;

- Report to the MS Project Leader;

- Liaise with ERETA relevant staff and other Egyptian administrations;

- Follow up progress in reform areas/policy developments at the national level that are relevant to the project.

Profile

- Senior civil servant, with a minimum of 10 years of experience, from a Member State administration.  Experience in real estate taxation is required;

- Excellent inter-personal and team work skills;

- Previous experience in project management/coordination (preferably coordination of a multi-disciplinary team);

- Excellent command of written and spoken English;

- University degree in a relevant field;

- Previous experience in EU funded twinning projects is advantageous;

- Experience/knowledge with ENP/Eastern European countries context is an asset.

### Profile and Tasks of the RTA Assistant

The RTA will have an Assistant, who will support him/her in the performance of his/her duties during the entire project period. She/He should be well aware of the local conditions and support the PL, RTA and STEs during the project period.

- The RTA assistant is expected to have the capability to:

- Translate from Arabic to English and vice versa;

- Act as interpreter in discussions with stakeholders in the project;

- Give advice and assistance for travelling schedules, ticket and hotel reservations etc;

- Excellent computer skills;

- Assist in the work with drafting of financing and activity reports;

- Excellent communication skills.

- It is expected that the RTA assistant have relevant academic degree and training to succeed in the above mentioned tasks.

Working Groups

The establishment of one or more Working Groups should be considered. These groups should meet regularly to review progress, schedule activities and address any issues or constraints that may have arisen.

The membership of this/these Working Groups should be selected by the Beneficiary Institutions and should be conveyed to the Contracting Authority during the Inception Phase.

### Profile and Tasks of the Short-term and Medium-term Experts

The RTA will be assisted by a full time Assistant that is based in the BC. The RTA will be assisted by short-term experts so as to cover the full range of expertise required. These will be suitably qualified and capable to provide the necessary skills according to the activities mentioned above.

| TYPE | Tasks | PROFILE |
| --- | --- | --- |
| Component I: Property Tax Administration |  |  |
| 1 MTE (Component Leader) and 2-5 STEs | I.1 System and process of taxable property MTE Tasks: H/She will be in charge of leading and coordinating the STEs team under this component. He will be technically leading the Tax Administration System assessment and all tasks that require strategic view and linkages among subcomponents, as well as ensure the coherence among all subcomponents' activities. According to his experience and background, H/She may undertake technical responsibilities for implementing one of the sub-component's activities. | The MTE should have Solid experience in the Real Estate Tax administration (minimum of 15 years experience), particularly in institutional development in tax system in ENP/East Europe/ or developing countries. H/She may be technically in charge of one of the sub-components, in addition to leading and coordinating component I activities to ensure coherence and consistency of achieved results. H/She should have strong management and coordination skills. The aggregate experience of the MTE and the involved STEs should meet at least one or more of the following requirements: Strong experiences in developing and applying relevant methodologies, techniques and operational practices in Property identification and registration, valuation and tax assessment, in particular the use of mass appraisal techniques. -Deep technical expertise in the development of Real Estate Tax roll processing and billing systems. - Experience in developing procedures, systems of appeals and methods of compliance and tax enforcement. |
|  | 2-5 STEs will be responsible for undertaking the following tasks: All activities specified for property identification and registration, valuation and assessment techniques, tax roll processing and billing systems, appeal system and procedures, tax collection system, and compliance processes, procedures and enforcement. The breakdown of tasks among the STEs should be further specified in the MS Twinning proposal according to the experience and background of both experts. The STEs will perform their tasks under the leadership of the MTE Component leader. |  |
| Component II: Regulatory and Legal Framework for Effective Administration |  |  |
| 2 STEs | 2 STEs will be in charge of all specified activities under this component. The breakdown of tasks between the STEs should be further specified in the MS Twinning proposal according to the experience and background of both experts. | .- Good experience in legal and regulatory reforms of real estate tax. - Strong knowledge of European best practices, models, and relevant aquis of real estate tax laws and administration in different European Member States. - Experience in drafting legislation and associated executive regulations. - University degree, or higher, in public law, |
| Component III. ERETA’s External Communication function and Taxpayer Services |  |  |
| 1 MTE (Component Leader) and 1 STEs | MTE Tasks: H/She will be in charge of leading and coordinating the activities under this component. He will be technically leading and implementing activities specified under this component, in particular, assessing the strategic outlook of the communication and tax payers' function, the institutional set up and mechanism for implementation, and advising on communication policy and platforms. 1 STE will work in close coordination with the MTE in drawing up the framework of the communication function and undertaking the implementation of proposed measures, in particular, the design and launch of awareness activities, the launch of a pilot project, and training selected ERETA staff. | The MTE should have at least 10 years experience in the development of outreach/external communication mechanisms; preferably, in the area of real estate tax services/tax services. H/She will act as the component leader and must have excellent management and communication skills. H/She must have relevant experience in setting institutional frameworks for outreach/external communications and taxpayers services. The STEs should have good experience in the abovementioned areas, with relevant experience/knowledge of the use of ICT and MIS in the area of outreach and tax services. |
| Component IV: Supporting Functions Development |  |  |
| 1 MTE- Component Leader | MTE- Component Leader Tasks: H/She will be in charge of leading and coordinating the STEs team under this component. | At least 12 years of experience in leading and managing task-force team of multiple areas, preferably in the areas of planning and policy development, or human and institutional capacity building. Experience in the field of property taxes/tax administration is highly advantageous. . University degree or higher in management, public policy/administration, or any other relevant field. Good knowledge/experience of ICT and MIS applications in public sector reforms. The aggregate experience of the two STEs should meet at least one or more of the following requirements: |
| 2 STE Expert in planning and policy support | 2 STEs will be in charge of all specified activities under this sub-component. The breakdown of tasks between the STEs should be further specified in the MS Twinning proposal according to the experience and background of both experts. | Good experience in public policy, organisational planning and development, strategy development. Extensive knowledge/experience of organisation/strategy development techniques in particular value chain development/integration, the use of Enterprise Resource Planning ERP, as well as organisational learning is an advantage. Experience in real estate tax/tax administration system is an asset. |
| 2 STEs in Information and Content Management | 2 STEs will be in charge of all specified activities under this sub-component. They will work in close coordination with the IT Component experts. The breakdown of tasks between the STEs should be further specified in the MS Twinning proposal according to the experience and background of both experts. | The aggregate experience of the STEs for this subcomponent should meet at least one or more of the following: Extensive experience in developing and managing information architecture and flow, in particular, integrating operations and records classification system, Records Management System and standards, and knowledge management. Experience in real estate tax/tax administration system is highly preferred. |
| 2 STEs in Quality Assurance of Real Estate Tax Administration | 2 STEs will be in charge of all specified activities under this sub-component. The experts will be responsible for setting up the function/mechanism for Quality Assurance in ERETA. The breakdown of tasks between the STEs should be further specified in the MS Twinning proposal according to the experience and background of both experts. | Experience in the management and development of quality assurance of real estate tax administration. For either or both experts, experience in institutional development is required. Experience in ENP/Eastern European Country is an asset. |
| 2 STEs for Information Technology | 2 STEs will be in charge of all specified activities under this sub-component. The breakdown of tasks between the STEs should be further specified in the MS Twinning proposal according to the experience and background of both experts. | For the STEs, at least 10 years of experience is required. Experience in developing and implementing IT and MIS applications in public administrations, with emphasis on tax administration systems. Experience in portal design for public services, in particular, tax services, is required. Experience in developing and implementing IT applications and web/portal design in public administrations, with emphasis on tax administration systems. Experience in portal design for public services, in particular, tax services, is required. Good command of written and spoken English. |
| 1 STE for Training Capacity and Human Capacity Building | 1 STE will be in charge of implementing all activities specified under this subcomponent. He will be responsible for the development of the Training function. | At least 10 years in developing training capacities, with emphasis on setting up/operationalisation of training division/mechanism in public administrations. Experience in conducting training needs assessment, training modules design and Train of Trainer and coaching techniques. |

# INSTITUTIONAL FRAMEWORK OF THE TWINNING PROJECT

Most of the Twinning activities will be undertaken in ERETA, as the direct beneficiary of this twinning project. ERETA's main offices are located in Cairo, with the possibility to implement pilots under some components in selected governorates/districts.   All relevant Divisions related to Property Tax administration within ERETA will be involved.

All other relevant administrations that have direct linkages to the Property Tax System are direct stakeholders, in particular, the Egyptian Surveys Authority and Buildings Register and local authorities.

The BC is committed to make available the necessary office space and equipment for the MS partners to carry the project's activities. This includes access to the Internet as well as computer/s and necessary equipment (printer, photocopier, telephone, fax, etc.). It also includes the provision of suitable venues/material/equipment for training and meetings in the BC.  During the implementation period, the RTA will be accommodated with an appropriate office space and communication tools.

The Beneficiary administration will be committed to assign relevant staff to cooperate and work closely with their MS counterparts. ERETA will assign two main staff members:

## Egyptian Project Leader

The Egyptian Project Leader (PL) is a senior civil servant at decision maker level. H/She will act as the counterpart of the Member State PL. H/She will ensure the overall steering and coordination of the project from the Egyptian side, including proper policy dialogue and political support.

The PL's seniority will ensure his/her ability to mobilize the necessary staff in support of the efficient implementation of the project.

H/She will lead/coordinate Project Steering Committee (PSC) from the Egyptian side.

## RTA Counterpart

The RTA Counterpart is a senior civil servant who will work with the RTA on a daily basis to ensure proper coordination and implementation of all the activities of the project and achieve an efficient transfer of knowledge and information. He/she may be involved in one or more of the components of the twinning fiche and should preferably have good command of written and spoken.  He/she will be responsible, together with the RTA, of finalizing the reports to be submitted to the PLs which will be discussed and approved by the Project's Steering Committee.

# BUDGET

The maximum estimated budget for this twinning project is 1.585.000 Euros.

# IMPLEMENTATION ARRANGEMENTS

## Implementing Agency Responsible for Tendering, Contracting and Accounting

The Programme Administration Office (PAO) is in charge of the coordination of all the activities and the administrative management of the Support to the Association Agreement Programme. The PAO will be the responsible institution for the management of this twinning project. It manages the tenders, contracts and payments and this, in accordance with the procedures of ex-ante control defined in the Practical Guide to contract procedures financed from the General Budget of the EC in the context of external actions.

Contact person at the PAO:

Name: Hassan Mostafa

Title: Projects Manager

Address: 9 Abd El-Kader Hamza St, Garden City, Cairo, Egypt

Tel.: +202 279 3438

Fax: +202 792 05 83

Email: hassan.mostafa@ee-aa.net

## Main counterpart in the Beneficiary Country

Egyptian Real Estate Taxation Authority

Project Leader: (MS Project Leader Counterpart)

Name: Eng. Tarek Farrag

Title: President Egyptian Real Estate Taxation Authority

Address: 15 Mansour St. Lazoughly, Cairo, Egypt

Tel: +202-27950566

Fax: +202-27950566

Project Director (and RTA counterpart)

Name: Alaa Samaha

Title: Advisor to the Minister of Finance

Address: Ministry of Finance Towers, Minister Office – Tower # 2 – 14 Floor Ramses St. Extension, Cairo, Egypt

Tel: +202 26861300

Fax: +202 26861561

Email: alaa.samaha@mof.gov.eg

## Contracts

The PAO intends to enter into Supply Contracts as required for the different components of the twinning project. This will be funded separately from the SAAP budget. The supply will be provided upon the needs assessment that will be undertaken by the experts during the implementation of the twinning project.

There may also be other outsourcing contracts linked to the Twinning Project, but not part of it. These will be the responsibility of the beneficiary.

# INDICATIVE IMPLEMENTATION SCHEDULE

  - Launching of the call for proposals: January, 2011

  - Start of project activities: October, 2011

  - Project completion: March, 2014

  - Duration of the execution period: 30 months ( plus 3 months closure)

# SUSTAINABILTY

The transfer of knowledge by institutional twinning with a corresponding EU institution is expected to provide sustainable developments; this is envisaged if the results outlined are fully achieved. To maximise sustainability there must be a particular focus on the maintaining leadership by ERETA management and continuous training programmes.

# CROSSCUTTING ISSUES

Equal opportunity principles and practices in ensuring equitable gender participation in the project will be guaranteed. Male and female participation in the project will be based on the relevant standards of the EU. The main criteria for staff recruitment will be appropriate qualifications and experience in similar projects, not sex or age. Both men and women will have equal opportunities and salaries.

# CONDITIONALITY AND SEQUENCING

The success of this Twinning Program will, basically, hinge upon two elements:

- The full political support of the Egyptian governmental authorities to fully implement a modern RET and to modernize the structure and functions of ERETA.

- The support of ERETA management officers and staff regarding the RTA activities and the Twinning project.

Other minor commitments, such as the provision by ERETA authorities of premises for RTA activities and several auxiliary manpower hours are of the minor relevance for the success of the project. Training infrastructure and equipment will be also provided by the Egyptian authorities, but some exceptional training tools.

The BC will also ensure operational and logistical support to the RTA and the Twinning experts in terms of ensuring operational coordination with the other Egyptian Public institutions, aside ERETA, involved in the project, collecting and processing the information needed and to provide contacts and information concerning private entities that would be involved during the Twinning activities.

The underlined idea for the successful implementation of the Twinning is that the ERETA employees will be fully supportive of twinning activities.

# ANNEXES

- The consulting company scope of work

- Logical framework Planning Matrix

- Indicative Implementation Timetable for the Project

# ANNEX I: The Consulting Company scope of work

Upon the ratification of the new law, the consulting company was asked to develop an approach for the Egyptian Real Estate Tax Authority to develop the transformation strategy with the objective of enabling ERETA to roll out and administer the new real estate tax. The consulting company proposed a three-phase transformation program as indicated below:

Phase I involved situational analysis of the current organization and setting the transformation strategy going forward as well as outlining possible quick wins and involved  3 months.

Phase II (currently underway since June, 2009) involves a 7 month mandate to setup a functioning pilot office in 6th October City as well as designing a national rollout plan.

Phase III will involve implementation of the national rollout plan as well as organizational transformation.

Additionally a contract has been awarded to a government contractor to supply ERETA with installation of an IT network and required IT workstations as well as a functioning GIS system.

# ANNEX II: Log-frame planning matrix

Programme: Modernisation of the Real Estate Tax Administration in Egypt-   Developing Capacities of the Real Estate Taxation Authority

| Overall Objective | Benchmarks |
| --- | --- |
| To improve the Real Estate Tax system in Egypt within the context of the national reform priorities and in line with the EU and international best practices. |  |
| Project Purpose | Benchmarks | Source of information | Assumptions |
| To support the Egyptian Real-Estate Taxes Authority in undertaking the relevant measures to develop its core functions and reinforce an effective real estate tax system. | Real Estate Tax system in place and well-functioning. | - Official government reports. - Press statements. - Public opinion polls/surveys - Project's progress reports - ENP Subcommittee and progress reports | Commitment of the Egyptian Government to pursue reform in that area, in particular, MOF and ERETA at all levels. This should entail strong political backing. Allocation of sufficient human and financial resources needed to efficiently implement the project activities and ensure the sustainability of this project after its finalisation. Commitment and appropriate level of coordination among all stakeholders within the Real Estate Tax system. |

| Results | Benchmarks | Source of information | Assumptions |
| --- | --- | --- | --- |
| Component 1. Property Tax Administration The capacity to improve the property tax administration has been developed and reinforced to ensure an effective implementation of ERETA's mandate. 1.1 System and process of Taxable Property identification and registration have been upgraded. 1.2 Property Valuation and Assessment Techniques have been developed. 1.3 Tax Roll Processing and Billing Systems have been developed. 1.4 Appeals System and procedures have been enhanced. 1.5 Improvements in the Tax Collection system and processes have been proposed and implementation has been initiated on a pilot basis. 1.6 Compliance systems, processes, and procedures are developed to ensure better enforcement of property tax system; and implementation is initiated on a selected pilot. | - System and process of taxable property identification and registration functions, and performance indicators are defined and measured on regular basis. - Percentages of accurate fiscal cadastre. - Set of selected valuation & tax assessment techniques. - Percentage of regional coverage of taxable property using the new valuation and assessment techniques. 5. Number of appeals and types and quality of information accessible to the public about the appealing system. 6. Guidelines and measures of the tax collection system, workflow and methods are set.\ 7. Manuals of procedures for all sub-components areas are drafted and approved. 8. Gradual and prioritised set of reform measures are drafted and a pilot is put in place 9. Training Plan developed and implemented for all selected staff at different sub-components. 10. Modules for human capacity building are designed and implemented for all sub-components. | - Official government reports - ERETA'S Organisational Performance Indicators - Mission reports - Certificate of attendance for trainees - Training evaluation sheets | - The ERETA & MOF are committed to implement institutional changes - Level of resistance to change by staff members does not drastically preclude reform efforts - Assigning needed staff for the component |
| Component 2: Regulatory and Legal Framework for Effective Administration The legal and regulatory framework to effectuate a developed real estate tax system has been proposed and reform has been initiated. | - Gap analysis for legal and regulatory framework is conducted. - Proposal of legal and regulatory reforms is presented. | - Approximated legislations published in official journal - Press releases and statements - Mission reports | Political commitment to support legal framework development |
| Component 3: ERETA’s Communication function and Taxpayer Services ERETA's Communication and Taxpayers Services function has been reinforced; with focus on creating a sustainable mechanism for external communication. 3.1 A division for Taxpayers Communication and Taxpayers services has been set up/upgraded 3.2 Communications platforms and dissemination tools have been defined and put in place. 3.3 Public Awareness of ERETA's role has been improved. | - Mission, scope of work and specific outputs are identified for the Division. - Division's performance standards are developed. - Service Quality (ServQual) model is designed and implementation is initiated. - A manual of operations and procedures for the Division is developed. - Templates and forms for different taxpayers’ services and citizens’ inquiries are developed. - Customer Service system/mechanism is in place (Pilot basis), including awareness and outreach. | - Taxpayers' feedback comments on services (through website and services) - Mission and progress reports - Communication and Taxpayers' services Division's reports - Certificate of attendance and training evaluation sheets - Visibility events - Promotion material - Publications | - Commitment of the ERETA and the MOF to implement the new system. - Assignment of needed staff for the newly established division |
| Component 4: Upgrading of the Supporting Functions (Horizontal Operations) ERETA's sustained capacity for modernising and maintaining an efficient tax administration has been upgraded (training capacity at ERETA has been enhanced and sustained). 4.1 Planning and Policy Support - Framework for the planning and policy support function at ERETA has been proposed and appropriate measures have been initiated. - The organisation has been aligned towards adopting the proposed model, including defined performance measures. - An in-house capacity in value chain integration and operations for continuous improvement has been developed. 4.2 Information Management - Current Information architecture/framework has been improved. - Capacity of ERETA's assigned staff for this function has been upgraded. 4.3 Quality Assurance and Audits - Quality Assurance function has been developed. (A Quality Assurance unit or department has been established). - Quality standards for different areas and for the whole system have been defined. - Quality Assurance and Audit have been initiated (a programme approach for QA and Audit on a selected pilot). - Capacity of selected staff has been upgraded. 4.4 Information Technology Related Functions - Capacities, functions, tasks, and plans of the IT function/Division have been updated. - The system with the needed equipment and software has been operated. - A web-mechanism for interacting among different stakeholders, including citizens, has been functioning. 4.5. ERETA's Training Capacity Developed - Foundation for setting up/upgrading ERETA's Training Division has been finalised and proposed mission, objectives, scope of work, workflow, output and the resources needed have been finalised. - Training Division's staff capacity has been enhanced with focus on the principles and tools of the Training Division. | - An assessment for developing the planning and policy support function is conducted. - Mechanism for planning and policy support is set up (including relevant institutional measures) - A Road Map for aligning the organisation into the new model and integrating planning and policy support function is drafted. - Training module/s is designed and delivered. - Assessment of the current information layout and flow is conducted (The assessment should address the breakdown of data and information across the organisation, and their inter-linkages, including information and data flows from and to other administrations (intra-organisational information framework ) - A framework for developing the overall information layout/structure is developed and proposed (information/data layout should be articulated in terms of type, format, periodicity, units and staff in charge) - An Action Plan for putting the proposed information architecture model in place is drafted and presented (including specific resources, means of implementation and timeframe) - Manual of operations is drafted and approved. - Training module/s and guidelines are prepared and delivered. - A methodology for establishing a quality assurance approach/function is defined. - Road Map for developing the QA and Audit function is developed (especially for valuation and assessment quality programmes). Resources needed for implementation are identified, and implementation initiated. - A Quality Assurance unit/department is established. - Operational manual for the Quality Assurance function/unit is drafted and approved. - Training module/s is designed and delivered. - Assessment of the IT function and capacities is performed. - Tender dossier for equipment and software is launched. Equipment and Software are installed. - Training module/s designed and delivered. - Manual of operations for the IT Department is updated/developed. - First edition of the Real Estate Tax Portal is finalised and launched. - Work Plan for the Training Division, manuals of operations/procedures including different templates are drafted and approved. - Training module/s, including the Training of the Trainer (ToT) are designed and conducted for the Training Division staff. | - Organisation Policy Statement - Mission and progress reports - MoU between ERETA and other administrations - Divisions' Periodic Reports - Certificate of Attendance | The ERETA’s staff are cooperative - Timely supply of IT equipment including software - Assignment/appointment of staff and appropriate financial resources from ERETA to launch new division and the portal |

Activities

Component 1: Property Tax Administration System and Process of Taxable Property Identification and Registration - Assessing and analysing current System and Procedures in comparison to selected experiences at the EU MS. - Developing a Strategy for improving the framework and system of cadastre information for taxable property and Action Plan for alternative reform measures. - Implementing proposed reforms on selected pilot/s including building the capacities of related ERETA staff. Activities Linked to Property Valuation and Assessment Techniques - Reviewing current system, periodicity, and procedures of the valuation and assessment techniques at the central and local levels. - Proposing detailed recommendations for developing techniques, methodologies, and applications of valuation and assessment techniques. - Assisting ERETA in upgrading the institutional set-up/workflow of the Valuation and Assessment and the related internal functions, including building the capacities of related ERETA staff. Activities Linked to Tax Roll Processing and Billing Systems - Reviewing current system and capacity of tax roll processing; and defining systems gaps in light of European and international best practices/standards. - Developing a Road Map for tax roll processing and billing system, and gradual automation system based on identified set of priorities. - Implementing the Road Map on a pilot basis and build the capacities of related ERETA staff. Activities Linked to Appeals System and Procedures - Conducting a gap analysis of current systems and procedures of appeals in line with European and international best practices. - Developing recommendations and Road Map for developing the appeals system and procedures. - Implementing reforms of activities linked to Appeals System and Procedures and build the capacities of related ERETA staff. Activities Linked to Tax Collection System - Reviewing current system, methodology, standards, and capacities of property tax collection, in light of European and international best practices. - Develop a Road Map for upgrading the system of property tax collection in Egypt, the Road Map should address the roles and responsibilities of the central and local levels and their interrelations (in coordination with the legal component). - Initiating the implementation of the Road Map on a selected pilot/s including assisting in developing the institutional, human, and technical capacities within ERETA (at central level). Activities Linked to Compliance Systems, Processes, and Procedures and Enforcement - Assessing current system and methods as well as inherent capacities for property tax compliance in light of European and international best practices. - Developing a strategy for upgrading the system and innovative methods of compliance and enforcement. - Implementing the proposed reforms including building the capacities of related ERETA staff.

Component 2. Regulatory and Legal Framework for Effective Administration - Conducting a gap analysis of the regulatory and Legal Framework, in line with the European best practices and proposing a refined Legal Framework in line with selected EU and international best practices. - Designing training modules to improve the capacity of the Legal Division of ERETA staff and others in charge of appeals on the proposed legal measures and executive regulations.

Component 3: ERETA's Communication Function and Taxpayer Services - Assessing ERETA’s capacities to perform outreach and taxpayers services and conducting a gap analysis in relation to selected best practices in the EU Member States and other international experiences. - Putting the framework for developing the Division for Taxpayers Services and External Communication; to build on existing capacities. - Specifying the needed equipment and software for the Division of Taxpayers Services centre/contact point. - Implementing a pilot project for taxpayers’ services centre/contact point. - Assisting ERETA in designing and implementing an awareness/outreach campaign to foster public support for property tax reform and tax compliance.

Component 4: Upgrading of the Supporting Functions Activities Linked to Planning and Policy Support - Assisting ERETA in developing an integrated model (Strategic Outlook) for ERETA within the overall Real Estate Tax context. The proposed model will ensure the integration of ERETA's value chain and will define means to direct the organisation towards defined/targeted core competencies. The outputs of this activity may serve as inputs for developing a sustainable policy support system. - Setting the ground for the planning and policy support role (objectives, scope, workflow, outputs, and resources). - Assisting ERETA in drafting the related manuals of operations as a reference for the planning and policy support functions. Activities Linked to Information Management - Conducting an assessment of the ERETA’s information layout; to evaluate interrelation and accessibility of information sources, platforms/formats, processing, flows and outputs at various organisational levels. - Assisting ERETA in developing a Strategic Plan for developing its information system with a focus on internal and external information resources with other/stakeholders. This activity will be very much linked to different other components (e.g. IT). The Road Map should include the breakdown and types of data, classification, formats, and purposes. A proposed information flow within the whole organisation should be also articulated. Activities Linked to Quality Assurance - Analysing current principles and methods for quality assurance. - Assisting ERETA in defining and developing an approach and methodology for quality assurance system in ERETA. - Supporting ERETA to set-up the groundwork and institutional framework for the QA and Audit function/unit/mechanisms. - Implementing the proposed measures on a selected pilot. Activities Linked to Information Technology - Conducting an assessment of current IT capacities, needs and existing plans. - Assisting ERETA in developing an update of the current ERETA's IT plan. - Drafting tender dossier/s for the needed equipment/software for the different components of the twinning project and providing training for related staff. - Designing a dynamic web-portal which would upgrade existing ERETA’s website. Activities Linked to Developing a Sustainable Training Capacity at ERETA - Assisting ERETA in setting up/upgrading its Training Division organisationally and institutionally. - Enhancing the capacities of the staff at the Training Division in the different related functions.

# ANNEX III: Indicative Implementation Timetable for the Project

Modernisation of the Real Estate Tax Administration in Egypt-   Developing Capacities of the Real Estate Taxation Authority

| Year | 2011 |  |  |  |  |  |  |  |  |  |  |  | 2012 |  |  |  |  |  |  |  |  |  |  |  | 2013 |  |  |  |  |  |  |  |  |  |  |  | 2014 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | J |
| Launch |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Selection |  |  |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contracting |  |  |  |  |  | x | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |

Approximately 90% of the real estate market is unregistered.