## Schedule of Activities
ANNEX 2: Indicative Project Implementation Schedule
Support the National Commission for State Energy and Public Utiities Regulation (NEURC) of Ukraine in the Process of Electricity Market Reform
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28
Quarterly reviews
A0.1 | Opening and closing workshops
COMPONENT 1: Project support and specialized language training
A1.1 | Coordination and liaison with the Energy Community Secretariat and ACER
A1.2 | Organization and conducting of English training with emphasis on literature used in the electricity sector
COMPONENT 2: Access of market actors to electricity networks
A2.1 | Development of Third Party Access Rules and Standard Contracts (Market part)
A2.2 | Review and Amendments of connection rules (Physical part)
COMPONENT 3: Switching electricity supplier, switching/appointment of Default Supplier / S of LR
A3.1 | Formulation of Rules for switching to/from electr. supplier and of Standard Supply Contracts
A3.2 | Organization and execution of Study Tour on switching, replacement and appointment of El. Supplier Reg.
COMPONENT 4: Regulation of Default supplier / Supplier of Last Resort operation
A4.1 | Preparation of Rules for Default/Last Resort Suppliers operation
A4.2 | Identification of License conditions for Default/Last Resort Suppliers
A4.3 | Preparation of tariff (price) methodologies for Default/Last Resort Suppliers
A4.4 | Organization and execution of Study Tour on electricity supply regulation
COMPONENT 5: Support in the development of Day-ahead Market Rules
A5.1 | Development of Rules of Day-ahead Market
A5.2 | Development of Recommendations for Day-ahead Market operation
A5.3 | Organization and execution of Study Tour on Day-ahead market operation
COMPONENT 6: Support in the implementation of TSO and DSO unbundling
A6.1 | Preparation and execution of Information Campaign to Distribution Companies
A6.2 | Development of compliance Monitoring in unbundling of Distribution from supply
A6.3. | Development of legal framework for TSO unbundling according to the 3rd Energy Package
A.6.4. | Development of NEURC procedure for TSO certification
A6.5 | Organization and execution of Study Tour on TSO and DSOs unbundling implementation
Quarterly SC meetings
Component Activities
Startup and closure of project