STANDARD TWINNING PROJECT FICHE

Assistance to the Commission for Protection of Competition (CPC) for State Aid Control

- Basic Information

  - Programme: IPA -Transition Assistance and Institution Building (TAIB) 2009

  - Twinning Number: MK2009/IB/FI/01

  - Title: Assistance to the Commission for Protection of Competition (CPC) for state aid control

  - Sector: Competition policy

  - Beneficiary country: the former Yugoslav Republic of Macedonia

- Objectives

  - Overall Objective (s):

The overall objective is to promote and strengthen market competition through improvement of the state aid system thereby favouring continuing economic growth in the country.

  - Project purpose:

The purpose of the project is to enhance the capacity of CPC to manage and enforce EU state aid policies, to raise knowledge and understanding by state aid providers and to improve the overall planning, reporting and monitoring of state aid.

  - Contribution to National Development Plan/Cooperation agreement/Association Agreement/Action Plan

    - Link with Accession Partnership (AP)

The Accession Partnership with the former Yugoslav Republic of Macedonia (2007) includes among the key priorities: "Enhance the general business environment by further improving the rule of law, strengthening the independence of regulatory and supervisory agencies, speeding up legal procedures and continuing registration of property rights."  The short-term priorities in the area of competition policy are:

- Establish effective ex-ante control of state aid;

- Strengthen the administrative capacity of the CPC and provide the adequate budget and staff;

- Fully ensure the transparent and non-discriminatory application of competition law;

The following medium-term priorities are identified:

- Further align the legislation with the EU

- anti-trust and state aid acquis;

- Further improve the enforcement record in the areas of anti-trust and state aid control;

- Increase awareness among government institutions, business and the general public.

    - Link with National Development Plan

The activity for improving business area in the NDP specifically says that "markets will have to become more efficient and competitive as a result of closer compliance with the EC acquis and EU best practice (e.g. market for electronic communications, energy market, financial services, general service activities, etc.)".

    - Link with the SAA

In accordance with Article 69 paragraph 1 point iii of the Stabilisation and Association Agreement (SAA) between the EC and the former Yugoslav Republic of Macedonia, any public aid which distorts or threatens to distort competition by favouring certain undertakings or certain products is incompatible with the proper functioning of the Agreement insofar as they may affect trade between the Community and the former Yugoslav Republic of Macedonia. The parties agreed that the duration of the provision of article 69 point iii shall be prolonged and that any public aid granted by the former Yugoslav Republic of Macedonia shall be regarded as an area identical to those areas of the Community described in Article 87(3) (a) of the Treaty establishing the European Community. Any practices contrary to this Article shall be assessed on the basis of criteria arising from the application of the rules of Articles 81, 82 and 87 of the Treaty establishing the European Community. Each Party shall ensure transparency in the area of public aid, inter alia by reporting annually to the other Party on the total amount and the distribution of the aid given and by providing, upon request, information on aid schemes. Upon request by one Party, the other Party shall provide information on particular individual cases of public aid.

    - Link with Progress report

The European Commission’s 2007 Progress Report underlined that: "Enforcement in the antitrust field has improved, but still needs to be strengthened and should concentrate on the most serious infringements of competition (cartels and abuse of a dominant position).Concerning enforcement, the CPC must make further efforts to put in place an effective system of ex-ante state aid control.  The CPC prepared a partial inventory of state aid measures for the period 2001-06.  Unauthorised state aid granted by several government institutions was approved retroactively.  On the basis of this inventory, aid schemes need to be aligned.  As regards administrative capacity, additional employees were recruited, but their number and level of training remain insufficient in order to perform the complex task of monitoring state aid."

The European Commission’s 2008 Progress Report underlined that: The regional State aid schemes have been developed and are aligned with the State aid legislation.

The decisions of the CPC on State aid are respected. The CPC compiled the inventory of State aid measures for the period January-June 2008. The inventory includes decisions on compatibility of State aid approved in 2006 and 2007. However, the administrative capacity is not sufficient for proper monitoring of State aid: the number of staff of the CPC is still not adequate to respond to its complex tasks. An effective and comprehensive system for ex-ante control of State aid is not yet in place. Some bodies that grant State aid are still reluctant to report on the form and intensity of the State aid that they provide. Overall, preparations in the area of State aid are advanced.

The European Commission’s 2009 Progress Report underlined that: There has been some progress in the field of State aid. The regional aid map was adopted. Amendments to the Law on Technological-Industrial Development Zones, aimed at bringing it in line with the acquis, were adopted by the government and submitted to the Parliament for enactment in September 2009. The number of ex ante State aid decisions increased. Efforts have been made to establish an effective and comprehensive system for ex ante control of State aid. The number of reporting institutions has increased. However, the ex ante control of State aid is partial and confined to a few large State aid providers. Some institutions, in particular those providing indirect aid, are still reluctant to send notifications to the CPC. The awareness of State aid regulations among government institutions, business and the general public has somewhat increased, but remains inadequate. The administrative capacity of the CPC, though increased, still needs to be strengthened to ensure proper monitoring of State aid. In the area of State aid the country is advanced.

- Description

  - Background and justification:

In 2005 the existing Monopoly Authority which had been established in 1999, was renamed the Commission for Protection of Competition (CPC).

The basic competences of the CPC include the enforcement of provisions stipulated in the Law on protection of competition and the Law on state aid: to monitor and analyse the conditions on the market to the extent necessary for the development of free and efficient competition; to conduct procedures and make decisions according to the legal provisions. The Commission is an independent state body with the status of a legal entity, independent in its work and decision-making process. It consists of a President and four members appointed for a five-year period by Parliament, with the right to reappointment. The President and at least two members are professionally engaged in the Commission’s operations. The investigative and other expert activities are performed by the professional staff, which is organised in four departments with two units in each department all managed by a secretary general, appointed by the Commission. The CPC has altogether 16 qualified staff.

In March 2003, Parliament adopted the Law on State Aid. In December 2003, the Government adopted three Regulations: Regulation on the Forms and Procedure of Notification to the State Aid Commission and for Assessment of State Aid; Regulation on Establishing Conditions and Procedure for Granting Regional Aid; and Regulation on Establishing Conditions and Procedure for Granting Aid for Rescue and Restructuring of Firms in Difficulty.  Additionally, in December 2007, the Government adopted a Regulation on Establishing Conditions and Procedure for Granting Horizontal Aid. This Regulation determines the conditions and the procedure on granting state aid in the areas of research and development, environmental protection, employment, training, services of general economic interest and risk capital. In September 2009, the Government adopted a Regulation amending the Regulation on establishing condition and procedure for granting regional aid and also regional aid map was adopted. In this way the legal framework was established.

During the period 2001-2008 the Commission issued 30 decisions mostly related to the following areas: Protection of the Environment, Employment, Employment of Handicapped Persons, Economic Promotion, Cultural Heritage Protection, Overcoming Difficulties in the Economic Development and Regional Aid.

The number of opinions issued by CPC increased progressively since 2006 when CPC had been granted exclusive competence on state aid control. The progressive trend is also due to an increased public awareness of the state aid legislation. Only two state aid cases were referred to the Administrative Court since 2006 until present: In both cases ceiling of state owned land with the price lower than market price was considered as an incompatible aid. Aid receivers complained against the decisions of the CPC. In the first case, the court proceedings are on going. In the second case, the Administrative Curt annulled the decision of the CPC and returned the case back for further consideration.

By amendments to the Law on State Aid, adopted in 2006, the control and approval of the state aid became the competence of the Commission for Protection of Competition. The Act stipulates the jurisdiction of the CPC over the granting, monitoring of implementation and return of general and individual state aid, with the exception of those in the field of agriculture and fisheries.

Hence, the CPC is facing the task of adjusting its internal structure to the jurisdiction conferred on it. This implies amongst other aspects:

- establishment of the new internal structure of the CPC capable of handling aid issues;

- employing both expert and support staff;

- and education programmes for the staff.

More information about the activities of the CPC and recent research in the field of state aid can be found in its annual report of 2007 and 2008, on the web-site of the CPC.

The legislation in the area of state aid is mostly in line with the acquis. According to the Regulation on the forms and procedure of notification to the State Aid Commission and for assessment of state aid, state aid providers shall submit a complete notification to the Commission. In cases of serious doubts about the compatibility of the state aid with the State aid Law, the Commission shall decide to open a formal investigation procedure. The Commission initiates a procedure for assessment of the compatibility of each State aid with the Law on its own initiative or on a request by third persons. However, some of the acquis related to state aid for setting a methodology for the level of compensation for companies performing services of general economic interest, has yet to be transposed.

The number and the level of trained staff remains insufficient to perform the complex task of monitoring state aid. Measures have been taken to increase awareness among state institutions and cooperation between the various aid providers and the CPC.  Still, the notification by some of the state aid providers is unsatisfactory. The reports that the CPC sends to DG Competition are limited to a modest number of notified and approved state aid cases.

Administrative capacity, independence, transparency and the accountability of the competition authority in the field of state aid have been strengthened in the last couple of years. However, the CPC still needs more, better qualified staff and adequate funding. Further efforts are also needed to increase awareness of the benefits of competition policy among the general public, and especially in the understanding of the state aid control system among state aid providers.

Awareness of state aid rules and cooperation among the state aid providers is still insufficient. The number of notification is still limited to few major aid providers in the country. The awareness of state aid regulations among government institutions, businesses and general public has increased in the last years but remains inadequate. With the project, this lack of understanding of state aid issues should be significantly addressed. This project will achieve general improvement for the state aid providers, which shall then result in better handling of state aid.

The project should help the CPC carry its tasks in the field of state aid. This will improve the enforcement record in the field of state aid control. Training of state aid staff will contribute to the more efficient knowledge about procedure and enforcement related to the state aid issues and effective implementation in the daily practise. This project will also contribute to increase the cooperation between the state aid providers and CPC. By raising awareness of all stakeholders in this area, it will also significantly aid the process of better allocation of resources and market competition.

  - Linked activities (other international and national initiatives)

Title: Approximation of the legislation in the competition policy and strengthening of the administrative capacity of the body for competition protection

Donor: Germany (Bundeskartellamt and Bundesnetzangentur).

Duration: February 2006 – September 2007

Description: This project was implemented as Twinning project in cooperation with the relevant German authorities (Bundeskartellamt and Bundesnetzangentur). Activities regarding the institutional component were implemented within the framework of the project in 2007, i.e. training for Commission employees and judges, as well as raising public awareness on competition law and policies. At the end of the project, various brochures on the LPC and bylaws were prepared with assistance from the Twining project experts ( Guidelines to the LPC; Guidelines on the Regulation on Block Exemption Granted to Agreements on Distribution and Servicing of Motor Vehicles; information Leaflet on Restrictions of Competition According to the LPC; information Leaflet on Control of Concentration According to the LPC; information Leaflet on the Regulation on Block Exemption Granted to Vertical Agreements; and information Leaflet on Agreements of Minor Importance).The LPC, bylaws Regulation, as well as Guidelines and information leaflets adapted by the Commission were printed as part of the project.

Title:  BERIS (Business Environment Reform and Institutional Strengthening Project)

Donor: World Bank funded

Duration:  2005-March 2010

Description: This project provides for realisation of activities that will include the activities of the Commission as a whole, and not only separate sectors. The project includes technical assistance in regards to following, studying and implementing the European legislation on competition; operational assistance to the Commission activities to develop a monitoring system; assistance and training, including study visits to competition authorities in the EU, for the propose of strengthening procedures for investigative actions, technical improvements of market definitions, assessment of the degree of competition and development of clear guidelines and interpretations of the Law and the criteria used in decision-making, as well as development of procedures and mechanisms for institutional communication between the Commission, sector regulators, governmental bodies and the Consumers’ Associations.

Title: Strengthening of the administrative capacity of the CPC for enforcement of anti-trust and state aid legislation

Donor: British Project- Programme Office Foreign Commonwealth Office

Duration: April 2009 and is foreseen to end in March 2011.

Description: The project includes participation in competition events; participation in state aid events; seminar for judges; public awareness events for target groups relevant for ensuring free competition.

  - Results:

The Project is consisted of two components:

Component 1: Strengthening institutional and administrative capacity of the CPC, in line with EU acquis and European good practice in the field, through establishment of a functioning State Aid monitoring, notification and control system in the country

The mandatory results to be achieved under Component 1 are:

- Complement the existing legal gap analysis of primary and secondary legislation  (in case of detected necessity);

- Regional  State Aid schemes are developed;

- A transparent and reliable operational database for de minimis and Services of General Economic Interest is in function;

- A State aid monitoring methodology for de minimis aid, preliminary and full investigations, enforcement is developed and implemented by CPC;

- Acquired capacity to draft comprehensive State Aid annual reports;

- CPC case –handlers trained on State Aid case law, economics and procedures.

Component 2: Improvement of state aid awareness making the CPC recognisable in the wider public, and improvement of control and enforcement in state institutions, government agencies, regional and local government, the judiciary, and the business sector.

The mandatory results to be achieved under Component 2 are:

- Established internal procedures and methodologies for reporting and information flows from state aid providers to the CPC, including local government units and state funds and agencies;

- State aid providers (Government of the former Yugoslav Republic of Macedonia, state administrative organs, units of local self-government and other organ or institution providing or planning to provide State aid )  are aware of state aid rules in terms of increased number of  initiate  procedure for assessment of the compatibility of State Aid on a request by third parties;

- Raised awareness of the business community, about state aid rules and procedures (i.e. how to complain on state aid);

- Judiciary is trained to deal with state aid cases in terms of increased number of judges dealing with state aid, track-records and improved quality of court decisions;

- State aid inventory at local self-government level is better structured.

  - Activities

The set of proposed activities will be further developed with the Twinning partner when drafting the Twinning work plan, keeping in mind that the final list of activities will be decided with the Twinning partner,. The components are closely interlinked and need to be sequenced accordingly.

The activities can be organized in two components:

3.4.1 Component 1: Strengthening institutional and administrative capacity of the CPC, in line with EU acquis and European good practice in the field, through establishment of a functioning State Aid monitoring, notification and control system in the country.

- Activity 1: Providing of legal gap analysis;

- Activity 2: The MS Partner in cooperation with CPC will design, implement and put in function an operational state aid database;

- Activity 3: The MC Partner, together with the CPC, will design and put in place a methodology to draft state aid annual reports and to develop state aid schemes;

- Activity 4:The MS Partner, together with the CPC, will develop methodologies and procedures to facilitate the decision making process, this will include also monitoring and investigations as well as handling particularly sensitive sector/ cases;

Activity 5: On-the-job training of 6-10 CPC staff in order to deepen and specialise the knowledge in state aid case law, economics and procedures ;

- Activity 6: Conducting of Training needs assessment for CPC staff ;

- Activity 7: Study visit for 10 participants from the CPC to familiarize  with  up-to-date state aid  practises in areas of ( non exhaustive list)  aid for financial sector, fiscal aid, risk capital, regional aid, rescue and restructuring aid, de minimis inventory  with smaller number of cases currently encountered; this trip will show to the employees of the CPC daily work and best practise of the counterpart in the MS;

- Activity 8: Study visit for 10 participants from the CPC to familiarize  with  up-to-date state aid  practises in areas of ( non exhaustive list)   SME’s aid, environmental aid, training aid, employment  aid, research and development with smaller number of cases currently encountered; this trip will show to the employees of the CPC daily work and best practise of the counterpart in the MS;

- Activity 9: 4 seminars in EU Member States on Regional Aid, Rescue and Restructuring Aid, Environmental protection, Services of General Economic Interest, respectively for  5 persons from the CPC;

3.4.2. Component 2: Improvement of state aid awareness making the CPC recognisable in the wider public, and improvement of control and enforcement in state institutions, government agencies, regional and local government, and the business sector.

- Activity 1: Deliver seminars and in-house workshops with state institutions and local government units in order to raise awareness on state aid policy and rules, including reporting and operation of the inventory; increase awareness of aid providers and disseminate information to the CPC and the public;

- Activity 2: Develop, organise, and deliver training to at least 20 government officials, mainly targeting the bodies implementing state aid policy in related areas, as well create ex-ante notification discipline and ex-post monitoring of CPC’s decisions and opinions;

- Activity 3: Organize information campaign for business sector specifically targeted at sectors receiving state aid;

- Activity 4: 6 Workshops for judges in order to familiarize with up-to-date judiciary state aid practice;

- Activity 5: Provide expertise on structuring of inventory on a local self-government  level;

- Activity 6: Organize information campaign for journalist who work on economic and legal issues.

- Activity 7: Awareness raising activities concerning state aid policy targeting the business sector and public companies.

The principal participants during the trainings, study visit and internships should be civil servants coming from the beneficiary institutions in agreement with both, the EU Delegation's Task Manager and the Contracting Authority.  However, other beneficiary staff may be included on a need basis based on prior approval.

  - Means/Input from the MS Partner Administration:

Project will be implemented in the form of a Twinning contract between the country and an EU Member State. The implementation of the project requires one Project Leader with responsibility for the overall coordination of project activities, one Resident Twinning Adviser to manage project activities and preferably up to 20 Short-Term Experts. It is essential that the team have sufficiently broad expertise to cover all the areas included in the project description. The interested Member State institution shall include in its proposal the CVs of the designated Project Leader, Resident Twinning Adviser and the proposed Short-Term experts and the specific tasks to which they will be assigned. Provided that consistency within a consortium can be secured, two Member States may form a consortium of one senior and one junior partner.

3.5.1 Profile and tasks of the Project Leader

Profile

The Project Leader from the Member State must be a high-ranking official, but preferable the Head of a Member State competition / state aid authority that deals with state aid issues. The MS Project Leader will detail, coordinate and control the overall thrust of the project, lead project activities, and ensure the attainment of the projected outputs. The Project Leader is fully responsible for co-ordination of the work of the experts. The MS Project Leader will manage the implementation of the project with the Project Leader from the Beneficiary Country and is expected to devote a minimum of 3 days per month to the project in his/her home administration with an on-site visit at least every 3 months. The PL's seniority will ensure his/her ability to mobilise the necessary staff in support of the efficient implementation of the project. In addition, he/she should coordinate, on the Member State side, the Project Steering Committee (PSC), which will meet in Skopje at least every three months.

The proposed Project Leader must be a public servant of a Member State administration or of a mandated body.

Qualifications and skills

- Education at least up to a University degree(where a university degree has been awarded on completion of four years of study in a university or equivalent institution) and at least 10 years of general professional experience

- Fluent written and spoken English

Professional experience ( high ranking official)

- His/her working experience in the field of state aid should be of at least 3 years within a relevant Authority that deals with issues in the field of state aid

Additional advantages are:

- Experience in implementing Acquis  requirements in European Union Member State legislation in practice;

- Prior experience as Project Leader/Coordination/Manager

Tasks:

- General oversight of the project;

- Overall project co-ordination;

- Liaison with the Project Leader from the Beneficiary Institution;

- Co-chairing, with the Beneficiary Country Project Leader, the regular project implementation steering committee meetings;

- Executing administrative issues (i.e. signing reports, side letters, etc.).

    - Profile and tasks of the RTA

Duration of the RTA secondment:   18 months

The Resident Twinning Adviser should be a Member State official within an Administrative body with at least 5 years of competences on state aid matters or practitioner in the field of state aid-related matters-i.e lawyer or economist. Longer experience will be considered as an advantage in the selection process. He/she is expected to be working on a permanent basis in the beneficiary country for 18 months.

Comparative knowledge of other MS systems, as well as good management, communication and reporting skills are an asset for the RTA.

The RTA will lead project implementation He/she will be the primary interlocutor for both the Beneficiary and the Contracting Authority.

The RTA will have a key role in the coordination of the inputs required for the successful implementation of the project activities. He/she shall support by Short-Term experts from the European Union Member States.

Qualifications and skills of the RTA

- Education at least up to University degree  in economic or law field (where university degree has been awarded on completion of four years study in a university or equivalent institution), or at least 7 years experience in state aid matters;

- Knowledge of relevant EU projects, rules and procedures;

- Professional experience (minimum 5 years relevant professional experience);

- Background in drafting and implementing strategies, policies and regulations in the field of competition and state aid;

- Practical experience from a Member State aid monitoring agency;

- Fluent written and spoken English;

Tasks of the RTA:

- To design a work plan for the implementation of the project and to participate in drafting  of a twinning contract;

- To participate in the preparation of all strategic project documents (quarterly monitoring reports, final project report etc.);

- To ensure continuity of the implementation through the execution of the day- to -day management;

- To work on a daily basis with the Beneficiary Country staff to implement the project;

- To plan, coordinate and to ensure proper quality of outputs;

- Together with the Project Leader, to nominate, mobilize and supervise the Short-Term experts;

- To coordinate and organize training activities, workshops and public awareness activities;

- To be responsible for the implementation of each of the activities foreseen in the fiche;

Additional assets are:

- Practical experience from a Member State competition agency;

- Experience in implementing acquis requirements in EU Member states legislation in practice;

- Previous experience as project coordinator/ project manager;

- Sound knowledge of the situation in recent accession countries and/or SAA countries regarding state aid and competition issues;

- A master degree in competition (state aid included);

A RTA Counterpart will be assigned by the CPC. Ideally, this person should have at least 3 years of employment within the CPC.

    - Profile and tasks of the Short-Term Experts

Preferably up to 20 Short-Term experts

Other specialist will be made available by the Twining Partner to support the implementation of the project. Short-Term-Experts support the Resident Twining Adviser in the transfer in the technical know-how on specific matters and issues within the limits of the budget. The interested Member State Institution shall include in its proposal the CV’s of all proposed short term experts and specific task to which they will be assigned.

Tasks:

More specifically, the Short-Term experts will:

- prepare and implement specific tasks based mainly on practical cases and experience in compliance with their mission description and in accordance with Project activities;

- provide practical expertise/advices to relevant staff for execution of different tasks related to the project

- assist in key tasks, e.g. in the field of administrative capacity building, procedures compliance, training, legal development and others;

- address cross-cutting issues

The STEs will:

- be civil servants or to be currently employed by an EU Mandated body;

- have at least university degree and 3 years minimum  of experience in the field they will cover;

- have excellent communication skills, fluent in English and computer literate;

- be acknowledgeable in the latest development in the EU state aid and competition law.

Non-exhaustive list of short term expertise:

- regional aid;

- environmental aid;

- SME aid ;

- Trainings ;

- Risk capital aid;

- rescue and restructuring aid;

- state aid inventory ;

- Institutional Framework

4.1 Beneficiary institution

The beneficiary of the Twinning project is the Commission for Protection of Competition (CPC).

The monitoring and control of State aid in the former Yugoslav Republic of Macedonia is competence of the Commission for Protection of Competition (CPC). The reason for assigning this competence to the CPC is the direct impact of the state aid on the impediment of the competition. Namely, the uncontrolled granting of state aid would lead to favouring of the enterprises that receive the aid and their better position on the market compared to the participants in the market struggle that compete without state subsidies. Due to this, the CPC has the legal opportunity to impose return of the state aid that has been unlawfully granted. The state aid in itself is very complex matter and its identification and control involves set of activities that need to be undertaken by the CPC and the providers of state aid, in order to determine whether any measure contains elements of state aid.

The Law on State Aid, adopted in April 2003 and the amendments to the Law, adopted in 2006, regulates the field of control of state aid in the former Yugoslav Republic of Macedonia. It provides a legal framework that regulates the procedure and monitoring of granted state aid with aim of implementing the principles of commitments undertaken by international agreements ratified by the former Yugoslav Republic of Macedonia, containing state aid provisions.

The act for amendments to the Law on State aid, adopted in 2006, stipulates the jurisdiction of the CPC over the granting, monitoring of implementation and return of general and individual state aid, with the exception of those in the field of agriculture and fisheries. The monitoring and control of state aid is also strengthened with the Regulation on Form and Procedure of Notification to the State aid Commission and for Assessment of State aid; Regulation on Establishing Conditions and Procedure for granting Regional aid; Regulation on Establishing Conditions and Procedure for granting Rescue and Restructuring of Firms in Difficulty and Regulation on Establishing Conditions and Procedure for granting Horizontal aid.

The providers of state aid, which are the Government, the bodies of the state administration, the local self-government units and all other institutions which provide or plan to provide state aid shall be obligated to observe the provision of the legislation concerning the state aid. The state aid bodies shall submit their plans and projects for granting of state aid to the CPC. It shall evaluate their eligibility against the criteria laid down in the legal acts and shall decide either to approve and grant the state aid in accordance with the requirement or to refuse granting of state aid.

The organisational structure of the CPC is consisted of four Departments: Department for general and financial affairs; Department for economic analysis; Department for conduction of procedure and EU legislation; and Department for State Aid Control.  Department for State Aid Control is consisted of Unit for State Aid Identification and Unit for Case Evaluation.

The work of the Unit for identification of state aid is connected with the cooperation of this Unit with all state aid providers. State aid providers are obliged to notify planning state aid and the aim of this unit is to determine if there are elements of state aid. Also, the task of this Unit is after receiving the notification for planning state aid from the state aid provider, by analysing of the concrete case, to appoint if there is state aid in the case involved. This Unit makes identification of the state aid in accordance with the Law on state aid as a way on proceeding try the procedure if there is established that elements of state aid are involved.

After the determinations of elements of state aid, Unit for evaluation brings a draft-decision about compatibility with the Law on State Aid. After the evaluation of the cases, the Unit of CPC for evaluation may ask for additional information from the state aid provider for the purpose of making final decision. The task of this Unit is by analysing of the concrete case, to determine if the planning aid is compatible with the Law on state aid or not. In both cases, CPC brings a decision about compatibility of the aid. This Unit for evaluation, by making draft of final decisions, controls the state aid in the country by not letting unlawful aid to be granted.

The project proposed should contribute to the more efficient fulfilment of the tasks the CPC has in the field. This will improve the enforcement record in the field of state aid control.

Training of the state aid staff will contribute to the building more knowledge about procedures and enforcement related to the state aid issues and so helping more effective implementation in the daily practise.

4.2 Project Steering Committee (PSC)

A PSC will be established at the beginning of the project comprising senior representatives of the CPC, other relevant government bodies (if relevant), the Delegation of the European Union and the Member State(s) partner in accordance with the requirements of the Twinning manual. The final composition of the Steering Committee has to be agreed with the Contracting Authority (CFCD).

The PSC will monitor, supervise and co-ordinate the overall progress and implementation of the project and will provide guidance for the different components of the project.

The PSC members will meet quarterly or more frequently, if required. The meetings are called and chaired by both Project Leaders. The PSC will take the necessary decisions related to project facilitation and progress and will be the forum to discuss any unforeseen difficulties. Extraordinary PSC meetings can be convoked in case of exceptional needs.

4.3 Reporting requirements as per Art 6.4 of the Twinning Manual

Every three months, the MS Project Leader in co-operation with the BC Project Leader will prepare and submit interim quarterly reports at least 2 weeks prior to each PSC meeting. Each report will cover a three months period calculated from the date of notification of endorsement / signature of the contract. The first report will be due in the fourth month counting from the date of notification of endorsement / signature of the Twinning contract. Interim quarterly reports will be prepared and distributed to all the participants in advance of the meetings of the Project Steering Committee.

The MS Project Leader shall submit the final report before the end of the legal duration of the Twinning contract. The final report will be accompanied by a verification expenditure report.

Reports will follow the templates of Annex C4/Annex C5 of the Twinning Manual. In addition to these formal reporting stages, the twinning partners are obliged to inform in writing the Contracting Authority (CFCD) as well as the final beneficiary of the action of any critical aspects or conditions of project implementation, or any amendments/modifications necessary within the budget.

All reports must be produced in the English in electronic and hard copy.  These reports shall be signed by both Project Leaders. Each report must be presented in electronic format two weeks prior to the Steering Committee meetings and in two hard copies to the Project Beneficiary, the Contracting Authority, the members of the Steering Committee Meeting and the EU Delegation.

The final versions should incorporate any comments and discussions during the Steering Committee meetings. The template of the report is detailed in Annex C4 to the Twinning manual.

Failure to submit satisfactory reports in time may lead to the decision to suspend EU financing for the project.

- Budget

The project will be implemented through a Twinning Contract with a maximum budget of EUR 1.000.000, out of which 95% IPA funds and 5% National co-financing.

Apart from the National co-financing, all twinning contracts as a rule must provide Beneficiary co-financing on the side of the Beneficiary institution (Commission for Protection of Competition), for the purpose of covering costs not covered by the EU as per Twinning manual, point 5.13:

- Travel by the beneficiary officials from their countries to a MS or between MS;

- Facilities for the Member State experts: adequately equipped office space, telephone, e-mail services, fax, photocopiers, computer, internet access, secretarial support and access to information.

- Organisation of seminars (incl. hall rental, provision of refreshments, printing seminar materials and other logistical support)

For the needs of the project, a full time assistant and a full time translator-interpreter has to be appointed under the project budget.

The full time translator will be involved in the training activities as translator. Where necessary (for example during training activities, translation of project documents/reports and materials, organizational activities) the project will hire an additional translator with costs covered by the project.

The following expenses are also to be covered with the project funds:

- Visibility Cost (max up to EUR 5000 );

- Audit certificate cost;

- Translation of training materials, legislation, reports, etc

- Per diems and incidental costs for the study tour and intern ship activity.

The location of the project will be at the premises of the Beneficiary, the Commission for Protection of Competition (CPC). The Beneficiary will ensure appropriate support and basic equipment for the work of the experts. This includes, office space, telephone and fax and other necessary facilities. This contribution should also include selection of trainees (in consultation with the MS experts), as well as providing the MS experts with the documents necessary for project implementation.

The twinning partner (project beneficiary) shall provide all available assistance to solve unforeseen problems that the MS twinning partner(s) might face.

- Implementation Arrangements

6.1 Implementing Agency responsible for tendering, contacting and accounting

The CFCD will be the implementing agency and will be responsible for all procedural aspects of the tendering process, contracting matters and financial management including payment of project activities. The Head of CFCD will act as the Programme Authorizing Officer (PAO) of the project:

Mrs. Radica Koceva (PAO)

Central Financing and Contracting Department

Ministry of Finance

e-mail: radica.koceva@finance.gov.mk

6.2 Main counterpart in the BC

Project Leader shall be the main counterpart in the BC, and will be directly responsible for co-ordination and management of the project from the beneficiary side and will support the Twinning project team in organisational and technical matters.

Commission for Protection of Competition

Contact persons and contact details

BC Project Leader

Chedomir Kraljevski,

President of the Commission

Mito-Hadzi Vasilev Jasmin b.b 1000 Skopje

Tel: +389 2 3298 666

Fax: +389 2 3296 466

e-mail: cedomir.kraljevski@kzk.gov.mk

RTA counterpart

Jovan Todorov,

Head of State Aid Control Department

Dame Gruev 1, 1000 Skopje

Tel: +389 2 3298 666

Fax: +389 2 3296 466

e-mail: jovan.todorov@kzk.gov.mk

6.3 Contracts

One (1) Twinning contract is foreseen for the implementation of the above mentioned activities.

- Implementation  Schedule (indicative)

7.1 Launching of the call for proposals (Date)

March 2011

  - Start of project activities (Date)

January 2012

  - Project Completion (Date)

The project implementation period (duration of the work plan) will be completed 18 months after the commencement date of the Project.

  - Duration of the execution period (number of months)

The project will have 21 months overall execution period with an implementation period of 18 months. (The duration of the Twinning work plan is increased by 3 months, to cover the initial setting in of the RTA and the proper wrapping up of the Twinning Project).

- Sustainability

By strengthening capacities of the CPC and state aid providers to enforce legislation, the project is expected to contribute to the development of effective state aid policy and ex-ante monitoring.

Further improvement of the accountability and transparency in state aid programming will have a positive influence on increasing trust of the general public for the budget management system, and for increasing of the competitiveness of the economy.

The project will upgrade the level of professional competence of the CPC staff in the area of state aid control and will furthermore ensure effective enforcement of EU competition and state aid policy.

The achievements of a Twinning project (with its mandatory results) should be a permenant asset to the CPC and  appropriately mechanisms should be put in place by the Commission in order to disseminate and consolidate the results of the project.

The enhanced capacity of the CPC staff will be long lasting depending on the effective knowledge transfer to be developed by the Twinning.

- Crosscutting issues (equal opportunity, environment, e.t.c)

The cross-cutting issues will be addressed throughout the project. Up to 10% of the budget for capacity building – through short term expertise - may be allocated to assist the beneficiary to comply with European standards and best practices, implement relevant existing Government strategies and develop internal measures to ensure each cross-cutting issue is appropriately mainstreamed.

The mainstreaming of the cross cutting issues is regarded on two different levels:

Ensuring that the internal policies, structure or operating procedures of the beneficiary agency will conform to and promote the relevant principles outlined per section below.

Ensuring that the products, outputs produced by the beneficiaries (e.g. laws, regulations, policies, and strategies) will conform to and promote the relevant principles outlined per section below.

  - Civil Society development and dialogue

Civil society issues will be taken into consideration of such issues where relevant and appropriate in the project.

  - Environmental considerations

Any ecological friendly initiative which can be taken will have to be implemented.

  - Equal Opportunity and non-discrimination

The training activities will include a specific component to train beneficiary staff in the implementation of the Government Gender Strategy, while reference will be made to the EC Programme of Action for the mainstreaming of gender equality in community development cooperation (2001-06).

  - Minority and vulnerable groups'

Whereas the main reference in the country in relation to minority groups is the Ohrid Framework Agreement, in an EU context, reference is made to the “Race directive” of 2000 (200/43/EC of 29 June), which has an important impact on employment (including vocational training, working conditions, social protection etc.) and is also a crucial aspect of the acquis. The beneficiary will be assisted to implement an ‘internal minority and vulnerable group assessment’ to identify areas where it could improve its internal performance vis-à-vis minorities or other vulnerable groups. In view of the specific sector, it is not expected that the minority aspects will be of prime relevance for the outputs the CPC.

  - Good governance, with particular attention to fight against corruption

Specific action instruments for the good governance, with particular attention to fight against corruption, will be incorporated on a horizontal basis, as part of the training activities. To this aim, particular attention will be put in the prevention of corrupt practices, mainly through the raising political and public awareness.

  - Communication and publicity

All requirements to ensure the visibility of EU financing will be fulfilled in accordance with R. (EC). N. 718/2007.

- Conditionality and sequencing

  - Conditionality

In order to enable successful implementation of the project, following preconditions must be met before the start of the implementation:

- Endorsement by all key stakeholders of the Twinning Fiche, specifications for the individual contracts to be engaged;

- Timely allocation of working space and facilities by the beneficiary for the twinning project before the completion of the tender procedure;

- Participation in the selection process by the beneficiary as per EU Twinning regulations;

- Appointing counterpart personnel by beneficiary prior to launch of the project fiche ;

- Provision of necessary authorisations for co-operation and sharing of information with all key stakeholders, co beneficiaries and related deployed advisory resources;

- Appointing relevant staff by the beneficiaries to participate in training activities;

- Organisation and appointment of members of working groups, steering and coordination committees, as per work plan of the project;

  - Sequencing

Keys milestones will be:

  - Approval of the Twinning project fiche;

  - Completion of the selection of the twinning partner;

  - Signature of the Twinning contract, including the Twinning Work Plan;

  - Commencement of the implementation of the twinning (inter alia, the arrival in the country of the Resident Twinning Adviser);

  - End of the implementation period;

  - Submission of the final report.

ANNEXES TO PROJECT FICHE :

  - Logical framework matrix in standard format (compulsory)

  - List of relevant Laws and Regulations (optional)

ANNEX 1: Logical framework matrix in standard format (compulsory)

| LOGFRAME PLANNING MATRIX FOR | Programme name and number IPA - Transition Assistance and Institution Building (TAIB) 2009; Twinning Number: MK2009/IB/FI/01 |  |  |
| --- | --- | --- | --- |
|  | Contracting period expires two years from the date of the conclusion of the Financing Agreement | Execution period expires two years from the final date for contracting | Disbursement period expires one year from the final date for execution of contracts |
|  | Total budget: EUR 1.000.000 |  | IPA budget: EUR 950.000 |

| Overall objective | Objectively verifiable indicators | Sources of Verification |
| --- | --- | --- |
| The overall objective is to promote and strengthen market competition through improvement of the state aid system thereby favouring continuing economic growth in the country. | Enforcement records of competition and state aid acquis in line with Internal Market practise | CPC records EU Commission reports NPAA State Aid Annual Report |

| - Project purpose | - Objectively verifiable indicators | - Sources of Verification | - Assumptions |
| --- | --- | --- | --- |
| The purpose of the project is to enhance the capacity of CPC to manage and enforce EU state aid policies, to raise knowledge and understanding by state aid providers and to improve the overall planning, reporting and monitoring of state aid. | Increased number and improved quality of decisions taken by the CPC Improved public perception of the Competition authority as a protector of a free market competition Implementation of effective compliance programme | Annual report of the CPC EU Commission’s Regular Report other CPC records Project reports Court records survey of public perception State Aid Annual Report | Good and continuous interaction between the CPC and other stakeholders relevant to the enforcement of state aid and competition rules |

| - Results | - Objectively verifiable indicators | - Sources of Verification | Assumptions |
| --- | --- | --- | --- |
| The mandatory results to be achieved under Component 1 are: - Complement the existing legal gap analysis of primary and secondary legislation (in case of detected necessity); - Regional State Aid schemes are developed; - A transparent and reliable operational database for de minimis and Services of General Economic Interest is in function; - A State aid monitoring methodology for de minimis aid, preliminary and full investigations, enforcement is developed and implemented by CPC; - Acquired capacity to draft comprehensive State Aid annual reports; - CPC case –handlers trained on State Aid case law, economics and procedures. | Measurable indicators for Component 1: - Legal gap analysis completed ; - Increased number of regional aid schemes developed - Increased amount of data available in the operational database; - 6 -10 state aid case-handlers trained on how to conduct monitoring and investigation, as well as on legal, economic and sector specific cases - More detailed annual reports - 20 CPC participants to 2 study visits; 20 CPC participants to 4 seminars | Project reports CPC records State Aid Annual Report New visual identity of the CPC | Continuation of keeping records including interchange of information on court decisions etc. CPC has the budget, staff etc. required for enhancing capacity. |
| The mandatory results to be achieved under Component 2 are: - Established internal procedures and methodologies for reporting and information flows from state aid providers to the CPC, including local government units and state funds and agencies; - State aid providers (Government of the former Yugoslav Republic of Macedonia, state administrative organs, units of local self-government and other organ or institution providing or planning to provide State aid ) are aware of state aid rules in terms of increased number of initiate procedure for assessment of the compatibility of State Aid on a request by third parties; - Raised awareness of the business community, about state aid rules and procedures (i.e. how to complain on state aid); - Judiciary is trained to deal with state aid cases in terms of increased number of judges dealing with state aid, track-records and improved quality of court decisions; - State aid inventory at local self-government level is better structured. | Measurable indicators for Component 2: - Increased number of notifications by state aid providers of at least 20%; - Increased number of initiated procedures for assessment of compatibility of state aid of at least 20%; - At least 20 governmental officials trained on state aid rules and procedures; - At least 400 representatives of the business community participating to the information campaigns; - Indicatively, 18 Seminars and in-house workshops for expert staff members of the state aid providers - At least 3 judges trained on state aid cases | CPC records Project reports New state aid database CPC records (number of antitrust decisions brought) | Continuation of keeping records including interchange of information With state aid providers, etc. CPC has the budget, staff etc. required for enhancing capacity. |

| Activities | Means | Costs | Assumptions |
| --- | --- | --- | --- |
| - Component 1: Strengthening institutional and administrative capacity of the CPC, in line with EU acquis and European good practice in the field, through establishment of a functioning State Aid monitoring, notification and control system in the country. - Activity 1: Providing of legal gap analysis; - Activity 2: The MS Partner in cooperation with CPC will design, implement and put in function an operational state aid database; - Activity 3: The MC Partner, together with the CPC, will design and put in place a methodology to draft state aid annual reports and to develop state aid schemes; - Activity 4:The MS Partner, together with the CPC, will develop methodologies and procedures to facilitate the decision making process, this will include also monitoring and investigations as well as handling particularly sensitive sector/ cases; - Activity 5: On-the-job training of 6-10 CPC staff in order to deepen and specialise the knowledge in state aid case law, economics and procedures; - Activity 6: Conducting of Training needs assessment for CPC staff ; - Activity 7: Study visit for 10 participants from the CPC to familiarize with up-to-date state aid practises in areas of ( non exhaustive list) aid for financial sector, fiscal aid, risk capital, regional aid, rescue and restructuring aid, de minimis inventory with smaller number of cases currently encountered; this trip will show to the employees of the CPC daily work and best practise of the counterpart in the MS; - Activity 8: Study visit for 10 participants from the CPC to familiarize with up-to-date state aid practises in areas of ( non exhaustive list) SME’s aid, environmental aid, training aid, employment aid, research and development with smaller number of cases currently encountered; this trip will show to the employees of the CPC daily work and best practise of the counterpart in the MS; Activity 9: 4 seminars in EU Member States on Regional Aid, Rescue and Restructuring Aid, Environmental protection, Services of General Economic Interest, respectively for 5 persons from the CPC; - Component 2: Improvement of state aid awareness making the CPC recognisable in the wider public, and improvement of control and enforcement in state institutions, government agencies, regional and local government, and the business sector. - Activity 1: Deliver seminars and in-house workshops with state institutions and local government units in order to raise awareness on state aid policy and rules, including reporting and operation of the inventory; increase awareness of aid providers and disseminate information to the CPC and the public; - Activity 2: Develop, organise, and deliver training to at least 20 government officials, mainly targeting the bodies implementing state aid policy in related areas, as well create ex-ante notification discipline and ex-post monitoring of CPC’s decisions and opinions; - Activity 3: Organize information campaign for business sector specifically targeted at sectors receiving state aid; - Activity 4: 6 Workshops for judges in order to familiarize with up-to-date judiciary state aid practice; - Activity 5: Provide expertise on structuring of inventory on a local self-government level; - Activity 6: Organize information campaign for journalist who work on economic and legal issues - Activity 7: Awareness raising activities concerning state aid policy targeting the business sector and public companies.. | Twining arrangement | Total budget EUR 1.000.000 IPA budget: EUR 950.000 | Project will be building on achieved results of the 2004 CARDS twinning project on Approximation of the legislation in the competition policy and strengthening of the administrative capacity of the body for competition protection. |

ANNEX 2: List of relevant Laws and Regulations (optional)

- Law on protection of competition (Official Gazette of Republic of Macedonia No. 4/05)

- Law amending the law on protection of competition (Official Gazette  of Republic of Macedonia no.70-06)

- Law amending the law on protection of competition (Official Gazette of Republic of Macedonia no.22/07)

- Regulation on block exemption granted to technology transfer agreements licence know-how (06.06.2006)

- Regulation on block exemption of granted to agreements on distribution and servicing of motor vehicles (06.06.2006)

- Regulation on block exemption granted to horizontal specialisation agreements (06.06.2006)

- Regulation on the form and the content of the notification and criteria on concentrations' evaluation (06.06.2006)

- Regulation on block exemption granted to vertical agreements (06.06.2006)

- Regulation on block exemption granted to agreements in the insurance sector (06.06.2006)

- Regulation on block exemption of horizontal RD agreements (06.06.2006)

- Regulation on Agreements of minor importance (06.06.2006)

- Law on state aid (Official Gazette of Republic of Macedonia No.. 24/03)

- Law amending the law on state aid (Official Gazette of Republic of Macedonia No. 70/06)

- Law amending the law on state aid (Official Gazette of Republic of Macedonia No. 55/07)

- Regulations on procedures and forms of notification of state aid (Official Gazette of Republic of Macedonia  No. 81/03)

- Regulations establishing conditions and procedures for granting aid for rescue and restructuring of firms in difficulty (Official Gazette of Republic of Macedonia No. 81/03 & 83/07)

- Regulations establishing conditions and procedures for granting regional aid (Official Gazette  of Republic of Macedonia No. 81/03)

- Regulations establishing conditions and procedures for granting horizontal aid (Official Gazette of Republic of Macedonia No. 157/07)

- Annual Report of the Commission for Protection of Competition for 2007

- Regulation amending the Regulation on establishing condition and procedure for granting regional aid (Official Gazette of Republic of Macedonia No.118/09)

- Annual Report of the Commission for Protection of Competition for 2008

List of abbreviations:

  - AP- Accession Partnership

  - BERIS- Business Environment Reform and Institutional Strengthening Project

  - CFCD- Central Financing and Contracting Department

  - CPC-Commission for protection of competition

  - LPC-Law on protection of competition

  - MS-Member state

  - PSC- Project Steering Committee

  - RTA- Resident Twinning Adviser

  - SAA- Stabilisation and Association Agreement

  - SME’s- small and medium sized enterprises

  - STE- short-term experts

  - TAIB- Transition Assistance and Institution Building

?	See. Article 62 and 63. of R. (EC). N. 718/2007