TWINNING PROJECT FICHE

- Basic Information

  - Programme: Support to the Implementation of the Action Plan Programme (SAPP-I)

  - Twinning Number: JO10/ENPAP/TR/15

  - Title: The Implementation of the Roadmap for the Conclusion of the Agreement on Conformity Assessment and Acceptance of Industrial Products (ACAA)

  - Sector: Trade and Industry

  - Beneficiary country: The Hashemite Kingdom of Jordan

2.    Objectives

2.1 Overall Objective:

The overall objective of the project is to fulfil the commitments of the Government of Jordan in the context of the EU-Jordan Association Agreement which will lead to the free movement of goods in certain industrial sectors between Jordan and the European Union through the signature of the ACAA Agreement.

2.2 Project purpose:

The purpose of the project is to assist Jordan Institution for Standards and Metrology (JISM) and relevant stakeholders in implementing the ACAA Roadmap in preparation for the negotiation and signature of the ACAA Agreement.

2.3 Contribution to National Development Plan/Cooperation agreement/ Association Agreement/ Action Plan

The project will contribute in general to the Execution Programme for Economic and Social Development for 2010-2012, and in specific to Component 2: Developing and Enhancing the Business Environment, and its two relevant initiatives:

- Programme to Support the Industry; and

- Enhancing the Competiveness of the Jordanian Product in International Markets and Exporting to New Markets.

This project is also relevant to Article 68 of the EU-Jordan Association Agreement, which states that: Cooperation in this field will be aimed in particular at:

- Increasing the application of community rules in the field of standardization, metrology, quality standards, and recognition of conformity;

- Upgrading the level of Jordanian conformity assessment bodies with a view to the establishment, in due time and to the extent feasible, of agreements of mutual recognition of conformity assessment;

- Developing structures and bodies for the protection of intellectual, industrial and commercial property, for standardization and for setting quality standards.

Thus, the project will contribute to the facilitation of Jordanian exports to the EU through the approximation and enforcement of EC horizontal and vertical legislations as well as the EC regulatory framework in the fields of conformity assessment, market surveillance and accreditation, in the context of the European Neighbourhood Policy and Palermo Action Plan for the Free Movement of Industrial Products, as well as the requirements of Article 21 of the EU-Jordan Action Plan, aiming at facilitating market access of industrial products, which will result in the conclusion of the Agreement on Conformity Assessment and Acceptance of Industrial Products, the so-called ACAA, in priority sectors. The conclusion of the ACAA Agreement is the key constituent towards the creation of an EU-Jordan free trade area.

3.    Description

  - Background and Justification:

The implementation of the EU Jordan Association Agreement requires the adoption of several measures to enhance trade facilitation between the two trading partners. This is done through the approximation and enforcement of EC legislations and the regulatory framework as well as the application of European practices in the fields of conformity assessment, market surveillance and accreditation, in accordance to the Palermo Action Plan for the Free Movement of Industrial Products, which will eventually lead to the signature of the Agreement on Conformity Assessment and Acceptance of Industrial Products (ACAA) in priority sectors.

In this context, and through the EU funded a Twinning Project under the Support to the Implementation of the EU-Jordan Association Agreement Programme (SAAP I) entitled “Strengthening of the Jordan Institution for Standards and Metrology (JISM) for its compliance with the EU-Jordan Association Agreement”, JISM has upgraded its legislative framework and practices and gained international recognition and acceptance. For instance, an amendment to the Law no. 22/2000 of Standards and Metrology has been drafted and the draft Law on Accreditation has been developed. Accreditation has been granted for the testing and certification services, as well as for the Jordanian National Metrology Institute, while the Jordan accreditation body is on the way to sign the bilateral agreement for recognition at the European and international levels. In addition, JISM has become an affiliated member of the CEN and a partner in Perinorm database that provides monthly updated information on international, European, American and other national standards and technical regulations. Moreover, the implementation of a proactive market surveillance concept has been initiated, and the approximation of EC Directives of the New Approach that cover the priority industrial sectors, i.e.  Electrical products, Toys, Construction Products, Gas Appliances, Pressure Equipment and Measuring Instruments, and the adoption of referenced harmonized standards have been initiated.

Another EU funded complementary Technical Assistance Project for the Approximation of the EC legislations in Priority Sectors under Support to the Implementation of the EU-Jordan Association Agreement and the Action Plan of the European Neighbourhood Policy  (SAAP II), that started in October 2008 and ended by August 2009, resulted in identification of industrial products under the scope of the ACAA and all other additional EC legislations relevant to those products, i.e. Electromagnetic Compatibility, Energy Efficiency for Specific Household Appliances, Energy Labelling of Household Appliances, Efficiency Requirements for New Hot Water Boilers Fired with Liquid or Gaseous Fuels, Eco Design, Restrictions of Certain Dangerous Substances and Preparations, Restriction of Use of Certain Hazardous Substances, Packaging and Packaging Waste, Cosmetics, Simple Pressure Vessels, Transportable Pressure Equipment, Pre-packaging, and Non Automatic Weighing Instruments.  Regulatory bodies and market surveillance authorities that will approximate and enforce those legislations were specified, and a gap analysis study with the current legislative situation in Jordan was conducted. The economic and social impact of implementing the vertical EC legislations has been assessed and inspectors as well as economic operators got acquainted with the technical aspects of the European legislations through trainings and awareness seminars. A market strategy and annual plan was drafted and the terms of reference for the Market Surveillance National Committee was prepared and circulated through the first meeting of the Committee. A major output of the Technical Assistance Project was the development and approval of ACAA Roadmap by high officials from the relevant legislative authorities, which needs to be implemented in order to start the official negotiations of the ACAA Agreement. The ACAA Road is annexed in Annex III.

Therefore, this Project will contribute to the implementation of the major steps of the ACAA Roadmap in order to prepare Jordan for the signature of the ACAA. This project is vital to assist Jordanian regulatory authorities in the approximation of the identified EC legislations as Jordanian legislations and the withdrawal of conflicting legislations. The project shall also facilitate the assessment of economic and social studies prior to the enforcement of the approximated legislations, in order to identify technical challenges that will be faced by the industry and accordingly to specify the necessary transitional periods before the enforcement.

On the other hand, the Project shall support the operation of proactive market surveillance activities on those priority products to ensure that only safe products which comply to the essential requirements of the approximated legislations are placed in the Jordanian Market, and thus assure the protection of consumers' heath and safety and prevent the circulation of dangerous products between Jordan and the EU. Apparently, the market surveillance system in Jordan will be reinforced through the implementation of EC regulations and decisions on market surveillance, marketing of products and product safety, together with the use of an electronic system to exchange information on detected dangerous products in the market.

Likewise, in order to assist the Jordanian industry in complying with the essential requirements of the approximated EC legislations and in using the adopted referenced harmonized standards, information and technical help services need to be developed with competent staff to assist the industry in identifying the legislations and standards relevant to their products and to help them overcome their technical problems.

Finally, Jordanian conformity assessment bodies need to be qualified and notified to the European Commission to become competent notified bodies, so as to support the Jordanian industry in performing the vital conformity assessment procedures according to the conformity assessment modules specified in the EC Directives, based on which the CE Mark is affixed on their products. These notified bodies with be authorized and notified by a notifying authority that will be established and operational under this Project. The notifying authority will use the services of the national accreditation body, upon the qualification and expansion of the accreditation scope within this Project, to assess the competence of the notified bodies.

3.2 Linked activities (other international and national initiatives):

The project entitled “Strengthening of the Jordan Institution for Standards and Metrology (JISM) for its compliance with the EU-Jordan Association Agreement” that was implemented from September 2005 till December 2007 and had assisted in developing the quality infrastructure and the technical capacities in the fields of standards, metrology, conformity assessment and accreditation. In addition to another EU funded complementary Technical Assistance Project for the Approximation of the EC legislations in Priority Sectors under Support to the Implementation of the EU-Jordan Association Agreement and the Action Plan of the European Neighbourhood Policy (SAAP II) that started in October 2008 and ended by August 2009.

In addition to the two above mentioned EU funded projects, other EU funded programmes and projects such as those granted to the Jordan Enterprise Development Corporation (JEDCO) to promote Jordanian exports should be associated to the results of the impact assessment studies and the identification of technical and technological obstacles that the industry might encounter in the implementation of the approximated EC legislations and the referenced harmonized standards.

3.3 Results:

The expected results from the project are:

- Approximation and enforcement of all identified and valid EC legislations, including the adoption of referenced harmonized EN standards, relevant to the industrial products which have been selected as priority sectors.

- Legal framework required for the introduction of EU regulations is established.

- All EN harmonized standards relevant to priority sectors are adopted as national standards.

- Proactive market surveillance activities are operated and instructions for market surveillance are established.

- A market surveillance concept  in conformity with the EU system is developed and implemented effectively.

- A National Market Surveillance Committee is established.

- Market Surveillance responsibilities on the different sectors are designated and accordingly a market surveillance strategy and plan is established and implemented.

- Advanced training on approximated legislations and adopted standards is provided to market surveillance staff.

- A notifying authority is established and in operation, and accordingly at least one competent Jordanian notified body for each selected EC Directive is accredited and notified.

- Potential notified bodies are qualified to be approved by the European Commission.

- Staff trained in all scopes of approximated legislations and adopted standards.

4.  Information and technical help is provided to the industry, and close cooperation with European bodies in charge of legal and scientific metrology (EURAMET and WELMEC)

- Technical information centre established and technical help services are available to be provided by the centre to the relevant industries.

- Information Centre staff are trained in all scopes of approximated legislations and adopted standards.

3.4 Activities:

The activities that will be carried out to achieve each of the expected results are:

1. Approximation and enforcement of all identified and valid EC legislations, including the adoption of referenced harmonized EN standards, relevant to the industrial products which have been selected as priority sectors.

1.1 Clarify and update a list of all current and latest EC legislations relevant to the priority products.

1.2 Identify gaps and contradicting Jordanian legislations issued by relevant authorities.

1.3 Conduct consultation campaigns with stakeholders and impact studies on all EC legislations to be approximated, so as to identify the effect on the industry and technical problems and obstacles faced by them and also in testing capabilities to be used for market surveillance purposes.

1.4 Train legislative authorities on all identified EC legislations.

1.5 Conduct awareness seminars and product oriented training sessions to the industry.

1.6 Assess any technical conflicts with other free trade agreements and international relations and organizations such as the World Trade organization / Technical Barriers to Trade Agreement (WTO/TBT), including trade concerns of WTO/TBT members on relevant EC legislations.

1.7 Assist in drafting the approximated Jordanian legislations and in the amendment of conflicting legislations, and provide advice on modifying these drafts based on the feedback from the European Commission on their legal texts.

1.8 Assist in issuing and enforcing the approximated legislations in consultation with the Jordanian industry and other stakeholders, and provide advice on transitional periods according to the results of the impact studies.

1.9 Select three pilot industrial companies per priority sector and provide consultation services to fully comply with EC legislations.

1.10 Involve policy makers to further implement EC legislations.

1.11 Assist in adoption of all harmonized EN standards and withdrawal of conflicting Jordanian Standards.

1.12 Provide guidance in applying to join CENELEC as an affiliated member and in participation in meetings of Technical Committees in the areas of priority sectors at CEN and CENELEC.

2. Proactive market surveillance activities are operated and instructions for market surveillance are established.

2.1 Assist in establishing new market surveillance instructions as stated in the amendment of Law on Standards and Metrology, in accordance to the new European Regulation No 765/2008 on requirements for accreditation and market surveillance relating to the marketing of products  that have been effective since the beginning of 2010, and consult on adjusting the quality management system accordingly.

2.2 Train inspectors on the lately approximated EC legislations and on preparations for market surveillance, conduction of inspections and follow-up activities.

2.3 Conduct joined market surveillance inspections in Jordan and in EU countries.

2.4 Establish communication and coordination mechanisms to acquire and provide the necessary information on accidents relevant to unsafe products.

2.5 Coordinate market surveillance activities within the Market Surveillance National Committee, as per the amendment of Law on Standards and Metrology, and develop and launch Market Surveillance plans accordingly.

2.6 Establish links of the Jordanian market surveillance system to the European system.

3. A notifying authority is established and in operation, and accordingly at least one competent Jordanian notified body for each selected EC Directive is accredited and notified.

3.1 Develop instructions and operational procedures on how to assess and notify competent notified bodies, according to the Decision No 768/2008/EC of the on a common framework for the marketing of products.

3.2 Identify potential notified bodies to be granted assistance, perform an initial assessment on their capabilities, and provide consultations accordingly.

3.3 Train potential notified bodies on EC legislations and EN standards.

3.4 Set rules of coordination with the Jordanian Accreditation Body on assessments to be conducted on potential notified bodied, under the supervision of the European Commission.

3.5 Develop accreditation policies and procedures for accreditation of notified bodies according to European legislations.

3.6 Train assessors on EC legislations and on how to conduct assessments on notified bodies relevant to EC Legislations and EN standards.

3.7 Identify major technical gaps at selected potential notified bodies.

3.8 Qualify a number of potential notified bodies to be granted accreditation and recognition by the notifying authority.

3.10 Establish official contacts with European notified bodies.

4. Information and technical help is provided to the industry and close cooperation with European bodies in charge of legal and scientific metrology (EURAMET and WELMEC)

.

4.1 Establish an information centre and technical help services to be provided to the industry.

4.2 Train information staff on EC legislations and EN standards.

4.3 Train staff on how to provide information services and technical help.

4.4 Provide advice on communication tools and media used to provide information services.

4.5 Conduct five informational events for the public.

4.6 Publicize and market information services and technical help, including preparation of promotional materials and publications.

3.5 Means/ Input from the MS Partner Administration:

    - Profile and tasks of the Project Leader

      - Tasks

- He/she will act as the counterpart of BC Project Leader and ensures in close cooperation the overall steering and coordinate of the project;

- MS Project Leader, who continues to work in his/her MS administration but who devotes a portion of his/her time to conceiving, supervising and coordinating the overall thrust of the project;

- He/she will be the one to sign all official documents yet MS PL can delegate RTA to sign side letters on his/her behalf;

- He/she will also co-ordinate the Project Steering Committee (PSC) from the MS side, which will meet every three months at the Jordan Institution for Standards and Metrology.;

- He/she acts as the counterpart of the MS Project Leader and ensures in close co-operation the overall steering and co-ordination of the project.

      - Profile

- University degree in a related field or equivalent;

- At least 15 years experience in providing training and consultation services in the field of EC vertical and horizontal legislations;

- Working experience in assisting regulatory bodies, market surveillance authorities, accreditation bodies and notified bodies is an asset;

- Previous experience in managing similar EU funded projects would be an asset;

- In-depth knowledge of the EU Aquis Communautaire;

- Experience on the enforcement and implementation of the EC Regulations and decisions relevant to marketing of products, product safety, market surveillance, accreditation, conformity assessment  and notification requirements;

- Capacity to monitor and evaluate the project logframe and action plan;

- Capacity to establish efficient working relations;

- Excellent project management capacities;

- Strong communication and presentation skills;

- Good working knowledge of English including effective spoken and written reporting abilities.

    - Profile and tasks of the RTA

      - Tasks

- The Resident Twinning Advisor will take responsibility for the smooth and proficient implementation of the project, while ensuring that the specific objectives and activities outlined are fully achieved;

- He/she will coordinate closely with all relevant institutions involved in the work of the Jordan Institution for Standards and Metrology as well as with any other relevant stakeholder;

- He/she will meet with the Jordan Project Leader at least once a week, and hold regular meetings with other counterparts as regularly as possible;

- The RTA will co-ordinate with the MS Project Leader in ensuring that each input is fulfilled, by ensuring that each Medium and Short-Term Expert (MTE & STE) has prepared a clear curricula and detailed Terms of Reference to be included during the preparation of the contract.

      - Profile

- University degree in a related field or equivalent;

- At least 10 years experience in supervising technical assistance and capacity-building activities in the field of EC vertical and horizontal legislations;

- Working experience in a regulatory body, market surveillance authority or a notified body is an asset;

    - In-depth knowledge of the ACAA Agreement and of the approximation and enforcement of the EC horizontal and vertical legislations;

- Experience on the enforcement and implementation of the EC vertical and horizontal legislations, markets surveillance activities as well as on the operation of notified bodies;

- Capacity to supervise and co-ordinate all administrative and technical aspects of the project;

- Capacity to establish efficient working relations;

- Excellent project management capacities;

- Good working knowledge of English; including effective spoken and written reporting abilities;

- Strong communication and presentation skills.

3.5.3 Profile and tasks of the mid-term and short-term experts

Four medium term experts are expected to work in this twinning project with the following qualifications for each of the project components

3.5.3.1 Mid term Expert 1:

The Senior Legal Advisor will be responsible for legal activities of the project regarding the approximation and enforcement of the EC legislations.

He must have the following qualifications and skills:

- University degree in a related field or equivalent;

- At least 10 years experience in legal advice in the field of EC Directives and horizontal legislations;

- At least 10 years of relevant experience, preferably in accession countries or Turkey;

- In-depth knowledge of the approximation and enforcement of the EC horizontal and vertical legislations;

- Legal advice experience on legal cases regarding the essential requirements of the EC Directives;

- Capacity to establish efficient working relations;

- Good working knowledge of English; including effective spoken and written reporting abilities;

- Strong communication and presentation skills.

3.5.3.2 Mid-term expert 2: Senior expert on Market Surveillance

The senior expert on market surveillance will be responsible for the achievement of the results expected in the market surveillance component of the project, in cooperation with the counterpart from JISM. Both will be responsible for coordination with the RTA, JISM and other organizations involved for a successful implementation of the market surveillance component.

He must have the following qualifications and skills:

- University degree in engineering or science;

- At least 5 years experience in supervising capacity-building activities in the field of market surveillance;

- At least 10 years of relevant valid experience in market surveillance according to European practices;

- Previous relevant experience in market surveillance technical assistance projects implementation;

- Has performed market surveillance and inspection activities;

- Has experience in using RAPEX and any other European market surveillance information system;

- Has developed market surveillance procedures and inspection product checklists while working with a European market surveillance authority;

- Experience in the requirements of the European Regulation No 765/2008 on requirements for accreditation and market surveillance relating to the marketing of products;

- Good knowledge of the situation in Jordan regarding socio-economic development and quality infrastructure development would be an advantage;

- Capacity to establish efficient working relations;

- Good working knowledge of English; including effective spoken and written reporting abilities;

- Strong communication and presentation skills.

3.5.3.3 Mid-term expert 3: Senior expert on Notification and Accreditation

The senior expert on notification and accreditation will be responsible for the achievement of the results expected in the accreditation and notification component of the project in cooperation with the counterpart from JISM. Both will be responsible for coordination with the RTA, JISM and other organizations involved for a successful implementation of the notification and accreditation component.

He must have the following qualifications and skills:

- University degree in engineering or science;

- At least 5 years experience in supervising capacity-building activities in the field of notification and accreditation of notified bodies;

- At least 5 years experience in supervising capacity-building activities in the field of product certification and testing;

- At least 10 years of relevant and recent experience working in a national accreditation body of testing laboratories, inspection and certification bodies which is a full member of the International Laboratory Accreditation Cooperation (ILAC) and International Accreditation Forum (IAF) and/or a notifying authority in EU countries;

- Previous experience of working at a notified body is an asset;

- Has performed audits on notified bodies;

- Experience in the development of European accreditation practices (standards, guidelines and procedures) and/or notification practices would be preferable;

- Capacity to establish efficient working relations;

- Excellent project management capacity;

- Good knowledge of the situation in Jordan regarding socio-economic development and quality infrastructure development would be an advantage;

- Good working knowledge of English; including effective spoken and written reporting abilities;

- Strong communication and presentation skills.

3.5.3.4 Mid-term expert 4: Senior expert on Information and Technical Help

The senior expert on information and technical help will be responsible for the achievement of the results expected in the information and technical help component of the project in cooperation with the counterpart from JISM. Both will be responsible for coordination with the RTA, JISM and other organizations involved for a successful implementation of the information and technical help component.

He must have the following qualifications and skills:

- University degree in engineering or science;

- At least 5 years experience in supervising capacity-building activities preferably in providing services of information and technical help relevant to the implementation of EC legislations;

- At least 10 years of relevant and recent experience working in an information centre or notified body in an EU country, which provides information or technical help relevant to the implementation of EC legislations;

- Previous experience of working at Euro Info Centre is an asset;

  - Practical and substantial experience in publicizing and marketing of information and technical help services, including the preparation of promotional materials and publications and conduction of awareness events;

- Capacity to establish efficient working relations;

- Excellent project management capacity;

- Good knowledge of the situation in Jordan regarding socio-economic development and quality infrastructure development would be an advantage;

- Good working knowledge of English; including effective spoken and written reporting abilities;

- Strong communication and presentation skills.

3.5.4. Tasks

The MTEs will be responsible for:

- Reviewing the current systems tackled by this twinning project.

- Providing suggestions, recommendations for improvement of current systems.

- Conducting local training courses and workshops according to the detailed log Frame matrix

- Suggesting detailed work plan for the implementation of their recommendations in lien with the achievements of the project’s mandatory results out lined in the log Frame matrix.

In coordination with the RTA, the Short terms curricula would be verify during the preparation of the contract and insert in it

The RTA and the mid-term experts will be assisted by a number of short-term experts identified accordingly to the activities mentioned above .

An indicative number of 5 CVs for short-term experts other than mid-term experts to cover the above-mentioned components should be provided within the proposal and examined prior to the signature of the contract for the implementation of the Project. All short-term experts must have a minimum of 7 years relevant experience in the appropriate field and a relevant university degree. The role, profile and duration of the short-term experts will be defined in the work plan in accordance to the activities to be undertaken.

4. Institutional Framework

The main beneficiary institution is the Jordan Institution for Standards and Metrology and its relevant technical departments such as the Standardization Department, the Inspection and Surveillance Department, the Accreditation Unit, the Stakeholder Support Unit, the Metrology Department and the Knowledge Management Department. The organizational Structure of the Jordan Institution for Standards and Metrology is annexed in Annex II.

Other regulatory bodies and market surveillance authorities might be involved in the project depending on their mandate and scope of responsibilities regarding the selected priority sectors in the ACAA Road Map, e.g. Ministry of Industry and Trade, Ministry of Health, Ministry of Environment, Ministry of Energy, Ministry of Public works and Housing, Food and Drug Administration. However, JISM will ensure coordination with those authorities within the Advisory Committee of the ACAA and its relevant technical working groups, and also in the National Market Surveillance Committee. Moreover, industries and conformity assessment bodies e.g. testing laboratories relevant to the scope of the ACAA will be provided with consultations through this Project.

The implementation of the project requires full commitment and participation of the senior management and staff within JISM. They must be fully involved in the development and implementation of the laws, regulations, policies, instructions and procedures delivered as the project results. Senior management of all other relevant authorities must also ensure that appropriate staff is made available to work with JISM. They will also make sure that all legislations and other regulations necessary for the implementation of the project are made available.

- The Coordination Mechanism :

The Implementation of the Project will be coordinated on its administrative part by the Ministry of Planning and International Cooperation, Programme Administration Office for the EU-Jordan Association Agreement in close cooperation with the Delegation of the European Union in the Hashemite Kingdom of Jordan. The technical supervision and coordination will be provided by the main beneficiary “Jordan Institution for Standards and Metrology”.

The Project Steering Committee (PSC) will be established for the supervision and coordination of the project activities and for ensuring that an effective coordination takes place between the different components of the project. PSC will meet quarterly, and ad hoc as required, and will be chaired by the Jordan Institution for Standards and Metrology. The Steering Committee members shall include the EU MS Twinning Partner, the Jordan Institution for Standards and Metrology, the Ministry of Planning and International Cooperation and the EU Delegation (as observer) .

5. Budget

Budget amount: EUR 1.200.000

6. Implementation Arrangement

6.1 Implementing Agency responsible for tendering, contracting and accounting (AO /CFCU /PAO/ Commission).

Ministry of Planning and International Cooperation

Marwan Al-Refai

Programme Administration Office

Support to the implementation of the EU-Jordan Association Agreement

P.O. Box 555 Amman, 11118 Jordan

Tel: 00 962 6 464 4466

Fax: 00 962 6 464 9024

Marwan.r@mop.gov.jo

6.2 Main counterpart in the BC

The main Jordanian counterparts for this project are as follows:

The Jordanian Project Leader:

Ms. Rula Madanat

Title: Assisstant Director General for Technical Affairs

Address: P.O. Box 941287 Amman 11194 Jordan

Phone: +962-6-5301238

Fax: +962-6-5301249

E-mail: rmadanat@jism.gov.jo

Jordan Institution for Standards and Metrology

RTA Main counterpart

Mr. Amer fakhouri

Title: Director of Stakeholder Support Unit

Address: P.O. Box 941287 Amman 11194 Jordan

Phone: +962-6-5301225 (ext. 1210)

Fax: +962-6-5301249

E-mail: afakhori@jism.gov.jo

Jordan Institution for Standards and Metrology

- The counterpart for Approximation of Legislations(Component 1):

Ms. Nesreen Khammash

Title: Head of Technical Regulations Preparation Division

Address: P.O. Box 941287 Amman 11194 Jordan

Phone: +962-6-5301225 (ext. 1132)

Fax: +962-6-5301249

E-mail: nkhammash@jism.gov.jo

Jordan Institution for Standards and Metrology

- The counterpart for Market Surveillance(Component 2):

Mr. Hussein Daradka

Title: Director of Inspection and Surveillance Department

Address: P.O. Box 941287 Amman 11194 Jordan

Phone: +962-6-5301225 (ext. 2002)

Fax: +962-6-5301249

E-mail: hdaradka@jism.gov.jo

Jordan Institution for Standards and Metrology

- The counterparts for Notification and Accreditation(Component 3) :

Mrs. Ola Zawati

Title: Director of Accreditation Unit

Address: P.O. Box 941287 Amman 11194 Jordan

Phone: +962-6-5658036

Fax: +962-6-5301249

E-mail: ozawati@jism.gov.jo

Jordan Institution for Standards and Metrology

- The counterpart for Information and Technical Help (Component4):

Mrs. Zainab Khalil

Title: Head of  TBT Enquiry Point Division

Address: P.O. Box 941287 Amman 11194 Jordan

Phone: +962-6-5301225 (ext. 1065)

Fax: +962-6-5301249

E-mail: zkhalil@jism.gov.jo

Jordan Institution for Standards and Metrology

7. Implementation Schedule (indicative)

7.1 Launching of the call for proposals: September, 2010

7.2 Start of project activities: April, 2011

7.3 Project Completion: March, 2013

7.4 Duration of the execution period: 23 months

8. Sustainability

The achieved results of the Project will be sustained through the issuance and enforcement of new and amended legislations including Laws and approximated technical regulations. Another important aspect of sustainability is the approval and implementation of policies, instructions and work procedures, which is based on European decisions, regulations and practices, and their incorporation in JISM integrated management system that will be audited and continuously improved on a continuous basis.

Moreover, high level national committees such as the Advisory Committee of the ACAA and the National Market Surveillance Committee will sustain the continuous updating of approximated legislations and their enforcement. Furthermore, the accreditation of notified bodies will ensure their continued competence through annual surveillances, and the established links and memberships with European organizations and groups relevant to accreditation, market surveillance and notified bodies in addition to the use of electronic systems will guarantee that Jordanian authorities and organizations is kept updated with information on the latest valid EC legislations and practices, and will ensure transfer of know-how on their enforcement and implementation.

9. Crosscutting issues

JISM will ensure equal opportunities between male and female in the management and implementation of the Project, including equal opportunities in training, site visits and participation in all of the Projects' missions and events; contributing thus to the promotion of gender equality

Moreover, JISM need the support and full cooperation of all relevant stakeholders who are involved in this project e.g. Industrialists, traders and conformity assessment bodies,  in addition to the regulatory bodies, market surveillance authorities, notifying authority and the accreditation body to ensure the successful implementation of the project's activities and to achieve its results and objectives.

JISM will also ensure adequate support and basic equipment for the work of the Twinning partners. This includes office space, local phone and fax, access to Internet and translation (when necessary).

10. Conditionality and sequencing

The activities of the Project of the different components should be performed in parallel to achieve successful results in the duration of the project, as all components are interlinked. For instance, the drafts of EC legislations need to be prepared before their endorsement, while inspectors are being trained on their requirements so that market surveillance activities will be performed upon the legislations' entry in force. Meanwhile, the potential notified bodies need to be qualified and assessed to perform conformity assessment procedures according to the approximated legislations and upon their enforcement, and the technical help services should be ready to assist the industry in implementing the legislations.

The precondition for achieving the Project's results is the endorsement of two laws:

- The Amendment of Standards and Metrology Law that includes new provisions relevant to product safety, marketing of products, market surveillance activities, legal metrology, responsibilities of traders and industrialists for the safety of their products and actions to be taken to ensure that, the introduction of a conformity mark (CE Mark), in addition to amendment on penalties and sanctions.

- The Accreditation Law for the establishment of an autonomous national accreditation body under the name "Jordan Accreditation Commission" so as to fulfil the international requirements of integrity and impartiality, and thus to become a signatory of the EA bilateral recognition agreement and ensure the acceptance of the notification of notified bodies by the European Commission.

Annex A.1 – Logical Framework Analysis

|  | Intervention logic | Objectively Verifiable Indicators (Benchmarks) | Sources of information | Assumptions (external to project) |
| --- | --- | --- | --- | --- |
| Overall Objective: | To fulfill the commitments of the Government of Jordan’s in the context of the EU-Jordan Association Agreement which will lead to the establishment of a free trade area between Jordan and the European Union through the signature of the ACAA Agreement | Free movement of products of priority exchanged in trade between Jordan and the European Union | ACAA Agreement | The Jordanian Government and the European Commission are willing to sign the ACAA Agreement |
| Project Purpose: | To assist JISM and relevant stakeholders in implementing the ACAA Roadmap in preparation for the negotiation and signature of the ACAA Agreement | - Major steps of the ACAA Roadmap are implemented - The negotiation of the ACAA Agreement is concluded. | - Mission Reports - Quarterly Reports - Final report | - Amendment Law of Standards and Metrology is endorsed. - Law of Accreditation is endorsed. - JISM and other stakeholders are ready to implement steps of the ACAA Roadmap. |
| Mandatory Results (Components): | - Approximation and enforcement of all identified and valid EC legislations, including the adoption of referenced harmonized EN standards, relevant to the industrial products which have been selected as priority sectors. | -Legal framework required for the introduction and enforcement of EC regulations is set up. - All EN harmonized standards relevant to priority sectors are adopted as national standards. - A list of all current and valid EC legislations is documented. - Sources to check updates on EC legislations are identified and documented. - A list of all relevant current Jordanian legislations is documented. - Gap report including a list of all conflicting Jordanian legislations is documented. - Lists of required new/ amendments/ withdrawals of Jordanian legislations is documented. - Regulatory Impact Assessment studies are documented. -Validation of Regulatory Impact Assessment studies through consultations is conducted, - Gaps in testing capabilities relevant to priority sectors are identified and documented. - A number of Training courses on all identified EC legislations are conducted. - A number of oriented training sessions to the industry are conducted. - A number of awareness seminars on identified EC legislations are conducted. - List of all trade issues in conflict with other free trade agreements are identified and resolved. - List of all trade concerns on EC legislations relevant to priority sectors which are raised against the EU is identified and justifications are comprehended and documented. - Final drafts of approximated Jordanian legislations and draft amendments of conflicting legislations are ready for issuance. - Approximated legislations are issued and transitional periods are determined - List of identified pilot companies. - Consultation reports and action plans for each company are documented. - Policy makers are invited to 5 VIP awareness seminars. - All relevant harmonized EN standards are adopted - Application to join CENELEC is prepared and accepted by CENELEC. - CEN and CENELEC Technical Committees Meetings relevant to priority sectors are attended by Jordanian experts. | -Interim quarterly reports. - Mission reports. - European Commission's review reports of approximated legislations. - Publication of approximated legislations and notices on adoption of harmonized standards in the official gazette. - EU legislations list - Jordanian legislations - Training and seminars evaluation reports. - Publication of draft legislations on relevant websites. - Publication of approximated legislations in the Official Gazette. - Notices on publication of adopted standards in the Official Gazette. - Study visit reports | - Amendment of Law on standards and Metrology No. 22/2000 is issued. - JISM and other Jordanian regulatory bodies as well as market surveillance authorities are ready to approximate and enforce EC horizontal and vertical legislations and to withdraw conflicting legislations. - Technical assistance is provided to the industry through other complementary projects to enable the implementation of the approximated legislations. - Access to required information is allowed by the European Commission. - Cabinet and parliament approve the legislations. - Policy makers are willing to participate. - CENELEC accepts Jordan’s memebership. |
|  | 2. Proactive market surveillance activities are operated and instructions for market surveillance are established in conformity with EU system. | - A market surveillance concept is developed and implemented effectively. - A National Market Surveillance Committee is established. - Market surveillance responsibilities on the different sectors are designated and accordingly a market surveillance strategy and plan is established and implemented - Advanced training on approximated legislations and adopted standards is provided to market surveillance staff. - Market surveillance instructions are issued by mid of 2011. - Quality management system for market surveillance is amended and implemented effectively by end of 2011 - A number of training courses on identified EC legislations and adopted harmonized standards are conducted. - A number of hand-on trainings on market surveillance and conduction of inspections are conducted. - A number of joint market surveillance inspections are conducted in Jordan and another 5 as study visits in Europe. - Weekly reports are exchanged with Civil Defense Department, National Security Department etc. on accidents and their causes. - Market Surveillance strategy and plans are documented, coordinated and implemented. - Jordanian market surveillance authorities are members to relevant European committees and groups. | - Interim quarterly reports. - Mission reports. - Reports on dangerous products issued by market surveillance authorities. - Minutes of meetings of the National Market Surveillance Committee. - Published market surveillance strategy and plan. - Evaluation reports of training programmes provided to market surveillance staff. - Issuance of market surveillance instructions in the Official Gazette. - Audit report on quality management system of market surveillance. - Study visit reports. Training evaluation reports. - Membership documents | - Amendment of Law on Standards and Metrology No. 22/2000 is issued. - The Prime Ministers decree to form a National Market Surveillance Committee is issued. - Market Surveillance identified needs are fulfilled including budget, inspectors and testing facilities. - European commission permits access of the Jordanian market surveillance system to the European system. |
|  | 3. A notifying authority is established and in operation and accordingly at least one competent Jordanian notified body for each selected EC Directive is accredited and notified. | - Potential notified bodies are qualified to be approved by the European Commission. - Accreditation and notifying staff is trained in all scopes of approximated legislations and adopted standards. - Notifying instructions and operational procedures are issued and are implemented - List of potential notified bodies and their scopes and capabilities are documented. - Initial assessments on at least one potential notified body per priority sector are conducted. - Rules on coordination with the Jordanian Accreditation Body are issued by JISM Board of Directors. - Policies and procedures for accreditation of notified bodies are developed and implemented. - A number of training courses on identified EC legislations and adopted harmonized standards are conducted. - a number of hand-on trainings on assessment techniques and procedures. - Initial assessments are conducted on potential notified bodies. - Consultations on how to close deviations as a result of initial assessments are provided to notified bodies - Final assessments are conducted on notified bodies. - European Commission supervises and approves results of assessments conducted on notified bodies. - Jordanian notified bodies are members to relevant European committees and groups. | - Interim reports - Mission reports. - Reports on results of evaluations of potential notified bodies under the supervision of the European Commission - Training evaluation reports. - Issuance of Notifying Instructions in the Official Gazette. - Audit reports on initial assessments of potential notified bodies. - Decisions of JISM Board of Directors. Decisions of the Accreditation Board of Directors. - Quality management system of the Accreditation body - Assessment report on implementation of Policies and procedures for accreditation of notified bodies. - Assessment reports of notified bodies. - Publication of competent notified bodies and their addresses at the Official Gazette. - Membership documents. | - The Accreditation Law is endorsed. The Jordanian Accreditation system is a signatory to Bilateral Agreement with EA. - Potential notified bodied are willing to close all identified technical gaps. The ACAA Agreement is signed. - Accreditation system is signatory to Bilateral Agreement with EA. - European Commission permits access of the Jordanian notified bodies to the European system |
|  | 4. Information and technical help is provided to the industry and close cooperation with European bodies in charge of legal and scientific metrology (EURAMET and WELMEC) . | - Technical help services are available to be provided to the relevant Industries. - Information Centre staff is trained in all scopes of approximated legislations and adopted standards. -Information and technical help services are developed. - Operating procedure to provide information and technical help services are documented and implemented. - a number of training courses on identified EC legislations and adopted harmonized standards are conducted. - A number of hand-on trainings on technical help and information services are provided. - Promotion and communication plan is developed and implemented. - A number of awareness seminars on identified EC legislations are conducted. - Promotional materials and publications are developed and distributed according to the promotion plan. | - Interim reports - Mission reports - Reports on results of evaluations of potential notified bodies under the supervision of the European Commission - Training and seminars evaluation reports. - Quality management system of the information centre. | - All resources needed to establish an information centre and technical help services are available including budget, staff and information sources. - Approval of JISM Board of Directors. - Resources; staff, information resources and budget are available. |
| Mandatory Result (Component): | Activities | Means | Costs | Pre-conditions |
| Component 1 Component 2: Component 3: Component 4: | Clarify and update a list of all current and latest EC legislations relevant to the priority products. Identify gaps and contradicting Jordanian legislations issued by relevant authorities. Conduct consultation campaigns and impact studies on all EC legislations to be approximated so as to identify effect on the industry and technical problems and obstacles faced by them and also in testing capabilities to be used for market surveillance purposes. Train legislative authorities on all identified EC legislations. Conduct awareness seminars and product oriented training sessions to the industry. Assess any technical conflicts with other free trade agreements and international relations and organizations such as the World Trade organization / Technical Barriers to Trade Agreement (WTO/TBT), including trade concerns of WTO members on relevant EC legislations. Assist in drafting the approximated Jordanian legislations and in the amendment of conflicting legislations, and provide advice on modifying these drafts based on the feedback from the European Commission on their legal texts. Assist in issuing and enforcing the approximated legislations in consultation with the Jordanian industry and provide advice on transitional periods according to the results of the impact studies. Select three pilot industrial companies per priority sector and provide consultation services to fully comply with EC legislations. Involve policy makers to further implement EC legislations. Assist in adoption of all harmonized EN standards and withdrawal of conflicting Jordanian Standards. Provide guidance in applying to join CENELEC as an affiliated member and in participation in meetings of Technical Committees in the areas of priority sectors at CEN and CENELEC Assist in establishing new market surveillance instructions as stated in the amendment of Law on Standards and Metrology, in accordance to the new European Regulations that have been effective since beginning of 2010, and consult on adjusting the quality management system accordingly. Train inspectors on the lately approximated EC legislations and on preparations for market surveillance and conduction of inspections. Conduct joined market surveillance inspections in Jordan and in EU countries. Establish communication and coordination mechanisms to acquire and provide the necessary information on accidents relevant to unsafe products. 2.5 Coordinate market surveillance activities within the Market Surveillance National Committee, as per the amendment of Law on Standards and Metrology, and develop and launch Market Surveillance plans accordingly Establish links of the Jordanian market surveillance system to the European system. Develop instructions and operational procedures on how to assess and notify competent notified bodies. Identify potential notified bodies to be granted assistance and perform an initial assessment on their capabilities. Set rules of coordination with the Jordanian Accreditation Body on assessments to be conducted on potential notified bodied, under the supervision of the European Commission. Develop accreditation policies and procedures for accreditation of notified bodies according to European legislations. Train assessors on EC legislations and on how to conduct assessments on notified bodies relevant to EC Legislations and EN standards. Identify major technical gaps at selected potential notified bodies. Qualify a number of potential notified bodies to be granted accreditation and recognition by the notifying authority. Notify the competent notified bodies to the European Commission and officially announce and publish their names and addresses. Establish official contacts with European notified bodies. Establish an information centre and technical help services to be provided to the industry. Train staff on how to provide information services and technical help. Provide advice on communication tools and media used to provide information services. Conduct informational events for the public. Publicize and market information services and technical help, including preparation of promotional materials and publications. | Twinning Agreement | €1,200,000 |  |

Annex I

EC horizontal Regulations Relevant to the Project

- 765/2008/EC Framework Regulation on Requirements for accreditation and market surveillance relating to the marketing of products.

- 768/2008/EC Decision on a common framework for the marketing of products.

- 85/374/EEC Product liability

- 2001/95/EC General Product Safety Directive (GPSD)

- 2006/95/EC Low Voltage Directive (LVD)

- 2009/48/EC Directive on the Safety of Toys

- 2009/142/EC Gas Appliances Directive (GAD)

- 97/23/EC Pressure Equipment Directive (PED)

- 2004/22/EC MID

- 89/106/EEC CPD

- 76/769/EEC Restrictions of certain dangerous Substances and Preparations

- 94/62/EC Packaging and Packaging Waste  (Art. 11)

- 2000/14/EC Outdoor Noise

- 92/42/EEC Efficiency requirements for new hot water boilers fired with liquid or gaseous fuels

- 2004/108/EC Electromagnetic Compatibility (EMC) Directive

- 96/57/EC Energy Efficiency for spec. household Appliances

- 92/75/EC Energy labelling of household Appliances and its implementing Directives

- 2002/95/EC ROHS Restriction of use of certain hazardous Substances

- 2005/32/EC Eco Design

- 76/768/EEC Cosmetics Directive

- 90/384/EEC Non Automatic Weighing Instruments

- 2007/45/EC Pre-packaging

- 2009/105/EC Simple Pressure Vessels Directive (SPVD)

- 1999/36/EC Transportable Pressure Equipment Directive (TPED)

ANNEX II

Organizational Structure

Jordan Institution for Standards and Metrology