IPA 2010 MONTENEGRO

STANDARD TWINNING PROJECT FICHE

Achieving highest safety and technical quality of construction

1.	Basic Information

1.1	Programme: IPA 2010 (Priority Axis 3- Ability to assume obligations of membership)

1.2	Twinning Number: MN 10 IB FI 01

1.3	Title: Achieving highest safety and technical quality of construction

1.4	Sector:

ELARG Statistical code: 	1 – free movement of goods

1.5	Beneficiary country: Montenegro

2.	Objectives

2.1	Overall Objective(s):

The overall objective of this project is achieving highest safety and technical quality of Montenegrin construction.

2.2	Project purpose:

To create prerequisites for the harmonization of national regulations and standards for structural analysis and design with the regulations and standards of EU and for building capacities for their successful adoption, implementation and use.

2.3	Contribution to National Development Plan/Cooperation agreement/Association Agreement/Action Plan

The January 2007 European Partnership document emphasizes the need of establishing a legal and institutional set-up in the field of standardization, market surveillance, certification, metrology, accreditation and conformity assessment in order to create conditions favourable to trade. It envisages develop standardization, particularly through the adoption of the European standards. The European partnership document foresees the adoption of the European standards through short-term and middle-term priorities.

On the basis of the Stabilization and Association Agreement signed between the European Communities and their Member States and the Republic of Montenegro in March 2007, responsibilities have been taken, inter alia, concerning harmonization of existing legislation in Montenegro with the European Community legislation and its effective implementation, whereby Montenegro will seek to ensure gradual harmonization of its existing laws and future legislation with the acquis communautaire and adequate implementation and enforcement of existing and future legislation.

Harmonization is expected to start on the date of signing of the Stabilization and Association Agreement, and will gradually extend to all elements of the acquis by the end of a five-year transition period.

In the part of the Stabilization and Association Agreement relating to standardization, metrology, accreditation and conformity assessment, in Article 77, it is expected that Montenegro will take the necessary measures to gradually achieve compliance with technical regulations of the Community and European standardization, metrology, accreditation and procedures for conformity assessment.

In accordance with Article 77, paragraph one of the Stabilization and Association Agreement, (Title IV, Approximation of Laws, Law Enforcement and Competition Rules) Montenegro should ensure gradual harmonization of its existing laws and future legislation with the acquis communautaire and ensure adequate implementation of existing and future legislation. Montenegro should take measures to gradually achieve compliance with technical regulations and standards of the European Community and European standardization, metrology, accreditation and screening.

To achieve the above goals, the Parties to the Stabilization and Association Agreement shall seek to:

- promote the use of Community technical regulations, European standards and conformity assessment procedures;

- provide assistance to fostering the development of quality infrastructure: standardisation, metrology, accreditation and conformity assessment;

- promote the participation of Montenegro in the work of organisations related to standards, conformity assessment, metrology and similar functions (e.g. European Committee for Standardisation, European Committee for Electro technical Standardisation, European Telecommunications Standards Institute, European cooperation for Accreditation, European Cooperation in Legal Metrology, European Organisation of Metrology);

- where appropriate, conclude an Agreement on Conformity Assessment and Acceptance of Industrial Products once the legislative framework and the procedures of Montenegro is sufficiently aligned on that of the Community and appropriate expertise is available.

Multi-annual indicative planning document 2009-2011 (2.3.1.3. Priority line 3 – Capacity for taking over responsibilities which derive from the membership) attaches great importance to legislation in the field of internal market and its implementation, including that concerning the free movement of goods (standardization, conformity assessment, metrology, accreditation, market surveillance, and consumer protection);

National Program for Integration of Montenegro into the EU (NPI) for the period of 2008-2012 presents detailed activity plan to prepare Montenegro for taking over responsibilities which derive from the EU membership to the year 2012. The Sector for construction in the Ministry for economic development of that time was engaged in preparing the section 3.1.3.21 of the National Program for integration of Montenegro into the EU for the period of 2008-2012 related to the free movement of goods - construction products.

The draft Strategy for the development of civil engineering by the year 2020, envisages the adoption of European standards (Eurocodes) and rulebooks with the mandatory application by the end of the year 2014.

Strategy has defined seven strategic orientations, standards and regulations in the construction industry are covered through the first and third strategic orientation. First strategic orientation, Integration of Montenegro into the EU and sustainable development, the development of civil engineering is presented as an integral part of the process of EU integration and sustainable development of Montenegro. This commitment stems not only from the fact that the strategic orientation of economic policy of Montenegro is joining the EU system, but also the new economic environment to be established, in which the civil engineering needs to act in the near and the wider environment.

Through the third strategic orientation (technical regulations as a basis for quality systems in civil engineering) proposal system of quality construction in civil engineering that is based on technical regulations and standards that enable easier and simpler movement of services and materials in world trade. Standardization involves establishing a basic institutional framework for tracking and control of the process. This segment is provided for the adoption of the Eurocodes whose application in EU and EFTA Member Stats will start in 2010.

3.	Description

3.1	Background and justification:

Service sector, especially tourism, financial intermediation and real estate remained the main driver of growth, producing 70% of gross value added (GVA). Montenegro has, following its acquisition of independence on 3rd July 2006, continued to use the standards in the field of civil engineering that are based on 'JUS' standards (Yugoslavian standards-YUS) from the year 1981, which are inherited from the previous common state. Namely, the current Rulebook on the basis of which calculations of buildings on the seismic effects are performed (1981-1990) is the Rulebook on technical standards for construction of high buildings in seismic area (Official Gazette of the FRY, no. 31/81, 49/82, 29/83, 21/88, 52/90).

In the middle of 90s of the past century, although our former state union (Serbia and Montenegro) had not been a member of CEN (the European Committee for Standardization), our civil engineers, especially constructors in this period, under conditions of sanctions of the United Nations, tried to follow the efforts of Europe on adoption of ENV Eurocodes (Version of Eurocodes published by CEN as a pre-standard for subsequent conversion into European Norm -EN). In the First Symposium on the Eurocodes for construction in Belgrade, 10 years ago, the constructors decided to accept the Eurocodes for construction as our future national standards.

The earthquake which occurred on April 15, 1979 and reached IX grade on the Mercalli intensity scale, caused catastrophic destruction along the entire Montenegrin coastline, in a length of over 100 km. Given the present risks and the fact that Montenegro is located in an area with high seismicity (the larger part of its territory is situated in a zone with intensity of IX on the Mercalli scale, which is characteristic for earthquakes with ruinous effect), it is necessary to introduce new seismic design standards - the Eurocode 8. This will allow to update the estimation of seismic hazard and to implement the highest available construction technology for seismic risk mitigation. As a consequence, the seismic safety of the new and existing civil and engineering structures will increase significantly, and therefore - human lives and property will be better protected.

Reasons for adoption of the Eurocodes in Montenegro are: political, economical and technical. Political, because it fulfils one of the conditions for EU membership. This will create conditions for free movement of products, services, capital and workers. Economical, because it will facilitate the access of Montenegrin businesses to the enlarged European market of 27 countries with 500 million potential customers. Technical reasons arise from the need for replacement of the outdated regulations and standards, which especially comes into play in this period of intensive construction, when many significant buildings are constructed and many foreign investors are investing. The Eurocodes are a world-class state-of-the art design standards which are built on best European practice, expertise and research achievements. They provide for the highest technical quality and safety in construction design.

The Eurocodes are a set of 10 European standards that contain common rules for structural design. The Eurocodes cover in a comprehensive manner all principal construction materials (concrete, steel, timber, masonry and aluminium), all major fields of structural engineering (basis of structural design, loading, fire, geo-techniques, earthquake, etc) and a wide range of types of structures and products (buildings, bridges, towers and masts, silos, etc). Publication of all 58 parts of the Eurocodes was completed in May 2007. Implementation of most parts is scheduled for 2010.

The Eurocodes serve as reference documents recognised by authorities of the Member States of the EU and the European Free Trade Association for the following purposes:

- as a means to prove compliance of buildings and civil engineering works with the Essential Requirements of the Construction Products Directive (Council Directive 89/106/EEC), particularly Essential Requirement 1: Mechanical resistance and stability and part of Essential Requirement 2: Safety in case of fire.

- as a basis for specifying contracts for public construction works and related engineering services. This relates to the Directive on the coordination of procedures for the award of public works contracts, public supply contracts and public service contracts (Directive 2004/18/EC of the European Parliament and of the Council).

- as a framework for drawing up harmonised technical specifications for construction products (harmonised European Standards and European Technical Approvals).

The Eurocodes establish a set of common technical rules for the design of construction works. However, the determination of safety level of construction works including aspects of durability and economy remains within the competence of the implementing country. National choice is provided by the Eurocodes with sets of recommended values, classes, symbols and alternative methods to be used as nationally determined parameters (NDPs). The NDPs take into account differences in geographical, geological or climatic conditions (e.g. wind, snow, isotherms and seismic maps); allow the implementing countries to decide the level of safety. The NDPs of individual countries shall be included in the national annexes to each Eurocode part.

To adopt each of the 58 Eurocodes parts, National Authorities and National Standards Bodies are requested by CEN to:

- translate the Eurocode part in authorised national language(s) or to adopt in one of the three official CEN languages,

- set the nationally determined parameters to be applied on their territory

- publish the national standard transposing the Eurocode Part and the national annex,

- adapt their national provisions so that the Eurocode part can be used on their territory,

- withdraw all conflicting national standards,

Eurocodes contain approximately 5000 pages of technical text, whose translation into national language is a huge task and requires not only linguistic, but also high level technical expertise because of the need of introduction of new technical terms into national technical vocabulary. Moreover, Eurocodes contain about 1500 nationally determined parameters. Some of them have recommended by CEN values which can be accepted after an expert discussion at national level. The rest of the nationally determined parameters, and especially those related to the local geographical, geological or climatic conditions (e.g. wind, snow, isotherms and seismic maps) and to the safety level (e.g. the partial safety factors) should be laid down to allow the application of the Eurocodes in Montenegro.

Besides, the experience of the EU Member States has shown that the successful implementation of the Eurocodes into construction practice requires a shared effort and close collaboration of all stakeholders, including: National Authorities, National Standards Body, Technical and Professional Associations, Academia and the Construction Industry. National implementation programme should be elaborated and the tasks of all stakeholders should be defined in order to address the following issues:

- awareness campaign on the importance of the Eurocodes and on the benefits emanating from their use,

- technical matters and impact on the profession, researchers and academia,

- transfer of knowledge from Eurocode experts to national trainers, and from the national trainers to the profession and students,

- Well-timed availability of guidance material.

All the above tasks require investment of considerable financial resources and efforts. Therefore, it is very important to get expert support and synergy from the experience of the countries, which already adopted and implemented the Eurocodes and to implement it with a thorough and careful planning of the needed actions.

The Department of construction within the Ministry of Sustainable Development and Tourism, having observed the issues: obligations undertaken by signing the Stabilization and Association Agreement, need to replace the outdated standards, intensive construction, growth of real estate trade and pursuit of Montenegro to become a member of the EU, saw the need for gradual harmonization of national regulations and standards for structural analysis and design with the regulations and standards of the EU and for creation of favourable conditions for their implementation.

The Government of Montenegro has already undertaken certain steps to improve the current situation by establishing the Institute for Standardization and Accreditation Bodies. Montenegro is affiliate member of CEN, participates to its work and has authorised access to all CEN standards. This membership is a good prerequisite for the successful performance of the tasks planned in the project.

Comparative studies between the Eurocodes technical rules and the Montenegrin standards for design of reinforced concrete structures, masonry structures, bridges, and seismic design have been performed in the Faculty of civil engineering in Podgorica. They show that no single Eurocode can be embedded into the Montenegrin standardisation environment for structural design due to the considerable difference of the safety factors. That is why implementation of all Eurocodes parts in thematic packages should be sought, as stipulated in Guidance Paper L.

By realization of this project the detailed action plan for adoption and implementation of the Eurocodes in Montenegro would be determined. Having in mind the high seismicity of Montenegro, special attention will be paid to the preparation for adopting Eurocode 8 (the Eurocode for seismic design). Expert assistance will be sought in the pilot project for preparation of a national annex to the Eurocodes – the national annex to Eurocode 8 part 1 “Design of structures for earthquake resistance - General rules, seismic actions and rules for buildings”. This is the main part of Eurocode 8 which specifies the seismic actions and the rules for seismic design of buildings.  In this pilot project the results of the NATO Science for Peace and Security project “Harmonization of Seismic Hazard Maps for the Western Balkans Countries” will be implemented for determination of seismic actions. The project, whose final aim is producing a seismic map of the Western Balkans consistent with the requirements of Eurocode 8, was launched in October 2007 and the final results are expected in the summer of 2010.

Main stakeholders of this project are: the Ministry of Sustainable Development and Tourism, the Institute for Standardization, the Engineering Chamber of Montenegro, the Faculty of Civil Engineering in Podgorica, Faculty of Architecture in Podgorica, the Ministry of Interior and Public Administration, the Seismological Survey, NGOs (Montenegrin Association for earth seismic engineering and Association of constructors of Montenegro), the Chamber of Commerce, the Hydro-Meteorological Institute, the Geological Institute, and the Centre for Eco-Toxicology.

  - Linked activities (other international and national initiatives):

During 2010 and 2011, an IPA 2007 project „Development of Quality Infrastructure in Montenegro“ (DQIM), EuropeAid/126524/C/SER/ME, is in operation. This project covers standardization and other sectors of the Quality Infrastructure, such as Technical Regulation (Directives), some of which are closely related to our twinning project „Achieving highest safety and technical quality of construction“. Therefore, the main beneficiaries of the two projects, Ministry of Economy (main beneficiary of the DQIM project - through its Department for Quality Infrastructure) and Ministry of Sustainable Development and Tourism will have to co-operate and co-ordinate their actions.

Among other co-beneficiaries of the DQIM project, there is inter alia also an Institute for Standardization of Montenegro (ISME). Since ISME is at the same time one of the intended co-beneficiaries of our twinning project „Achieving highest safety and technical quality of construction“, it will represent another natural link between the two projects. ISME will play an important role in both projects. Particularly because ISME, as the National Standardization Body of Montenegro, is responsible for the adoption of all the European standards, including the Eurocodes. It is also important to note that it is a responsibility of ISME to manage the process of drafting and adoption of the national annexes to the Eurocodes, which should normally be drafted by a relevant Technical Committee (TC) of a standardization body, with the participation of all interested parties and stakeholders (representatives of industry, consumers, building companies, architects, universities, etc., including the representatives of both the ministries - Ministry of Economy and Ministry of Sustainable Development and Tourism).

3.3	Results:

There are three main results of this project:

- action plan for adoption of the Eurocodes;

- action plan for implementation of the Eurocodes;

- national annex to Eurocode 8 part 1.

Measurable qualitative and quantitative indicators used to assess the achievement of results:

Result (1):

- the action plan for adoption of the Eurocodes officially adopted by the Montenegrin Government  in 12 months from the beginning of the implementation of the project;

- the action plan is used as the basis for the development of further actions and project proposals for the adoption of the Eurocodes;

- provision of IT equipment for elaboration of the nationally determined parameters to all Eurocodes in 18 months from the beginning of the implementation of the project.

Result (2):

- the action plan for implementation of the Eurocodes officially adopted by the Montenegrin Government in 18 months from the beginning of the implementation of the project;

- the Program is used as the basis for education and training on the Eurocodes.

Result (3):

- national annex to Eurocode 8 part 1 prepared and agreed with all relevant stakeholders in 18 months from the beginning of the implementation of the project;

- the national annex to Eurocode 8 part 1 is used as an example for preparation of the national annexes to the rest of the parts of the Eurocodes after 18 months from the beginning of the implementation of the project.

3.4	Activities:

Activities related to result (1) “Action plan for adoption of the Eurocodes” include:

  - timeline for preparation of national annexes to the different Eurocode parts providing to introduce in the first place the Eurocodes packages relevant to the most wide-spread structures in Montenegro;

  - determination of the methods to estimate or suggestion for the most appropriate values, of  the nationally determined parameters to all Eurocodes;

  - definition of list of IT equipment (specialised software and computers) to be purchased by the Ministry of Sustainable Development and Tourism for elaboration of the nationally determined parameters to all Eurocodes;

  - concept for establishing regional networking in translation of the Eurocodes parts;

  - concept for establishing regional cooperation in preparation of wind, snow, and isotherms maps;

  - roadmap for adaptation of the Montenegrin legislative framework for construction to allow the use of the Eurocodes;

  - provision of the IT equipment (specialised software and computers) determined by Activity 1.1 for elaboration of the nationally determined parameters to all Eurocodes.

Activities related to result (2) “Elaboration of action plan for implementation of the Eurocodes” include:

2.1 definition of the list for training material for continuous professional development to be prepared/adopted and provision of good practice examples, including: information leaflets on the implementation of the EN Eurocodes, designer handbooks and manuals, guidelines with worked examples (e.g. of common types of buildings and bridges), training and design software;

2.2 definition of concept for university programme of studies on the Eurocodes and provision of good practice examples for: lecturers’ notes, information leaflets on the implementation of the EN Eurocodes, guidelines with worked examples, training software;

2.3 planning of seminar on training the Montenegrin Eurocodes trainers;

2.4 elaboration of plan for intensive training of the Montenegrin construction professionals.

Activities related to result (3) “National annex to Eurocode 8 part “Design of structures for earthquake resistance - General rules, seismic actions and rules for buildings”, include:

3.1  determination of those nationally determined parameters of Eurocode 8 where specific for Montenegro values obligatory have to be introduced, and estimation of these parameters;

3.2  incorporation of results from the NATO Science for Peace and Security project “Harmonization of Seismic Hazard Maps for the Western Balkans Countries” for determination of the seismic actions (e.g. seismic map, response spectra, etc.);

3.3  elaboration of the text of the national annex in Montenegrin language.

3.5	Means/ Input from the MS Partner Administration:

3.5.1	Profile and tasks of the Project Leader (PL)

The PL should be a high ranking official with broad knowledge of all processes in the area of European standardisation system and legislation related to the construction industry in the EU, who, continuing to work at his/her Member State (MS) administration, will devote time and efforts to the successful implementation of the Twinning project. The PL will allocate a minimum of 3 days per month including one visit every three months to Montenegro as long the project lasts.

The profile of the PL includes:

- Excellent knowledge of all processes and strengthening the administrative capacity in the area of European standardisation system and legislation related to the construction industry;

- High-ranking official with ability to call on short term experts in support of the efficient implementation of the project;

- Overall understanding of the problems and solutions in the sector;

- Capable of unblocking any problems at highest level;

- Good leadership skills.

- Good command of English.

The PL tasks include:

- Overall project supervision and coordination to ensure high quality outputs and results;

- Co-chairing, with the Beneficiary's representative the regular Steering Committee meetings;

- Mobilising short- and medium term experts and approval of their performance;

- Executing administrative tasks (i.e. signing reports, side letters etc.).

3.5.2 Profile and tasks of the Resident Twinning Advisor (RTA)

- For the purpose of this project, the profile of the RTA includes:

- A senior official with at least 8 years of general  professional experience;

- Minimum 3 years of professional experience in the field of this project;

- Sound knowledge of EU legislative and institutional framework;

- Strong written, oral and inter-personal communication skills;

- Excellent oral and written English;

- Experience in similar technical and legal assistance assignments in third countries will be considered an asset.

The secondment of the official to act as RTA will be minimum 18 months. His/her tasks will include:

- Project management and coordination of the activities of the team members in line with the agreed work programme to enable timely completion of project results;

- Nomination, mobilisation and supervision of the short and medium term experts, together with the Project Leader;

- Facilitation of the contacts with institutions in EU member states in order to stimulate a proper exchange of information and data;

- Assisting in the preparation of all strategic project documents and provision of advisory services in project fields;

- Coordinating and organisation of the project activities, monitoring the delivery of the outputs according to the agreed timetable and ensuring the proper quality of the outputs;

- Preparation of the meetings of the Project Steering Committee and reporting on the project progress;

- Preparation of the project progress reports and supervision of the preparation and production of tasks reports

- Identifying and reporting to the Contracting authority, at early stage, all difficulties that may jeopardise the implementation of the project and the achievement of its results.

3.5.3 Profile and tasks of the short-term experts

- In addition to the RTA, the Members State Partner (MSP) must have quick and flexible access to a pool of short and medium-term experts from the EU Member States. These experts shall either work as advisors and trainers or perform specific studies or assignments within the scope of the twinning project.

Common to all experts:

- Relevant University degree, PhD will be an asset

- Minimum of 7 years professional experience in their respective field;

- Sound knowledge of the EU regulations and policies related to construction

- Sound knowledge of the Eurocodes system of standards

- Professional background and proven experience in adoption of the Eurocodes related to their specific tasks

- Good written and oral command of English

- Sound background in drafting and in implementing policies and standards

- Proven contractual relation to public administration or mandated body

Professional background, experience and recommended duration of mission of the short and medium term experts on the different twinning activities

| Expert | Professional background | Expertise in Eurocode/ activity | Duration of mission (weeks) |  |  | Total duration of mission (weeks) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Activity 1.1-1.6 | Activity 2.1-2.4 | Activity 3.1-3.3 |  |
| Expert 1 | Civil or structural engineering | EN 1990 and EN 1991 | 4 | 3 |  | 7 |
| Expert 2 | Civil or structural engineering, or meteorology | EN 1991 | 10 | 2 |  | 12 |
| Expert 3 | Civil or structural engineering | EN 1992 | 8 | 2 |  | 10 |
| Expert 4 | Civil or structural engineering | EN 1993 | 10 | 3 |  | 13 |
| Expert 5 | Civil or structural engineering | EN 1994 | 3 | 2 |  | 5 |
| Expert 6 | Civil or structural engineering | EN 1995 | 3 | 2 |  | 5 |
| Expert 7 | Civil or structural engineering | EN 1996 | 3 | 2 |  | 5 |
| Expert 8 | Civil, structural or geotechnical engineering | EN 1997 | 4 | 2 |  | 6 |
| Expert 9 | Civil or structural engineering, or seismology | EN 1998 | 2 | 2 | 6 | 10 |
| Expert 10 | Civil or structural engineering | EN 1998 | 3 | 2 | 6 | 11 |
| Expert 11 | Civil or structural engineering | EN 1999 | 3 | 2 |  | 5 |
| Expert 12 | Civil or structural engineering | Bridge design | 4 | 2 |  | 6 |
| Expert 13 | Civil or structural engineering or fire design | Fire design | 4 | 2 |  | 6 |
| Expert 14 | Civil or structural engineering | Teaching Eurocodes in University |  | 3 |  | 3 |
| Expert 15 | Civil or structural engineering | Teaching professionals to Eurocodes |  | 3 |  | 3 |
|  |  | subtotal | 61 | 34 | 12 |  |
|  |  | total |  |  |  | 107 |

4. 	Institutional Framework

A series of activities precedes adoption and acceptance of Eurocodes as national regulations for design of structures, and it requires a long period.

These activities shall include:

- translation of Eurocodes;

- elaboration of national annexes containing nationally determined parameters, and conduction of public hearing on their adequacy;

(for implementation of these activities a cooperation of the Ministry of Sustainable Development and Tourism, the Institute for Standardization of Montenegro, the Faculty of Civil Engineering, the Chamber of engineers, and the Chamber of Commerce is necessary);

- introduction of new methods of structural analysis and design in the curricula of faculties (The Faculty of Civil Engineering and the Faculty of Architecture);

- organizing seminars, conferences, symposia, on which the new methods would be presented to designers, contractors, investors, inspection, monitoring bodies;

(the Faculty of Civil Engineering in Podgorica, the Montenegrin Chamber of Engineers, the Association of Constructors of Montenegro are competent for organization of seminars, conferences, and consultations).

Ministry of Sustainable Development and Tourism shall perform administrative affairs relating to: integrated planning, management and valorisation of space; sustainable development; implementation of programs and projects of sustainable development within the competence of this ministry; provision of technical, organizational and administrative support to the work of the National Council for sustainable development; strategic planning of space and environment; elaboration of state planning documents; giving opinions and approvals of local planning documents; coastal zone management; elaboration and adoption of plans for temporary facilities in the area of coastal zone management and national parks; keeping documentation basis of space for purposes of monitoring the situation in the region and elaboration of planning documents; preparing reports on the state of spatial planning; elaboration of spatial planning programme; establishment and maintenance of spatial information system in cooperation with the authorities of state administration competent for information society; producing offprints and issuing urban-technical conditions, issuing building permits, issuing use permits; issuing approvals and urban-technical conditions for setting up temporary facilities; licenses for performing activities of elaboration of planning documents, preparation of technical documentation and construction of structures; management of development and strategic policy in the field of construction; energy efficiency through planning system and construction; tourism development, catering, tourist industry, operating conditions in tourism, selective forms of tourism; linking coastal and inland tourism; private sector development in tourism; establishing tourist sites and areas; categorisation and classification of tourist facilities; tourist flows at domestic and foreign markets; cooperation with tourism associations in Montenegro and abroad; sustainable valorisation of resources and environmental benefits of national parks and protected areas in terms of tourism development; realisation of investment programs of interest to sustainable tourism development; monitoring of infrastructure projects in terms of tourism development; monitoring and promotion of investments in the tourism sector; coordinating activities for preparation and monitoring of tourist seasons; organization, intermediation, supply of tourist areas and the structure of tourist spending; keeping records on the number of tourists, accommodation facilities, financial effects and operating results in tourism; organizing activities of tourist and information promotion activities; improvement of cooperation between the tourism sector and complementary sectors; cooperation with the National tourist organizations and organization of tourist offices in other countries; property; system of housing relations; management and maintenance of housing stock; conversion of specific and common parts of residential buildings in commercial premises; housing cooperatives; policy of improving the housing stock; private-public partnership in the field of housing; system of integrated environmental protection and sustainable use of natural resources; the area of environmental impact assessment and strategic impact assessment; integrated pollution prevention and control; nature protection; air quality; climate changes and approval and monitoring of projects being implemented in order to mitigate effects of climate changes; protection of the ozone layer; protection from noise and vibration; chemicals, radiation protection (radioactive substances and ionizing radiation), non-ionizing radiation, protection of land from pollution, integrated coastal zone management, integrated marine protection from pollution; industrial pollution control and risk management; application of new technologies and cleaner production; waste management and wastewater management; system of utility services; coordination of regional water supply system; genetically modified organisms within the competence of the Ministry; hydrographical activities; elaboration of environmental protection standards; monitoring the state of environment; monitoring of investments from the field of the ​​ministry; cooperation with international financial institutions and funds of the European Union in the implementation of projects in the field of environmental protection and utility services; cooperation with NGOs; proposing measures and current development policies and analyzing their impact on the economic position of businesses and entrepreneurs; promotional activities within the competence of the Ministry, international cooperation and international agreements within the competence of the Ministry; harmonization of national regulations within its jurisdiction with the legal system of the European Union; administrative oversight in the field for which the Ministry is founded; as well as other tasks assigned to its competence.

Department of Construction

shall perform affairs related to: management of development and strategic policy in the field of construction, as well as monitoring and taking measures for their implementation; improvement of aseismic planning, design and construction; development of strategies, programs and projects in the field of construction and monitoring their implementation; making drafts and proposals laws and other regulations in the field of construction and construction products; participation in preparing and providing opinions on drafts and proposals of laws and regulations, prepared by other agencies; monitoring the EU accession process; giving suggestions for the adoption of Montenegrin standards in the field of construction; harmonization of national legislation with EU legislation in the field of the construction; issuing decisions in administrative affairs and administrative supervision; issuance, verification, revoking of licenses and cancellation of license verifications for elaboration of technical documentation and construction; providing expert guidance, opinions and interpretations; preparation of responses for review of constitutionality and legality of laws, regulations and general acts; preparation of complaints and responses to complaints; participate in disputes in front of the Constitutional Court of Montenegro in the cases in this field; conduct second-instance administrative proceedings; enforcement of laws and other regulations in the field of construction; supervision over implementation of laws and regulations in the field of construction; monitoring and study of economic conditions and economic position of businesses in the field of construction and proposing measures of current development policy, as well as analyzing their impact on economic position of businesses in this field; monitoring and analysis of service quality in construction; monitoring and improvement of personnel resources in this field; cooperation with educational institutions and professional associations with a view to improve work in this industry; monitoring international best practice in the field of the Department and proposing measures accordingly; monitoring the application of new technologies and best practices in the field of construction, particularly directed towards ECO solutions; issuance of building and use permits, as well as solutions for technical inspections of facilities; cooperation with other institutions involved in issuing building and use permits; international and regional cooperation in the field of construction; supervision over institutions of this department over which the administrative surveillance is conducted by the Ministry; establishing cooperation with NGOs and other civil society organizations; preparation and submission of data for managing and updating the site, promoting activities of the Department; managing and updating the register of licenses; participation in the preparation of tender documents for procurement within the competence of the Department; making information, reports and other activities in accordance with the regulations; preparation and management of projects and programs in the field of construction; improving business environment; establishing the methodology of classification of existing buildings, determine the methodology of classification of structural and seismic stability of existing buildings; determining structural and seismic stability of certain high-risk areas where informal settlements are built; collection, processing and establishment of database for informal settlements and facilities; determination of methodology of reconstruction and redesigning of facilities; determining safety of use of facilities; determining the procedure of issuing building permits and use of illegally constructed buildings; preparation and management of projects and programs of the European Structural Funds (IPA, other funds and instruments); international and regional cooperation in the field of construction; establishing cooperation with other organizational units, in order to collect and consolidate data for making information from the Ministry; communication and coordination with the Department for international cooperation and sustainable development; monitoring legislation in the field construction.

Institute for Standardization of Montenegro (ISME) provides a basis for drafting regulations, establishing the infrastructure of advisory and technical bodies (technical committees) involved in the work on Montenegrin standardization and ensures compatibility of Montenegrin standards and related documents with international and European standards and related documents.

For elaboration of national annexes to Eurocodes seismic maps, snow, wind, and isotherm maps are necessary.

Chamber of Engineers of Montenegro was established for the purpose of ensuring expertise and protection of public interest, the persons working on activities of spatial development and construction of structures, prescribed by this Law and acquiring membership in the Chamber in the area of spatial development and construction of structures (hereinafter: the Chamber).

The Chamber has the capacity of a legal person with rights and responsibilities established by Law and the Articles of Incorporation of the Chamber and shall perform the following activities:

- keep the registry of the Chamber members;

- ensure improvement and education of the members of the Chamber;

- adopt the code of ethics and ensure its implementation;

- conduct disciplinary proceedings against its members and impose measures;

- determine minimum price for technical documentation, review, technical inspections and supervision for residential and residential-business structures;

- control the application of the price referred to in item 5 of this Article;

- organize and enforce the taking of professional examination according to the provisions of this Law;

- determine the amount of membership fee and registration fee of its members;

- protect and represent the interests of its members;

- perform other activities based on Law and Articles of Incorporation of the Chamber.

Faculty of Civil Engineering is a scientific and teaching unit of the University of Montenegro, which is developing scientific research as a basis for teaching activities in the field of civil engineering. In addition, a significant segment of the activities of the Faculty is solving problems encountered in design, construction, and operation of complex and specific construction projects.

Faculty of Architecture of the scientific and teaching unit of the University of Montenegro, which is developing a critical level of professional knowledge and the general public in the field of architecture and urbanism of Montenegro that will stop the adverse trends of degradation of space and turn them into a process of affirmation of the importance and protection of national resources and raising the quality of space. The Faculty of Architecture in Podgorica forms the architectural staff, who will, based on the best world of knowledge in this field and their practical application to developing and implementing plans and projects in the area, make a well valorization of space with the goal of sustainable development in relation to a protected architectural and natural heritage of the human impact amended - built space.

Seismological Observatory of Montenegro was founded with the main task of seismic monitoring and researching of seismic activity of the Montenegro territory and is responsible for elaboration of seismic maps. Apart from fundamental seismological observations and analyses of earthquakes, not only for the Montenegrin territory, but for the whole World, Montenegro Seismological Observatory also performs professional jobs at the area of applied or engineering seismology - in order to define relevant seismic parameters for terrain sites planed for high building constructions, for seismic regionalization of the whole Republic territory, etc.

Chamber of Economy of Montenegro is organized in several association boards, including the Association of Civil Engineering, Industry for Building Materials and Public Utility Services. The primary goal of the Association is to discuss and resolve issues that come under competences of these branches, give opinions on issues of common interests for all members of this Association.

Hydrometeorological Institute of Montenegro is responsible for elaboration of wind, snow and isotherm maps, as well as observing, measuring and collecting of meteorological, hydrological and ecological parameters.

Geological Survey of Montenegro performes researches of the State interest according to mid-term and annual programs that are set by the Ministry of Economics of the Government of the Republic of Montenegro, which is in charge of geological research.

Program of works of the Geological Survey, which includes every planned activity that is subject of approval of the Government of the Republic of Montenegro, represents the synthesis of the geological research of the State interest, financed through annual programs of geological research in Montenegro, and geological research focused on current public economy issues that are financed by the interested investors. Geological Survey’s Program of works includes projects, studies and issues of State interest in the filed of:

- Basic geological research

- Basic and detailed geological research of mineral resources outside the exploitation sites

- Compiling complex geological maps and  databases and studies for giving particular mineral resources concessions

- Geoecological research

- Publishing activities and development projects

PI Centre for Ecotoxicological Research of Montenegro is founded for the purpose of monitoring of the all segments of environment of the Republic (air, waters, soils, waste, radioactivity, human and animal food), as well as a referent institution for food control and other products and diagnose of toxicants.

The Center is founded for performing activities of public interest, such as the following:

- ecotoxicological research of all the vital environment segments: air, drinking and sea water, soil, flora and fauna.

- research of ionising and non-ionizing radioactivity and climate variations,

- research of the noise and vibrations in the vital and working environment,

- making of special toxicological and expert studies, analyses and programs for the necessities of the University, State Institutions, Research Institutes, as well as other organisations,

- control and certification of the human and animal food and other turnover goods, imported, produced and exported,

- measurement of the emission at the contamination sources in the air, waters and soils.

- analysis in accidental situations,

- making studies for estimation of the effects on the environment ( EIA), consulting and planning services in the field of ISO 14000 ecological standards, and other related works in accordance with the activities of the Centre, if performing these works contribute to the development and progress of its basic activity,

- examination of working environment and working tools and safety at work,

testing of hazardous materials, determination, and classification of hazardous waste.

ORGANIZATIONAL CHARTS OF THE MAIN STAKEHOLDERS:

The Ministry of Sustainable Development and Tourism

The Institute for Standardization of Montenegro

Bodies of the Chamber of Engineers are the following: assembly, managing board, president, supervisory board and executive board of vocational chambers.

To achieve the objectives of the Chamber and perform tasks within the competence of professions, all in order to improve the professions and make the appropriate participation of professions in the work of the Chamber, the following vocational chambers are formed:

- vocational chamber of architects;

- vocational chamber of civil engineers;

- vocational chamber of electrical engineers;

- vocational chamber of mechanical engineers;

- vocational chamber of other engineers and planners non-engineers.

Bodies of the Chamber of Economy are the following: assembly, managing board, president, and supervisory board. The Chamber is organized in several associations for the following areas: bank and financial institutions, construction industry, informatics and communication technologies, small and medium-sized enterprises, agriculture, maritime economy, transport, forestry, textile industry, trade, tourism, energy and mining industry,  metallurgy and metal-working industry and shipping, as well as in several boards, such as:

- Foreign Economic Relations and European Integrations Association Board;

- Quality Management;

- Women Entrepreneurship;

- Energy efficiency and environment protection.

Hydrometeorological Institute of Montenegro is organized in four sectors with 114 full-time employees:

- Meteorology,

- Hidrology,

- Ecology,

- Hidrography.

Geological Survey of Montenegro is organized in four departments whose activities include performance of geological research in the area of fundamental and applied research. GSM’s departments are as follows:

- Department of regional geology, mineral resources and mineral resources concessions

- Department of engineering geology, hydrogeology, geotechnics and water concessions

- Department of mining works and research drilling

- Department of legal, financial and human resources affairs

The Centre for Ecotoxicological research

5. 	Budget

Maximum budget allocated is € 700 000.

6. 	Implementation Arrangements

6.1 	Implementing Agency responsible for tendering, contracting and accounting(AO/CFCU/PAO/ Commission), including contact person and full contact details.

Delegation of the European Union to Montenegro

Mr Nicola Bertolini, Head of Operations

Vuka Karadžića 12, 81 000 Podgorica, Montenegro

Telephone: +382 20 444 600

Fax: +382 20 444 666

E-mail: Nicola.BERTOLINI@ec.europa.eu

6.2 	Main counterpart in the BC, including contact person and contact details. Also include RTA counterpart and the BC Project leader

BC Project leader

Contact: Danilo Gvozdenović, acting deputy minister for construction

Ministry of Sustainable Development and Tourism

Department of construction

Address:IV Proleterske brigade 19, 81 000 Podgorica

Phone: +382 20 446 209

Fax: +382 20 446 214

E-mail: danilo.gvozdenovic@mrt.gov.me

RTA

Contact: Svetlana Vuksanović, Independent advisor

Ministry of Sustainable Development and Tourism

Department of construction

Address: IV Proleterske brigade 19, 81 000 Podgorica

Phone: +382 20 446 272

E-mail: svetlana.vuksanovic@mrt.gov.me

6.3 	Contracts

One Twinning Contract

One separate supply contract procured by the BC in order to provide IT equipment (specialised software and computers) for elaboration of the nationally determined parameters to all Eurocodes

7.	Implementation Schedule (indicative)

7.1	Launching of the call for proposals		Q2 2011

7.2	Start of project activities			Q4 2011

7.3	Project completion				Q1 2013

7.4	Duration of the execution period		18 months (legal duration 21 months)

8.	Sustainability

The project is well embedded into the institutional structure in Montenegro. In fact, the Ministry of Sustainable Development and Tourism of Montenegro is the institution responsible for the preparation of technical basis for drafting laws and other regulations in the field of civil engineering, adjustment of national legislation with EU legislation in the field of civil engineering, and standardization and conformity assessment in the field of civil engineering.

The Institute for Standardization of Montenegro provides the basis for drafting regulations, establishing infrastructure of advisory and technical bodies (technical committees) engaged on works of Montenegrin standardization and provides compatibility of Montenegrin standards and related documents with European and international standards and related documents

The newly created working group for monitoring and implementation of the adopted programs will be in the responsibility of the Ministry of Sustainable Development and Tourism, which will continue to work on harmonization of all the regulations and standards in the field of civil engineering with European regulations and their full application.

Moreover, by means of adopting the program a basis for further policy of adoption of other standards and legislation in construction will be created.

In the pilot project on the national annex to Eurocode 8 the results of the NATO Science for Peace and Security project “Harmonization of Seismic Hazard Maps for the Western Balkans Countries” will be implemented.

9.	Crosscutting issues (equal opportunity, environment, etc…)

Equal Opportunity

According Law on Gender Equality, State administration bodies, local administration bodies, public institutions, public enterprises and legal persons with public authority (hereinafter: organs), in all phases of planning, adopting and implementing decisions, and carrying out the activities, are obliged to assess and evaluate the impact of those decisions and activities upon the position of women and men, with the aim of achieving gender equality.

Environment

Designs according to Eurocodes provide increased safety and economy of construction works, which is relevant to sustainable use of natural resources. Also, the increased reliability of structures to withstand major natural and technological hazards will protect the environment from pollution and will reduce dramatically the need of demolition of structures and the respective amount of garbage to be tackled.

Minorities

The projects shall take into account the specific needs of ethnic communities, in particular Roma, who are generally considered to be the most marginalised ethnic in the region and those asylum seekers belonging to specific minorities or ethnic groups in their state of origin. The implementation of the Eurocodes will contribute the economic growth that is a precondition to create a society with greater social cohesion and less exclusion.

10.	Conditionality and sequencing

Pre-conditions

- establishing of a Montenegrin Project Steering Committee;

- provided national co-financing;

- the English version of the EN Eurocodes standards provided by the Institute for Standardization to the Montenegrin participants in the project;

- creation of 12 working groups of the Montenegrin participants mirroring the CEN TC250/SCs on EN 1990 to EN 1999 and the Horizontal Groups on bridge and fire design;

- availability of the results from the NATO project “Harmonization of Seismic Hazard Maps for the Western Balkans Countries” for incorporation in the national annex;

- availability of sufficient staff of the Ministry of Sustainable Development and Tourism for implementing the activities.

ANNEXES TO PROJECT FICHE

1. 	Logical framework matrix in standard format (compulsory)

2. 	Detailed implementation chart (optional) Not included

3. 	Contracting and disbursement schedule by quarter for full duration of programme (including disbursement period) (optional)

4. 	Reference to feasibility /pre-feasibility studies. For all investment projects, the executive summary of the economic and financial appraisals, and the environmental impact assessment should be attached (optional) Not included

5. 	List of relevant Laws and Regulations (optional)

6. 	Reference to relevant Government Strategic plans and studies (may include Institution Development Plan, Business plans, Sector studies etc) (optional) Not included

ANNEX I: Logical Framework Matrix

| PROJECT DESCRIPTION | OBJECTIVELY VERIFIABLE INDICATORS | MEANS OF VERIFICATION | ASSUMPTIONS |
| --- | --- | --- | --- |
| Overall objective: Achieving highest safety and technical quality of Montenegrin construction | - Adoption of the Eurocodes will provide the basis needed for harmonization of existing legislation in Montenegro in construction with the acquis communautaire as regards the Construction Products Directive (Directive 89/106/EEC) and the Directive on the coordination of procedures for the award of public works contracts, public supply contracts and public service contracts (Directive 2004/18/EC). - By the end of the year 2014, 80% of national provisions and standards from the area of civil engineering will comply with EU provisions and standards. This is a precondition for abolishment of technical barriers to trade between Montenegro and the EU and EFTA Member States. - Replacement of the outdated national standards for structural analysis and start designing with the most up-to-date standards in the world, which provide highest safety and technical quality. | - Commission's Progress Reports and other documents related to accession, - Official gazette, - Report of the Sector for monitoring and development of civil engineering in Montenegro within the Ministry of Sustainable Development and Tourism, - Reports of competent institutions (the Ministry of Sustainable Development and Tourism, and Institute for Standardisation) on publication of standards and provisions in the field of civil engineering. |  |
| Project purpose: To create prerequisites for the harmonization of national regulations and standards for structural analysis and design with the regulations and standards of EU and for building capacities for their successful adoption, implementation and use. | - Montenegrin working groups mirroring the CEN Technical Committee 250 Sub-Committees have capacity (methodology, IT tools and the example of the national annex of the pilot project) to start preparation of the national annexes to all Eurocode parts. - Gradual adoption of the Eurocodes packages tailored to their relevance to the to the most wide-spread structural types in Montenegro; - Montenegrin trainers of professionals and University professors have capacity (plans, teaching and promotion material, good practice examples and had training) to start preparation of courses and guidelines on Eurocodes in Montenegrin language and to transfer their knowledge to local professionals and students. - First Eurocodes part (Eurocode 8 Part 1) is ready for publication as national EN Standard and serves as a good practice example for preparation of the rest of the national annexes. | - EC progress report - Official gazette - Report of the Group for monitoring and implementation on the program for adopting the Eurocodes, primarily Eurocode 8. - Reports of competent institutions (the Ministry of Sustainable Development and Tourism, and the Institute for Standardisation) on publication of Eurocode 8 Part 1 as national EN standard. | - Commitment of non-institutional actors (university, business entities in design and construction, inspections and supervisory bodies) to work on preparation of the national annexes to all Eurocode parts. - Commitment of the institutions in charge of standardisation in construction (the Ministry of Sustainable Development and Tourism, the Ministry of Interior and Public Administration, and the Institute for Standardization) for the adoption of European standards in the field of structural design. - Commitment of non-institutional actors (university, business entities) to perform teaching and promotion of the Eurocodes. - Availability of translation in Montenegrin (Serbian) language of Eurocode 8 Part 1 for its publication as national EN standard. |
| Results: 1. Approved action plan for adoption of the Eurocodes 2. IT equipment and methodology for elaboration of the nationally determined parameters to all Eurocodes is provided in 18 months from the beginning of the implementation of the project 3. Approved action plan for implementation of the Eurocodes. 4. National annex to Eurocode 8 part 1 prepared in Montenegrin language. | - 12 months from the beginning of the project the action plan for the adoption of the Eurocodes is officially approved by the Montenegrin Government; - Availability of the IT equipment for elaboration of the nationally determined parameters to all Eurocodes 18 months from the beginning of the project. - 18 months from the beginning of the project the action plan for the implementation of the Eurocodes is officially approved by the Montenegrin Government; - National annex to Eurocode 8 part 1 prepared in Montenegrin language is available after 18 months from the beginning of the project. It serves for the publication of the national EN standard on this part. Also, it will serve as an example for preparation of the remaining national annexes; - seminar for training the national trainers is performed in 18 months from the beginning of the project. | - Report of an external expert on the quality of elaborated action plan for adoption of the Eurocodes; - Report of an external expert on the quality of elaborated action plan for implementation of the Eurocodes; - Official notes on acceptance of the two action planes; - Report of an external expert on assessment of the national annex to Eurocode 8 part 1; - Official gazette; - EC progress report; - Report of project coordinator for the organized seminar; - Evaluation sheets on the seminar filled in by participants. | - Commitment of non-institutional actors (university, business entities in design and construction, inspections and supervisory bodies) to work on preparation of the national annexes to all Eurocode parts. - Commitment of the institutions in charge of standardisation in construction (the Ministry of Sustainable Development and Tourism, the Ministry of Interior and Public Administration, and the Institute for Standardization) for the adoption of European standards in the field of structural design. - Commitment of non-institutional actors (university, business entities) to perform teaching and promotion of Eurocodes. - Availability of the results from the NATO Science for Peace and Security project “Harmonization of Seismic Hazard Maps for the Western Balkans Countries” to be incorporated in the national annex. |
| Activities - timeline for preparation of national annexes to the different Eurocode parts providing to introduce in the first place the Eurocodes packages relevant to the most wide-spread structures in Montenegro; - determination of the methods to estimate or suggestion for the most appropriate values, of the nationally determined parameters to all Eurocodes; - definition of list of IT equipment (specialised software and computers) to be purchased by the Ministry of Sustainable Development and Tourism for elaboration of the nationally determined parameters to all Eurocodes; - concept for establishing regional networking in translation of the Eurocodes parts; - concept for establishing regional cooperation in preparation of wind, snow, and isotherms maps; - roadmap for adaptation of the Montenegrin legislative framework for construction to allow the use of the Eurocodes. - provision of the IT equipment (specialised software and computers) determined by Activity 1.1 for elaboration of the nationally determined parameters to all Eurocodes; 2.1 definition of the list for training material for continuous professional development to be prepared/adopted and provision of good practice examples, including: information leaflets on the implementation of the EN Eurocodes, designer handbooks and manuals, guidelines with worked examples (e.g. of common types of buildings and bridges), training and design software; 2.2 definition of concept for university programme of studies on the Eurocodes and provision of good practice examples for: lecturers’ notes, information leaflets on the implementation of the EN Eurocodes, guidelines with worked examples, training software; 2.3 planning of seminar on training the Montenegrin Eurocodes trainers; 2.4 elaboration of plan for intensive training of the Montenegrin construction professionals; 3.1 determination of those nationally determined parameters of Eurocode 8 where specific for Montenegro values obligatory have to be introduced, and estimation of these parameters; 3.2 incorporation of results from the NATO Science for Peace and Security project “Harmonization of Seismic Hazard Maps for the Western Balkans Countries” for determination of the seismic actions (e.g. seismic map, response spectra, etc.); 3.3 elaboration of the text of the national annex in Montenegrin language. | Means: Twinning (activities 1.1, 1.2, 1.3, 1.4, 1.5, 1.6, 2.1, 2.2, 2.3, 2.4, 3.1, 3.2, 3.3) Procurement of equipment - supply contract (activity 1.7) | Costs: Total: € 770,000 IPA funding: € 700,000 National contribution: € 70,000 | Assumptions: - Availability of experts; - Good cooperation between all Stakeholders. |

- Pre-conditions - establishing of a Montenegrin Project Steering Committee; - provided national co-financing; - the English version of the EN Eurocodes standards provided by the Institute for Standardization to the Montenegrin participants in the project; - creation of 12 working groups of the Montenegrin participants mirroring the CEN TC250/SCs on EN 1990 to EN 1999 and the Horizontal Groups on bridge and fire design; - availability of the results from the NATO project “Harmonization of Seismic Hazard Maps for the Western Balkans Countries” for incorporation in the national annex. - availability of sufficient staff of the Ministry of Sustainable Development and Tourism for implementing the activities (see Annex III)

ANNEX III:	amounts (in M€) Contracted and disbursed by quarter for the project

| Contracted | Q3 2010 | Q4 2010 | Q1 2011 | Q2 2011 | Q3 2011 | Q4 2011 | Q1 2012 | Q2 2012 | Q3 2012 | Q4 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contract 1 |  |  |  | 700.000 |  |  |  |  |  |  |
| Contract 2 |  |  |  |  |  |  |  | 70,000 |  |  |
| Cumulated |  |  |  | 700,000 | 700,000 | 700,000 | 700,000 | 770.000 | 770.000 | 770.000 |
| Disbursed |  |  |  |  |  |  |  |  |  |  |
| Contract 1 |  |  |  | 400.000 |  | 115.000 |  | 115.000 |  | 70.000 |
| Contract 2 |  |  |  |  |  |  |  | 70,000 |  |  |
| Cumulated |  |  |  | 400.000 |  | 515.000 |  | 700.000 |  | 770.000 |

ANNEX V

Reference to laws, regulations and strategic documents:

Laws

- Law on spatial development and construction of structures (»Official Gazette of the Republic of Montenegro«, No. 51/08);

- Law on economic societies (»Official Gazette of the Republic of Montenegro«, No. 06/02, 17/07);

- Law on state survey and real estate cadastre (»Official Gazette of the Republic of Montenegro«, No.29/07);

- Law on administrative fees (»Official Gazette of the Republic of Montenegro«, No.55/03, 46/04, 81/05, 02/06, 22/08);

- Law on energy (»Official Gazette of the Republic of Montenegro«, No.39/03);

- Law on protection and rescue (»Official Gazette of the Republic of Montenegro«, No.13/07 and 05/08);

- Law on environmental impact assessment (»Official Gazette of the Republic of Montenegro«, No. 80/05);

- Law on sanitary inspection (»Official Gazette of the Republic of Montenegro«, No.56/92, 27/94 and 14/07);

- Law on roads (»Official Gazette of the Republic of Montenegro«, No.42/04);

- Law on electronic communications (»Official Gazette of Montenegro«, No.50/08);

- Law on water (»Official Gazette of the Republic of Montenegro«, No.27/07);

- Law on agricultural land (»Official Gazette of the Republic of Montenegro«, No.15/92, 59/92, 27/94);

- Law on geological researches (»Official Gazette of the Republic of Montenegro«, No. 28/93,27/94, 42/94, 26/07);

- Law on air traffic (»Official Gazette of Montenegro«, No.66/08 from October 31, 2008);

- Law on protection of cultural monuments (»Official Gazette of the Republic of Montenegro«, No.47/91, 17/92 and 27/94);

- Law on safety at work (»Official Gazette of the Republic of Montenegro«, No.79/2004);

- Law on standardization (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.57/88, 23/91, 55/91);

- Law on measure units and measures (»Official Gazette of the Federal Republic of Yugoslavia«, No. 86/94, 83/94, 28/96 and 12/98);

- Law on telecommunications (»Official Gazette of the Republic of Montenegro«, No.59/00);

- Law on explosive materials and flammable liquids (»Official Gazette of the Republic of Montenegro«, No. 44/76, 49/79, 34/86, 11/88 and 29/89);

- Law on traffic safety on roads (»Official Gazette of Montenegro«, No.72/05);

- Law on public procurement (»Official Gazette of Montenegro«, No.46/06);

Regulations

In the field of architecture

- Rule Book on manner of keeping and content of a building log, a building book and an inspection book (»Official Gazette of Montenegro«, No.81/2008);

- Rule Book on manner of conducting review of conceptual project or main project (»Official Gazette of Montenegro«, No.81/2008);

- Rule Book on manner of conducting technical review (»Official Gazette of Montenegro«, No.33/2008) ;

- Rule Book on manner of developing and content of technical documentation (»Official Gazette of the Republic of Montenegro«, No.22/2002);

- Rule Book on contents of elaborate on preparatory works (»Official Gazette of Montenegro«, No.80/2008);

- Rule Book on detailed conditions and ways of adapting the facilities for access and movement of persons with reduced mobility (»Official Gazette of Montenegro«, No.10/2009);

- Rule Book on detailed conditions for establishing institutions in the field of education (»Official Gazette of the Republic of Montenegro«, No.40/2006);

- Regulation on spatial planning and arrangement, construction, reconstruction and maintenance of military facilities in the military circle (»Official Gazette of Montenegro«, No.48/2008);

- Rule Book on technical regulations for construction of warehouses and manner of maintenance and usage of warehouses (»Official Gazette of Montenegro«, No.44/2008);

- Rule Book on classification, the minimum conditions and categorization of catering facilities, restaurants (»Official Gazette of the Republic of Montenegro«, No.33/2007);

- Rule Book on minimum technical conditions for housing construction (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.15-7132/1969 and No. 32,33,34/1998);

- Rule Book on technical measures and conditions for the final works in the buildings (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.12213/1970);

- Rule Book on technical measures and conditions for the construction of housing according to the system of modular coordination (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.15-7133/1969);

- Rule Book on technical measures and conditions for hydrocarbon waterproofing of roofs and terraces (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.15-7131/1969);

- Rule Book on general measures and standards of occupational safety for buildings designed for the working and auxiliary facilities (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.49/2-9/1967);

- Rule Book on technical measures and conditions for thermal protection of buildings (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No. 9624/1/1970);

- Rule Book on technical measures and conditions for ventilation in residential buildings (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.9225/1/1970);

- Rule Book on technical measures and conditions for sound protection in buildings (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.9623/1/1970);

- Rule Book on technical measures and conditions for thermal energy in buildings (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.7-5132/1/1970);

- Rule Book on technical measures and requirements for building space and equipment for collecting and ablation of waste materials from residential buildings (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.15-7881/1/1970);

- Rule Book on general minimum technical conditions of devices and equipment for office space, commercial enterprises, commercial activities and commercial business units (»Official Gazette of the Federal National Republic of Yugoslavia" No.065613/2-59/1960);

- Rule Book on specific minimum technical conditions, devices and equipment, office space waste for transport companies and their business units (»Official Gazette of the Federal National Republic of Yugoslavia" No.06-4664/2-59/1960 and no. 011-106/1969);

- Rule Book on minimum technical and hygienic-technical conditions of premises, equipment and devices for resorts (»Official Gazette of the Federal National Republic of Yugoslavia" No.13469/1954);

- Rule book on storage and refueling (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.22-21/17/1971);

- Technical conditions for the performance of finishing works in construction, publisher “Zavraj”  Belgrade;

- Norms and standards in construction, publisher “Građevinska knjiga” Belgrade;

- Montenegrin standards (MEST EN) in the field of construction materials and construction;

- JUS Yugoslav standards in the field of construction materials and construction;

In the field of civil engineering

- Interim technical regulations for load building - only the Article 213 Load snow and 3rd chapters Supplementary loads (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.61/48);

- Rule Book on technical regulations for load construction facilities (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.26/88);

- Rule Book on technical regulations for warehouses (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.53/83);

- Rule Book temporary technical regulations for construction in seismic areas - does not apply to facilities construction (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.39/64);

- Rule Book on technical regulations for construction of buildings in seismic areas (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.31/81, 49/82, 29/83, 21/88 i 52/90);

- Rule Book on technical regulations for rehabilitation, strengthening and reconstruction of damaged high-rise buildings for earthquake reconstruction and revitalization (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.52/85) ;

- Seismologic map - Rule Book on technical regulations for construction of objects in areas of high seismicity;

- Rule Book on technical regulations for concrete and reinforced concrete (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.11/71);

- Rule Book on technical measures and conditions for concrete (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.51/71);

- Rule Book on technical regulations for concrete and reinforced concrete made of lightweight aggregate natural and artificial fillings (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.15/90);

- Rule Book on technical regulations for design, production and performance structures prefabricated elements not reinforced and reinforced cellular concrete (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.14/89);

- Rule Book on technical regulations for concrete and reinforced concrete facilities set forth to aggressive effects (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.18/92);

- Rule Book on technical regulations for steel wires, rods and ropes for prestressing construction (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.41/85 and 21/88);

- Rule Book on technical regulations for bearing steel structures (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.61/86);

- Technical regulations for simple construction of buildings by bearing steel structures (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.6/65);

- Technical regulations for light steel structures for bearing steel structures (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.6/65);

- Technical regulations on quality of welded joints for bearing steel structures (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.41/64);

- Technical regulations for tolerance of measures and forms of bearing steel structures (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.41/64);

- Rule Book on technical measures and conditions for the protection of steel structures (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.32/70);

- Rule Book on technical measures and conditions for installation of steel structures (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.29/70);

- Technical regulations for inspection and testing of bearing steel structures (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.6/65);

- Technical regulations for maintenance of steel structures during the exploitation of bearing steel structures (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.6/65) ;

- Rule Book on technical regulations for foundations for buildings (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.15/1990);

- Rule Book on technical measures and conditions for performing research work in the construction of large buildings (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.3/1970);

In the field of utilities

- Rule Book on manner of determining and maintaining zones and belts of sanitary protection of water sources and restrictions in these areas (»Official Gazette of Montenegro«, No.8/1997);

- Rule Book on the quality of wastewater and manner of their discharge into public sewers and natural recipient (»Official Gazette of Montenegro«, No.10/1997);

- Rule Book on criteria for selection of location, manner and procedure of waste disposal (»Official Gazette of Montenegro«, No.56/2000);

- Rule Book on manner of elaboration and content of technical documentation (»Official Gazette of the Republic of Montenegro«, No.22/2002);

In the field of mechanical engineering

- Rule Book on measures and standards of safety at work on instruments for work (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.15, 18/91) ;

- Rule Book on technical regulations for low voltage wiring (»Official Gazette of the Federal Republic of Yugoslavia«, No.br. 28/95) ;

- Rule Book on technical regulations for production and use of steam boilers, steam courts and water heaters (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 56, 61/72);

- Rule Book on technical regulations for pumps and compressors (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 32/74);

- Rule Book on technical regulations on lightning rods (»Official Gazette of the Federal Republic of Yugoslavia«, No.br. 11/96);

- Rule Book on technical regulations for electrically powered elevators for vertical transport of persons and goods (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 16/86);

- Rule Book on means of personal protection at work and personal protective equipment (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 35/69) ;

- Technical regulations for special protection of power plant fire (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 16/66, 58/72, 24, 75) ;

- Regulations on technical provisions for hydrant network for fire (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 30/91) ;

- Rule Book on technical regulations for warehouses (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 55/83);

- Rule Book on technical regulations for ventilation and air conditioning systems (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 38/89);

- Rule Book on technical regulations for electrically powered elevators for vertical transport of persons and goods (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 16/86) ;

- EN 81-1‚:1998 safety regulations for construction and installation of elevators for transportation of persons and goods - Part 2, Annex E Electric elevators;

- Rule Book on technical regulations for electrically powered elevators for vertical transport of cargo, with the cabin to which people do not is not possible to access people (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 55/87);

- EN 81-3‚:2000 Safety rules form the construction and installation of elevators - Parts 3: Electric and hydraulic service elevators, Annex E.1.Annex E.2 ;

- EN 81-2‚:1998 safety regulations for the construction and installation of elevators for the transportation of persons and goods - Part 2, Annex E Hydraulic elevators;

- Rule Book on technical regulations for facade elevators on electric drive (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 19/86);

- Rule Book on technical regulations for electrically powered elevators for sidelong transport of persons and goods (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 49/86);

- Rule Book on technical regulations for moving staircase (escalator) and mobile routes to transport persons (»Official Gazette of the Federal Republic of Yugoslavia«, No.br. 83/94) ;

- Rule Book on technical regulations for electrically powered elevators for vertical transport of persons and goods (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.br. 16/86) Section XXIII.

- JUS Standards in the field of mechanical engineering;

- Montenegrin standards (MEST - EN) in the field of mechanical engineering;

High voltage wiring

- Rule Book on protective measures against the dangers of electricity in the work premises and work sites (»Official Gazette of the Republic of Montenegro", No. 6/86 and 16/86);

- Rule Book on technical measures and requirements for elevators (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No. 51/70 and 16/86);

- Rule Book on technical regulations for electrically powered elevators for vertical transport of persons and goods (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No. 16/86, 28/89, 22/92 i (»Official Gazette of the Federal Republic of Yugoslavia«, No. 47/95);

- Rule Book on technical regulations for Hanging scaffolding on electrical power (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No. 16/86);

- Rule Book on technical regulations for electrically powered elevators for vertical transport of cargo, with the cabin to which people do not is not possible to access people

- (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No. 55/87);

- Rule Book on technical regulations for cranes (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No. 65/91);

- Rule Book on technical regulations for moving staircase (escalator) and mobile routes to transport persons (»Official Gazette of the Federal Republic of Yugoslavia«, No.83/94);

- Rule Book on technical regulations for grounding power plant with a nominal voltage above 1000 V (»Official Gazette of the Federal Republic of Yugoslavia«, No.61/95);

- Rule Book on technical regulations for power plant with a nominal voltage above 1000V (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.4/74);

- Rule Book on technical regulations for protection of low voltage networks and associated substations (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.13/78 and No.37/95);

- Rule Book on technical regulations for protection of buildings from atmospheric discharges (»Official Gazette of the Federal Republic of Yugoslavia«, No.11/96);

- Rule Book on technical regulations for operation and maintenance of power plants and power lines (»Official Gazette of the Federal Republic of Yugoslavia«, No.41/93);

- Rule Book on technical regulations for low voltage wiring (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.53/88 and 54/88 and »Official Gazette of the Federal Republic of Yugoslavia«, No.28/95);

- Rule Book on technical regulations for construction of overhead power lines with nominal voltages from 1 kV up to 400kVA (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.65/88, »Official Gazette of the Federal Republic of Yugoslavia«, No.18/92);

- Rule Book on technical regulations for construction of medium voltage overhead lines with self bearing beam cable (»Official Gazette of the Federal Republic of Yugoslavia«, No.20/92);

- Rule Book on technical regulations for construction of low voltage overhead lines (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.6/92);

- Montenegrin standards (MEST EN) in the field of energy;

- JUS Yugoslav standards in the field of energy;

Low voltage wiring

- Standard DIN VDE 0888 (Part 1, 2, 3, 4 and 5) ;

- Standard DIN VDE 0472 (Part 1) ;

- Standard DIN VDE 0472 (TI.211, TI.213, TI.214, TI.221, TI.222, TI.223, TI.231, TI.232, TI.233, TI.234 ;

- ITU-T Directives: IEC G.652 ;

- Directives IEC 793 in IEC 794 ;

- Directives EN 187 000 in EN 188 000 ,

- Guideline on safety measures from electricity on electricity lines of the Yugoslav Rail -JŽ (Guideline 227, Beograd 1978) ;

- Rule Book on terms for elaboration of technical documentation for telecommunication network and telecommunication equipment (»Official Gazette of the Republic of Montenegro«, No.61/04) ;

- Recommendation of the Montenegrin Telekom for design and construction of telecommunication signal systems in housing objects;

- Montenegrin standards in the area of telecommunications MEST EN 50412-2-1:2009;

- Montenegrin standards for houses and buildings from MEST EN 50090-2-1:2009 to  MEST EN 50090-5-3:2009;

- Rule Book on technical requests for protection of garages for passenger cars from the fire and explosion   (»Official Gazette of Montenegro«, No.31/05 – 29th July 2005);

Fire protection

- Rule Book on technical regulations for access roads turntable and plateaus, fire engines nearby facilities with an increased risk of fire  (»Official Gazette of the Federal Republic of Yugoslavia«, No.8/95);

- Rule Book on technical regulations for hydrant network for fire (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.30/91);

- Rule Book on technical regulations for protection of high buildings from fire (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.7/84);

- Rule Book on accommodation and keeping of heating oil (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.45/67);

- Rule Book on technical regulations for protection from fire and explosion during clearing the courts for flammable liquids (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.44/83 and 60/86);

- Rule Book on technical regulations for protection from fire and explosion during clearing the courts for flammable liquids (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.44/83 and 60/86);

- Rule Book on technical regulations for systems of ventilation and air conditioning (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.38/89);

- Rule Book on technical regulations for planning for the automatic closing doors and flaps resistant to fire (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.35/80);

- Rule Book on technical regulations for systems for removal of smoke and heat caused by fire (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.45/83);

- Rule Book on technical regulations for design, construction, operation and maintenance of gas boiler-room (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.10/90 and 52/90);

- Rule Book on technical regulations for stable devices for extinguishing fire with carbon dioxide (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.44/83 and 31/89);

- Rule Book on technical requirements for fire pyrotechnic aerosol generated (»Official Gazette of the Federal Republic of Yugoslavia«, No.58/99);

- Rule Book on technical regulations for stable installation for fire notification (»Official Gazette of the Federal Republic of Yugoslavia«, No.87/93);

- Rule Book on technical regulations for elaboration of technical documentation that must be supplied systems, equipment and devices for fire detection and alarming (»Official Gazette of the Federal Republic of Yugoslavia«, No.30/95);

- Rule Book on technical requirements for protection of garages for passenger cars from fire and explosion (»Official Gazette of the Federal Republic of Yugoslavia«, No.31/2005);

- Rule Book on technical regulations for stable courts under pressure (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.16/83);

- Rule Book on technical regulations for mobile closed courts for compressed liquid and dissolved gases under pressure (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.25/80, 9/86 and the Federal Republic of Yugoslavia br. 21/94 and 56/95);

- Rule Book on technical regulations for stable courts under pressure liquid atmospheric gases (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.9/86);

- Rule Book on technical regulations for appointment of stable courts under pressure for liquid atmospheric gases (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.39/88);

- Rule Book on technical regulations for appointment of court stable under pressure for liquid carbon dioxide (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.39/90);

- Rule Book on technical regulations for stable installation for detection of explosive gases and vapors (»Official Gazette of the Federal Republic of Yugoslavia«, No.24/93);

- Instruction on the Prohibition of the use of petrol for degreasing, washing or cleaning of metal parts and articles of other materials (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.23/67);

- Rule Book on technical regulations for designing and laying of gas pipeline distribution of polyethylene pipes for operating pressure up to 4 bars (»Official Gazette of the Federal Republic of Yugoslavia«, No.20/92);

- Rule Book on technical regulations for house gas port for operating pressure up to 4 bars (»Official Gazette of the Federal Republic of Yugoslavia«, No.20/92);

- Rule Book on technical regulations for domestic gas installations (»Official Gazette of the Federal Republic of Yugoslavia«, No.20/92);

- Rule Book on technical regulations for low voltage wiring (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.53/88 and the Federal Republic of Yugoslavia No. 28/95);

- Rule Book on technical regulations for protection of electrical installations and equipment from fire (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.74/90);

- Rule Book on technical regulations for protection against static electricity (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.62/73);

- Rule Book on technical regulations for protection of electrical installations against overvoltage (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.7/71);

- Rule Book on technical regulations for protection of buildings from atmospheric discharges (»Official Gazette of the Federal Republic of Yugoslavia«, No.11/96);

- Rule Book on technical regulations for low voltage wiring (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.53/88, 54/88 and the Federal Republic of Yugoslavia No. 28/95);

- Rule Book on technical regulations for construction of overhead power lines with nominal voltage of 1 kV to 400 kV (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.65/88 and the Federal Republic of Yugoslavia No. 82/92);

- Rule Book on technical regulations for construction of low voltage overhead lines (»Official Gazette of the Federal Republic of Yugoslavia«, No.6/92);

- Rule Book on technical regulations for operation and maintenance of power plants and power lines (»Official Gazette of the Federal Republic of Yugoslavia«, No.41/93);

- Collection of Yugoslav standards-JUS for fire protection and explosions (Book I and Book II, issued by the Federal Institute for standardisation  of the Socialist Federal Republic of Yugoslavia;

- Montenegrin standards (MEST - EN) in the area of fire protection.

Traffic

- Resolution on spatial plan of Montenegro (»Official Gazette of Montenegro«, No.24/08);

- Rule Book on grounds that the public roads outside the towns and their elements must meet in terms of security of transport (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.35/81);

- Rule Book on technical conditions for dimensioning road constructions;

- Rule Book for concrete and reinforced concrete;

- Rule Book on traffic signs on the roads;

- Rule Book on detailed conditions and manners of adjusting facilities for access and movement of Persons with reduced mobility (»Official Gazette of Montenegro«, No.10/09);

- Rule Book on manner and procedure for performing expert supervision (»Official Gazette of Montenegro«, No.6/09);

- Rule Book on manner of keeping and content of a building log, a building book and an inspection book (»Official Gazette of Montenegro«, No.81/08);

- Resolution on public parking lots and garages (local provisions)

- Decisions of the Institute for standardisation of Montenegro on Montenegrin standards (»Official Gazette of Montenegro«, No.16/09);

- Yugoslavian standards-JUS;

Safety at work

- General Rule Book on hygienic and technical protection measures at work (»Official Gazette of the Federal National Republic of Yugoslavia" No. 16/1947, 18/47(»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.29/71-379);

- Rule Book on LSZNR (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.35/69);

- Rule Book on measures and regulations for protection from the noise at work (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.21/92);

- Rule Book on provision of location (»Official Gazette of the Republic of Montenegro«, No.5/86);

- Rule Book on qualifying of employees (»Official Gazette of the Republic of Montenegro«, No.79/04);

- Rule Book on procedures and terms (»Official Gazette of the Republic of Montenegro«, No.79/04);

- Rule Book on injuries at work (»Official Gazette of the Republic of Montenegro«, No.29/90);

- Rule Book on professional exam (»Official Gazette of the Republic of Montenegro«, No.79/04);

- Rule Book on risk assessment (»Official Gazette of the Republic of Montenegro«, No.79/04);

- Rule Book on working and utility rooms (»Official Gazette of Montenegro«, No.27/87);

- Rule Book on content of elaborate on arrangement of construction site (»Official Gazette of the Republic of Montenegro«, No.4/99);

- Rule Book on terms for authorised organisation (»Official Gazette of the Republic of Montenegro«, No.79/04);

- Rule Book on keeping files considering safety at work (»Official Gazette of the Republic of Montenegro«, No.79/04);

- Rule Book on safety at work in the field of civil engineering (»Official Gazette of the Socialist Federal Republic of Yugoslavia«, No.42/68, 45/68 , Article 69 of the Law RS 42/91-1649 , Article 15 of the rule book RS 31/92-1146);

- Rule Book on safety at work on machines (»Official Gazette of the Socialist Federal Republic of Yugoslavia« No.18/91);

- European Commission - Guidance Paper L (concerning the CPD – 89/106/EEC) Application and Use of Eurocodes