Programme: IPA 2007

Partner country: Croatia

Area of Cooperation: Internal market and trade

twinning fiche

Title of the Project: Implementing Croatian Competition and state aid policies

Twinning budget: € 1,000.000

TWINNING PROJECT FICHE

1. Basic information

1.1 Programme: IPA 2007

1.2 Twinning Number:   HR 07 IB FI 03

1.3 Title: Implementing Croatian Competition and state aid policies

1.4 Sector: Internal market, competition

1.5 Beneficiary country: Croatia

2. Objectives

2.1. Overall objective(s):

Enhance the competition environment and state aid policy through continuous support to Croatian competition authorities and its partners on the basis of EC rules and best practices.

2.2 Project purpose:

Provide Croatian Competition Agency (CCA) and other stakeholders in competition and state aid systems with sufficient capacity for efficient implementation of competition and state aid policies.

2.3 Contribution to the Accession Partnership/ Stabilisation and Association Agreement/

National Programme for Integration of the Republic of Croatia into the EU (NPIEU)

Activities under this project will be follow-up to the results of the PHARE 2005 project. They will provide CCA and other stakeholders with sufficient capacity for efficient implementation of new competition regime established through the new Competition Act, as well as implementation of state aid law and policy.

With a view to the future EU membership, this twinning project should have impact on the readiness of all relevant Croatian institutions to fully implement competition and state aid rules in accordance with the acquis. To that end, beside the CCA the project will reach out to the Croatian Competition Agency, judiciary and sectoral regulators.

Firstly, through the new competition regime the Agency shall be empowered to impose fines to the undertakings breaching the Competition Act and for those who cooperate in cartel cases, immunity or reduction of fines will be possible. These competences, which are in place in all similar bodies in the EU countries, will be completely new for the Agency and the transfer of knowledge from a twinning agency will be of crucial importance in that respect.

Secondly, according to the new Competition Act one court shall be responsible for deciding on the legality of Agency’s decisions and fines defined therein. Since the competition law is a relatively new area in which no court has been specialized so far, this project will be the first one to target a specialized court instead of many courts which in the end would not deal with competition cases, as it was the case in the previous projects.

And thirdly, the new Credit Institutions Act stipulates that the competence over competition issues in banking sector shall be given to the CCA upon the accession to the EU. In that context this project will significantly contribute to the exchange of expertise in this area between the National Bank and the CCA and thus prepare the CCA for its future role upon the accession to the EU.

In the area of state aid, where the competence over state aid issues shall be passed to the European Commission upon Croatian accession to the EU, internships and cooperation between the EC and the CCA shall be further reinforced with the assistance of this project. The envisaged activities shall address the issue of insufficient capacity of the Agency for solving the most complex cases in the area of state aid, which has been repeated on several occasions in both Croatian and EU strategic documents.

3. Description

3.1 Background and justification:

Pursuant to the obligations under the Stabilisation and Association Agreement (SAA) between the European Union and the Republic of Croatia from 13 December 2004, as well as membership obligations in the WTO, competition policy including antitrust and state aid is one of the priorities for the Government of the Republic of Croatia.

The application and enforcement of the Competition Act and State Aid Act is entrusted to the Croatian Competition Agency (CCA, the Agency). The Agency performs its tasks assigned to it by the acts and reports to the Croatian Parliament. Its activities are managed by the Competition Council and the President of the Council, who are appointed by the Parliament for a period of five years. The Council, which consists of five members, is the managing body of the Agency, while the President represents and speaks for the Agency and manages its activities. As of July 2008, the Agency employs 50 persons.

The European Partnership adopted along with the signature of the SAA highlights the following medium-term priorities: “Reinforce the antitrust and state aid authority and build up a credible enforcement record. Substantially improve transparency in the field of state aid; develop training on competition law and policy at all levels of administration and judiciary.”

Furthermore, European Commission’s Progress Reports for 2005, 2006 and 2007 raise the need to further strengthen the capacity of CCA, which entails necessary legislative changes ensuring the fulfilment of SAA obligations in this area.

## The National Programme for the Accession of the Republic of Croatia into the EU – 2008 (NPAEU) is the sixth annual programme of the Croatian Government, which contains activities to be undertaken on its way towards EU integration. The legislative obligation arising from the NPAEU 2008 for the CCA is the delivery of the amendments to the Competition Act in order to render the competition system more efficient and prepare it for the integration into the EU. The implementing measures defined for the CCA for this year refer to the area of state aid (dealing with issues such as shipbuilding and steel industries, as well as fiscal aid, together with the MELE and other stakeholders) and continuous strengthening of administrative capacities in both competition and state aid areas (with the assistance of the PHARE project).

EU accession negotiations in the chapter 8 of the acquis (“Competition”) have not yet been opened. The main pending issue for opening the chapter is the situation in the Croatian shipbuilding. The precondition for opening chapter 8 is restructuring of the shipbuilding industry.

Benchmarks (steel industry, alignment of fiscal aid and transparency in the area of automotive parts and textile industries) have been fulfilled. The only remaining benchmark is in the area of shipbuilding. Namely, the shipbuilding industry has to undergo privatization process, after which the Agency will resume its temporarily terminated proceedings on the assessment of individual restructuring plans of Croatian shipyards. The Croatian Government has made a proposal regarding the restructuring of the Croatian shipyards which was sent to Brussels. At present the Government is still awaiting the EC’s reply on the proposal.

This project is to build upon the results of the current PHARE 2005 project which comprises both competencies of the Agency, competition and state aid. Twinning component is being implemented since April 2007 with Germany as a twinning partner. In the competition part, main emphasis is on the drafting of the amendments to the Competition Act, as well as new bylaws which will be needed as implementing legislation arising from the changed Competition Act. Training on the implementation of the new Act will be needed within IPA project. In the state aid part of the project main activities are focused on on-the-job consultancy, primarily related to the most complex cases which are dealing with the issues arising from the SAA obligations and EU accession negotiation benchmarks. Further awareness raising is needed in this area, both on central and regional levels.

After several separate projects in the fields of competition and state aid respectively, PHARE project was the first one to encompass the Agency as a whole. The IPA project should build upon its results and strengthen the capacity of the Agency, as well as other stakeholders in the competition and state aid systems, implement new competition regime and state aid rules. The project consists of twinning and service component which will be implemented in parallel. It is envisaged that the Service component starts in September 2009.

With a view to the future EU membership, the twinning project should have an impact on the readiness of all relevant Croatian institutions to fully implement competition and state aid rules in accordance with the acquis. To that end, beside the CCA the project will reach out to the judiciary and sectoral regulators.

3.2 Linked activities:

| Project | Project Title | Beneficiary | Start Date End Date | Allocation (EUR) | Main Results |
| --- | --- | --- | --- | --- | --- |
| CARDS 2001 | Support to the Development of Competition Policy in Croatia in line with the EU Standards and Practice – TA(technical assistance), SU (supply) | CCA | March 2003 December 2005 | 650,000.00 | Assistance in legal drafting, CCA and external staff trained, IT equipment supplied |
| CARDS 2002 | Support to the Croatian State Aid System - facility | CCA | March 2004 November 2004 | 190,000.00 | Basis created for the subsequent twinning and supply |
|  | Support to the Croatian State Aid System – TW, SU | CCA | June 2005 April 2007 | 1,200,000.00 | CCA and external capacity raised, public awareness raised, state aid control system set up and database created |
| CARDS 2003 | Further strengthening of the Croatian Competition Agency and implementation of competition law and policy – TA | CCA | November 2005 February 2007 | 450,000.00 | CCA and government staff trained, public awareness raised |
| CARDS facility | Support to the Process of Restructuring the Shipbuilding Industry in Croatia - TA | CCA | March 2007 December 2007 | 190,000.00 | CCA assisted in assessing individual restructuring plans of Croatian shipyards |
| CARDS 2004 | Improving information to the Croatian business community | MELE | Ongoing since September 2007 | 1,500,000.00 | To generally improve the awareness of the business community in key legislative fields |
| PHARE 2005 | Strengthening of capacity to manage and enforce the EU competition and state aid policies – TW, SU | CCA | Ongoing since April 2007 | 1,900,000 | Assistance in legal drafting, training of CCA staff and other stakeholders, on-the-job consultancy |
| PHARE 2005 | Croatian Maritime Sector: State Aid and Market Access | Ministry of the Sea, Transport and Infrastructure; CCA | December 2007 – June 2008 | 200,000.00 | To improve policy making and policy implementation capacity of Croatian maritime administration |
| IPA 2007 | Implementing Croatian competition and state aid policies - TA | CCA | Envisaged start date - September 2009 | 1,000,000.00 | Provide the stakeholders in competition and state aid systems with sufficient capacity for efficient implementation of competition and state aid policies. |

CARDS projects

Anti-trust

1. The process of strengthening the CCA’s administrative capacity, especially the education of staff in the area of competition, as well as other officials enforcing the relevant legislation was already partly covered by CARDS 2001, “Support to the Development of Competition Policy in Croatia in line with the EU Standards and Practice” (€650,000.00), the first EU technical assistance project implemented in the CCA. The project’s three components (legal approximation, institutional capacity building and training, public and governmental awareness raising) were implemented and in 2005 the project was continued through training seminars for CCA staff and external stakeholders. Implementation was completed at the end of 2005.

Under the 2001 project CCA also benefited from the supply of IT equipment, including hardware and creation of a new website. For the purpose of successful implementation of the supply CCA employed an IT person to administer the IT system.

2. The implementation of the CARDS 2003 project ”Further strengthening of the Croatian Competition Agency and implementation of competition law and policy” (€ 450,000.00) comprised two components. One referred to the implementation and enforcement of competition legal framework within the government and private sector and the other to institutional and administrative capacity building of the CCA. It continued to build upon the training component of the CARDS 2001 project, proceeding with the training activities of the CCA staff as well as with the training of external stakeholders (government and private sector representatives). Implementation was completed in February 2007.

State aid

1. There was a short-term technical assistance project preparing the ground for the twinning CARDS 2002 project in the area of state aid (€190,000.00), which was completed in November 2004. This project was the first project in the CCA in the field of state aid. The project carried out the activities in the area of legal harmonisation, IT support system and training.

2. Twinning project CARDS 2002 was implemented from June 2005 until April 2007. It was envisaged to use the results and outputs of the above mentioned project as a basis for achieving its objectives. The consulting countries under the project were Germany and Slovenia. The objective of the project was to provide support to the CCA regarding the commitments undertaken pursuant to the Stabilization and Association Agreement. Given that, it was directed to:

  - capacity building of the CCA (through legislative review and drafting; update of the Training Needs Analysis and provision of training for CCA staff; internships; institutional assessment; development of guidelines and notification requirements and advice on ongoing cases),

  - setting up the state aid control system (through categorisation and methodology; process of alignment, amendment and elaboration of state aid schemes and annual reporting),

  - raising awareness and understanding state aid advocacy (through analysis of training needs for external target groups in the government and training; implementation strategy for the state aid objectives and support in practical state aid advocacy).

3. Separate subproject was state aid supply project (€400,000.00) aimed at the establishment of a comprehensive state aid data base in Croatia (CROSADS - Croatian State Aid Database System). The contracted local IT company procured the necessary hardware and developed software application for the database in close cooperation with the CCA and ECD.

4. CARDS facility project (€190,000.00), implemented between March and December 2007 aimed at giving assistance to the CCA in assessing restructuring plans of Croatian shipyards, so as to be able to fulfil a benchmark imposed by the EU for the opening of negotiation chapter on competition.

5. The most recent project is PHARE 2005 project, where the main beneficiary was Ministry of the Sea, Transport and Infrastructure and co-beneficiary was the CCA. It was implemented until June 2008.

Current project PHARE 2005 comprises both competencies of the Agency, competition and state aid. Twinning component is being implemented since April 2007 with Germany as a twinning partner. In the competition part, main emphasis is on the drafting of the amendments to the Competition Act, as well as new bylaws which will be needed as implementing legislation arising from the changed Competition Act. Trainings are being held for the CCA staff, judiciary (both at central and regional levels) and other stakeholders (business community, lawyers). In the state aid part of the project main activities are focused on on-the-job consultancy, primarily related to the most complex cases which are dealing with the issues arising from the SAA obligations and EU accession negotiation benchmarks. In both competition and state aid there have been two study visits to relevant German authorities. Implementation of the twinning is to be completed in February 2009.

Supply component of the project was completed in November 2008. The lots comprised the supply of hardware (IT equipment, IP telephony) and the creation of the document management system for the whole of the Agency, which is compatible with the CROSADS system previously created for the State Aid Sector of the Agency within the CARDS 2002 project.

Finally, also to be mentioned is CARDS 2004 project (within the Ministry of Economy, Labour and Entrepreneurship) titled “Information to the Croatian Business Community”. The project aims to strengthen the capacity for policy makers and business organisations to identify, analyse and communicate future impact of key regulatory areas for business in Croatia. The project also aims to generally improve the awareness of the business community in key legislative fields such as: public procurement, environment, standards for agriculture and industrial products, consumer protection, competition policy, state aid and intellectual property rights. The Agency is actively involved in the project.

3.3 Results:

The results to be achieved by the project are as follows.

- Capacity of CCA, judges and sectoral regulators strengthened

  - Improved capacity in handling anti-trust and state aid cases

- (indicator: at least 30 members of CCA staff trained on anti-trust and state aid during 21 month of the implementation of activities; strong enforcement record on substantial anti-trust and state aid cases)

  - Improved capacity of court system in handling competition cases

- (at least 20 relevant judges trained on anti-trust during 21 month of the implementation of activities; enforcement record of relevant court(s) strengthened through decisions on the legality of CCA’s decisions and on the fine reviews)

  - Improved capacity of relevant institutions in handling competition cases in telecom and banking sectors

- (at least 20 staff of relevant institutions trained on handling anti-trust cases in telecom and banking sectors during 21 month of the implementation of activities; quality decisions on anti-trust cases in relevant sectors, in which the application of relevant competition rules is ensured)

- It is expected that after 21 month of the implementation of activities relevant stakeholders (CCA, judiciary and sectoral regulators) will be trained so as to achieve sufficient level of capacity for efficient implementation of new competition regime and state aid law and policy.

3.4 Activities:

- Component 1 – Training of CCA

- Result of this component is the improved capacity in handling anti-trust and state aid cases. This result is to be achieved through the following activities:

  - Training of CCA staff in the institutions of European Communities and its Member    States:

  - one internship in European Commission with approximate duration of 3 months is planned for 2 CCA representatives (one person in charge of competition and one person in charge of state aid are foreseen to participate)

  - up to four study trips (“shadowing”) with planned duration of 2 weeks each, for 4 CCA representatives in selected Member State's institutions are envisaged

In this activity, twinning partner will during two years of the duration of the contract in cooperation with the representatives of the European Commission organize an internship for CCA representatives (one representative from state aid field and one representative from anti-trust field are foreseen to participate). Selection of CCA representatives will be done by DGCOMP, based on CVs proposed by the CCA. Preparatory activities should not consume more than a month.

Similarly, planned 2-week study trips will we organized in cooperation with relevant agency from an EU Member State for 1 CCA representative per study trip.  These study trips will take place twice in the first year of the project and twice in the second year, equally divided among anti-trust and state aid staff.

  - On-the-job training at CCA in anti-trust and state aid

  - consultancy on ongoing cases

In this activity, on-the-job training will be delivered for CCA staff, in anti-trust and state aid issues separately. This will include consulting case handlers, directors or Council members on ongoing cases selected by CCA. Where possible, emphasis should be put on comparison with the experience in similar cases in the twinning partner’s country. This consultancy shall be summarized in written document in sufficient detail so as to allow the CCA to use it later on (e.g. when deciding on a particular case in Council sessions). In order to facilitate this, draft materials, decisions or similar documents, needed to get an insight into a particular case, shall be ensured by the beneficiary institution.

Component 2 - Training of judges on anti-trust issues

- Result of this component is the improved capacity of court system in handling competition cases. This result is to be achieved through the following activity:

  - Holding of 12 seminars at Judicial Academy and 1 study trip to relevant EC institutions

During one year of the duration of the contract 12 seminars on competition issues will be delivered for judges, in cooperation with the Judicial Academy in Zagreb (project partner). It is expected that various experts cover different topics, as an introduction to competition law. Upon the completion of the course, selected judges will together with the representative of the twinning partner visit relevant EC institutions.

Component 3 - Training of relevant institutions on anti-trust in telecom and banking sectors

- Result of this component is the improved capacity of relevant institutions in handling competition cases in telecom and banking sectors. This result is to be achieved through the following activity:

  - Holding of 8 seminars in relevant institutions

- Here the twinning partner should ensure the participation of relevant experts who would cover four seminars on each of the two sectors. By the time the project will be implemented, it is expected that amendments to the telecom and credit-institutions laws will be brought, which would ensure the unique application of the Competition Act in all the sectors, telecom and banking being the only ones where this is not the case for the time being.

- In order to measure the success of the project activities, for the target groups (judges and sectoral regulators) a survey will be carried out to measure the knowledge of anti-trust and state aid, at the beginning and at the end of activities.

Two visibility events will be organized in the course of the implementation of the project; Kick-off meeting at the start of the implementation and the Final meeting at the end of the implementation of the project activities.

3.5 Means / Input from the MS Partner Administration:

3.5.1 Profile and tasks of the Project Leader

Profile of the Project Leader

Project leader shall be a senior official of the Member State responsible for managing the twinning project.

- university degree in law, economics or business/management;

- 5 years of working experience in the area of  Competition  policies (anti trust or state aid)

- background in drafting and implementing strategies, policies and regulations;

- knowledge of EU project rules and procedures;

- fluent written and spoken English.

Task of the Project Leader

● Overall management and coordination of the project in cooperation with RTA, RTA counterpart and Croatian Project Leader

● Coordination of MS experts’ work and availability

● Directing the implementation of the project in order to ensure that all planned activities and tasks will be leading towards the achievement of the projects results and the overall objectives

- Monitoring project implementation and proposing/undertaking corrective management actions if required;

●    Supporting study visits

●    Ensuring financial management, including budget monitoring and accounting

3.5.2 Profile and tasks of the Resident Twining Adviser

Profile of the Resident Twining Adviser

RTA shall be a senior official of the Member State, with the following profile:

- University degree in management, public/business administration, law or economics

- 5 years experience in the field of competition policy (anti trust)

- Sufficient understanding of the state aid policy field to be able to actively support the achievements of the project results

- Experience in  project management

- Excellent communication skills, with fluency in written and spoken English language, including excellent report-writing English language

- Computer literate

- Previous experience with EU twinning projects on competition would be an advantage

Tasks of the Resident Twining Adviser

- transfer of knowledge on the Competition and State Aid

- assisting in the on-the-job training through consultancy in the most complex cases in competition and state aid areas

- day-to-day management of the project in cooperation with the BC PL and RTA counterpart;

- coordination  of the work of STEs

- planning the project activities with the Agency’s PIU and holding regular meetings with the PIU in order to discuss current activities and possible problems;

- supporting the short-term experts in preparation of training activities in all three components, as well as the internship and study visits;

- networking with institutions relevant in this project in Croatia (Judicial Academy and the relevant court to be trained; The Croatian Post and Electronic Communications Agency (HAKOM); Croatian National Bank; state aid providers) and abroad (relevant MS institutions which will host the study trips, European Commission – DGCOMP);

Duration of the Resident Twinning Adviser secondment: 21 months

3.5.3 Profile and tasks of the short-term experts

Profile of the Short-term experts

- University-level degree in a relevant subject (law or economics) or equivalent work experience.

- 5 years relevant work experience including competition, legal drafting, institutional capacity building, public awareness matters

- Previous work experience with EU twinning projects on competition issues would be an advantage.

- Good interpersonal and communication skills, as well as the ability to work in a large team;

- Good command of written and spoken English.

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2

Tasks of the Short-term experts

- will be responsible, under the coordination of the Resident Twinning Adviser, for the activities not directly covered by the Resident Twinning Adviser. The main activities to be undertaken by the short-term experts are those described in detail under point 3.4.:

  - consulting case handlers, directors or Council members on ongoing cases selected by CCA in competition and state aid areas;

  - holding seminars for the relevant court in charge for competition cases;

  - holding seminars on competition in the sectors of telecom and banking.

- shall be involved in organising and providing training in the field of state aid and anti-trust law and policy, for specific sectors (e.g. restructuring aid, fiscal aid, regional aid) or specific staff (CCA, judges, other regulators), where they shall provide expertise on the implementation of legislation in the field of state aid and anti-trust.

4. Institutional framework

Croatian Competition Agency was established by a decision of the Croatian Parliament and became operational in 1997. Through Croatian Competition Act, the current one which has been harmonised with the EC acquis and applied since 2003, it is entrusted with dealing with the major areas of competitive restraints, namely, restrictive agreements and abuses of a dominant position and it is also responsible for merger control. Further, the Agency also has a competition advocacy role whereby it gives official opinions to the Croatian government on legislative proposals that raise competition issues. The Agency is also tasked with the enforcement of State aid in the Republic of Croatia.

The managing body of the Agency is the Competition Council. It consists of five members appointed by the Croatian Parliament, one of whom is appointed as president. The Council is appointed for a five-year term. Daily administrative and professional activities are undertaken by an expert team consisting of lawyers and economists. As of July 2008, the Agency counts 50 employees.

Organizational structure of the Agency is as follows:

COMPETITION COUNCIL

EXPERT STAFF

DIVISIONS

Competition

State aid

Legal system and economic analises

International Cooperation

| Name: | Function: |
| --- | --- |
| Nikola Popović | SPO Vice-president of the Council |
| Mladen Cerovac | Deputy SPO Member of the Council |
| Branimira Kovačević | Head of PIU Director of International Cooperation Division |
| Mirta Kapural | PIU member Head of Department in the International Cooperation Division |

The experience gained in the ten-year period, particularly in the part that has indicated the short backs and deficiencies of the existing system, induced the Agency to start adequate initiatives and propose solutions for which it considers will contribute to more efficient and effective enforcement of competition law and policy in the future. Namely, in the next period it will be necessary to change the parts of competition regime with the view to empowering the Agency to impose sanctions, to ensuring more efficient court review system and to creating a single competition regime in which the Competition Act would apply to all sectors. Namely, telecommunication sector partially and banking as a whole are regulated by separate rules. A number of issues of split jurisdiction encouraged the Agency to conclude cooperation agreements with all sector specific regulators.

Apart from legislative drafting and the everyday work on handling the cases, the activities of the Agency will also be linked to the negotiations for the accession of the Republic of Croatia to the EU, particularly in Chapter 8: Competition policy. In short, priorities of Agency’s work in the area of competition, defined in its Strategy Statement for the period 2007-2008 may be summarized as follows:

- enhancing effectiveness of the existing competition regime through necessary reforms of the legislative framework,

- efficient and effective enforcement and strengthening of the enforcement record, and

- strengthening of the administrative capacities through development and training to enable the handling of most serious cases of violation of competition rules.

The beneficiary institution will dedicate all necessary human and financial resources in order to guarantee an effective implementation of the respective project. In particular, the beneficiary institution will insure the availability of the following provisions:

- Adequately equipped office space for the RTA and the RTA assistant for the entire duration of their secondment (in particular a desk, a telephone line, PC with e-mail account and internet access, possibility to use fax & copy services).

- Adequate conditions for the STEs to perform their work while on mission to the BC.

- Training and conference venues as well as presentation equipment.

- Costs for travel by BC participants from their capitals to a MS or between MS (study visits).

- Its active involvement in preparation of the PIU and Steering Committee meetings and participation of its members on the same.

- The availability of the BC human resources (BC experts) during the implementation of the activities.

5. Budget

|  | Program Support |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Investment Support (I) | Institution Building (IB) | Total Program (=I+IB) | National Co-financing | IFI | TOTAL |
| Contract 1 Twinning |  | € 1 000 000 |  |  |  | € 1 000 000 |
| Total |  | € 1 000 000 |  |  |  | € 1 000 000 |

Interpretation costs will be reimbursed from the budget only for the purpose of workshops and seminars, up to 7% of the budget can be used for translations and interpretation purposes.

6. Implementation arrangements:

6.1 Implementing Agency responsible for tendering, contracting and accounting

Central Finance and Contracting Agency (CFCA)

Ulica grada Vukovara 284, object C

HR – 10000 Zagreb

Mrs. Marija Tufekčić, Director of the CFCA

Phone:+ 385 1 4591 245

Fax: +385 1 4591 075

E-mail: cfcu@mfin.hr

Twinning Administrative Office

Central Finance and Contracting Agency

Ulica grada Vukovara 284, object C

HR - 10000 Zagreb

Contact: Ms Štefica Belčić

Phone: +385 1 4591 060

Fax: + 385 1 4591 075

E-mail: twinning.cfcu@mfin.hr

6.2. Main counterpart in the BC

Senior Programme Officer

Mr Nikola Popović

Vice-president of the Competition Council

Croatian Competition Agency

Savska 41

HR - 10000 Zagreb

Phone: +3851 6176 448

Fax: +3851 6176 450

E-mail: nikola.popovic@aztn.hr

BC Project Leader

Ms. Branimira Kovačević

Director of the International Cooperation Division

Croatian Competition Agency

Savska 41

HR - 10000 Zagreb

Phone: +3851 6172 124

Fax: +3851 6176 450

E-mail: branimira.kovacevic@aztn.hr

RTA Counterpart

Ms. Mirta Kapural

Head of Department

Croatian Competition Agency

Savska 41

HR - 10000 Zagreb

Phone: +3851 6172 125

Fax: +3851 6176 450

E-mail: mirta.kapural@aztn.hr

6.3 Contracts:

## 1 Twinning contract is foreseen with an indicative amount of 1.000.000 EUR.

7. Implementation Schedule (indicative)

7.1 Launching of the call for proposals: 1 Q 2009 (indicative date)

7.2 Start of project activities: 1 Q 2010 (indicative date)

7.3 Project completion: 3 Q 2011 (indicative date)

7.4 Duration of implementation period: 24 months; 21 month for the implementation of the activities and 3 months for the starting up and closure of the Action.

8. Sustainability

The achievements of a twinning project (mandatory results) should be maintained as a permanent asset to the Beneficiary administration even after the end of the twinning project implementation. This presupposes inter alia that effective mechanisms are put in place by the Beneficiary administration to disseminate and consolidate the results of the project. All project materials (training materials and other) shall be kept by the beneficiary institution which will make it available to its existing and future staff. For this purpose, the document management system created under PHARE 2005 project shall be used.

9. Crosscutting issues

Equal Opportunity

Based on the fundamental principles of promoting equality and combating discrimination, participation in the project will be guaranteed on the basis of equal access regardless of sex, racial or ethnic origin, religion or belief, disability, age or sexual orientation.

10. Conditionality and sequencing

There is no conditionality to the project.

The sequencing of IPA activities is not predetermined.

ANNEXES TO THE TWINNING FICHE

1. Logical framework matrix in standard format

2. Detailed implementation chart

3. Contracting and Disbursement Schedule

4. Reference list of legislation

- ANNEX 1: Logical framework matrix in standard format

| IMPLEMENTING CROATIAN COMPETITION AND STATE AID POLICIES |  | Programme name and number # IPA 2007 |  |
| --- | --- | --- | --- |
| Croatian Competition Agency |  | Contracting period expires: 17.11.2010 | Disbursement period expires: 17.11.2013 |
|  |  | Total budget: € 1,000,000 | IPA budget: € 1,000,000 |
| Overall objective | Objectively Verifiable Indicators | Sources of Verification |  |
| Enhance the competition environment and state aid policy through continuous support to Croatian competition authorities and its partners on the basis of EC rules and best practices | Enforcement record of relevant competition and state aid legal framework | - Regular progress reports on Croatia - Enforcement record in the area of competition and state aid |  |
| - Project purpose | - Objectively Verifiable Indicators | - Sources of Verification | - Assumptions |
| Provide CCA and other stakeholders in competition and state aid systems with sufficient capacity for efficient implementation of competition and state aid policies | - Increased number of quality CCA decisions - Increased number and quality of relevant court decisions - Improved interaction with other stakeholders on competition and state aid cases | - CCA annual reports - Enforcement record in the area of anti-trust and state aid - Project reports - Court records | Good and continuous interaction between CCA and other stakeholders relevant for the enforcement of anti-trust and state aid rules |
| - Results | - Objectively Verifiable Indicators | - Sources of Verification | Assumptions |
| 1) Capacity of CCA, judges and sectoral regulators strengthened 1.1. Improved capacity in handling anti-trust and state aid cases 1.2. Improved capacity of court system in handling anti-trust cases 1.3. Improved capacity of relevant institutions in handling anti-trust cases in telecom and banking sectors | - At least 30 members of CCA staff trained on anti-trust and state aid; strong enforcement record on substantial anti-trust and state aid cases - At least 20 relevant judges trained on anti-trust; enforcement record of relevant court(s) strengthened through decisions on the legality of CCA’s decisions and on the fine reviews - At least 20 staff of relevant institutions trained on handling anti-trust cases in telecom and banking sectors; quality decisions on anti-trust cases in relevant sectors, in which the application of relevant competition rules is ensured | - CCA annual reports - CCA enforcement records - court records - enforcement records in the areas of telecom and banking | - Continuous exchange of information on anti-trust and state aid cases handled at relevant institutions - Keeping the level of CCA capacity in terms of budget and number of staff |
| Activities | Means | Specification of costs | Assumptions |
| - Component 1 – Training of CCA 1.1. Training of CCA staff in the institutions of European Communities and its Member States 1.2. On-the-job training at CCA in anti-trust and state aid Component 2 - Training of judges on anti-trust issues 2.1. Holding of 12 seminars at Judicial Academy and 1 study trip to relevant EC institutions Component 3 - Training of relevant institutions on anti-trust in telecom and banking sectors 3.1. Holding of 8 seminars in relevant institutions | Internship in European Commission Study visits Consultancy on ongoing cases Holding seminars at Judicial Academy Study visit Holding seminars | - Contract 1 (Twinning) € 1,000,000 | - successful implementation and completion of PHARE twinning and supply projects - IPA project to build upon the results of past CARDS and PHARE projects - Adequate number of CCA staff and their dedication in handling the workload emerged from the future tasks of the mentioned project, due to the need for qualitative processing of other regular and on going CCA activities |

ANNEX 2 – DETAILED IMPLEMENTATION CHART

| IMPLEMENTING CROATIAN COMPETITION AND STATE AID POLICIES | 2009 |  |  |  |  |  |  |  |  |  |  | 2010 |  |  |  |  |  |  |  |  |  |  |  |  | 2011 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | F | M | A | M | J | J | A | S | O | N | D |  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D |
| Twinning | T | T | T | T | C | C | C | C | C | C | S |  | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | R | R |  |

T- Call for proposals and evaluation

C- Contracting

S- Starting up

I- Implementation of activities

R- Report

ANNEX 3 – CONTRACTING AND DISBURSEMENT SCHEDULE

BY QUARTER FOR FULL DURATION OF PROGRAMME (INCLUDING DISBURSEMENT PERIOD)

| Implementing Croatian competition and state aid policies | Cumulative contracting schedule by quarters in EUR (provisional) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2009 |  |  |  | 2010 |  |  |  |
|  | I | II | III | IV | I | II | III | IV |
| Twinning – Contract 1 |  |  |  | 1.000.000 |  |  |  |  |
| TOTAL (EUR): |  |  |  |  |  |  |  |  |

| Implementing Croatian competition and state aid policies | Cumulative disbursement schedule by quarters in EUR (provisional) |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2009 |  |  |  | 2010 |  |  |  | 2011 |  |  |  |
|  | I | II | III | IV | I | II | III | IV | I | II | III | IV |
| Twinning – Contract 1 |  |  |  |  | 457.144 |  |  | 221.428 |  |  | 221.428 | 100.000 |
| TOTAL (EUR): |  |  |  |  | 457.144 |  |  | 678.572 |  |  | 900.000 | 1.000. 000 |

- ANNEX 4 -	Reference list of legislation:

- Reference list of relevant laws and regulations (for the texts see www.aztn.hr)

Anti-trust:

Competition Act, (Official Gazette No. 122/03)

Regulation on Notification and Assessment of Concentrations, (Official Gazette No. 51/2004)

Regulation on the Definition of Relevant Market, (Official Gazette No. 51/2004)

Regulation on Agreements of Minor Importance, (Official Gazette No. 51/2004)

Regulation on Block Exemption Granted to Certain Categories of Vertical Agreements, (Official Gazette No. 51/2004)

Regulation on Block Exemption Granted to Certain Categories of Horizontal Agreements, (Official Gazette No. 158/2004)

Regulation on Block Exemption Granted to Agreements on Distribution and Servicing of Motor Vehicles , (Official Gazette No.105/2004)

Regulation on Block Exemption Granted to Certain Categories of Technology Transfer Agreements, (Official Gazette No. 2/2005)

Regulation on Block Exemption Granted to Insurance Agreements. (Official Gazette No. 54/2005)

State Aid:

State Aid Act (Official Gazette No. 140/2005)

Regulation on State Aid (Official Gazette No. 50/2006)

- Reference to SAA

Article 69

1. The Parties recognise the importance of the approximation of Croatia's existing legislation to that of the Community. Croatia shall endeavour to ensure that its existing laws and future legislation will be gradually made compatible with the Community acquis.

2. This approximation will start on the date of signing of the Agreement, and will gradually extend to all the elements of the Community acquis referred to in this Agreement by the end of the period defined in article 5 of this Agreement. In particular, at an early stage, it will focus on fundamental elements of the Internal Market acquis as well as on other trade-related areas, on the basis of a programme to be agreed between the Commission of the European Communities and Croatia. Croatia will also define, in agreement with the Commission of the European Communities, the modalities for the monitoring of the implementation of approximation of legislation and law enforcement actions to be taken.

Article 70

Competition and other economic provisions

1. The following are incompatible with the proper functioning of the Agreement, in so far as they may affect trade between the Community and Croatia:

(i) all agreements between undertakings, decisions by associations of undertakings and concerted practices between undertakings which have as their object or effect the prevention, restriction or distortion of competition;

(ii) abuse by one or more undertakings of a dominant position in the territories of the Community or of Croatia as a whole or in a substantial part thereof;

(iii) any State aid which distorts or threatens to distort competition by favouring certain undertakings or certain products.

2. Any practices contrary to this Article shall be assessed on the basis of criteria arising from the application of the competition rules applicable in the Community, in particular from Articles 81, 82, 86 and 87 of the Treaty establishing the European Community and interpretative instruments adopted by the Community institutions.

3. The Parties shall ensure that an operationally independent public body is entrusted with the powers necessary for the full application of paragraph 1 (i) and (ii) of this article, regarding private and public undertakings and undertakings to which special rights have been granted.

4. Croatia shall establish an operationally independent authority which is entrusted with the powers necessary for the full application of paragraph 1 (iii) of this Article within one year from the date of entry into force of this Agreement. This authority shall have, inter alia, the powers to authorise State aid schemes and individual aid grants in conformity with paragraph 2 of this Article, as well as the powers to order the recovery of State aid that has been unlawfully granted.

5. Each Party shall ensure transparency in the area of State aid, inter alia by providing to the other Party a regular annual report, or equivalent, following the methodology and the presentation of the Community survey on State aid. Upon request by one Party, the other Party shall provide information on particular individual cases of public aid.

6. Croatia shall establish a comprehensive inventory of aid schemes instituted before the establishment of the authority referred to in paragraph 4 and shall align such aid schemes with the criteria referred to in paragraph 2 of this Article within a period of no more than four years from the entry into force of this Agreement.

7. (a) For the purposes of applying the provisions of paragraph 1(iii), the Parties recognise that during the first four years after the entry into force of this Agreement, any public aid granted by Croatia shall be assessed taking into account the fact that Croatia shall be regarded as an area identical to those areas of the Community described in Article 87(3)(a) of the Treaty establishing the European Community.

(b) Within three years form the entry into force of this Agreement, Croatia shall submit to the Commission of the European Communities its GDP per capita figures harmonised at NUTS II level. The authority referred to in paragraph 4 and the Commission of the European Communities shall then jointly evaluate the eligibility of the regions of Croatia as well as the maximum aid intensities in relation thereto in order to draw up the regional aid map on the basis of the relevant Community guidelines.

8. With regard to products referred to in Chapters II of Title IV:

- paragraph 1 (iii) shall not apply;

- any practices contrary to paragraph 1(i) shall be assessed according to the criteria established by the Community on the basis of Articles 36 and 37 of the Treaty establishing the European Community and specific Community instruments adopted on this basis.

9. If one of the Parties considers that a particular practice is incompatible with the terms of paragraph 1 of this Article, it may take appropriate measures after consultation within the Stabilisation and Association Council or after thirty working days following referral for such consultation.

Nothing in this Article shall prejudice or affect in any way the taking, by either Party, of antidumping or countervailing measures in accordance with the relevant Articles of GATT 1994 and WTO Agreement on Subsidies and Countervailing Measures or related internal legislation.