ANNEX C113

STANDARD TWINNING PROJECT FICHE

1. Basic Information

1.1 Programme:		IPA 2007

1.2 Twinning Number:	BA 07 IB TR 01

1.3 Title:	Assistance to the Ministry of Communications and Transport of Bosnia and Herzegovina (MoCT) concerning implementation of projects under the Instrument for Pre-Accession Assistance (IPA) Regulation

1.4 Sector:			Transport

1.5 Beneficiary country:	Bosnia and Herzegovina

2. Objectives

2.1 Overall Objective(s):

All agencies and institutions required for development, implementation and enforcement of policies related to the transport sector established and able to fulfil their mandates.

2.2 Project purpose:

The Ministry of Communications and Transport (MoCT) able to fulfil its mandate under the future Instrument for Pre-accession Assistance Regulation (CR EC No. 1085/2006), as well within the decentralised EC aid delivery environment.

2.3 Contribution to National Development Plan/Cooperation agreement/Association Agreement/Action Plan

In accordance with the requirements of:

- EP , Point 3.2, Medium-Term Priorities, Political Requirement:

- Governance: Ensure continued progress in taking full national responsibility for policy formulation and decision-making;

- Public Administration: Build training Capacity for civil servants within Bosnia and Herzegovina and continue improving policy-making and coordination capacities.

- SAA: 	Public administration reform.

- Council Regulation (EC) No 1085/2006 establishing an Instrument for Pre-accession Assistance (IPA) Regulation.

3. Description

3.1 Background and justification:

Ministry of Communications and Transport of B&H has successfully implemented a number of large scale projects funded by the World Bank (Project of Trade and Transport Facilitation in South East Europe and Project of Emergency Transport Reconstruction), and the European Union (Phare project Orasje border crossing point, etc.). The MoCT has actively cooperated with the Delegation of European Commission to BiH in implementation of transport sector components of OBNOVA and CARDS programmes, and currently is involved in programming of IPA components for transport sector. The MoCT is an active participant in management of preparatory activities to ensure improved transport services along the Pan-European Transport Corridor V-c.

However, no reliable independent assessments on appropriateness of the structure of the Ministry to meet demands of the forthcoming IPA programme, nor for taking its leading role under the future de-centralised setup of the EC aid delivery under the IPA Regulation (CR (EC) No 1085/2006, has been performed so far.

Having in mind the high scale of investment related to projects in transport sector (projects over 10 MEUR, in accordance to IPA Regulation), in particular for those considered a top priority country agenda, concern is raised that without benefiting from an immediate assistance from the Commission restructuring of the Ministry and training of its staff may be too late to meet the requirements of de-centralised aid delivery process, where the Ministry would be in a position to programme their activities, prioritise them, procure and implement the interventions, under the close monitoring of the Commission's services.. In practical terms, late transformation of the implementation services of the Ministry and lack of familiarity with EC procurement procedures and implementation rules promoted under the IPA Regulation are likely to cause delays and subsequently risk substantial loss of IPA funds. In turn there could be a risk that  transport sector in BiH, which is in need of substantial and costly interventions in order to be brought closer to EU standards, may not receive the investments that are required and to which BiH should be entitled under IPA. Furthermore, the impact of efforts already made by the EC and other donors and creditors would be significantly reduced. Lastly, BiH would not be able to meet obligations concerning the Trans-European networks and Pan-European Corridors, regional connecting priorities (defined inter allia through REBIS and SEETO Core Networks), and regional interconnecting and interoperability priority actions subject to bilateral and multilateral regional and EU initiatives and agreements.

BiH requires assistance to enable the Ministry to take an active role in IPA programming and implementation. This kind of assistance would also enable a gradual takeover of responsibilities by MoCT with the ultimate goal of establishing a decentralised implementation environment for the transport sector a twinning project would provide limited input from experienced Member State officials from the EU national authorities and is the preferred option for providing this assistance to BiH. At least 12 EU countries recently passed this process at some stage of their accession process. Assistance of the EU sectoral officials would enable on-the-job daily participation of the staff employed with the Ministry in implementation of the IPA programme, to enable not only training for the employees, but also positive and best-practice experience on real projects in progress.

It is foreseen that the twinners shall assist the Ministry for the period of at least 18 continuous calendar months (18 for implementation + 3 for administrative issues). The cost of this assistance shall not exceed the amount of 700,000 Euro. They will in particular assist in mapping the structure of its existing services in order to identify structural gaps in its present organisation and staffing that might prevent the Ministry from delivering an adequate performance as the implementation environment changes to the new decentralised EC aid system. Based on a gap analysis, a functional operating structure in line with IPA Regulation needs to be designed and proposed for adoption, in order to enable implementation of the IPA Regulation, specifically its Articles 28 and 31. It may be expected that the changed setup might require amendment of laws and regulations. This assistance should therefore enable identification and drafting of any required amendments.

Based on the proposed revised organisational scheme, detailed job descriptions will need to be drafted. Following the adoption of the job descriptions and recruitment of new staff, staff will require training. Project Cycle Management and the procedures regulated by the IPA Regulation will be particularly important to enable them to take over the full responsibility for their performance in the new de-centralised operating environment, and to comply to the IPA procedures required by the Commission.

Upon adoption of the Country Transport Strategy document, expected in 2008, the transformed services of the Ministry would require on-the-job training in development and maintenance of the strategic coherence framework to be established by BiH, in accordance with Article 154 of IPA Regulation. Improved capacity of the Ministry in strategic planning should result in establishment of flexible and effective strategic guidelines for the sector in mid to long-term prospective. This is considered of high importance, for prioritisation of projects to be foreseen for implementation under the Chapter III of IPA.

Training on how to create and decide on relevant prioritisation criteria, and how to apply the criteria and prioritise actions within the strategic coherence framework of interventions in the sector would be highly relevant for the future performance of the operational services of the Ministry in the framework of the IPA implementation, in particular its Chapter III.

It is expected that the Ministry would have to substantially increase its contribution in programming and implementation of the IPA assistance almost immediately. Its responsibility for the aid delivery under the IPA shall be further increased with the availability of Chapter III of IPA to the  BiH authorities, expected  at the end of this particular assignment: end of 2009-beginning of 2010. At the same time, de-centralisation of the aid delivery should be achieved, and the complexity and the major scale of the projects to be managed by the Ministry would require its full compliance with the structural setup required by IPA Regulation, and an excellent knowledge of the regulations to be applied.

All the outputs from this assignment shall be made for the Ministry in one of the local languages, Latin letters, in at least 10 hard and electronic copies (CDs). Therefore, the twinners shall have to foresee translation and quality binding services for the outputs (benchmarks and reports). Translation services need to be foreseen to maintain the dialog with civil servants not directly involved who might not have command of English.

The project shall be steered by the steering committee. The steering committee shall include representatives of the twinning team, the MoCT of BiH, the Entity Ministries of Transport and Communication and the EC.

This project should enable better efficiency and responsiveness of the services of the Ministry concerning implementation of the high-scale projects in transport sector supported by the EC under IPA Chapter III. In particular, attention needs to be paid to the performance of the services of the Ministry in a de-centralised implementation environment. The Ministry would benefit from establishment of an administrative capacity (i.e. operational structure) to support institutional decision making, which is capable of negotiating strategic issues and prioritising at regional level. At present the tendency is rather towards individual-related actions. This improved mechanism would directly strengthen regional cooperation through functional structures such as the SEETO and the Sava River Commission.

Since the accession prospective for BiH is unlikely to be  imminent, it should be expected that restructuring of the Ministry and training of its employees, including on–the-job training on smaller-scale projects, would be completed prior to de-centralisation of the EC aid deliver, thus enabling access to IPA Chapter III assistance.

Stable and continuing financing of the Ministry is assured through state budget allocations.

3.2 Linked activities (other international and national initiatives):

The Twinning project for Ministry of Communications and Transport of B&H related to the European Integrations and harmonization with Transport Acquis was implemented under CARDS 2004, to check compliance with BiH legislation in transport sector with the Acquis and recommend further actions. Under CARDS 2005, training is being provided to the Ministry of Communications and Transport of B&H in preparation of Terms of Reference to increase their capacity and enable their response and improve their capacity for participation in EC programmes.

Also referring to:

- EP , Point 3.2, Medium-Term Priorities, Political Requirement:

- Developing institution and capacity of relevant authorities in transport sector to align with the Acquis. Please also refer to:

http://ec.europa.eu/regional_policy/funds/ipa/index_en.htm .

- PRSP-V.8.Sector Priorities: Infrastructure, Goals:

- Create a legislative and institutional basis in BiH that is compatible with the European regulations

- Generate broader economic development through the implementation of concrete projects in transport sector in Bosnia and Herzegovina

- Ensure the cost-effective transport, reduction in number of traffic accident and reduction of negative effects on environment in compliance with the national and European norms

3.3 Results:

R 1.: 	Ministry of Communications and Transport of Bosnia and Herzegovina made progress towards taking its full responsibility for implementation of high-scale  projects in transport sector under de-centralised management.

(Recommended structures in place and staff recruited, deliverables produced: in priority setting, overall strategies, financial planning, and drafting of project fiches and terms of reference)

R 2.: 	Ministry of Communications and Transport of Bosnia and Herzegovina able to plan, manage and implement assistance financed under the IPA Regulation.

(Training (benchmark) successfully completed, possibly pilot project implemented)

R 3.:	Ministry of Communications and Transport of Bosnia and Herzegovina able to develop a strategic coherence framework (Art. 154 IPA Regulation) as required for component III of IPA.

(Training (benchmark) successfully completed, pilot framework delivered)

3.4 Activities:

R 1.:

A 1.1:	Mapping of the existing structure and staffing in the Ministry allocated to project implementation, IPA Regulation requirements and EC best practices.

A 1.2:	Identification of deficiencies and gaps in the Ministry.

A 1.3:	Drafting proposal for restructuring of the Ministry.

A 1.4:	Drafting job descriptions and job-holder profiles for proposed positions.

A 1.5:	Training in Project Cycle Management.

A 1.6:	Training in drafting of project fiches.

A 1.7.	Training in drafting of terms of reference.

R 2.:

A 2.1:	Training in strategic planning.

A 2.2:	Training in strategic coherence framework preparation.

A 2.3:	Training in prioritisation of activities and action planning.

R 3.:

A 3.1:	General training on principles of the EC procurement procedures.

A 3.2:	Training in application of IPA Regulation.

3.5 Means/Input from the MS Partner Administration:

3.5.1 Profile and tasks of the Team Leader

- The MSTL shall have a university degree and be able to demonstrate a minimum of 10 years general professional experience as civil servant. Experience in management of twinning projects, or technical assistance projects in excess of 1.0Meur, is considered a mandatory requirement .The member state team leader (MSTL) shall coordinate inputs of individual experts and retain overall accountability for the project.

- The BSTL shall have a university degree. The BSTL shall be experienced (min. 5 years general professional experience) civil servant, able to demonstrate experience in management of complex projects. Participation in twinning projects in the past would be considered an asset. The beneficiary state team leader (BSTL) shall coordinate inputs of local civil servants.

3.5.2 Profile and tasks of the RTA

- The RTA shall have a university degree and demonstrate at least 10 years of experience in management of implementation of high scale projects. The RTA shall be able to demonstrate familiarity with IPA regulation and experience in implementation of the transport sector infrastructure projects. Command of the one of local languages would be considered an asset. The resident twinning advisor (RTA) shall coordinate provision of implementation activities and assure quality of the outputs (benchmarks). The RTA shall be present in the beneficiary country throughout the whole duration of the project, except for the possible occasional short term absence due to professional or private reasons.

3.5.3 Profile and tasks of the short-term experts

- The short term experts shall have university degree in the relevant field of expertise and a minimum of 5 years experience in the relevant national body/ies. The short term experts shall be responsible for specific IPA Regulation related benchmarks to be considered under the twinning assistance: establishment of the functional scheme and the org chart, drafting regulations, drafting specific job descriptions, delivery of specific trainings and assistance in recruitment of staff, respectively.

4. Institutional Framework

Beneficiary institution:

Ministry of Communications and Transport of Bosnia and Herzegovina (MoCT),

Project Preparation and Implementation Unit (PIU);

Kemal Karkin, Senior Programme Officer (SPO)

Trg B&H 1, 71000 Sarajevo;

tel: ++387 33 269 470;

e-mail: k.karkin@mkt.gov.ba

5. Budget:

700,000 EURO

6. Implementation Arrangements

6.1 Implementing Agency responsible for tendering, contracting and accounting:

Delegation of the European Commission to Bosnia and Herzegovina

Mr. Goran Filipovic, Task Manager (TM)

Skenderija 3-a, 71000 Sarajevo

Bosnia and Herzegovina

tel: 		++387 33 254 778

e-mail: 	goran.filipovic@ec.europa.eu

6.2 Main counterpart in the BC:

Ministry of Communications and Transport of Bosnia and Herzegovina (MoCT),

Project Preparation and Implementation Unit (PIU);

Mr. Kemal Karkin, Senior Programme Officer (SPO)

Trg B&H 1, 71000 Sarajevo;

Bosnia and Herzegovina

tel: 		++387 33 269 470;

e-mail:		 k.karkin@mkt.gov.ba

RTA counterpart / BC Project leader: 	to be appointed

6.3 Contracts

Twinning contract, EORO 700,000, 18+3 months

7. Implementation Schedule (indicative)

7.1 Launching of the call for proposals (Date):			Q1 2009

7.2 Start of project activities (Date):					Q3 2009

7.3 Project completion (Date): 					Q3 2011

7.4 Duration of the implementation period (number of months):	18 for implementation + 3 for administrative issues

8. Sustainability

This project should enable better efficiency and responsiveness of the services of the Ministry concerning implementation of the high-scale projects in transport sector supported by the EC under IPA Chapter III. In particular, attention needs to be paid to the performance of the services of the Ministry in a de-centralised implementation environment. The Ministry would benefit from establishment of an administrative capacity (i.e. operational structure) to support institutional decision making, which is capable of negotiating strategic issues and prioritising at regional level. At present the tendency is rather towards individual-related actions. This improved mechanism would directly strengthen regional cooperation through functional structures such as the SEETO and the Sava River Commission.

Since the accession prospective for BiH is unlikely to be  imminent, it should be expected that restructuring of the Ministry and training of its employees, including on–the-job training on smaller-scale projects, would be completed prior to de-centralisation of the EC aid deliver, thus enabling access to IPA Chapter III assistance.

Stable and continuing financing of the Ministry is assured through state budget allocations.

9. Crosscutting issues (equal opportunity, environment, etc…)

- Equal Opportunity :

Ministry of Communications and Transport of BiH is an equal opportunity employer .The general employment policy in the Ministry requires adequate presence of all national and gender groups. The main criteria for recruitment will be qualifications and experience in similar projects, not sex, religion or age. Both men and woman will have equal opportunities and salaries.

- Environment : 	n/a

- Minorities :

Ministry of Communications and Transport of BiH is an equal opportunity employer enabling full participation of minorities based on presentation of the individual skills and expertise.

10. Conditionality and sequencing

The Council of Ministers of BiH has to approve changes in the Rule Book on internal organisation of the Ministry of Communications and Transport related to the possible need for restructuring of administration (i.e. implementing bodies).

ANNEXES TO PROJECT FICHE

- Logical framework matrix in standard format (compulsory)

- Detailed implementation chart (optional) – not applicable

- Contracting and disbursement schedule by quarter for full duration of programme (including

- Disbursement period) (optional) – not applicable

- Reference to feasibility /pre-feasibility studies. For all investment projects, the executive summary of the economic and financial appraisals, and the environmental impact assessment should be attached (optional) – not applicable

- List of relevant Laws and Regulations (optional)

- Reference to relevant Government Strategic plans and studies (may include Institution Development Plan, Business plans, Sector studies etc) (optional).

## ANNEX I: Logical framework matrix in standard format

| LOGFRAME PLANNING MATRIX FOR Project Fiche | Programme name and number: Technical assistance to the Ministry of Communications and Transport of Bosnia and Herzegovina (MoCT) concerning implementation of projects under the Instrument for Pre-accession Assistance (IPA) Regulation |  |  |
| --- | --- | --- | --- |
|  | Contracting period expires 31/12/2011 |  | Disbursement period expires 31/12/2014 |
|  |  | Total budget : 700,000 EUR | IPA budget: 700,000 EUR |

| Overall objective | Objectively verifiable indicators | Sources of Verification |  |
| --- | --- | --- | --- |
| MIPD aim defined in European standards –supporting the establishment and capacity building of agencies and institutions | Positive progress reported in the Country Review | - EC Report - Country Report |  |
| - Project purpose | - Objectively verifiable indicators | - Sources of Verification | - Assumptions |
| MoCT able to fulfil its mandate under the future Instrument for Pre-accession Assistance Regulation (CR EC No. 1085/2006), as well within the decentralised EC aid delivery environment | Operational services of the MoCT adequately transformed, structured and ready for to perform in accordance with IPA Regulation | - Org Chart - Rule book - Job Description - Training reports - Interim project progress reports |  |
| - Results | - Objectively verifiable indicators | - Sources of Verification | Assumptions |
| R 1.: Ministry of Communications and Transport of Bosnia and Herzegovina made progress towards taking its full responsibility for implementation of high-scale projects in transport sector under de-centralised management. R 2.: Ministry of Communications and Transport of Bosnia and Herzegovina able to plan, manage and implement assistance financed under the IPA Regulation. R 3.: Ministry of Communication and Transport of Bosnia and Herzegovina able to develop a strategic coherence framework (Art. 154 IPA Regulation) as required fro component III of IPA | - Recommended structures in place - Staff recruited, - Deliverables produced in priority setting, overall strategies, financial planning, - Drafted project fiches and - Drafted terms of reference - Training (benchmark) successfully completed, possibly pilot project implemented - Training (benchmark) successfully completed, pilot framework delivered - Strategic coherence framework in place in accordance with the country strategy and SEETO guidelines. - Quality standards and performance indicators prepared. - Prioritisation of the high priority actions developed in accordance with the strategic coherence framework. - Training Plan completed according to the Benchmarks. | - Project progress report |  |
| Activities | Means | Costs | Assumptions |
| R 1.: A 1.1: Mapping of the existing structure and staffing in the Ministry allocated to project implementation, IPA Regulation requirements and EC best practices. A 1.2: Identification of deficiencies and gaps in the Ministry. A 1.3: Drafting proposal for restructuring of the Ministry. A 1.4: Drafting job descriptions for proposed positions. A 1.5: Training in Project Cycle Management. A 1.6: Training in drafting of project fiches. A 1.7. Training in drafting of terms of reference. R 2.: A 2.1: Training in strategic planning. A 2.2: Training in financial planning. A 2.3: Training in strategic coherence framework preparation. A 2.4: Training in prioritisation of activities and action planning. R 3.: A 3.1: General training on principles of the EC procurement procedures. A 3.2: Training in application of IPA Regulation. | Technical assistance for MoCT in transformation and transition towards performance in project management and implementation under the IPA Regulation | € 700.000 |  |
|  |  | Pre-conditions |  |

- ANNEX III:	amounts (in €) Contracted and disbursed by quarter for the project

| Contracted | 2nd Quarter 2009 | 3rd Quarter 2009 | 4th Quarter 2009 | 1st Quarter 2010 | 2nd Quarter 2010 | 3rd Quarter 2010 | 4th Quarter 2010 | 1st Quarter 2011 | 2nd Quarter 2011 | 3rd Quarter 2011 | 4th Quarter 2011 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Twinning Contract 1.1 |  | 0.7 M |  |  |  |  |  |  |  |  |  |
| Total |  | 0.7 M |  |  |  |  |  |  |  |  |  |
| Cumulated |  | 0.7 M |  |  |  |  |  |  |  |  |  |
| Disbursed | 2nd Quarter 2009 | 3rd Quarter 2009 | 4th Quarter 2009 | 1st Quarter 2010 | 2nd Quarter 2010 | 3rd Quarter 2010 | 4th Quarter 2010 | 1st Quarter 2011 | 2nd Quarter 2011 | 3rd Quarter 2011 | 4th Quarter 2011 |
| Twinning Contract 1.1 | 0 | 0 | 0.38 M | 0 | 0 | 0.15 M | 0 | 0.10 M | 0 | 0 | 0.07 M |
| Total | 0 | 0 | 0.38 M | 0 | 0 | 0.15 M | 0 | 0.10 M | 0 | 0 | 0.07 M |
| Cumulated | 0 | 0 | 0.38 M | 0 | 0 | 0.53 M | 0 | 0.63 M | 0 | 0 | 0.70 M |

ANNEX VI:	Reference to laws, regulations and strategic documents:

Reference list of relevant laws and regulations:

- Law on ministries of B&H

- Law on Council of Ministers of BiH

- Rule Book of the Ministry of Communications and Transport of BiH

ANNEX VII:	Reference to strategic documents:

Reference to AP /NPAA / EP / SAA:

      - Council Regulation (EC) No 1085/2006: Instrument for Pre-accession Assistance (IPA) Regulation

      - Public Administration Reform, restructuring and strengthening of the state level institutions.

Reference to MIPD:

- European Standards (chapter 2.2.3.3.MIPD 2007-2009)

Reference to National Development Plan:

- Country transport strategy is under preparation.

Reference to national / sectoral investment plans:

      - Reconstruction of the railway network, EBRD/EIB loan funded, cca. 160 MEUR

      - Reconstruction of the railway network, Kuwait Fund, and OPEC Fund, cca. 30 MEUR

      - Construction of the motorway along the V-c Pan-European Corridor, partly to be consessioned (predominantly BOT model), total cost 3.1 BEUR.

      - Revitalisation of the Sava River navigation route, including the respective river ports, total cost cca. 50 MEUR.