Twinning project fiche

MD/13/ENP/TR/14

Strengthening of the standards and metrology sector according to the best practice in the EU Member States

List of acronyms

AP – Action Plan

BC – Beneficiary country

CEN - the European Committee for Standardization

CENELEC – European Committee for Electro technical Standardisation

CIPM MRA - the Arrangement on Mutual recognition of national measurement standards and of calibration and measurement certificates issued by national metrology institutes of the International Committee of weights and measures

COOMET - Euro-Asian Co-operation of governmental metrology institutions

DCFTA - Deep and Comprehensive Free Trade Agreement

ENP - European Neighbourhood Policy

GCPM - General Conference on Weights and Measures

ISO – International Organisation for Standardisation

NIS – National Institute of Standard

NIM – National Institute of Metrology

MoE – Ministry of Economy

CAMC – Centre for Applied Metrology and Certification

PCA – Partnership and Co-operation Agreement

PL – Project Leader

RTA – Residential Twinning Adviser

STE – short term expert

TBT – Technical Barriers to Trade

WELMEC – European Cooperation in Legal Metrology

WTO – World Trade Organisation

Twinning Project Fiche

1. Basic Information

1.1. Programme: ENPI 2011 (CRIS ENPI 2011/022-679)

1.2. Twinning number: MD/13/ENP/TR/14

1.3. Title: Strengthening of the standards and metrology sector according to the best practice in the EU Member States.

1.4. Sector: Trade and Industry

1.5 Beneficiary country: Moldova (Ministry of Economy, National Institute of Standardization and National Institute of Metrology).

2. Objectives

2.1 Overall Objective

To implement best practices in the sector with the aim of preparation for international agreements on the free movement of goods (DCFTA).

2.2 Project Purpose

To upgrade standards and metrology sectors in Moldova according to the best practices of the EU Member States.

2.3 Contribution to the Partnership and Cooperation Agreement and ENP Action Plan

Article 50 of the EU-Moldova Partnership and Cooperation Agreement (PCA) as signed in 1994 and entered into force on 1998 promotes cooperation between the contracting parties in the sectors of standardization and conformity assessment among others.

In the framework of the European Neighbourhood Plan, an Action Plan has been adopted for Moldova in November 2006. The Twinning Project will be particularly relevant for Chapter 2.4 of the Action Plan “Trade - related issues, market and regulatory reforms” and its section on “Standards, technical regulation and conformity assessment procedures (EU harmonised areas)”.

This Twinning project should contribute favourably to the above Action Plan priority actions and objectives through specific and measurable results. The project aims at building upon previous technical assistance activities. Through the support of well-established Member State Institutions, National Institute of Standardization (NIS) and National Institute of Metrology (NIM) will, inter alia, be able: 1. to perform as modern and effective institutions in standardisation and metrology; 2. participate in international work of international and regional standardisation and metrology organisations; 3. provide for necessary platform in setting up institutional capacities in conformity assessment field; and 4. improve business environment in Moldova strengthening export capacities.

The alignment of the Technical regulations and Quality Infrastructure with that of the EU is key component in the implementation of the forthcoming Deep and Comprehensive Free Trade Agreement.

The DCFTA, in particular, de facto aims at including Moldova into the European economic space. This treaty therefore opens great opportunities for Moldova, for both the market access it provides and the deep structural reforms it requires and favours. At the same time, as the removal of barriers to trade with the EU is reciprocal, the DCFTA poses challenges to the Moldovan economy, especially in the short to medium term. Improving the quality infrastructure is crucial both to make full use of the opportunities opened by the DCFTA, and to face the challenges it brings.

3. Description

3.1 Background and justification

Area of Technical Barriers to Trade (TBTs) has been considered as one of the key priorities in the preparatory process for future negotiations of DCFTA between the EU and Moldova. To the overall EC assessment, Moldova has also made progress in the implementation of the PCA and ENP AP objectives of establishment of a legislative and institutional framework in the TBTs areas compatible with the EU and international standards, but standards, informal restrictions on trade remain as areas of concern.

Essential and substantive amendments were made in relevant laws on Technical Regulations, Metrology, Standardisation, Accreditation and Conformity assessment regulating the systems of technical regulation for transition period considering further revision thereof in line with international practice. The legislative reform introduced a number of innovations in line with international practice: transition from mandatory standardization system to voluntary one; introduction of a concept of technical regulations, i.e. all Moldovan standards are voluntary.

According to the Law on Metrology, which is based on OIML D 1 document, the Central Metrology Authority and regulatory body in the field is the Ministry of Economy.

In order to improve the public property administration in line with principle of efficiency and transparency, as well as the need to implement the provisions of the Law nr.590-XIII dated 22.091995 on standardization, Law on metrology nr. 647-XVI dated 17.11.1995, and the Government Decision nr. 859 dated 31.07.2006 on the approval on quality infrastructure concept in the Republic of Moldova, the WTO commitments and European Commission recommendations, in 2013 the National Institute for Standardisation and Metrology was reorganised, being created two separate public bodies – National Institute for Standardisation and National Institute for Metrology (Government Decision nr. 996 of 27.12.2012).

NIM is in charge of general and legal metrology ranging from development and maintenance of state measurements standards and reference materials, to maintenance of the register of types of legal measuring instruments, to calibration and approval of the measuring instruments.

NIS is in charge of development and adoption of original Moldovan standards, as well as adoption of international and European standards as national standards

On international scale, NIM is a member of International standardisation organisation (ISO), an affiliate member of the European Committee for Standardization (CEN), an associate member of International Electro-technical Commission (IEC), a member of EuroAsian Interstate Council for standardisation, metrology, and certification (EASC). However, Republic of Moldova is associated member of the Meter Convention. NIM is a member of Euro-Asian Co-operation of governmental metrology institutions (COOMET). Moldova has implemented the code of good practice for the preparation, adoption and application of standards (Annex 3 of WTO TBT).

To date, although good progresses has been made in the approximation of vertical regulation and the structuring of institutions, this has not been matched with the alignment of details within legal framework and the development of the institutions that will enable the system of regulation to be implemented. The need for closer alignment of horizontal regulation is more urgent than the need for further vertical regulation.

The Ministry of Economy along with the former National Institute for Metrology has developed the Programme of National Base of Measuring Standards for 2011-2015, which is now in an operational phase.  This Programme ensures uniformity, accuracy and traceability of measurements in Moldova in order to protect society from the harmful effects of inaccurate or false measurements. The Programme focuses on the following components:

- Upgrading the measuring standards of the National Measuring Standards Base (NMSB);

- Creating new national references measuring standards in accordance with country’s needs;

- Conduct researches aiming to determine the measuring standards characteristics and stability over time;

- Participation in bilateral and multilateral inter-comparisons to confirm the measurement capabilities of NBB;

- Publication of CMC tables measuring capacity for recognition of international metrology community NBB.

Staff of NIM needs further integration into the national quality infrastructure and in the international community.

As a means, training of Moldovan experts both in Moldova and in Member state’s institutions should be seen as an important step into European Union work methods. To cope with highly demanding tasks to be performed by NIM as Moldovan National Metrology Institute (i.e. recognition of its calibrations and measurement capabilities), an involvement of its staff in the project activities shall be made to the widest possible extent. This relates to the calibrations and measurements, testing, conformity assessment, participation in international and bilateral inter-comparisons, development of its quality management system as a conformity assessment body. Seminars for stakeholders such as ministries, industry, calibration and testing laboratories, public institutions interested in market surveillance issues, accreditation body and other interested parties are seen as an excellent means to contribute to increasing the quality of measurements in the country. Nevertheless, this does not necessarily means to increase the overall number of NIM personnel, but is mostly aimed at ensuring sustainability of the results of the project.

3.2 Linked activities

In recent years, a number of projects financed by different donors have been contributing to development and strengthening of Moldovan quality infrastructure institutions (standardisation, metrology, and accreditation). Below is a summary of the main interventions.

EU financed project “HARMONISATION OF MOLDOVAN SYSTEM OF STANDARDISATION WITH EU” in 2003-2005 with a value of 1.4 million EUR. The project's overall objective is to help Moldova meet its obligations with the Technical Barriers to Trade agreement, to expand Moldavian Trade with European Union by harmonising its standardisation and to encourage foreign investment in the country.

The former NISM (recently split into NIS and NIM) was one of the beneficiaries of the WB projects: in 2010, in order to adopt European standards as Moldovan standards, NIS, with the support of the World Bank project on competitiveness  enhancement (UIPAC), purchased from Romanian standards organisation (ASRO) 2234 Romanian standards in the amount of 100 342 USD.

.

Furthermore, there is an on-going tender procedure for a WB financed project titled “Competitiveness Enhancement Project in Moldova: Consulting Services of a Twinning Partner for National Institute of Standardization and Metrology of Moldova in the Metrology Field”. This project will focus on training in the selected areas: chemistry, thermometry, mass.

It should be highlighted that the Twinning Project must as well be fully coordinated with the European Commission's activities and the other donors’ initiatives referring in particular to the implementation of the DCFTA in the area of technical regulations, standardisation, metrology, conformity assessment, market surveillance and accreditation.

3.3 Results:

Four mandatory results have been identified for the twinning project, which are grouped in two main headings as follows:

Results relating to the legal approximation conforming with the model employed in the organisation of the EU’s internal market:

1. Three New and Old Approach EU directives in legal metrology and pre-packaging field transposed and implementation started,

Results relating to the infrastructure capacity building implementation and improving quality management system:

2. National systems for metrology aligned with internationally recognised best practices through implementation of international standards in quality management,

3. Approximation to EU internal market regulation requirements on measuring instruments infrastructure for conformity assessment developed

4.  Better understanding of the role of standards and strengthening the capacity to take part in European standardization work

3.4. Activities

The Twinning will allow for the development of a close relationship with a Metrology and Standardisation body of an EU Member state. The listed activities and the proposed means for achieving the activities are indicative and can be revised in the framework of the preparation of the contract between the twinned institutions.

3.4.1 General Activities

Activity 0.1 Kick-off Workshop

Method

The first month of the project will be used to allow the installation of the Resident Twinning Adviser (RTA) in Moldova. The RTA will have to be installed in his/her office at the MoE/NIM. She/he will be introduced to the BC stakeholders of the project and to his/her counterparts and staff. She/he will also hire an Assistant (RTA Assistant) through an appropriate selection procedure.

A one-day kick-off meeting will be organised in the first month aiming at launching and presenting the project to the stakeholders, the media and the public at large. In order to guarantee large public information about the start of the project, the meeting will be concluded with a press conference and a press release.

Benchmarks:	Stakeholders, media and public informed about the start and content of the project by start of month 2.

Resources:	RTA, PL.

Activity 0.2 Final Closing Conference

Method

During the last two months of the project, a closing conference will be organised at which the results of the project will be presented to the general audience. The state of play in the areas of the project’s interventions will be discussed with the beneficiary, the Moldovan Government, the civil society, European Commission relevant services and other donors and stakeholders. The conference will be concluded with relevant recommendations for possible follow-up and lessons learnt for similar projects.

Benchmarks:	Closing Conference organised,

Recommendations and Lessons learnt formulated and discussed,

Stakeholders, media and public informed about the results of the project at its end.

Resources:	RTA, PL.

3.4.2 Legal Approximation activities

The following activities group is linked to the achievement of the result 1 ‘Three New and Old Approach EU directives in legal metrology and pre-packaging field transposed’:

Activity 1.1. A seminar and a round table on the Principles of Technical Regulation.

Method

EU experts will develop necessary material and carry out seminar and a round table on how EU directives are being transposed in several EU member states. Relevant stakeholders, ranging to IINM, to line ministries, to conformity assessment bodies, should be present.

Benchmarks:	A seminar and a round table carried out, material distributed.

Resources:	15 w.d. and 3 flights for STE legal experts.

Activity 1.2 Review of Moldovan legislation (Laws on Technical Regulation, Standardization, Metrology, Accreditation and Conformity Assessment), regulatory impact assessment and submission of recommendations on harmonization with the EU requirements and on elimination of conflictual provisions.

Method

EU experts will perform careful analysis of laws in force and will develop necessary reports in writing. The reports shall be discussed (e.g. by the means of round-tables) with the high ranking civil servants from relevant ministries, other regulatory bodies and enforcement executives (e.g. market surveillance authorities) and representatives of industry and sectors (Business Associations, etc…).

Benchmarks:	Laws revised, recommendations submitted and discussed.

Resources:	20 w.d. and 2 flights for STE legal experts,

Activity 1.3. A conference on New and Global Approach, EU regulations on 765/2008, 764/2008 and EU Decision 768/2008/EC.

Method

The EU experts will develop necessary material, deliver drafts to the Ministry of Economy, NIM, NIS and regional laboratories for review and carry out a conference. The points to be explained are relating to the European market regulation model (Standardisation Directive, New Approach, Old Approach, Global Approach, Notifications system) and WTO system for technical harmonisation.

Benchmarks:	Seminars carried out, material distributed.

Resources:	3 STE legal experts for metrology and market surveillance, 15 w.d.

Activity 1.4. Review of relevant secondary legislation transposing 2004/22/EC measuring instruments directive and directives 76/211/EEC and75/107/EEC.

Method

EU experts will revise the existing legislation in force in metrology and pre-packaging, conformity assessment and deliver written recommendations on improving them. When relevant legislation is not yet in force, the experts will provide guidance to the working group engaged in drafting national regulations. After discussion with the beneficiaries and jointly working with the working groups set-up by Moldovan stakeholders, the EU experts will submit new drafts of legislation to the BC authorities.

Benchmarks:	Final draft legislation accepted by the beneficiary.

Resources:	2 STE, one in legal expert field and another in metrology/pre-packaging, 20 w/d.

Activity 1.5. Raising awareness about directive 2004/22/EC MID and directive 76/211/EEC on pre-packaging (2 seminars on directive 2004/22/EC MID, and 2 seminars on directive 76/211/EEC).

Method

EU experts will develop necessary material and carry out conference about the roles and obligations of notified bodies, manufacturers, importers, especially under New Approach principles, role of the CE marking and other relevant markings, their relation to the technical regulations, requirements to quantity of products in pre-packages. The conference is aimed at economic operators, consumer protection organisations, other interested parties.

Benchmarks:	Conference carried out, material distributed.

Resources:	4 STEs on metrology, 20 w.d..

Activity 1.6. Strengthening interaction among NIM, NIS, MoE and relevant ministries and other bodies with a view to DCFTA.

Method

EU experts will support NIM, NIS, MoE and the line ministries in Moldova engaged in negotiations and implementation of the DCFTA with a view in improving position of voluntary standards, measurements and their importance to national economy, protection of environment, healthcare, science and research, and other relevant sectors. Round tables and meetings with high ranking civil servants will be held. Reports will be produced.

Benchmarks:	Round table with the line ministries, reports submitted.

Resources:	10 w/d. STE on metrology.

Activity 1.7. Study visits to  member state administrations for Moldovan specialists.

Method

During the technical regulation drafting period eight specialists in charge of this task in Moldova will be given an opportunity of a study visit to a similar institution of the EU. They will use this period to discuss the draft laws and technical regulations and discuss enforcement issues, organisation and management of conformity assessment, market surveillance, accreditation, testing fields. As a part of mission, due attention and exchange of information shall take on experience in preparation of legal metrology experts.

Benchmarks:	Study visit report (to be submitted in two weeks after the visit).

Resources:	8 flight tickets, 48 per diems.

3.4.3 Infrastructure capacity building activities

The following activities group is linked to the achievement of the result 2 ‘National systems metrology aligned with internationally recognised best practices through implementation of international standards in quality management’:

Activity 2.1 Training of technical assessors on standard ISO/IEC 17025.

Method

EU experts will discuss the existing needs with the beneficiary, develop necessary training material on relevant issues, such as uncertainty of measurements for calibration and testing laboratories with practical examples in at least three fields and carry out training. IINM, MoE and selected private and public regional calibration laboratories staff will participate in the training event.

Benchmarks:	Training carried out, certificates issued.

Resources:	2 STE, one on metrology and one on accreditation, 20 w.d..

Activity 2.2. Training on organisation of inter-laboratory comparisons.

Method

EU experts will discuss the existing needs with the beneficiary, selection procedure of the experts to be trained, develop necessary training material on relevant issues with practical examples and carry out training. NIM, MoE, Centre of Accreditation and selected public and private laboratories’ staff will participate in the training event.

Benchmarks:	Training carried out, certificates issued.

Resources:	10 w/d. and 1 flight for an STE on metrology,.

Activity 2.3. Study visits to NMIs operating QMS to ISO 17025 and accredited bodies to ISO 17020 or ISO/CEI 17065.

Method

At least four specialists of the NIM, Centre of Accreditation will be given an opportunity of study tours in relevant institutions of the EU. In addition, an institution should be a notified body to relevant conformity assessment procedures according to the MID directive. They will draft a report in which they will underline the benefit of the new practices they got acquainted to and, when relevant, propose amendments to the documents on quality management system.

Benchmarks:	Study visits performed, certificates issued, reports produced.

Resources:	48 per diems, 8 flight tickets.

Activity 2.4. Support in development procedures to ISO 17025.

Method

EU experts will assess, discuss and make written recommendations on implementation of ISO 17025 in NIM CMACfor calibration and testing of selected measuring instruments. These written recommendations should be summarised in a report and discussed with the beneficiary. Task groups will be made and guidance on development of quality management systems provided.

Benchmarks:	Recommendations and task groups.

Resources:	2 STEs, one on metrology and one on quality management and accreditation, 30 w/d. and 3 flights each STE.

Activity 2.5. Advice on upgrading of laboratories.

Method

EU experts will review current and future needs of Moldovan economy and future plans on transposition of relevant EU legislation and provide recommendations on setting up new measurement capabilities or upgrade existing in Moldova.

Benchmarks:	Analysis and reports.

Resources:	10 w.d. and 1 flight for an STE on metrology,.

The following activities group is linked to the achievement of the result 3 ‘Approximation to EU internal market regulation requirements on measuring instruments infrastructure for conformity assessment developed':

Activity 3.1. Strengthening conformity assessment of utility meters.

Method

EU experts will develop a training programme, draft testing and inspection procedures based on relevant tests and calibrations based on EU harmonised standards, other international documents of OIML and WELMEC documents in the field of utility meters in the scope of the MID and deliver theoretical and practical training including demonstration of practical tests on installations with a view of NIM as a future notified body. Recommendations on suitable conformity assessment module to be implemented in NIM should be delivered in writing.

Benchmarks:	Recommendations, training performed, certificates issued.

Resources:	3 STEs on metrology, 10 w/d..

Activity 3.2. Strengthening conformity assessment of measuring systems for liquids other than water.

Method

EU experts will develop a training programme, draft inspection, calibration and testing procedures based on relevant tests and calibrations based on harmonised standards, other international documents and WELMEC documents on measuring systems for liquids other than water. They should deliver theoretical and practical training including demonstration of practical tests on installations with a view of NIM as a future notified body. Recommendations on suitable conformity assessment module to be implemented in NIM should be delivered in written form.

Benchmarks:	Recommendations, training performed, certificates issued.

Resources:	10 w/d. and 1 flight STE one metrology,.

Activity 3.3. Strengthening conformity assessment of automatic weighing instruments.

Method

EU experts will develop a training programme, draft inspection, calibration and testing procedures based on relevant tests and calibrations based on harmonised standards, other international documents and WELMEC documents for AWIs and pre-packages and deliver theoretical and practical training including demonstration of practical tests on installations with a view of INSM as a future notified body and a body engaged in control of pre-packages. Recommendations on suitable conformity assessment modules to be implemented in NIM should be delivered in written form. Checks at a packer’s site should be carried out subject to availability of test equipment.

Benchmarks:	Recommendations, training performed, certificates issued.

Resources:	20 w/d., 2 flights, 1 STE on metrology,.

Activity 3.4. Strengthening conformity assessment of gas exhaust analysers, dimensional measuring instruments, capacity and length measures.

Method

EU experts will develop a training programme, draft inspection, calibration and testing procedures based on relevant tests and calibrations based on harmonised standards, other international documents and WELMEC documents on gas exhaust analysers, dimensional instruments, capacity and length measures and deliver theoretical and practical training including demonstration of practical tests on installations with a view of NIM as a future notified body. Recommendations on suitable conformity assessment module to be implemented in NIM should be delivered in written form.

Benchmarks:	Recommendations, training performed, certificates issued.

Resources:	3 STEs on metrology, 10 w/d.

Activity 3.5. Support to organisation of inter-laboratory comparison in the selected field.

Method

EU experts and the Beneficiary will agree on a kind of inter-laboratory comparison related to conformity assessment with the beneficiary, prepare necessary documentation for it, assist NIM as a pilot laboratory, and produce and submit the draft report. Practical organisation of an inter-laboratory comparison of a priority measuring instrument for (ready-to-be) accredited laboratories in Moldova and evaluation of results in a one day conference.

Benchmarks:	Recommendations and report on inter-laboratory comparison.

Resources:	RTA, 1 STE on Proficiency Testing, 15 w/d.

Activity 3.6. Training on WELMEC documents and other standards used in conformity assessment.

Method

EU experts will develop a training programme in agreement with the beneficiary, draft training materials for MID and pre-packaging directives, carry out training for NIM, MoE and relevant private sector laboratories.

Benchmarks:	Recommendations, training performed, certificates issued.

Resources:	1 STE on metrology, 10 w/d..

Activity 3.7. Study visit on conformity assessment for measuring devices issues.

Method

Moldovan experts from IINM, Centre of Accreditation and MoE, will have an opportunity to discuss conformity assessment related issues during the study visit to EU member state administrations.

Benchmarks:	Study visit reports.

Resources:	6 flights, 36 per diems.

The following activities group is linked to the achievement of the result 4 “ Better understanding of the role of standards and strengthening the capacity to take part in European standardization work":

Activity 4.1. Preparation of information material on metrology and standardization.

Method

EU experts will discuss with the NIM, Centre of Accreditation, MoE on the kinds of information (relevant conformity assessment modules, market surveillance in the EU member states, RAPEX database etc.) and target groups, develop draft material and submit it for discussion with the beneficiary. the Ministry of Economy and target groups on the kinds of information on standardisation, technical regulations, technical barriers to trade, work of international and national standardisation bodies, develop draft material and submit it for discussion with the beneficiary Leaflets, brochures, will be printed and disseminated.

Benchmarks:	Information material produced.

Resources:	STEs x10 w/d on metrology and STEs 2x10 w/d on standardisation.

Activity 4.2. Training on standardisation and on best practices in collaboration among standardisation body and other stakeholders.

Method

EU experts will carry out needs assessment, develop necessary material and carry out 3 seminars for stakeholders, including MoE, other line ministries, industry and others aimed at strengthening perception of voluntary standardisation, better understanding of the role of standards and relationship between standardisation and regulation.

Benchmarks:	3 Seminars carried out, certificates issued.

Resources:	2 STEs on standardisation, 20 w/d.

Activity 4.3. Strengthening the capacities of national technical committees to participate in European standardization work.

Method

EU experts will carry out an assessment of national standardization technical committees (TC), will carry out 2 seminars on technical procedures of development and adoption of European standards and will assist in involving the national experts in CEN mirror TCs, as affiliate member to CEN.

Benchmarks:	Seminars carried out, active national TCs revigorated, experts involved in CEN mirror TCs.

Resources:	RTA, 2 STEs on standardisation, 20 w/d.

Activity 4.4 Internships and study visits to technical and management committees of relevant standardisation bodies and organisations from EU MS.

Method

During the implementation of the project activities, specialists of the NIS will be given an opportunity of internships and study visits to a similar institution of the EU. They will draft a report in which they will underline the benefit of the new practices introduced and, if relevant, propose amendments to the existing documents.

Benchmarks:	Recommendations.

Resources:	15 Flights, 140 per diems.

Activity 4.5 Assessment of national standards database and assistance in withdrawing conflictual or obsolete national standards.

Method

EU experts will carry out a general assessment of national standards database, with regard to identification of tools and criteria for withdrawal of conflicting or obsolete national standards, and a relevant training will be provided. EU experts will consult on planning for adoption of European standards for the next medium term, aiming at reaching a higher share of European standards in the total amount of national standards.

.

Benchmarks:	Assessment carried out, criteria for withdrawal defined, training provided.

Resources:	2 STEs on standardisation, 20 w/d.

Activity 4.6 Training in using the IT tools in standardization field.

Method

EU experts will carry out need assessment and will provide training in using the relevant ISO, IEC and CEN information technology tools. NIS staff should be trained in using these IT tools, being a modern and efficient solution in standardization work (drafting of standards, public enquiry, voting, adoption notifications etc.).

Benchmarks:	Training provided, IT tools used.

Resources:	1 STE on standardisation, 15 w/d.

3.5 Means/Input from the MS Partner Administration

3.5.1 Profile and tasks of the Project Leader (PL)

The PL will be expected to devote a minimum of 3 days per month to the project in his home administration. In addition, he will coordinate, from the Member state side, the Project steering Committee (PSC), which will meet in Moldova every three months.

Profile:

- At least 10 years experience either in the field of metrology or standardisation with good understanding of other subjects and, during that period, he/she must be in an active senior/medium management position in the Member State institution for at least 3 years;

- Have experience in the field of project management, institutional issues and organisation of national quality infrastructures to the European requirements;

- Excellent command of English.

Tasks:

- Overall coordination, guidance and monitoring of the project;

- Preparation of project progress reports with support of RTA;

- Timely achievement of the project results;

- Co-chairing of project steering committees;

- Provision of legal and technical advice and analysis whenever needed.

- Responsible of the well as management of the project administration;

3.5.2 Profile and tasks of the RTA

One Resident Twinning Adviser (RTA) over a period of 24 months as well as medium/short term experts will implement the above-listed components. The RTA has the responsibility to guide the work of the team and provide support in elaboration, implementation, auditing and peer-evaluation of QMS of NIM.

The RTA is expected to fill the following profile:

- Minimum University Degree in Law, Engineering, Natural Sciences and 7 years of experience in the field of metrology, standardisation or conformity assessment;

- Sound comparative knowledge of relevant EU legislative and institutional requirements related to the various components of this project;

- Wide knowledge of related good practice/EU legislation and demonstrated experience on transposition of New and Old Approach directives and relevant EU regulations on metrology and conformity assessment into national legislation;

- Solid knowledge of metrology, standardisation and conformity assessment legislation, work methods and procedures;

- Previous experience in project management would be an asset;

- Experience in working on similar projects would be an asset;

- Good training, public speaking, diplomatic and written communication skills;

- Excellent computer literacy (Word, Excel, Power Point);

- Excellent command of spoken and written English;

- Fluency in State Language or Russian would be an asset;

- Experience in implementation of QMS according ISO/IEC 17020 or ISO/IEC 17025 would be an asset;

Tasks:

- Overall supervision of the project implementation on its day by day and coordination of all activities;

- Coordination of the activities of the team members in line with the agreed work programmes to enable timely completion of project outputs;

- Provide technical input to the project whenever needed and provision of advise in his field of expertise;

- Liaise with MS and BC Project Leaders and daily contacts with BC RTA counterpart;

- Liaison with EU Project Manager;

- Liaison with other relevant projects and Moldovan institutions.

3.5.3 Profile and tasks of the medium/ short-term experts

Tasks of medium and short term expertise

In addition to the RTA, the Member State Partner (MSP) must have a quick and flexible access to a pool of short-term experts from the EU MS. These experts shall either work as advisors and trainers or perform specific studies or assignments within the scope of the twinning project. Their specific profile has been described in the presentation of activities.

As an indication, the profiles are the following:

STE Legal expert

University degree in Law or equivalent professional experience of a minimum of 8 years in the field of metrology

At least 5 years’ experience in harmonization of legislation and technical regulation with the EU Acquis and experience in awareness raising campaigns, including New Legal Framework.

At least 5 years' experience in support in drafting metrology legislation harmonized with EU Acquis and transposition of NAWI, MID, units of measuring Directives and experience in awareness raising campaigns in this field will be required for activity 1.3.

STE Expert in pre-packaged products

University degree in Law or equivalent professional experience of a minimum of 8 years in the field of metrology legislation

At least 5 years’ experience with regulation and control of pre-packages or working in a National Metrology Institute

At least 5 years’ experience in support in drafting metrology regulation and transposition of pre-packaged products regulation according to the EU Directive EC/76/211 and experience in awareness raising campaigns in this field

STE Metrology expert

University degree in Law, Engineering, Physics, Chemistry, Metrology or equivalent professional experience of a minimum of 8 years in the field of metrology.

Experience in setting up and leading public relations department.

At least 5 years’ experience in harmonization of legislation and technical regulation with the EU Acquis, removal of TBTs.

Experience in a State Metrology Institute on managerial level and experience in testing on pre-packages would be an asset.

At least 5 years' experience in WELMEC Working Groups would be required for the activity 3.6

STE quality management and accreditation expert

University degree in physics, metrology, chemistry or equivalent professional experience of a minimum of 5 years in the field of institutional building for metrology and accreditation.

At least 5 years' experience with calibration laboratories and National Metrology Institutes.

STE standardisation expert

University degree in Physics, Chemistry or Metrology or equivalent professional experience of a minimum of 5 years in the field of Standardisation.

Good knowledge of procedures in operation of WTO enquiry point, use of IT technologies in standardisation.

Experience in training and preparation of information materials.

Setting up and leading a Technical Committee (TC) in a national standardisation body is an advantage.

Preferably at least 5 years' experience in CEN/CENELEC and/or ISO.

STE Proficiency Testing (PT)

University degree in Quality Management or equivalent professional experience of a minimum of 5 years' in the field of implementation of PT schemes.

At least 5 years of experience in a Metrology Institution with an accreditation for PT schemes.

Preferably at least 5 years experience in supporting and training for PT activities.

In addition to their missions in Moldova, the short-term experts are expected to contribute actively to elaborating the programmes of the foreseen study visits and internships.

4. Institutional Framework

In terms of the institutional set-up, the former monopolistic system of GOSSTANDART, which incorporated all administrative bodies of the technical regulation sphere, was abolished. As a result, National Institute for Standards and Metrology (INSM) under the Ministry of Economy of Moldova was established in 2008. Later, at the beginning of 2013, the National Institute of Standardisation and National Institute of Metrology was created from scratch, being transferred from INSM all the competences related to standardization and respectively general and legal metrology.

NIM is in charge of general and legal metrology ranging from development and maintenance of state measurements standards and reference materials, to maintenance of the register of types of legal measuring instruments, to calibration and approval of the measuring instruments. The institute employs 70 persons;

Main objectives of NIM are participation in elaboration and implementation of the state policy on metrology, maintaining the national measurement standards and ensuring the traceability of measurements.

NIS is in charge of development and adoption of original Moldovan standards, as well as adoption of international and European standards as national standards. Currently NIS employs 40 persons;

Main objectives of NIS are adoption of at least the 80% European standards, ensuring availability of relevant standards to industry and stakeholders  and withdrawal of national conflicting and obsolete standards.

Both Institutes will take part in the project.

In the Ministry of Economy, there is a quality infrastructure and conformity assessment department, which shall be involved in project activities. The leading beneficiary will be the Ministry of Economy.

In accordance with PCA and the forthcoming DCFTA, progress on the implementation of the current project will be regularly reported in the framework of the reinforced EU-Moldova regulatory cooperation.  The European Commission's Directorate General for Enterprise and Industry (in charge of sector policy) will be kept informed on the progress of implementation of the project.

Furthermore, the other stakeholders as the Ministries, public agencies and private or semi-private organisations such as testing and calibration laboratories will be involved in the execution of the project activities. Universities should also be invited to take part in certain meetings and trainings.

5. Budget

The beneficiary will provide in kind contribution in the form foreseen in the twinning manual.

The maximum total budget available of the action is € 1.1 million.

6. Implementation Arrangements

6.1. Implementing Agency

The person in charge of this project from the Delegation of the European Union to Moldova is:

Ms Speranţa Olaru

Project Manager

6.2 Main counterpart in the Beneficiary Country:

Project leader:

Mr. Dumitru Godoroja,

Vice minister,

Ministry of Economy

tel.: (373 22) 250 672

RTA counterpart:

Ms. Victoria Prisac

Head of division “Quality infrastructure General Division”

Ministry of Economy

tel.: (373 22) 250 677

6.3. Contracts

The project will be implemented through one twinning contract.

7. Implementation schedule (indicative)

7.1. Launching of the call for proposals (November 2013)

7.2. Start of the project activities (July 2014)

7.3. Project completion (July 2016)

7.4. Duration of the execution period (number of months) 27 months with an implementation period of 24 months (presence of the RTA in Moldova)

8. Sustainability

The sustainability of the project will be achieved through a suitable implementation of the project activities and availability of trained personnel in the metrology and standardisation infrastructure. Transfer of know-how within the institutions involved (at NIM and NIS and relevant stakeholders) and liaison of NIS and NIM with international platforms will contribute to sustainability. All training materials elaborated under the Twinning Project will continue to be used by the NIS and NIM after the project's completion. All materials - Training Materials, Methods and Manuals elaborated within the project shall be submitted, both in English and in Moldovan, where relevant, so as to ensure smooth dissemination of the project results and sustainability of results. The Moldovan Government, through the provision of relevant funding to NIS and NIM in order to implement its tasks, will ensure the financial sustainability of the outputs attained by the project. The institutional sustainability of the project results will also be guaranteed by the direct involvement of the NIS and NIM, which will ensure improved connections of staff with other relevant actors in the field of metrology and standardization.

In addition, the preparation process for DCFTA clearly indicates that a reform process in the quality infrastructure, focused on metrology and standardization, in line with the harmonization to the EU Acquis, represents a high priority for the cooperation between Moldova and the European Union in the next coming years; in this sense, the key role of the NIM in coordinating and facilitating the process of providing traceability is expected to become even more important in the future. Furthermore, needs of the local and international businesses in calibrations and measurements as well as needs of public authorities in technical issues and participation in (inter)national metrology activities are expected to contribute to maintaining high level services on a constant basis in NIM.

# Finally, the firm commitment of Moldovan stakeholders involved in metrology at all levels (Relevant Ministries, State Universities, Metrology laboratories and industry will guarantee the internal dissemination and communication of the results and output).

9. Cross cutting issues

9.1. Equal Opportunity

The principle of equal opportunity will be integrated into all stages of the project implementation. Practices in ensuring equitable gender participation in the project will be guaranteed. Male and female participation in the project will be based on the relevant standards of the EU. Accordingly, the project will seek to ensure that there is equal treatment accorded to male and female staff in NIS and NIM and the other stakeholders participating in the project activities and training programs.

The main criteria for staff recruitment will be appropriate qualifications and experience in similar projects, not sex or age. Both men and women will have equal opportunities and salaries.

9.2. Environment

Implementation of the project will have no adverse effect on the environment.

10. Conditionality and sequencing

There is no precondition set for this twinning project. Nevertheless, it is important that Moldovan authorities, NIS and NIM are committed to implement the recommendations in order to achieve the targeted results, purposes and overall objective of the project bringing NIS and NIM, CMAC to the success of a process of continuing improvement towards increasing the operational efficiency and effectiveness in line with the EU and international standards and best practices. The MoE and NIM will ensure operational and logistical support to the RTA and the Twinning experts in terms of ensuring operational coordination with the other Moldovan public institutions involved in the project, collecting and processing the information needed and to provide contacts and information concerning private entities that would be involved during the Twinning activities. Finally, it is also important that individual staff members at all levels understand that it is their responsibility to ensure the quality of their work. In this regard, the NIS and NIM needs to ensure that the staff pay structure is commensurate with the qualifications and skills required of the staff.

There are no other requirements on sequencing, except for those mentioned in relevant activities.

List of Annexes to the Fiche

Annex I – Logframe Matrix

Annexes to project Fiche  - Annex I

| ANNEX I - LOGFRAME PLANNING MATRIX FOR twinning fiche Strengthening standards and metrology in Moldova |  | Programme name and number |  |
| --- | --- | --- | --- |
|  |  | Total budget: €1,100,000 |  |
| Overall objective | Objectively verifiable indicators | Sources of Verification | Assumptions |
| To implement best practices in the sectors with the aim of preparation for international agreements on the free movement of goods (DCFTA). | - Number of regulations/legal acts adopted - Number of calibration services provided to laboratories and industry - Number of inter-laboratory comparisons performed or participated in - Number of international meetings attended - Number of European standards adopted and national conflicting standards withdrawn | - Reports of the ministries responsible for trade and finance including publication of technical regulations - Statistics report (trade sector) - EC annual progress report - Project reports - Conference/meetings reports and photos - Approved inter-comparison reports - Calibration and testing certificates issued |  |
| Project purpose | Objectively verifiable indicators | Sources of Verification | Assumptions |
| To upgrade standards and metrology sectors in Moldova according to the best practices of the EU member states | - Gaps in legislation eliminated. - Progress report to present the quality management system at COOMET Quality Forum - Number of measurement procedures developed and approved. | Official gazette COOMET TC Quality Forum report Reports of peer assessors Certificates of scopes of accreditation | Government’s commitment on adoption of EU legislation continued. Delays in case of legislation preparation and modification. Unsuccessful results in international comparisons. Availability of local staff |

| Results | Objectively verifiable indicators | Sources of Verification | Assumptions |
| --- | --- | --- | --- |
| - Three New and Old Approach EU directives in legal metrology and pre-packaging field transposed and implementation started. - National systems for metrology aligned with internationally recognised best practices through implementation of international standards in quality management. - Approximation to EU internal market regulation requirements on measuring instruments infrastructure for conformity assessment developed - Good knowledge by conformity assessment operators dealing with measuring instruments about the roles and obligations under New Approach principles achieved; knowledge on CE marking and other relevant markings disseminated and interaction among stakeholders improved. | Draft regulations transposing directives 76/211, 80/181, 2004/22, 75/107/EEC measurements submitted for adoption. Regulation impact assessment report elaborated Technical regulations on transposition of the MID and the other directives drafted and adopted, human capacities developed Business plan for NIM developed. Quality management system in NIM in place. Inter-laboratory comparison performed. Personnel trained. CMCs developed and submitted for international assessment. CMCs approved by the relevant COOMET TCs. NIS. CMAC and relevant laboratories implementing conformity assessment standards. Personnel trained. Conferences run. Personnel trained Leaflets, brochures printed and disseminated Seminars/conferences run. Personnel trained. Relevant legislation developed and approved. | # Texts of the draft regulations. # Project reports. # Conference reports. # Participants’ reports and certificates of trainings. # RIA report # Report on peer assessment. # Evaluation report by the COOMET Quality Forum. # COOMET TC reports # Project reports. # Certificates of training. # Conference reports. # Intermediate and final reports. # Certificates of training. | Availability of human resources and their sufficient knowledge of foreign languages and up-to-date technical knowledge, Availability of suitable equipment to perform the necessary inter-laboratory comparisons both on an international scale and on national level, Availability of sufficient national financial resources for co-financing of the project activities by the NIM, NIS Excellent co-operation among relevant national public institutions and other stakeholders Availability of suitable premises for laboratories, training and conferences in the NIM, NIS. |

| Activities/Components or input | Means | Assumptions |
| --- | --- | --- |
| - Kick-off Workshop - Final Closing Conference - Seminar and round table on the Principles of Technical Regulation. - Review of Moldovan legislation (Law on Technical Regulation, Standardization, Accreditation, Conformity assessment and Metrology), regulatory impact assessment and submission recommendations on harmonization with the EU requirements and on elimination of conflictual legislation - A conference on New and Global Approach, EU regulations on 765/2008, 764/2008 and Decision 768/2008/EC. - Review of relevant secondary legislation (under the law) transposing 2004/22/EC measuring instruments directive and directives 76/211 and 75/107/EEC. - Raising awareness about directive 2004/22/EC MID and directive 76/211/EEC on pre-packaging - Strengthening interaction among NIM, NIS, MoE and relevant ministries and other bodies with a view to DCFTA. - Study visits to at least 2 member state administrations for Moldovan specialists. | PL, 3 wd, 1 flight, PL, 3 wd, 1 flight 1 STE, 15 wd, 3 flights 2 STEs, 20 wd, 4 flights 3 STEs, 15 wd, 3 flights 2 STEs, 20 wd, 4 flights 4 STE, 20 w.d. 4 flights 1 STE, 10 wd, 1 flight 8 flight tickets for experts, 48 per diems. | Necessary local resources available Strategy developed |
| 2.1. Training of technical assessors on ISO 17025. 2.2. Training on organisation of inter-laboratory comparisons. 2.3. Study visits to NMIs operating QMS to ISO 17025 and accredited bodies to ISO 17020 or ISO/IEC 17025 2.4. Support in development procedures to ISO 17025 2.5. Advice on upgrading of laboratories. | 2 STEs, 40 wd, 4 flights, interpretation, rent of venue/equipment 1 STE, 10 w.d., 1 flights, 48 per diems, 8 flights, inter-city costs, incidentals 2 STEs, 60 wd, 6 flights, translations 1 STE, 10 wd, 1 flight | Necessary local resources available |
| 3.1. Strengthening conformity assessment (modules B and F) of utility meters. 3.2. Strengthening conformity assessment of measuring systems for liquids other than water. 3.3. Strengthening conformity assessment of automatic weighing instruments. 3.4. Strengthening conformity assessment of gas exhaust analysers, dimensional measuring instruments, capacity and length measures. 3.5. Support to organisation of inter-laboratory comparison of a measuring instrument. 3.6. Training on WELMEC documents and other standards used in conformity assessment. 3.7. Study visits on conformity assessment related to measuring instruments and market surveillance issues. | 3 STEs, 30 wd, 3 flights STE, 10 wd, 1 flights, translation, interpretation 1 STE, 20 wd, 2 flight, translation, printing 3 STEs, 30 wd, 3 flights, translation, interpretation 1 STE, 15 wd, 3 flights, interpretation 1 STEs, 10 wd, 1 flights, translation, interpretation 6 return flights, 36 per diems, incidentals, | Necessary local resources available |
| 4.1. Preparation of information material on metrology and standardisation 4.2. Training on standardisation and best practices in collaboration among standardisation bodies and other stakeholders. 4.3. Strengthening the capacities of national technical committees to participate in European standardization work. 4.4 Internships and study visits to technical and management committees of relevant standardisation bodies and organisations from EU MS. 4.5. Assessment of national standards database and assistance in withdrawing conflicting or obsolete national standards. 4.6. Training in using the IT tools in standardisation field | 4 STEs, 40 wd, 4 flights, translations 2 STEs, 20 wd, 2 flights, interpretation and translation, 2 STEs, 20 wd, 2 flights, interpretation 140 per diems, 15 flights, incidental costs, 2 STEs, 20 wd, 2 flights, translation, interpretation 1 STE, 15 wd, 2 flights, interpretation and translation | Necessary local resources available |

Several MS, in case of a consortium