- 2012 Annual Programme

- Support to Public Administration Reform: 01/2012/1

- Identification

| Project Title | Support to Statistics |
| --- | --- |
| Programme | IPA 2012 Annual Programme |
| Twinning Number | KS 12 IB ST 01 |
| CRIS Decision number | 2012/022-940 |
| Project no. | 01 |
| MIPD Sector Code | 1. Public Administration Reform |
| ELARG Statistical code | 02.32 |
| DAC Sector code | 16062 |
| Total cost (VAT excluded) | € 1.5 million |
| EU contribution | € 1.5 million |
| Management mode | Centralised |
| EU Delegation in charge | European Union Office in Kosovo* |
| Implementation management | European Union Office in Kosovo |
| Implementing modality | Twinning |
| Project implementation type | C01 |
| Zone benefiting from the action(s) | Kosovo |

- Rationale

2.1 	Project context: issues to be tackled and needs addressed

This project will support the Kosovo Agency of Statistics (ASK). Quality statistics is vital for the design of economic policy and play an important role in monitoring the situation and progress in poverty reduction, economic development and all fields to be negotiated in the process of European integration.

Official statistics are used for decision-making by policy makers, businesses and society at large. They are an essential tool for the development of democratic and market oriented societies. Building a sustainable statistical system according to EU and international standards is a demanding and lengthy process. Kosovo is at very early stage of this process. According to the Progress Report 2011, there has been some improvement as regards the statistical infrastructure. A CEO was finally appointed in autumn 2011for a three-year period and the Law on Official Statistics entered into force in December 2011. In addition, ASK expects to hire new staff with adequate qualifications in the near future. However, the organizational capacities of ASK remain weak which hampers the production of core statistical products. The Statistical Agency needs to improve and standardise its internal procedures and in order to ensure more efficient data production and better use of the available resources. Therefore, building professional capacity in the various departments of ASK, evaluating and reorganising workflows and procedures and establishing a quality management system for the key processes in the production of statistics are the main focus in this component.

Furthermore, the project will address economic statistics and information technology. The issues to be tackled in the field of economic statistics are improvement of business and macro-economic statistics: improvement of data sources of economic statistics for the accounts; introduction of quarterly national accounts and improving of short-term statistics indicators, which will be an important data source for quarterly national accounts. Introduction of the NACE Rev. 2 classification of economic activities into the business register has started. The business register is operational, but is not updated regularly. Timeliness of national accounts according to the expenditure approach has improved significantly, but not for production approach. ASK does not yet produce quarterly national accounts.

Whereas in the field of information technology, ASK needs to improve the IT system by creating of a unified system of information technology fit for needs of the ASK.  ASK will also need to strengthen the IT and Methodology Department which provides the basic quality and computer systems infrastructure on which much of the required improvements will depend. For all these activities substantial support from the Government is required in terms of additional budget, personnel and space.

This project is expected to support the ASK to:

- Enhance its internal organisation and capacities in order to ensure more efficient production of statistics and better use of available resources.

- Improve the quality of statistics; in particular national accounts and business statistics, by implementing methodology according to EU standards and improving data sources.  Improving the coverage of short-term statistics indicators, which will also be an important data source for developing quarterly national accounts.

- Strengthen capacities on information technology system, preparing program application, developing software application for data collection (for different surveys carried out in ASK).

- Build upon internal computer network (Intranet) for ASK and the regional offices (software &hardware)

- Professional support in the field of dissemination in particular improving web dissemination of statistical data

All of these activities aim at increasing the capacities of the ASK staff to produce quality statistics in the near future.

2.2	Link with MIPD and Sector Strategies

The Multi-annual Indicative Planning Document (MIPD) 2011-2013 for Kosovo, under the sector for public administration reform, recognises the improvement of the production of statistics as a priority.

The Strategic Development Plan for the Kosovo Agency of Statistics (ASK) for 2009 - 2013 sets the following priorities and needs for the statistical system;

- Macroeconomic statistics; the focus will be on the development of national accounts according to ESA95 (European System of Accounts 1995), introduction of quarterly gross domestic product (GDP) by production and expenditure approach method, estimation of national accounts in constant prices based on improved price indices, economic statistics and other relevant fields of statistics in generally.

- Business statistics; improve the Structural Business Statistics (SBS), including data collection, data processing, timeliness and coverage, new short-term indicators and short-term statistics according to NACE Rev. 2  (The Statistical Classification of Economic Activities in the European Community ) prepared and published.

- Developing an IT Development Strategy for the period 2010-2015.

- Begin the development and introduction of IT protocols and software for data collection through electronic data transfer systems.

- Introducing data transfer and data capture by electronic means will bring savings in time and resource use.

- Dissemination.

- Improve the website and set up a data library.

- Monitor the dissemination list and introduce User Satisfactory Surveys.

2.3	Link with Accession Partnership (AP) / European Partnership (EP) / Stabilisation and Association Agreements (SAA) / Annual Progress Report

The European Partnership document highlights the strengthening of the qualitative capacities of the personnel through trainings and an increase in number of staff as priorities in the area of statistics in order to prepare for producing EU-harmonised statistics. In addition, the European Partnership lists following priorities for statistics:

Short term priorities:

1.	 Strengthen the administrative capacity of the Kosovo Agency of Statistics and improve its operational and financial independence. Ensure the reliability of the statistics including that survey respondents provide quality data to the Statistical Agency in a timely manner, free of charge.

2.	Continue developing economic statistics and accelerate the development of social statistics.

Medium term priorities:

1.   Increase cooperation and coordination within the Kosovo statistical system, develop a quality management system and document, and standardize production and dissemination procedures.

The Progress Report 2011 recognises that some progress has been made as regards the statistical infrastructure. The cooperation of the Kosovo Agency of Statistics with other institutions has improved. The amendments to the law on tax procedures now allow the tax administration to provide the Office with the necessary administrative data for the statistical business register. However, the statistical infrastructure of Kosovo needs to be further strengthened and the Progress Report notes that the Agency lacks the necessary resources.

Furthermore, the Progress Report highlights that there has been limited progress on classifications and registers. Efforts are needed to implement the European classification of economic activities NACE (Statistical nomenclature of economic activities in the European community) Rev. 2.

2.4	Problem Analysis

Official statistics are used for decision-making by policy makers, businesses and society at large. They are an essential tool for the development of democratic and market oriented societies. Building a sustainable and reliable statistical system according to EU and international standards is a demanding and lengthy process. Kosovo is at very early stage of this process.

Despite progress made in several areas of statistics, ASK continues to face problems related to producing statistics on time, with reliable quality and in line with the standards of European Union countries and international methodologies. Other concerns that need to be addressed are: publication of GDP by production approach using supply and use tables (SUT)(last year published 2007), the lack of quarterly national accounts, structural business statistics (SBS), annual and short-term statistics (STS), statistical register of  businesses, use of new international classifications, lack of social statistics in quarterly basis respectively statistics on labour market, strengthen existing capacity in the field of IT, for the consolidation of the integrated system we collect and manage data (managing databases in a common system). Training needs, especially in SQL and Windows Server 2008.
All the above mentioned challenges demonstrate the need to increase existing capacities of ASK in order to approximate the statistics of Kosovo with the European Union countries and Eurostat standards.

2.5	 Linked activities and donor coordination

A number of donor initiatives have supported the statistical system in Kosovo. The EU has been supporting ASK since early 2000. Both components of the project will build on the EU assistance already provided.

Support to ASK in preparation of the 2011 census

Technical assistance supported ASK in the preparation and implementation of the 2011 population census. The objective is to increase the capacity of ASK to prepare and carry out the population and housing census and disseminate the results in line with international standards and requirements.

The EU also supported the Population and Housing Census Trust Fund and the International Monitoring Operation for the 2011 census.

IPA regional statistics programme for the Western Balkans

The IPA regional programme consists of two main parts. One is covers activities such as participation in Eurostat Working Group meetings, training courses, study visits and short-term consultancy services.

The second part consists of pilot projects covering data collection and methodological development for, among other, external trade statistics, price statistics (purchasing power parities and harmonised index for consumer prices), national accounts, structural business statistics and business register,  agricultural statistics and population censuses plus data transmission.

For example, with regards to national accounts, within the regional IPA 2007 Project, ASK has finished the “Description of sources and methods used for compilation of central accounts” whereas the main objective of the IPA 2008 Project was to improve the GFCF estimates for the non financial and financial units, improvement the GFCF and CFC for government and NGOs and improvement of GVA estimates for transport and restaurants. Main objective of IPA 2009 Project is to improve the basis of the annual and quarterly constant price estimates.

SIDA’s support to the Statistical Agency

SIDA/Statistics Sweden’s assistance is focused on agricultural statistics and especially on agriculture Price Index and Economic accounts in agriculture, environment, energy and price statistics. The current project between the ASK and Statistics Sweden started in 2002 and will run up to August 2012 with the aim to be extended until 2015. The aim of the project is focused on price statistics, business surveys, statistical business register and short term statistics (from 2010). As soon as the proposed IPA project will start, SIDA will stop the support in SBS and STS. The project also supports ASK in capacity building by offering subject-matter training courses, methodology training and English language training. The project has initiated a “Trainee Component” which provides ASK an extra five junior experts yearly.

In addition to the above-mentioned projects, DfID, IMF, Unicef, the UNFPA and JICA also support the Statistical Agency. IMF’s assistance is limited to one short-term expert mission per year on expenditure approach whereas the others have a more permanent support role.

Evidently, donor activities need to be coordinated in order to make maximum use of the absorption capacity of the beneficiary institutions and to ensure the sustainability of the results. It is crucial that the sub-sectoral donor working group that was convened for the first time in March 2012 will continue to meet in order to ensure that the support is well coordinated and ASK can benefit of synergies between different projects.

Furthermore, the Government of Kosovo adopted in 03 Jun 2011 the Regulation No. 04/2011 On Donor Coordination. The aim of this regulation is to increase the role of the Government of Kosovo in the coordination of foreign aid, creating a system that ensures the effectiveness and transparency between the activities of the Government of Kosovo and the Donor Community. The Regulation establishes High Level Forum, Sector Working Groups and Sub Working Groups as mechanisms to coordinate, review and supervise progress of donor assistance.

2.6      Lessons learned

ASK have been supported over the last years by several projects funded by different donors. Previous experience indicates that there is a need for better coordination between projects, avoiding overlaps and in particular increased coordinating role and ownership from the Kosovo institutions itself.

Coherence between various projects should be ensured in the framework of the overall Public Administration Reform. It is also crucial to maintain staff knowledge, institutional memory and procedures to ensure sustainability of projects results and benefits.

The introduction of a sector-based approach to plan and implement assistance will increase the effectiveness of technical assistance projects. This will further enhance the effectiveness of policy coordination initiatives, increase ownership of Kosovo institutions and improve efforts to avoid overlapping in donor assistance.

The statistical work plan will also help Kosovo to move forward in that direction.

In ASK, particular attention should be paid to staffing and the transfer of ownership and knowledge. Project implementation can easily be hampered by insufficient staff and turnover of trained staff. The availability of the needed human resources at ASK has to be considered as a pre-condition for the project. ASK must also take ownership of all the activities and ensure that the skills and expertise acquired during the project will constructively increase the capacity of the whole organisation.

3. Description

  - Overall objective of the project

- To strengthen the statistical system of Kosovo, with a focus on improving national accounts and business statistics according to EU standards, and to modernise the IT systems and web dissemination.

  - Specific objective(s) of the project

- To strengthen the capacities of ASK and enable ASK to carry out its core activities in a standardised manner,

- To improve the quality of annual national accounts and start the compilation of quarterly accounts

- To improve structural business statistics and increase the coverage of short-term business statistics,

- To strengthen the ASK IT system and web dissemination of statistics.

  - Results

Component 1: A quality system for the production of statistics

- Statistical work plan up dated and followed;

- Policies and guidelines prepared for the implementation of the quality system.

Component 2: National accounts

- Increased compliance with ESA 95, including improvement in the estimation of production, intermediate consumption and value added for all activities of the economy. Estimation of national accounts in constant prices based on improved price indices.

Component 3: Business statistics

- Improved Structural Business Statistics, including data collection, data processing, timeliness and coverage:

- New short-term indicators, including industrial production and output prices prepared and published;

- Short-term statistic according to NACE Rev. 2 prepared and published;

- Improvements of the Statistical Business Register.

Component 4: Information technology system

- Improved IT system and Programming (software application & data maintained);

- Developing IT system and Web dissemination.

  - Main Activities

Component 1: A quality system for the production of statistics

1.1. Review and update on the statistical work plan, implementation of the five-year work programme;

1.2. Define the policies and guidelines for the work of the ASK covering inter alia planning, classifications, questionnaires, instructions, computer applications, data verification, confidentiality, dissemination and publication and to institutionalise the usage of the quality system;

1.3. Training on the concepts of quality management and support in the implantation in especially within the areas of component 2, 3 and 4.

Component 2: National accounts

2.1. Review of national accounts and analyses of the available data sources.

2.2. Review compilation of annual accounts by production and expenditure approach and in constant and current prices, following ESA 95;

2.3. Implement the relevant recommendations of the Action Plan for compiling and publishing comprehensive statistics on national accounts and labour market and carry out revision of annual national accounts based on the new sources and improved methodology.

Component 3: Business statistics

3.1. Assess the current situation of business statistics and identify available sources, both administrative and statistical sources;

3.2. Revise questionnaires used for the SBS and the data collection system, review the sampling method and improve the IT system;

3.3. Design new STS surveys, carry out pilots and start regular production and publishing of short-term indicators for industrial production and output prices;

3.4. Start producing short-term business statistics according to NACE Rev. 2 and revise the time series;

3.5. Upgrade the Statistical Business Register to improve the accuracy of the population of business entities and establish a system for regular updating of the register.

Component 4: Information technology system

4.1. Provide training to the ASK IT department based on training needs assessment;

4.2. Build an internal network (Intranet) for ASK and the regional offices; and assist in preparing the technical specifications for the IT supplies contract;

4.3. Improve web dissemination for selected statistics including improvement of ASK’ website to make it a more user-friendly and flexible dissemination tool;

4.4. Develop guidelines for the design of tables and graphs, also to 	be applied for dissemination on the web;

4.5. Develop a dissemination database, including more complete metadata covering different aspects related to data quality;

4.6. Build up a unified system in the field of information technology.

  - ASSESSMENT OF PROJECT IMPACT, CATALYTIC EFFECT AND CROSS BORDER IMPACT (WHERE APPLICABLE)

Not applicable.

  - Sustainability

In order to ensure sustainability for NA and business statistics, ASK should ensure sufficient financial and human resources order to increase efficiency and functionality and thus stability within the office. ASK is currently in the process of internal reorganization which is expected to increase the accountability of officials in charge of the particular project as the responsible persons should be assigned for each activity at the beginning of the project.;

Finally, the Business register needs to include both NASE Rev.1 and NACE Rev. 2 classification codes for all entities.

  - Assumptions and preconditions

The main assumptions and preconditions are as follows:

- Sufficient resources (human and material) allocated to achieve project outputs.

- Effective communication and active participation of all stakeholders.

- More sufficient and qualified staff in ASK

- Data provided by Tax administration and Agency for registration of businesses and other administrative data providers in Kosovo for timely updating of business register.

- Reorganisation of ASK together with the 5 year work plan and statistical programme has been prepared.

4. Implementation issues

The project will be implemented through 1 twinning contract of € 1.5 million.

The project will be implemented over a period of 24 months.

4.1	Indicative budget

Indicative Project budget (amounts in €) (for centralised management)

| PROJECT TITLE |  |  |  | SOURCES OF FUNDING |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | TOTAL EXPENDITURE | IPA CONTRIBUTION |  | BENEFICIARY CONTRIBUTION |  |  |  |  | PRIVATE CONTRIBUTION |  |
|  | IB (1) | INV (1) | EUR (a)=(b)+(c)+(d) | € (b) | % (2) | Total € (c)=(x)+(y)+(z) | % (2) | Central € (x) | Regional/Local € (y) | IFIs € (z) | € (d) | % (2) |
| Contract (Twinning) | X |  | 1.5 | 1.5 | 100 |  |  |  | - | - | - | - |
| TOTAL IB |  |  | 1.5 | 1.5 | 100 |  |  |  | - | - | - | - |
| TOTAL INV |  |  | - | - | - | - | - | - | - | - | - | - |
| TOTAL PROJECT |  |  | 1.5 | 1.5 | 100 |  |  |  | - | - | - | - |

NOTE: DO NOT MIX IB AND INV IN THE SAME ACTIVITY ROW. USE SEPARATE ROW. Amounts net of VAT

(1)	In the Activity row, use "X" to identify whether IB or INV

(2)	Expressed in % of the Total Expenditure (column (a)

There is no specific co-financing for this project, it will be mainly in-kind contribution from the beneficiary i.e. office space for the project, conference rooms for events and other logistical support, whereas the government contribution on Statistics comes from the Agriculture Census project (under the Support to Agriculture and Rural Development sector) whereby the Government has committed a total of EUR 0.5 million co-financing.

4.2	Indicative Implementation Schedule (periods broken down by quarter)

Dates indicated in the schedule cannot go beyond the contracting and execution deadlines in the financing proposal

| Contracts | Start of Tendering/ Call for proposals | Signature of contract | Project Completion |
| --- | --- | --- | --- |
| Contract | Q4 2012 | Q2 2013 | Q2 2015 |

4.3	Cross cutting issues

4.3.1	Equal Opportunities and non discrimination

Equal opportunity will be taken into account in the preparation of all tender documents and in the recruitment of personnel through the placement of appropriate wording.

4.3.2	Environment and climate change

The project is of a purely technical nature of the does not have a direct impact on environment.

However, during implementation of the project production of printed material will be kept to the strictest minimum.

Disaster resilience and risk prevention and management should be integrated in the planning, preparation and implementation of projects.

4.3.3	Minorities and vulnerable groups

Beneficiaries' staff will have to be appropriately sensitised to the principles of fair treatment of minorities in public sector employment policy and practice.

Reliable and comprehensive statistics will enable policy and decision makers to monitor the key economic and social indicators on ethnic minorities.

4.3.4	Civil Society/Stakeholders involvement

Civil Society/stakeholder involvement will be taken into consideration in all aspects of EU-funded activities in order to support civil society organisations to strengthen their capacities and professionalism, allowing them to engage in an effective dialogue with public and private actors and to monitor developments in areas such as public finance and statistics.

- ANNEX 1: Logical framework matrix in standard format

| LOGFRAME PLANNING MATRIX FOR Project Fiche |  | Project title and number |  | Support to Statistics |
| --- | --- | --- | --- | --- |
|  |  | Contracting period expires 3 years after signing the financing agreement |  | Execution period expires 2 years following the final date for contracting |
|  |  | Total budget | € 1.5 million |  |
|  |  | IPA budget: | € 1.5 million |  |
| Overall objective | Objectively verifiable indicators (OVI) | Sources of Verification |  |  |
| To strengthen the overall statistical system of Kosovo with focus on improving economic statistics and align them with EU standards and to modernise the IT systems and web dissemination. | Expended range and quality of economic statistics in Kosovo. Data published in accordance with the EU standards | SAPD conclusions Government Reports on the implementation of Kosovo budgets ASK website Eurostat’s publications and reports Contractor's report |  |  |
| - Specific objective | - Objectively verifiable indicators (OVI) | - Sources of Verification |  | - Assumptions |
| - Activity 1: Statistics - 1. Strengthen the capacities of ASK and enable ASK to carry out its core activities in a standardised manner, - 2. To improve the quality of annual national accounts and start the compilation of quarterly accounts - 3. To improve structural business statistics and increase the coverage of short-term business statistics, - 4. To strengthen the ASK IT system and web dissemination of statistics. | More user – friendly website for ASK | EC Progress Reports SAPD conclusions ASK website Eurostat publications and reports Contractor's report European Commission progress reports ASK report and Government report |  | Commitment by government Sufficient resources (both human and material resources) Ownership of ASK Absorption capacity |
| - Results | - Objectively verifiable indicators (OVI) | - Sources of Verification |  | Assumptions |
| Activity 1: Statistics Component 1: A quality system for the production of statistics 1. Statistical work plan up dated and followed; 2. Policies and guidelines prepared for the implementation of the quality system. Component 2: Beneficiary accounts 3. Increased compliance with ESA 95, including improvement in the estimation of production, intermediate consumption and value added for all activities of the economy. Estimation of beneficiary accounts in constant prices based on improved price indices. Component 3: Business statistics 4. Improved Structural Business Statistics, including data collection, data processing, timeliness and coverage: 5. New short-term indicators, including industrial production and output prices prepared and published; 6. Short-term statistic according to NACE Rev. 2 prepared and published; 7. Improvements of the Statistical Business Register. Component 4: Information technology system 8. Improved IT system and Programming (software application & data maintained); 9. Developing IT system and Web dissemination. | Standardised procedures for developing statistical products in place Guidelines and manuals for the various steps of the statistical production produced Quality reports according to Eurostat standards prepared in selected domains. Recommendation of Action Plan implemented in production of central accounts. Increased level of alignment with ESA 95 and the acquis. Annual GDP by production and expenditure approach published simultaneously. Response rate for SBS significantly increased. (The response rate is below 50%) Improved timeliness of SBS publication New questionnaires prepared. Pilots surveys carried out. Regular surveys carried out New short-term indicators published. Revised STS time series according to NACE Rev 2 published. Procedure for regular updating of the Statistical Business Register in place. New internal network in place for ASK and regional offices. Modernised web dissemination. | EC Progress Reports SAPD conclusions ASK website Eurostat publications and reports ASK Report Government annual report |  | Stakeholder’s commitment to carry on policy coordination and economic and fiscal surveillance. Stability of staff of, ASK and other institutions involved during implementation. Effective communication and active participation of all stakeholders. |
| Activities to achieve results | Means / contracts | Costs |  | Assumptions |
| Activity 1 – Statistics Component 1: A quality system for the production of statistics 1.1 Review and update on the statistical work plan, implementation of the five-year work programme; 1.2. Define the policies and guidelines for the work of the ASK covering inter alia planning, classifications, questionnaires, instructions, computer applications, data verification, confidentiality, dissemination and publication and to institutionalise the usage of the quality system; 1.3. Training on the concepts of quality management and support in the implantation in especially within the areas of component 2, 3 and 4. Component 2: Beneficiary accounts 2.1. Review of beneficiary accounts and analyses of the available sources. 2.2. Review compilation of annual accounts by production and expenditure approach and in constant and current prices, following ESA 95; 2.3. Implement recommendations of Action Plan and carry out revision of annual beneficiary accounts based on the new sources and improved methodology. Component 3: Business statistics 3.1. Assess the current situation of business statistics and identify available sources, both administrative and statistical sources; 3.2. Revise questionnaires used for the SBS and the data collection system, define list of units and improve the IT system; 3. 3. Design new STS surveys, carry out pilots and start regular production and publishing of short-term indicators for industrial production and output prices; 3.4. Start producing short-term business statistics according to NACE Rev. 2 and revise the time series; 3.5. Upgrade the Statistical Business Register to improve the accuracy of the population of business entities and establish a system for regular updating of the register. Component 4: Information technology system 4.1. Provide training to the ASK IT department based on training needs assessment; 4.2. Build an internal network (Intranet) for ASK and the regional offices; and assist in preparing the technical specifications for the IT supplies contract; 4.3. Improve web dissemination for selected statistics including improvement of ASK’ website to make it a more user-friendly and flexible dissemination tool; 4.4. Develop guidelines for the design of tables and graphs, also to be applied for dissemination on the web; 4.5. Develop a dissemination database, including more complete metadata covering different aspects related to data quality; 4.6. Build up a unified system in the field of information technology. | 1 Twinning contract | € 1.5 million |  | Sufficient resources (both human and material resources) allocated to achieve project outputs. and low turnover. Effective communication and active participation of all stakeholders. Readiness to actively participate in capacity building events. Sufficient and qualified staff available at beneficiary institutions respectively ASK; Clear schedule of activities; Stability of high ranked official and regular reports. |

- Description of Institutional Framework

Kosovo Agency of Statistics (ASK)

Kosovo Agency of Statistics (ASK) was set up as an independent institution in 1999 as an executive agency attached to the Ministry of Public Administration (MPA). ASK is regulated by Law on Official Statistics, Law no. 04/L-036, which entered into force on December 2011. ASK is a professional institution, independent, carrier and distributor of official statistics and coordinator of Kosovo's official statistics, which operates now under the Prime Minister's Office (PMO). ASK sets annually priorities and designing of the work plan for respective year, based on priorities established by ASK Management in cooperation with other stakeholders in the field of official statistical researches.

The main objectives of the Office are to collect, process, analyse and publish statistical data. It also provides evaluations and surveys on demographic, social and economic phenomena in Kosovo. To achieve this objective, the Office uses methodologies, nomenclatures and classifications accepted by international statistical organisations, including Eurostat.

Kosovo Agency of Statistics under the Law on Official Statistics takes different role and content from those that had before the adoption of this law. Therefore in this context, ASK will design a new mid-term five-year plan 2013-2017, which will be the guide of statistical research activities in the future.

- Reference list of relevant laws and regulations only where relevant

Law on Official Statistics, Law no. 04/L-036.

As the derivative of this law ASK is currently preparing the below administrative instructions;

- Administrative direction for restructuring;

- Administrative direction for generating incomes:

- Administrative direction for storage of statistical material.

- Details per EU funded contract(*) where applicable:

One Twinning contract; €1.5 million

The Project Fiche for the twinning contract will be circulated as per EU procedures related to the tendering and contracting of twinning contracts. The period of implementation shall be 24 months.

The twinning partner(s) will be responsible for delivering all the project results. The twinning team will be led by a Project Leader who will have overall management of the inputs of the member state(s). He/she must have good leadership skills and a broad knowledge of policies and processes in the area of statistic and economy.

The team will include:

A Resident Twinning Advisor (RTA) with preferably the following profile:

- A university degree in statistics, economics or another relevant discipline;

- Sound communication skills and previous experience of working in multi-disciplinary and multi-national team;

- Fluency in both written and spoken English;

- A minimum of 10 years of professional experience in official statistics preferably working in a National Statistical Institute of a Member State or in Eurostat;

- A minimum of 3 years professional experience of project and/or team management;

- Expert knowledge in national accounts and business statistics;

- Experience of providing technical assistance and training to Governments in transitional economies would be an asset.

Short-term experts with experience and competence matching the project components should have relevant university degree, professional experience in the relevant field, experience with on-the-job-training and knowledge transfer, fluency in English, computer skills and ability to work in team.

Main outputs expected from the contractor

- A quality system for the production statistics in place

- Increased compliance with ESA 95

- Improved Structural Business Statistics, including data collection, data processing, timeliness and coverage:

- New short-term indicators

- Short-term statistic according to NACE Rev. 2 prepared and published;

- Improved Statistical Business Register.

- Improved IT system and Programming

5. Project visibility activities

The European Union Office in Kosovo has developed clear visibility guidelines and ensures that all projects which are implemented in Kosovo are fully in line with these guidelines. Project visibility is also clearly stipulated in all contractual documents whereby the contractors/implementers are obliged to adhere to all EU visibility requirements.

The total project cost should be net of VAT and/or of other taxes. Should this not be the case, clearly indicate the amount of VAT and the reasons why it is considered eligible.

*	This designation is without prejudice to positions on status, and is in line with UNSCR 1244 and the ICJ Opinion on the Kosovo declaration of independence.