TWINNING PROJECT FICHE

Reinforcement of the Consumer Protection

Framework in Egypt

and Upgrading the Capacity of the Consumer Protection Agency

Prepared on behalf of the

EUROPEAN COMMISSION

Under the

Support to the EU-Egypt Association Agreement Programme (SAAP)
Table of Content

The page number is always 3 for all sections!

List of useful abbreviations	3

1.	BASIC INFORMATION	4

2.	OBJECTIVES	4

2.1.	Overall Objective	4

2.2.	Project Purpose	4

2.3.	Contribution to National Development Plan/Cooperation Agreement/Association Agreement/Action Plan	5

3.	DESCRIPTION	6

3.1.	Background and Justification	6

i.	The Regulatory and Legislative Framework	7

ii.	Institutional Framework and CPA's Internal Capacities	7

3.2.	Linked Activities	12

3.3.	Expected Results	12

3.4.	Activities	14

3.4.1.	Component 1: Legal and Regulatory Framework for Consumer Protection	14

3.4.2.	Component II: Institutional Framework and CPA's Sustainable Capacity	15

3.4.3.	Component III: Consumer Protection Associations	16

3.4.4.	Component IV: Awareness and Information Management	16

3.4.5.	Project Visibility	Error! Bookmark not defined.

3.5.	Means	17

3.5.1 Profile and tasks of the Project Leader (PL)	17

3.5.2 Profile and tasks of the Resident Twinning Advisor (RTA)	17

3.5.4. Profile and tasks of the RTA Assistant	18

3.5.4. Profiles and Tasks of the Short and Medium Term Experts	19

4. INSTITUTIONAL FRAMEWORK OF THE TWINNING PROJECT	24

5. BUDGET	24

6. IMPLEMENTATION ARRANGMENTS	24

6.1. Implementing Agency responsible for tendering, contracting and accounting	24

6.2. Main counterpart in the Beneficiary Country	25

6.3. Contracts	25

7. INDICATIVE IMPLEMENTATION SCHEDULE	25

8. SUSTAINABILITY	26

9. CROSSCUTTING ISSUES	26

10. CONDITIONALITY AND SEQUENCING	26

11.	ANNEXES	26

ANNEX I: Indicative Implementation Timetable for the Project	28

ANNEX II: Logframe planning matrix	29

| # List of useful abbreviations |  |
| --- | --- |
| AA | EU-Egyptian Association Agreement |
| AP | Action Plan |
| BC | Beneficiary Country |
| CCP | OECD Committee on Consumer Policy |
| CLDP | US Federal Trade Commission and US Commercial Law Development Program, Department of Commerce. |
| CPA | Egyptian Consumer Protection Agency |
| CPL | Consumer Protection Law |
| CPSC | US Consumer Product Safety Commission |
| ECD | Delegation of the European Commission in Egypt |
| ENP | European Neighbourhood Policy |
| ICPEN | International Consumer Protection Enforcement Network |
| IS | Information Systems |
| IT | Information Technology |
| MIS | Management Information Systems |
| MOU | Memorandum of Understanding |
| MS | Member State of the European Union |
| MTI | Ministry of Trade and Industry |
| OECD | Organisation for Economic Co-operation and Development |
| PAO | Programme Administration Office in Egypt |
| PL | Project Leader |
| PR | Public Relations |
| PSC | Project Steering Committee |
| RTA | Resident Twinning Advisor |
| SAAP | Support Association Agreement Programme between EU and Egypt |
| SAAP II | Support to the Implementation of the Action Plan and Association Agreement |
| STEs | Short Term Experts |
| USAID | United States Agency for International Development |
| WTO | World Trade Organisation |

STANDARD TWINNING PROJECT FICHE

# BASIC INFORMATION

| - Programme: | Support to the Implementation of the Action Plan and Association Agreement (SAAP II) |
| --- | --- |
| 1.2 Twinning Number: | EG10/ENP-AP/HE/15 |
| 1.3 Title: | Reinforcement of the Consumer Protection Framework in Egypt and Upgrading the Capacity of the Consumer Protection Agency |
| 1.4 Sector: | Health and Consumer Protection |
| 1.5 Beneficiary Country: | Egypt |

# OBJECTIVES

## Overall Objective

To contribute to the overall development of consumer protection framework in Egypt that would best ensure balanced interests of all market stakeholders, safeguard consumers' rights, in line with the pertinent Egypt’s national priorities, and with relevant approximation of national laws to the EU aquis and best practices.

## Project Purpose

To support the Egyptian Consumer Protection Agency (CPA), as the lead national authority, in undertaking the relevant measures to strengthen its core functions and reinforce an effective consumer protection framework. In particular, the project aims at the following:

Development of the legal and regulatory framework of consumer protection in Egypt with relevant approximation to the EU aquis and best practices.

Institutional strengthening of the CPA and reinforcement of its internal capacities (core and supporting/horizontal) functions.

Supporting the CPA in strengthening the capacities of consumer protection agencies and NGOs, with focus on institutional development and the development of synergies among such institutions.

Setting-up/developing CPA’s capacities to communicate and raise the awareness of all relevant stakeholders (including consumers, traders etc.).

## Contribution to National Development Plan/Cooperation Agreement/Association Agreement/Action Plan

The Egyptian Government has embarked on an economic reform and structural adjustment programme since 1991. In recent years, social and political reform dimensions have been integrated in the overall development process. The latest Constitutional amendments in 2006 acknowledged the Country's system as "Democratic" and referred to "citizenship rights" as the foundation for that system.  Developing an enabling framework for citizens and market stakeholders to better communicate and safeguard a fairly competitive environment would contribute to accumulating trust between the Government and Egyptian citizens and improving citizens' participation- which is considered amongst national priorities (Presidential Platform and subsequent Prime Minister's Policy Statement).

It is expected that a twinning project in the area of consumer protection would improve competitiveness of Egyptian products, contribute to trade promotion and access to the EU and international markets, thus, supporting Egypt to fulfilling its trade agreements and priorities. The EU-Egypt agreement on the liberalisation of agricultural products, processed agricultural products and fishery products has entered into force in June 2010 after ratification by the Egyptian Parliament. The core of the Association Agreement is the establishment of a Free Trade Area between the EU and Egypt, which implies reciprocal tariff liberalisation for industrial and agricultural goods. The EU is the first trade partner for Egypt, trade with the EU represents over 40% of Egypt’s total trade . The agreement with Egypt incorporates free trade arrangements for industrial goods, concessionary arrangements for trade in agricultural products, and opens up the prospect for greater liberalisation of trade in services, and farm goods. It is noteworthy that Egypt is also a member of other multilateral and bilateral agreements, in addition to being a member of the World Trade Organisation (WTO).

The twinning project will be in line with the EU-Egyptian Association Agreement (AA) and the European Neighbourhood Policy (ENP)/Action Plan (AP) with Egypt AP. In particular, the AA and AP encourage respective partners to utilise their best endeavours to approximate their respective laws with the EU aquis and standards. The AP refers to "Institutional Twinning" as viable EC instrument to align to the EU standards and best practices, contributing to further integration into the European Union's economic, social and technological structures, thereby enhancing prospects for trade, investment and growth.

Under Article 61 of the AA, co-operation in the field of "consumer protection" is geared to making consumer protection schemes in the European Community and Egypt compatible and should, as far as possible, involve:

Increasing the compatibility of consumer legislation in order to avoid barriers to trade;

Establishing and developing of systems of mutual information on dangerous food and industrial products and interconnecting them (rapid alert systems);

Exchanging of information and experts;

Organising training schemes and supplying technical assistance.

The Twinning project would contribute to the implementation of the Action Plan through the development of an enabling environment to foster the role of the civil society and enhance its capacity to contribute more effectively to the development process.  It would also support the Egyptian government's efforts to protect human rights and fundamental freedoms (AP, 2.1.1).

# DESCRIPTION

## Background and Justification

Consumer protection movement in Egypt is an integral part of national efforts to create a dynamic culture among producers, traders, and consumers, whereas consumers are encouraged to exercise their rights through relevant mechanisms/channels as well as to contribute to better shaping industry value chains through increased efficiency, transparency, and competitiveness of the marketplace.  A well-developed consumer protection mechanism is highly dependent on the institutional and human capacities of government and non-state actors involved, it is also dependent on the level of market efficiency and access to information, as well as laws and regulations directly or indirectly linked to consumer protection.

Although the standing of Egyptian consumers has been progressively regulated since the 1950s through different scattered laws and regulations, the legal system has improved significantly pursuant to the adoption of the Consumer Protection Law in May 2006, and the establishment of the Consumer Protection Agency in 2007. Nevertheless, there are still challenges that impede an effective and efficient functioning of a consumer protection framework in Egypt, related to the following:

- The regulatory and legislative framework

- Institutional framework that governs Consumer Protection and CPA's internal capacities

- Consumer Protection Agencies and NGOs in that field

- Awareness of consumers, traders, and other stakeholders

- It is noteworthy that Egypt has achieved considerable progress in developing its legal and regulatory framework as regards to competition and investment. Having achieved concrete reform steps towards economic reform is a significant catalyst for market efficiency, which reflects much transparency and access to improved quality products.

### The Regulatory and Legislative Framework

The basic legal framework for consumer protection is the Consumer Protection Law (CPL)-adopted on 19 May 2006 and its Implementing Regulation in November 2006. In addition, numerous other pieces of law regulate particular issues related to consumer protection and governed through different other institutions than the CPA. Conflict and/or redundancy of law and jurisdiction are not yet systematically and fully settled. In particular, although the legal scope of Consumer Protection is broad, concepts are regulated superficially in short articles without clear criteria for the application of the substantive rules. The procedural rules in the CPL and in the executive regulations lead to conflict of law/jurisdiction situations for the parties involved in consumer disputes.

Consumer rights are generally formulated in rather general terms in the existing Egyptian legislation which jeopardises effective access to justice even if the consumer is trying to defend his/her rights.

The CPL specifies the mandate of the CPA, which sets the work plans and programmes to protect consumer’s rights, receives and investigates complaints made by the consumers and associations, coordinates with the State’s different authorities to implement the provisions of CPL's executive Regulations.  Relevant authorities and institutions are bound to provide needed information and advice requested by the Agency concerning matters related to the complaints made by consumers and associations. The “Decree of the Minister of Trade and Industry of 2006 on the Enactment of the Executive Regulations of the Consumer Protection Law, issued by Law (67) of 2006”, is mainly dealing with the internal organisation and procedures of the CPA and not specifying further its tasks.

In complaint handling, the mandate of the CPA is limited to assistance when dealing with products. However, the Agency is planning to deepen competencies in this area also as regards other administrations which undertake their own complaint handling services (such as electricity, water, real estate, public transport etc.).

The work of the consumer NGOs follows the regulations of the CPL; as far as donations are concerned, it was also referred to the Non-Governmental Organization Law, which provides different possibilities of getting donations (Article 17). Harmonisation of legal conflicts/redundancy is highly needed.

Through the twinning project, there will be an opportunity to review the existing legislations, and provide suggestions for amendments, or additions (for instance, the possibility to include provisions for protecting consumer children).

### Institutional Framework and CPA's Internal Capacities

CPA is a government independent legal entity affiliated to the Ministry of Trade & Industry. It has two offices in Cairo and started to extend its outreach programmes through branch offices in other governorates such as Alexandria and Sharqiya. The total number of the CPA workforce is about 80 employees, as of June 2010.

At present, it is difficult to recognize a clear system in the administrative structure of consumer protection in Egypt. Several authorities base their mandates/some consumer protection related functions on laws and regulations dealing with, for instance: market surveillance, operating laboratories, providing assistance to consumers. Even within the jurisdiction of the Ministry of Trade and Industry, several sub-authorities are performing similar or equal functions (particularly as regards to complaint handling). Consumers may have to consult different authorities before effectively seeking assistance (e.g. the CPA Complaint Handling Division when the consumer intends to complain about products, several regulatory bodies when public services are at stake, the Ministry of Finance for financial services, the Supply Police in cases of misbehaviour of shopkeepers like wrong labelling or stockpiling of products, etc.

As one reform alternative, the CPA is not yet entitled to perform the function of a central institution which receives and re-directs complaints to the relevant authorities. Regardless of the possible ranges of further regulatory and institutional reform steps, individual consumers should know the specific channels through which they may turn to.

The Consumer Protection Law regulates in detail the tasks and the structure of the Consumer Protection Agency (in articles 12-22). It also describes the tasks and the rights of the consumer associations (in article 23). In the same article, a “Special Union” to be formed by consumer associations is mentioned, which does not yet exist. However, several (local) consumer associations formed already two umbrella organisations which might be considered as the precursors of the future “Special Union” of consumer associations at national level.

Article 13 of the CPL is listing up a series of institutions which – besides of the Ministry of Trade and Industry, which is the apex body of the CPA – are forming the Board of Directors of the CPA. These are:

The Special Union of consumer associations, at present replaced by qualified members of consumer associations, appointed by the Ministry of Trade and Industry on proposal of the associations;

The Central Consumer Cooperative Association;

The General Association of Chambers of Commerce; and

The Association of Egyptian Industries.

The CPA coordinates with other government partners through numerous channels; mainly the Consumer Protection Supreme Committee (reports to the MTI Minister). In addition, there is coordination between the CPA (through complaints handling.  and comparative studies/research) and: the i) Supply Police ii) Ministry of Health iii) Internal trade authority. One of the challenges which face the CPA is the mechanism for better inter-institutional coordination.

Since its establishment in 2006, the CPA received 27004 complaints, of which 86% were solved. The total number of court cased during the same period were 148 cases, 85 cases of them were ruled for the interest of the CPA and 29 other cases were filed due to the yield of the consumers after their settlements.  It is worth mentioning that the CPA did not lose any case.

The following is the current organisation structure of CPA:

Executive Director

Market Intelligence & Research Division

Management

Division

IT

Chairman

Board of Directors

Quality and Specs Auth.

Enforcement Division

Other authorities

Industrial Inspectorate

Administration & HR

Financial Office

Legal affairs & Govt. relations

Consumer complaints

NGO’s

Call Center, Website

Mail, Complaint center

NGO’s Outreach Division

Awareness Division (monitoring of advertising education & awareness)

Dispute Committee

Purchasing & Warehouse

Investigation coordination Unit

Secretariats

Secretariats

Higher complaints committee

Engineering

Auto

Media

Compl. Committees

International Relations Division

Remarks:

Two other Divisions/Functions were foreseen but not set up so far:

A Division dealing with consumer education, awareness campaigning, marketing and PR, where awareness function should address citizens, producers and shopkeepers:

A Division in charge of Market Intelligence, particularly with the monitoring of deceptive advertisement and of unfair terms of contract.

It is also envisaged through the legal mandate to set up the “consumer research function”, there are possible alternatives for further upgrading consumer research capacities, for instance to empower (as already the case) some consumer protection organisations and NGOs to conduct such studies in collaboration with CPA. The extent to which the CPA should engage itself in conducting research should be further assessed within the framework of the twinning project. One challenge that faces consumer agencies & NGOs is to raise funds for research.

- Given that the NGO Outreach Division in the CPA already has accumulated experiences with fund raising for conducting research studies, the Twinning Project might contribute to developing the capacities of existing NGOs and consumer agencies to raise funds.

- As regards complaint handling, numerous authorities are dealing with complaint handling. The centralisation of these activities in the CPA might not be feasible because of legal obligations of other authorities to provide assistance to individual consumers, and also because the subjects of complaints arriving in these authorities may be more closely related to the main tasks of the correspondent authorities.  Nevertheless, there is a need to “harmonise” assistance through common training in complaint-related matter, access to and usage of a common database and consumer protection portal for complaint handling, advice giving techniques, and other relevant services.  Depending on further institutional and legal diagnoses and training needs assessment, such training might be coordinated/ provided.

- Consumer Protection Agencies and NGOs

- The CPL provides six rights specifically granted to consumer protection associations:

To bring legal actions related to consumers’ interests or intervene in them;

To carry out surveys, comparative studies (including price and quality comparisons), to verify the correctness of related data that indicate contents of products and services, and to notify the concerned entities of violations in such regard;

To present information to the concerned governmental entities concerning problems related to the consumers’ rights and interests, and to present recommendations for mitigating such problems;

To receive and verify individual consumers’ complaints

To assist consumers who have been prejudiced as a result of buying the commodity or receiving the service in making complaints to the concerned entities, including the CPA, and to undertake the necessary legal measures to protect the consumers’ rights and interests;

To participate in spreading the culture of consumer rights and to improve citizens’ awareness of their rights, and to establish the necessary databases to fulfil their functions;

- Grants or financial aid to consumer organisations by businesses are prohibited by law.

- These rights of the consumer associations are in general in conformity with the five consumer rights recognized in 1975 by the Council of the European Economic Community and the consumer rights adopted by the UN 1985 and amended in 1998.

- There is a need for consumer organisations to have different sources of funding, to allow such organisations to operate with greater independence and to ensure sustainability. Some financial support granted by the CPA to selected Consumer Organisations for a limited time span proved to be an effective tool to lay the ground for professional development of the NGOs.

In this context, and since 2009, the CPA’s financial support to the consumer protection NGOs in Egypt has been through two main approaches:

  - Top-down strategy: Coordination with the USAID to provide funds necessary to finance the activities of two umbrella NGOs, in Cairo and Alexandria, that will work through network relationships with community -based consumer organizations all over Egypt, in order to ensure proper consumer protection service delivery to the most remote areas

  - Bottom-up strategy: Providing 14 NGOs located all over Egypt with monthly financial allowances to perform a set of agreed upon consumer protection activities. Work plans are approved, and achievements evaluated, on a monthly basis.

In addition, CPA provides them with the necessary financial support to conduct various comparative market research studies

- However, Consumer Organisations are still weak and scattered into many small organisations; they hardly can fulfil their role as consumer advocates and as sources of neutral consumer information. Networking and effective communication among existing organisations is not therefore at optimum level, relevant mechanisms and tools should be embedded to effectuate an umbrella organisation and improve networking (different umbrellas at the local/regional level do exist, the ultimate objective is to strengthen their roles at the local level, and at a subsequent stage, a consolidation of the efforts and coordination mechanisms of these umbrellas would be aggregated at the state level through an overall umbrella for consumer protection).

- In terms of organisations' “specialisation”, there is limited diversification in terms of areas or sectors.  Most of these organisations deal with product safety. There is a need to ensure relevant and wide-ranged consumer representation.

- Consumer organisations’ knowledge of CPL and all related consumer rights should be improved in order to effectively accomplish their mandate. There is a need for by-laws/statutes describing the specific tasks of such and/or rules of procedures necessary to regulate internal responsibilities/tasks. Further assessment and concrete steps should be undertaken to develop the internal capacities of such organisations, in conformity with the existing law/s, or to propose for possible amendments in the legal framework/regulations.

- The division of the NGOs outreach at the CPA plays a key role as a contact point between the consumer NGOs and the CPA. It aims to provide them with all the necessary technical support and guidance in order to ensure harmonization between these NGO's activities and plans and the CPA's goals.

- Awareness of Consumers, Traders, and Other Stakeholders

- Consumer awareness of their rights is widely lacking among Egyptian consumers. It is also perceived as one of the biggest obstacles to improve relations between businesses and consumers. Awareness problem is not just one of consumers; many – especially small – shopkeepers are lacking the necessary knowledge of consumer rights as well. In cooperation with the business community, particularly with the Chambers of Commerce and Industry, as well as the media (which by itself needs sufficient awareness), the CPA should be enabled to lead nationwide consumer education movement.

- The CPA plans to enhance the Division for awareness/outreach and external communication, it is envisaged that the Twinning project would support the CPA in setting-up/developing sustainable capacities related to awareness and communication with all relevant stakeholders.

## Linked Activities

Since its establishment, CPA managed to undertake the following activities:

- Arranged a number of workshops and seminars in Cairo/ Egypt with the financial and technical support of the US Federal Trade Commission and US Commercial Law Development Program (CLDP), Department of Commerce.

- Worked with the USAID in a number of awareness campaigns since the its’ establishment.

- Became a member at the International Consumer Protection Enforcement Network (ICPEN) since 2007 where the CPA benefits from the accumulated experiences and best practices of the member countries as well as engages in the network enforcement & awareness joint projects.

- An observer member at the OECD Committee on Consumer Policy (CCP) with an aim to benefit from the research studies and policies proposals in the field of product safety, consumer education and e-commerce, in addition to integrate the challenges of the Egyptian market and its region into the scope of the OECD for further discussion.

- CPA signed a Memorandum of Understanding (MOU) with the US Consumer Product Safety Commission (CPSC) for technical cooperation.

- Signed a MOU with the Saudi Arabia Consumer Protection Organization for technical cooperation.

- Signed a MOU with the French General Directorate for Competition policy, Consumer Affairs and Fraud Control

These MOUs were adopted to enhance bilateral technical cooperation and to exchange information and data about product recalls and safety hazards.

## Expected Results

Result 1: A simple legal framework and better representation of consumers’ interests is proposed drawing on EU best practice in the field and measures for better enforcement are defined and initiated, focusing on the following core areas:

- All legislations that directly or indirectly relate to consumer protection

- Jurisdictions of the CPA and other administrations

- Legal responsibilities of Consumer Agencies

- Sources of legal related data and information, and information access and dissemination

Result 2: The CPA is better functioning as the leading agency for consumer protection in Egypt, and relevant mechanism for inter-institutional coordination is proposed, focusing on the following core areas:

- CPA internal structure and process flow.

- Operations’ modalities, structure, and functions of core areas such as research and surveillance (particularly monitoring of advertising and use of unfair contracts, research on consumer behaviour and trends), and other possible core functions (e.g. consumer education, compliant handling, and training functions).

- Inter-institutional consultation and coordination mechanisms, in particular, for monitoring internal market, unfair practices, understanding consumer behaviour and trends, comparative studies, product testing, and any other collective actions to safeguard consumer and public interests.

- Human capacities.

Result 3: The CPA developed its mechanism and capacity to work effectively with the Agencies (the NGO Outreach Division), including improving the capacity of such agencies, focusing on the following areas:

- Internal capacity of the CPA (NGO Outreach Division)

- Capacities of selected number of consumer organisations and the set-up of an umbrella organisation

Result 4: Capacity of the CPA to better communicate with all relevant stakeholders and improve awareness is upgraded including the institutionalisation of the awareness division and its operational mechanisms, focusing on the following areas:

- Networking/functioning mechanisms among the organisations, consumers, CPA, municipalities, and other stakeholders

- The set-up of role-model consumer advice centres/services at the local level

## Activities

### Component 1: Legal and Regulatory Framework for Consumer Protection

This component will support the CPA to identify and propose specific measures to improve the legal and regulatory consumer protection framework, by addressing current shortcomings, with the aim of legal approximation to the relevant EU aquis and best practices.

Focus under this component will address all legislations that directly or indirectly relate to consumer protection, Jurisdictions of the CPA and other administrations, Legal responsibilities of Consumer Agencies and Sources of legal related data and information, and information access and dissemination. Activities should include but not be limited to the following:

- Conducting an assessment of the legal and regulatory context of Consumer Protection system, in comparison to the EU best practices, including analysis of mandate and regulations governing the higher council for consumer protection.

- Proposing reform measures for developing the legal and regulatory context for consumer protection in line with the EU acquis will be presented and approved by the CPA. Measures (including an update legal draft) should address all shortcomings and other enforcement challenges, particularly those related to conflicts of jurisdictions, improving CPA’s capacity to better function as the leading consumer protection agency. The proposed reform measures should address both primary and secondary legislations, and should pave the way for implementing gradual reforms in priority areas specified in this project (all other components). Furthermore, the project should assist the CPA to propose relevant legal reforms to improve coordination aspects at the ministries' level, and among CPA, relevant administrations, and stakeholders (including Consumer Associations and others).

- Designing and putting in place a database/library for legal-related consumer protection information. The database should indicatively include all pertinent laws, regulations, and final litigations relevant to consumer protection (e.g. quality and industrial standards applicable in Egypt in the field of consumer protection, judicial precedents and, where appropriate, the corresponding executive regulations and administrative practices). It should also include regular updates of legal precedents and information from other relevant divisions (e.g. Complaint Handling). The database should be nucleus to developing an effective knowledge management system within the CPA, linked and accessible to other relevant administrations, and will constitute the backbone of the “external communication and awareness mechanism, as well as Complaint Handling Divisions).

- Designing and conducting tailored training, based on proposed reform measures, covering manual of operations for developing and maintaining the database. Mechanisms/solutions for acquiring/communicating information regarding legal precedents and case handling between the CPA, Consumer Agencies at regional/local level, and other competent authorities (e.g. Ministry of Justice) shall be defined and proposed.

### Component II: Institutional Framework and Capacity Building

This component aims at reinforcing sustainable capacities within the CPA. The project should support the CPA to develop/upgrade the appropriate set up for inter-institutional framework for consumer protection (e.g. functioning modality and capacity building for improved consultation and coordination mechanisms). Upon completion of that component, the CPA should better function as the leading agency for consumer protection in Egypt, and relevant mechanism for inter-institutional coordination will be proposed.

Focus under this component will address CPA organisational development and institutional set-up, Operations’ modalities, structure, and functions of core areas such as research and surveillance (particularly monitoring of advertising and use of unfair contracts, research on consumer behaviour and trends), and other possible core functions (e.g. consumer education, complaint handling, and training functions).

Also inter-institutional consultation and coordination mechanisms, in particular, for monitoring internal market, unfair practices, understanding consumer behaviour and trends, comparative studies, product testing, and any other collective actions to safeguard consumer and public interests, in addition to CPA’s horizontal functions and its entailed human capacities. Activities should include but not be limited to the following:

- Conducting diagnostic analysis of CPA and the institutional framework for consumer protection in Egypt benchmarking them to best practices in selected EU Member States.

- Proposing reform measures with recommendations for a developed structure of CPA’s core functions and interdepartmental linkages.

- Defining mandate of the inter-institutional consultation and proposing coordination mechanisms with specific tasks and reform measures

- Developing a roadmap for CPA Organisational development an institutional framework among different administrations

- Improving the Complaint Handling Division by building and raising the capacity of the division team and developing effectiveness and efficiency complaint handling cycle

- Upgrading CPA capacity to outreach and better communicate with all relevant stakeholders, this shall include the institutionalisation of the Outreach Division

- Building CPA capacity to improve awareness including operations mechanisms

- Conducting an assessment of current functions, capacities and practices of Market Intelligence and Research.

- Proposing institutional and operational measures to develop/upgrade the Market Intelligence and Research functions within the CPA focusing on "monitoring of advertising" and initiate implementation

- Conducting regular updates, specialised studies and comparative testing in relation to market Intelligence and Research functions

- Upgrading CPA capacities to perform market Intelligence and Research functions.

- Upgrading CPA capacity to communicate relevant information within the CPA and with the public.

- Defining the organisational-related information outputs/deliverables/flows

- Upgrading the capacity of the Information Technology Division

- Conducting an assessment for "product recall"

- Setting up mechanisms and measures for "product recall" and initiate implementation

- Proposing and assisting in implementing institutional measures to set-up the training function at CPA and improving capacities of related staff.

### Component III: Consumer Protection Associations

This component will support the CPA to reinforce capacities of the Consumer Agencies and their overall functioning network/umbrella. Upon completion of this component, the CPA will have developed its mechanism and capacity to work effectively with the Agencies (the NGO Outreach Division). Activities should include but not be limited to:

- Assessing the capacities of CPA in relation to reinforcing the roles of the Consumer Protection Associations.

- Assessing the capacities of the existing and potential umbrella Associations.

- Assisting the CPA in designing and implementing a capacity building program for selected Associations.

- Proposing effective Networking mechanisms among the organisations, consumers, CPA, municipalities, and other stakeholders.

- Developing a pilot project to upgrade the human, institutional, and operational capacity of role-model consumer advice centre/services at the local level.

- Internal capacity of the CPA (NGO Outreach Division)

- Capacities of selected number of consumer organisations and

### Component IV: Awareness and Information Management and Visibility

This component will support CPA promoting its activities and improving communication among its stakeholders, this will take place through a web portal that will serve as an interactive communication interface between the CPA and different stakeholders, and with consumers and producers- the public in general. The Complaint Handling Division and other administrations will be able to communicate via this portal. Awareness activities and other relevant information about consumer protection will be also available on this portal.

Upon completion of this component, the CPA will have developed its awareness department with efficient staff and effective mechanisms. Activities should include but not be limited to:

- Assessing the current awareness capacity/activities at the CPA.

- Proposing relevant institutional and operational measures to set up an awareness division.

- Conducting selected awareness activities.

- Designing and launching a portal for consumer protection related information building on the current CPA website www.cpa.gov.eg, this portal will serve as an interactive communication interface between the CPA and different stakeholders, and with consumers and producers - the public in general, linked to complaint handling division and awareness.

- Drafting a tender dossier for the needed equipment and software for the consumer protection portal and installed data bases, including staff training.

Throughout the course of the project, enough visibility should be given to the achievements. This will notably be achieved through  the following promotional activities:

- Conducting a kick off meeting at the beginning of the project inviting all stakeholders to provide them with a background on the project components, this activity takes place with the aim of increasing project visibility.

- Holding a final meeting to ensure that the results achieved by the end of the project are made available to all stakeholders, this activity will be held to ensure awareness and visibility.

## Means

### 3.5.1 Profile and tasks of the Project Leader (PL)

The Project Leader will be responsible for the overall conception and direction of the MS involvement in the twinning project. The PL will be expected to devote a minimum of 3 days per month to the project in his home administration. In addition, he/she will be responsible for the organisation, from the Member State side and in coordination with the BC Project Leader, the Project Steering Committee (PSC), which will meet in Egypt at least every three months.

Tasks

The main tasks of the Member State (MS) Project Leader are to ensure:

- The overall coordination of the Project;

- The achievement of the mandatory results.

- The overall follow-up on the project progress.

Profile

- Long-term civil servant from a Member State administration with at least 10 years experience in consumer protection.

- Have relevant education or experience in the field of project management, institutional development and supervision of consumer protection projects.

- Excellent command of written and spoken English.

- Excellent inter-personal and leadership skills.

- Experience or relevant knowledge of ENPI context/reforms is advantageous.

- University degree or higher in a relevant field.

- Experience/knowledge of reforms in ENP/Eastern European countries is an asset.

### 3.5.2 Profile and tasks of the Resident Twinning Advisor (RTA) and RTA Assistant

a) The Resident Twinning Advisor (RTA) will provide at least 24 months input on site. S/he will lead all aspects of the work of the MS team and will work directly with the BC project leader and RTA counterpart on a daily basis to support and coordinate the activities being implemented in the BC. His/her role is not purely administrative as the RTA is expected to provide high level advice and direction on all project activities.

Tasks

- Manage the day-to-day coordination and progress of the project's activities (necessary office accommodation will be provided by the CPA)

- Liaise with the Beneficiary Country (BC) Project Leader and RTA counterpart

- Report to the MS Project Leader

- Liaise with the CPA relevant staff and other Egyptian administrations

- Follow up progress in reform areas/policy developments at the national level that are relevant to the project.

- Excellent inter-personal and leadership skills

- The RTA is expected to ensure, together with the host administration, the achievement of the results mentioned. In order to meet these objectives the expert may propose alternative and/or complementary project activities and/or outputs to those identified, if regarded as necessary and justified.

- Previous experience in similar  projects would be an advantage

Profile

- Senior civil servant, with a minimum of 10 years of experience, from a Member State administration.  Experiences in the consumer protection field and the EU related legislations and European best practices are required.

- Previous experience in project management/coordination (preferably coordination of a multi-disciplinary team).

- Experience in institutional capacity building projects/interventions, and a regulatory reform is highly preferable.

- Excellent command of written and spoken English.

- Previous experience in EU funded twinning projects is advantageous.

- Experience/knowledge with ENP/Eastern European countries context is an asset.

b) The RTA will have an Assistant, who will support him/her in the performance of his/her duties during the entire project period. S/he should be well aware of the local conditions and support the PL, RTA and STEs during the project period.

- The RTA assistant is expected to have the capability to:

- Translate from Arabic to English and vice versa;

- Act as interpreter in discussions with stakeholders in the project;

- Give advice and assistance for travelling schedules, ticket and hotel reservations etc;

- Excellent computer skills;

- Assist in the work with drafting of financing and activity reports;

- Excellent communication skills;

- It is expected that the RTA assistant have relevant academic degree and training to succeed in the above mentioned tasks.

Working Groups

The establishment of one or more Working Groups should be considered. These groups should meet regularly to review progress, schedule activities and address any issues or constraints that may have arisen.

The membership of this/these Working Groups should be selected by the Beneficiary Institutions and should be conveyed to the Contracting Authority during the Inception Phase.

### 3.5.3. Profiles and Tasks of the Short and Medium Term Experts

| Type | Task | Profile |
| --- | --- | --- |
| Component I: Legal and Regulatory Reform |  |  |
| Short-term Legal Experts | Conduct an assessment of the legal and regulatory framework, in line with the European acquis and best practices in selected Member States. Assist in drafting legal and regulatory reform measures and approximations. Participate in, and lead the process of setting up the legal-information database, in coordination with the IT and information experts, and the CPA assigned staff. | - University degree in law. - at least 8 years of experience in developing and enforcing legal reforms (adoption or approximation of the EU relevant consumer protection acquis) - Experience in the EU legal practices of consumer protection is highly preferable. |

| Component II: Institutional Framework and CPA Internal Capacity |  |  |
| --- | --- | --- |
| Medium-term Expert in Organisational and Institutional Development | The medium-term expert will be in charge of the following tasks: Lead and undertake the diagnostic analysis and proposed measures of the institutional framework and internal structure of the CPA. Act as the component II leader. | - At least 7 years of experience in institutional and organisational development. - Experience in consumer protection field is required. |
| Short-Term Experts for Complaint Handling | Undertake a review of the Complaint Handling Cycle and capacity and advise on proposed reforms. Assist the CPA in implementing reforms and provide relevant training/coaching. | - Good experience in the field of consumer protection and complaint handling function. - University degree in law or any other relevant field. |
| Short-term expert for Outreach and Awareness | Define the mandate, responsibilities, and resources needed for developing the function of outreach and awareness at the CPA. Assist the CPA to put in place the institutional set-up of the outreach function, and draft the manual of operations. Assisting the CPA in developing an Annual Action Plan for the Outreach and Awareness division and conducting selected awareness activities. Providing training/coaching to selected CPA staff. | - At least 7 years of experience in the field of consumer protection and external communication/consumer relations. - University degree in management, mass communication, or any other relevant field. |
| Short-term experts for market surveillance and research | Assessment of current mandate, capacities and activities of the surveillance and research functions. Advise and assist in implementing institutional and operational measures to developing/upgrading the two functions within the CPA. Providing training/coaching to selected CPA staff. | - Good experience in market surveillance and consumer protection field. - Familiarity with different national models for surveillance, including monitoring of advertising and unfair deceptive practices. - Good experience in market research, in particular consumer protection field. - Experience in institutional development is an asset. |
| Short-term Experts for Training Capacity | Define the mandate, responsibilities, and resources needed for developing the Training Division/function at the CPA. Assist the CPA to put in place the institutional set-up and draft the training division manual of operations. Assisting the CPA in developing an Annual Action Plan for the Training division. Providing training/coaching to selected CPA staff. | - Post graduate degree in Human Resources Management or Management. - Strong experience in human capacity building and the training field. - Familiarity with different training and coaching approaches such as Train of the Trainer and e-learning. |

| Component III: Consumer Protection Associations |  |  |
| --- | --- | --- |
| Medium term and Short term experts for Consumer Protection Associations | Conduct an assessment of the internal CPA capacity to reinforce consumer protection associations. Conduct an assessment of consumer protection associations and related umbrellas. Design a capacity building programme for the CPA related staff and consumer protection associations. Lead the implementation of the capacity building programme. Lead the implementation of a pilot project at the local level for consumer advice services. Short term experts for implementing the capacity building programme The experts will assist the MTE in designing the capacity building programme. Delivering training in selected areas such as project management, public relations, etc. | Medium term Expert for Consumer Protection Associations - At least 7 years of experience in Non-Government Organisations, in particular leading/coordinating with consumer protection associations. - Experience in designing capacity building related programmes is required. - Knowledge of different models of consumer protection associations and mechanisms of networking umbrellas. - Familiarity with the work modalities and perquisites for setting up consumer advice centres/units. Short experts for implementing the capacity building programme - Extensive experience in designing and delivering training modules designed for consumer protection associations/stakeholders |

| Component IV: Awareness and Information Management and Visibility |  |  |
| --- | --- | --- |
| Short-term experts for Awareness | Define the mandate, responsibilities, and resources needed for developing the function of outreach and awareness at the CPA. Assist the CPA to put in place the institutional set-up of the outreach function, and draft the manual of operations. | - Extensive experience in the field of consumer protection and external communication/consumer relations. - University degree in management, mass communication, or any other relevant field. |
| Short-term experts for information and content management | Assisting the CPA in developing an Annual Action Plan for the Outreach and Awareness division and conducting selected awareness activities. Providing training/coaching to selected CPA staff. | - Extensive experience in the field of information and content management, in particular in consumer protection related area. - Excellent command of English language. |
| Short-term IT/MIS Experts | Drafting tender dossier for the needed equipment and software. Train assigned CPA staff to install and use the new system/equipment/software | - University degree in IT - Extensive experience in the field of information technology and MIS. - Experience in drafting tender dossier and EU procurement procedures is an asset. - Excellent command of English language. |
| Short-term Experts in portal web-design | Assist in defining and lead the preparation of the Consumer Portal's content. Assist in designing and launching the portal's first edition. | - Good experience in the field of web/portal design, particularly, consumer protection related area. |

N.B. All experts should be proficient in the English Language (both written and spoken)

Previous experience in ENP countries will be considered an asset.

# 4. INSTITUTIONAL FRAMEWORK OF THE TWINNING PROJECT

Most of the Twinning activities will be undertaken in CPA, as the direct beneficiary of this twinning project. CPA’s main office is located in Cairo, with the possibility to implement pilots under some components in selected governorates/districts. All relevant Divisions related to the project components within CPA will be involved.

The BC is committed to make available the necessary office space and equipment for the MS partners to carry the project's activities. This includes access to the Internet as well as computer/s and necessary equipment (printer, photocopier, telephone, fax, etc.). It also includes the provision of suitable venues/material/equipment for training and meetings in the BC. During the implementation period, the RTA will be accommodated with an appropriate office space and communication tools.

The Beneficiary administration will be committed to assign relevant staff to cooperate and work closely with their MS counterparts. CPA will assign two main staff members:

- Egyptian Project Leader

The Egyptian Project Leader (PL) is a senior civil servant at decision maker level. H/She will act as the counterpart of the Member State PL. H/She will ensure the overall steering and coordination of the project from the Egyptian side, including proper policy dialogue and political support.

The PL's seniority will ensure his/her ability to mobilize the necessary staff in support of the efficient implementation of the project.

H/She will lead/coordinate Project Steering Committee (PSC) from the Egyptian side.

- RTA Counterpart

The RTA Counterpart is a senior civil servant who will work with the RTA on a daily basis to ensure proper coordination and implementation of all the activities of the project and achieve an efficient transfer of knowledge and information. He/she may be involved in one or more of the components of the twinning fiche and should preferably have good command of written and spoken. He/she will be responsible, together with the RTA, of finalizing the reports to be submitted to the PLs which will be discussed and approved by the Project's Steering Committee.

# 5. BUDGET

The maximum estimated budget for this twinning project is 1.400.000 Euros.

# 6. IMPLEMENTATION ARRANGMENTS

## 6.1. Implementing Agency responsible for tendering, contracting and accounting

The Programme Administration Office (PAO) is in charge of the coordination of all the activities and the administrative management of the Support to the Association Agreement Programme. The PAO will be the responsible institution for the management of this twinning project. It manages the tenders, contracts and payments and this, in accordance with the procedures of ex-ante control defined in the Practical Guide to contract procedures financed from the General Budget of the EC in the context of external actions.

Contact person at the PAO:

Name: Mrs. Riham El-Ezaby

Title: Projects Manager

Address: 9 Abd El-Kader Hamza St., Garden City, Cairo, Egypt

Tel.: +202 279 3438

Fax: +202 792 05 83

Email: riham.elezaby@ee-aa.net

## 6.2. Main counterpart in the Beneficiary Country

Consumer Protection Authority

Project Leader Counterpart

Name: Mr. Amr Fahim

Title: Executive Director

Address: 96 Ahmed Oraby St., Mohandessin, Giza, Egypt

Tel: +202 33055795-7

Fax: +202 33055753

Email: afahim@cpa.gov.eg

RTA counterpart

Name: Mr. Ahmed Bedewi

Title: External Relations Manager

Address: 96 Ahmed Oraby St., Mohandessin, Giza, Egypt

Tel: +202 33055795-7

Fax: +202 33055753

Email: ahmed@cpa.gov.eg

## 6.3. Contracts

The PAO intends to enter into Supply Contracts as required for the different components of the twinning project. This will be funded separately from the SAAP budget. The supply will be provided upon the needs assessment that will be undertaken by the experts during the implementation of the twinning project.

There may also be other outsourcing contracts linked to the Twinning Project, but not part of it. These will be the responsibility of the beneficiary.

# 7. INDICATIVE IMPLEMENTATION SCHEDULE

7.1	Launching of the call for proposals: February/March, 2010

7.2	Start of project activities: December, 2011

7.3	Project completion: November, 2013

7.4	Duration of the execution period: 27 months

# 8. SUSTAINABILITY

The transfer of knowledge by institutional twinning with a corresponding EU institution is expected to provide sustainable developments; this is envisaged if the results outlined are fully achieved. To maximise sustainability there must be a particular focus on maintaining leadership by CPA management and continuous training programmes.

# 9. CROSSCUTTING ISSUES

Equal opportunity principles and practices in ensuring equitable gender participation in the project will be guaranteed. Male and female participation in the project will be based on the relevant standards of the EU. The main criteria for staff recruitment will be appropriate qualifications and experience in similar projects, not sex or age. Both men and women will have equal opportunities and salaries.

# 10. CONDITIONALITY AND SEQUENCING

The success of this Twinning Program will, basically, hinge upon two elements:

  - The full political support of the Egyptian governmental authorities to fully modernize the structure and functions of CPA.

  - The support of CPA management officers and staff regarding the RTA activities and the Twinning project.

In general, the CPA will be committed, within its available budget, to allocate needed human and financial resources to set-up proposed Divisions/functions. The twinning project will contribute to building capacity of those Division/assigned team.

Other minor commitments, such as the provision by CPA authorities of premises for RTA activities and several auxiliary manpower hours are of the minor relevance for the success of the project. Training infrastructure and equipment will be also provided by the Egyptian authorities, but some exceptional training tools.

The BC will also ensure operational and logistical support to the RTA and the Twinning experts in terms of ensuring operational coordination with the other Egyptian Public institutions, aside CPA, involved in the project, collecting and processing the information needed and to provide contacts and information concerning private entities that would be involved during the Twinning activities.

The underlined idea for the successful implementation of the Twinning is that the CPA employees will be fully supportive of Twinning activities.

# ANNEXES

- Indicative Implementation Timetable for the Project

- Logical framework Planning Matrix

## ANNEX I: Indicative Implementation Timetable for the Project

Reinforcement of the Consumer Protection Framework in Egypt and Upgrading the Capacity of the Consumer Protection Agency

| Year | 2011 |  |  |  |  |  |  |  |  |  | 2012 |  |  |  |  |  |  |  |  |  |  |  | 2013 |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N |
| Launch | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Selection |  |  | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contracting |  |  |  | x | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Implementation |  |  |  |  |  |  |  |  |  | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |

ANNEX II: Logframe planning matrix

Programme: Modernisation of the Consumer Protection Framework, practices, and institutional capacity

| Overall Objective | Benchmarks |
| --- | --- |
| To contribute to the overall development of consumer protection framework in Egypt that would best ensure balanced interests of all market stakeholders, safeguard consumers' rights, in line with the pertinent Egypt’s national priorities, and with relevant approximation of national laws to the EU acquis and best practices. |  |
| Project Purpose | Benchmarks | Source of information | Assumptions |
| To support the Egyptian Consumer Protection Agency (CPA), as the lead national authority, in undertaking the relevant measures to strengthen its core functions and reinforce an effective consumer protection framework. | Egypt's Consumer Policy is developed, discussed among all relevant stakeholders, presented, approved, and publicised. | - Official government reports. - Press statements. - Public opinion polls/surveys - Project's progress reports - ENP Subcommittee and progress reports | Commitment of the Egyptian Government to pursue reform in that area, in particular, Ministry of Trade and Industry. This should entail strong political backing. Allocation of sufficient human and financial resources needed to efficiently implement the project activities and ensure the sustainability of this project after its finalisation. Commitment and appropriate level of coordination among all stakeholders involved in the different project levels and areas. |

| Results | Benchmarks | Source of information | Assumptions |
| --- | --- | --- | --- |
| Component I: Legal and Regulatory Framework A simple legal framework and better representation of consumers’ interests is proposed drawing on EU best practice in the field and measures for better enforcement are defined and initiated | Legal and regulatory assessment conducted, in comparison to the EU acquis and best practices. Draft legal documents are presented and approved by the CPA and steps for adoption are initiated. Legal and regulatory reform measures are presented and approved by the CPA. A database/library is set up, including all relevant legislations, decrees, and information about litigations and cases precedents. Relevant staff are trained on the proposed regulatory and enforcement mechanisms; particularly (1) legal reform measures; (2) developing and maintaining the database; (3) communicating with stakeholders. | - Official government reports - Mission reports - Certificate of attendance for trainees - Training evaluation sheets - Approximated legislations published in official journal - Press releases and statements - Mission reports - Assessment Report on Legal and regulatory framework | The CPA & MOT are committed to implement institutional changes Level of resistance to change by other stakeholders does not drastically preclude reform efforts Assigning needed staff for the component Political commitment to support legal framework development |
| Component II: Institutional Framework and CPA’s Sustainable Capacity The CPA is better functioning as the leading agency for consumer protection in Egypt, and relevant mechanism for inter-institutional coordination is proposed. | Assessment and proposed reform measures of the CPA internal set-up and the institutional framework for consumer protection in Egypt are performed. Mandate of the inter-institutional consultation and coordination mechanism is defined, approved by the CPA, and presented for approval at Cabinet level. An Action Plan/Roadmap for CPA organisational development and the overall institutional framework is developed and approved by the CPA. Measures for developing the internal structure and institutional framework are proposed and implementation initiated. Possible means to improve Complaint Handling function and cycle are assessed and proposed, in line with the proposed legal reforms and inherent CPA’s resources. Manual of procedure for the Complaint Handling Cycle is upgraded-developed. Relevant training modules are designed. Training is conducted to selected staff. Assessment report and Action Plan for developing the intelligence function. Assessment report and Action Plan for developing the research function. Feasibility study on developing function of "Comparative Testing". Manuals of operations for the surveillance and research. Assessment developing the training functions at the CPA, including needed resources. Manual of operations for the Training Division, including templates for Training Needs Analysis. Number of staff trained | - CPA’s Organisational Performance Indicators - Consumers’ feedback/comments on services (through website and services) - Mission and progress reports - Communication and Consumer Protection services Functions’ reports - Certificate of attendance and training evaluation sheets - Visibility events - Promotion material - Publications - Divisions' Periodic Reports - MoU between CPA and other administrations - Organisation Policy Statement - Mission and progress reports - Certificate of Attendance | Commitment of the CPA and the MOT to implement the new mechanism. Availability of financial and human resources for the newly established divisions. Timely supply of IT equipment including software |
| Component III: Consumer Protection Associations The CPA developed its mechanism and capacity to work effectively with the Agencies (the NGO Outreach Division), including improving the capacity of such agencies. Component IV: Awareness and Information Management and Visibility Capacity of the CPA to better communicate with all relevant stakeholders and improve awareness is upgraded including the institutionalisation of the awareness division and its operational mechanisms. | Assessment of the CPA internal capacity to outreach and develop NGOs and Consumer Protection Agencies. Assessment of the framework for NGOs' functioning mechanisms and communication, as well as capacities, including work of umbrella organisations. Action Plan on developing capacities of Consumer Protection Agencies, including umbrella organisations, and development of a pilot organisation and consumer advisory function. Pilot of consumer protection agency and advisory function at the local level launched. Selected CPA staff and members of NGOs trained. Outreach Division's mandate, tasks, and operations are well-defined. Manual of Operations for the Division is developed. Number of staff trained. An assessment of the information/data platform, types, periodicity, that is communicated between the CPA, administrations, and consumer agencies, and with the public. Number of awareness activities conducted. A one-year Action Plan for the Division is developed Portal content defined and design approved. 1st Edition of the portal launched. Number of staff trained. Action Plan for upgrading the IT function is developed. | Organisations policy statements. Mission and progress reports. Certificates of attendance. Training evaluation sheets. | Availability of competent NGOs especially the umbrella organisations. Commitment of selected NGOs. |

Activities

Component I: Legal and Regulatory Framework for Consumer Protection - Conducting an assessment of the legal and regulatory context of Consumer Protection system in Egypt, in comparison to the EU best practices, including analysis of mandate and regulations governing the higher council for consumer protection. - Proposing reform measures for developing the legal and regulatory context for consumer protection in line with the EU aquis will be presented and approved by the CPA. Measures (including an update legal draft) should address all shortcomings and other enforcement challenges, particularly those related to conflicts of jurisdictions, improving CPA’s capacity to better function as the leading consumer protection agency. The proposed reform measures should address both primary and secondary legislations, and should pave the way for implementing gradual reforms in priority areas specified in this project (all other components). Furthermore, the project should assist the CPA to propose relevant legal reforms to improve coordination aspects at the ministries' level, and among CPA, relevant administrations, and stakeholders (including Consumer Associations and others). - Designing and putting in place a database/library for legal-related consumer protection information. The database should indicatively include all pertinent laws, regulations, and final litigations relevant to consumer protection (e.g. quality and industrial standards applicable in Egypt in the field of consumer protection, judicial precedents and, where appropriate, the corresponding executive regulations and administrative practices). It should also include regular updates of legal precedents and information from other relevant divisions (e.g. Complaint Handling). The database should be nucleus to developing an effective knowledge management system within the CPA, linked and accessible to other relevant administrations, and will constitute the backbone of the “external communication and awareness mechanism, as well as Complaint Handling Divisions). - Designing and conducting tailored training, based on proposed reform measures, covering manual of operations for developing and maintaining the database. Mechanisms/solutions for acquiring/communicating information regarding legal precedents and case handling between the CPA, Consumer Agencies at regional/local level, and other competent authorities (e.g. Ministry of Justice) shall be defined and proposed. Component II: Institutional Framework and CPA Sustainable Capacity - Conducting diagnostic analysis of CPA and the institutional framework for consumer protection in Egypt benchmarking them to best practices in selected EU Member States. - Proposing reform measures with recommendations for a developed structure of CPA’s core functions and interdepartmental linkages. - Defining mandate of the inter-institutional consultation and proposing coordination mechanisms with specific tasks and reform measures - Developing a roadmap for CPA Organisational development an institutional framework among different administrations - Improving the Complaint Handling Division by building and raising the capacity of the division team and developing effectiveness and efficiency complaint handling cycle - Upgrading CPA capacity to outreach and better communicate with all relevant stakeholders, this shall include the institutionalisation of the Outreach Division - Building CPA capacity to improve awareness including operations mechanisms - Conducting an assessment of current functions, capacities and practices of Market Intelligence and Research. - Proposing institutional and operational measures to develop/upgrade the Market Intelligence and Research functions within the CPA focusing on "monitoring of advertising" and initiate implementation - Conducting regular updates, specialised studies and comparative testing in relation to market Intelligence and Research functions - Upgrading CPA capacities to perform market Intelligence and Research functions. - Upgrading CPA capacity to communicate relevant information within the CPA and with the public. - Defining the organisational-related information outputs/deliverables/flows - Upgrading the capacity of the Information Technology Division - Conducting an assessment for "product recall" - Setting up mechanisms and measures for "product recall" and initiate implementation - Proposing and assisting in implementing institutional measures to set-up the training function at CPA and improving capacities of related staff. Component III: Consumer Protection Associations Assessing the capacities of CPA in relation to reinforcing the roles of the Consumer Protection Associations. - Assessing the capacities of the existing and potential umbrella Associations. - Assisting the CPA in designing and implementing a capacity building program for selected Associations. - Proposing effective Networking mechanisms among the organisations, consumers, CPA, municipalities, and other stakeholders. - Developing a pilot project to upgrade the human, institutional, and operational capacity of role-model consumer advice centre/services at the local level. Component IV: Awareness and Information Management and Visibility - Assessing the current awareness capacity/activities at the CPA. - Proposing relevant institutional and operational measures to set up an awareness division. - Conducting selected awareness activities. - Designing and launching a portal for consumer protection related information building on the current CPA website www.cpa.gov.eg, this portal will serve as an interactive communication interface between the CPA and different stakeholders, and with consumers and producers - the public in general, linked to complaint handling division and awareness - Drafting a tender dossier for the needed equipment and software for the consumer protection portal and installed data bases, including staff training. - Conducting a kick off meeting at the beginning of the project inviting all stakeholders to provide them with a background on the project components, this activity takes place with the aim of increasing project visibility. - Holding a final meeting owing to ensure that the results achieved by the end of the project are made available to all stakeholders, this activity will be held to ensure awareness and visibility.

http://europa.eu/rapid/pressReleasesAction.do?reference=MEMO/08/206&format=HTML&aged=0&language=EN&guiLanguage=en

Division marked in light blue, are not yet set-up or require substantial capacity building.

Council Resolution of 14 April 1975 on a preliminary programme of the European Economic Community for a consumer protection and information policy, OJ C092, 25-04-1975, p.2