2009 Project Fiche Kosovo – IPA centralised programmes

KS 09 IB OT 01

1. Basic information

1.1   CRIS Number:			2009/021-145

1.2   Title: 		Strengthening the human resources and the institutional capacity of the Kosovo Local Public Administration

1.3   ELARG Statistical code: 		01.34

1.4   Location:				Kosovo (UNSCR 1244)

Implementing arrangements:

1.5   Contracting Authority (EC): 	European Commission Liaison Office to Kosovo

1.6   Implementing Agency: 		N/A

1.7   Beneficiary (including details of project manager):

| Project activity/component | Beneficiary institution | Contact point responsible for project/activity coordination |
| --- | --- | --- |
| Integrated support to Decentralisation - all municipalities and the Ministry of Local Government Administration (MLGA) | MLGA | Permanent Secretary of MLGA |

Financing:

1.8   Overall cost (VAT excluded):  EUR  5.0 million

1.9   EU contribution:		  EUR  5.0 million

1.10 Final date for contracting: Three years after the signature of the financing agreement between the European Commission and the Kosovo Authorities.

1.11 Final date for execution of contracts: Two years after the final date for contracting.

1.12 Final date for disbursements: One year after the final date for the execution of contracts.

2.   Overall Objective and Project Purpose

2.1 Overall Objective:

The overall objective of this intervention is to contribute to the development of public administration that can better meet the demands of a functioning society in a transparent and accountable manner.

2.2 Project purposes:

Support in developing a professional administrative capacity for implementation of the European Partnership Action Plan towards a more effective and efficient service delivery and dialogue with citizens.

2.3 Link with AP/NPAA / EP/ SAA:

This project responds to the Mid-Term Priority of the European Partnership by addressing EU sectoral policies and standards, including: “Strengthen public administration reform:  implement a Public Administration Reform in order to streamline public administration and build a professional and accountable civil service able to attract and retain qualified staff….”

The European Partnership Action Plan (EPAP – July 2007) underlines the need for enhancement of civil service capacities with the aim to effectively lead the Kosovo’s process of European Integration.

With the aim of providing quality services, municipalities shall prepare the following plans regulating municipal territories, pursuant to the Law on Spatial Planning: Municipal Development Plan, Urban Development Plan and Urban Regulatory Plan.

The European Commission’s 2008 Progress Report on Kosovo, published in November 2008, points out that "Overall, despite some progress related to the adoption of an action plan and some legislation, public administration reform still needs to be implemented...Ensuring the delivery of public services to all people in Kosovo and establishing a professional, accountable, accessible and representative public administration is a key priority in the European Partnership for Kosovo".

The report also points out that only five municipalities have signed local environmental action plans and concludes that overall, there is limited progress to report in the field of environment.

Local self-government and decentralisation in Kosovo is based upon the principles of good governance, efficiency and effectiveness in public service and in particular the principle of subsidiarity, as foreseen in the Comprehensive Proposal for the Status Settlement of Kosovo. This project intends to support the implementation of the status settlement through supporting delegated competencies and the development of urgently needed development plans in municipalities.

2.4 	Link with the Multi-Annual Indicative Planning Document (2009-2011) for Kosovo (MIPD)

The project fully reflects the MIPD’s Main priorities and objectives for the period 2009–2011, which stresses that EC assistance should be drawing on Kosovo's strengths: its young population, with its motivation linked to Kosovo's integration into the region.

Among the Strategic Objectives for IPA assistance over the period 2009-2011, MIPD under Axis 2 Economic Criteria and Axis 3 European Standards includes capacity building and the approximation of legislation as identified in the European Partnership. These include: internal market issues, freedom, security and justice, food safety, veterinary and phytosanitary, statistics, public procurement, data protection and protection of intellectual property rights, fiscal and financial management, auditing and accounting procedures, improvement of the investment climate, trade opportunities, and development of the energy, environment, transport, agriculture and rural development, media and electronic communication etc.

MIPD further on stipulates that "key challenges such as…failure to prepare and enforce environmental and local development plans…need to be tackled".

2.5 Link with National Development Plan:

The Mid Term Expenditure Framework (MTEF) 2009-2011 provides that Kosovo’s ultimate destination is Europe and that the MTEF exercise can be interpreted as an important component of the Government’s effort to establish the crucial first steps towards achieving this primary objective. Four over-arching priorities have been identified and agreed by the Government: Economic growth, successful implementation of the Status Settlement, Good Governance, and Social Stability including Poverty Alleviation. Each of these is composed of specific policy priority areas corresponding to the European Standards as outlined in MIPD and judged necessary for Kosovo to move in the direction of an EU compliant growth path.

Implementation of delegated competencies, which includes inter alia preparation of municipal development /urban plans is also strongly pointed out throughout the MTEF.

2.6 Link with national/ sectoral investment plans:

The Plan on EU Integration 2008-2010 was adopted by the Government in April 2008 and aims to bring Kosovo institutions, management capacity and administrative and judicial systems up to Union standards with a view to implement the acquis effectively or, as the case may be, to be able to implement it effectively in a timely fashion before accession.

The Public Administration Reform Strategy (PARS) 2007-2012 and its Action Plan were approved by the Government in March 2007.  The Strategy has identified eight strategic policy areas in which public administration reform should be focused. This project aims to assist the Kosovo institutions in implementing the reform strategy specifically in the field of advancing the development, approximation and implementation of policies and legislation in line with EU standards, as one of the main objectives of the PARS.

3. Description of project

3.1 Background and justification:

The Ministry of Local Government Administration (MLGA) was established in December 2004 with UNMIK regulation 2004/50, with the mandate to support and advise the municipalities in their daily work and monitor performance of municipal services, inter-municipal cooperation, etc.

Under the UNMIK Regulation 2007/30, elections for Municipal Assemblies and for Mayors of Municipalities of Kosovo were held on 17 November 2007. These were the first election in Kosovo fully administered by local election institutions.

The new leadership expressed its commitment to establish effective, transparent and accountable local authorities that provide services on an equal basis to all of Kosovo's communities, which will be crucial to ensure a durable peace and development of Kosovo's post-conflict society. The final goal is to improve and standardize municipal operations and ensure that municipalities effectively serve the people.

The Kosovo Assembly has recently approved a number of important laws related to local self-government as part of the Ahtisaari Proposal, which will bring considerable changes to the number of municipalities, their structures and competencies.

The Government reviewed and accepted the Decentralisation Action Plan 2008-2010, which was designed by the MLGA. Implementation of this Action Plan is under the direction of Inter-ministerial group for decentralisation led by MLGA and four Working groups on decentralisation providing guidance for the implementation of the decentralisation process and makes recommendations for permanent administrative structures to be created in response to the Status Resolution Proposals. With the adoption of a time frame for the post-status arrangements, the Government has committed itself to a broad based, interactive and public process for the creation and staffing of new municipalities, in line with the interest of the local communities.

The Government has already launched the implementation of a decentralisation process. UNMIK and the Government approved five pilot projects (only 3 created) for modelling the ‘pilot municipalities’ and to bring services closer to citizens. The core aim was to provide wider opportunities for minority inclusion in local governments, particularly in areas with a “minority majority” of inhabitants. The planned decentralisation process has become highly politicised and progress has been slow. However, with the declaration of independence Kosovo Government has committed for full implementation of the Ahtisaari Proposal and the Kosovo Assembly has recently approved a number of important laws related to local self-government, which will bring considerable changes to the number of municipalities, their structures and competencies.

Based on the Law 03/L-040 on local self government municipalities have (see for details Annex 6):

I. own competences in several fields such as: local economic development; urban and rural planning; land use and development; provision and maintenance of public services and utilities, including water supply, sewers and drains, sewage treatment, waste management, local roads, local transport, and local heating schemes etc;

II. Delegated competencies such as:  cadastral records; civil registries; voter registration; business registration and licensing; forestry protection etc

III. Enhanced municipal competencies: certain municipalities have their own competencies enhanced in the areas of health, education and cultural affairs and have participatory right in selecting local station police commanders.

Successful decentralisation requires the transfer of a meaningful set of competencies to local governments, the transfer of sufficient financial resources, and the right of local governments to organise their own work. Elected representatives should guarantee democratic decision making and control. Nonetheless decentralisation and overall implementation of local government reform will work if the capacity of the people and the organisations is sufficient. Building on and consolidating previous phases of EC assistance, this project aims to deliver significant positive impact through strengthening the professional capacity of Kosovo’s municipal authorities. The explicit intention is to establish an enabling framework for enhancing capabilities and capacities of local self government to meet EU standards of good governance and to improve the efficiency of the public services, including service delivery.

Local authorities have been facing an increasing number of tasks and responsibilities, due to an ongoing process of decentralisation; therefore the purpose of the project is to ensure modernisation of service provision provided by local administration.

As the fiscal decentralization and transfer of sufficient financial resources to local level is a crucial factor for successful local governance, the project will ensure improvements of the system for financing local governments. Currently the central government sets constraints on the levels of staffing and operational expenditure of the municipalities as part of the general fiscal controls with an aim of maintaining macroeconomic stability.  The municipalities, however, find it difficult to reconcile these constraints with their own freedom to determine their budget structure and to meet local demands for services. Hence the project will aim at supporting a policy and fiscal decentralized framework, which is conducive to accountable democratic governance, whilst maintaining fiscal discipline (required by the central government).

3.2 Assessment of project impact, catalytic effect, sustainability and cross border impact: (where applicable)

The project will have a positive impact through strengthening capacity of Kosovo’s institutions, line ministries and municipalities in improving performance and reaching the benchmarks related to priorities deriving from European Partnership. The wider impact of the project is to dramatically and visibly improve the ability of local governance to better serve their citizens and to support a policy and fiscal framework, which is conducive to accountable democratic governance.

The project will also deliver a positive impact through the targeted policy interventions in conjunction with mayors and the Association of Kosovo Municipalities to improve the transparency, accountability and effectiveness of local governance structures. An important success factor is the degree to which local leaders feel their responsibility is to solve local problems rather than being a traditional party politician.  Strengthening of this sector acts as a catalyst for further sector specific initiative that accelerates the implementation of European standards and improves the quality of life for all citizens.

3.3 Results and measurable indicators:

Result 1 (Completed Planning Framework) – All Kosovo municipalities exercise their competences in accordance with a comprehensive set of municipal plans fully integrated with the municipal budget

Measurable indicators:

- Capacity and Capability Assessment Reports prepared  for all municipalities

- All municipalities have published their core planning documents in accordance with legal planning requirements

- The municipal policy framework is improved allowing for increased decentralization in decision making, appropriate fiscal disciplines,  and clearer definition of responsibilities between the local and central level

- The planning framework embraces European values and includes priorities derived from the European Partnership

- Municipal officials and their staff have a greater focus and clarification to their tasks

Result 2 (Implementation of Municipal Plans) – Citizens receive municipal social and regulatory services in accordance with the stated planning intentions of the municipality

Measurable indicators:

- Assembly, Director and Management meetings of the municipality are focused around the delivery of the municipal plans

- Performance indicators are developed that track in implementation of service plans

- A selection of municipalities, chosen according to weaker planning capabilities, commit to improvement in planning and the delivery of services

- Improved efficiency and financial management of the respective municipal staff

- Expenditure of the municipalities is incurred in support of the planning intentions and in a manner that is sustainable

Result 3 (Improvement Cycle) – Municipal services are improved

- Measurable indicators:

- Mid-year and end of year reports are presented to Municipal Assemblies and to citizens

- Municipalities that have improved performance receive public recognition of service quality (including financial incentives)

- Government approves legal, institutional and fiscal reforms necessary to promote decentralized service delivery

- The policy framework allows for decentralized power in decision making and local exercise of fiscal controls

- Components of the European Partnership Action Plan are identified as complete

3.4 Activities:

Activities for achieving Result 1

- A baseline analysis is conducted through all Kosovo municipalities identifying the current level of preparation of municipal plans and identifying the gaps in plans preparation

- Consultation workshops take place between local and central levels to increase dialogue and understanding of the legal planning requirements in all areas of municipal service

- The European Partnership and the Action Plan for implementation of the partnership are fully analyzed to identify actions required by the municipalities

- Training is provided, as identified as necessary, to improve the knowledge and value of service planning

- The financial control environment is critically analyzed and recommendations are made for the local exercise of sustainable fiscal disciplines

Activities for achieving Result 2:

- Management audits of municipalities are undertaken in order to verify the extent to which internal municipal processes support the implementation of service plans

- Existing performance data is collected and used, and further performance indication processes are developed, as necessary, in order to report on the quantity and quality of municipal services and barriers to municipal performance

- Twinning arrangements are deployed to exemplify, develop, encourage and implement European practice in planning and delivery of municipal services

- Financial management reports are developed that accurately report the level of municipal expenditure incurred to implement municipal plans

Activities for achieving Result 3:

- Assistance is given to municipalities to assist the transparency of public reporting

- Competitive mechanisms are developed that identify and reward municipalities for consistent high performance and significant improvement in performance

- Consultative processes are developed that allow municipal performance to be reflected into local and central-local policy and in the setting of future year plans including fiscal policy

- Municipal are engaged in activities linked to European integration

Contracting arrangements

A twinning arrangements in envisaged

3.5 Conditionality and sequencing:

It is of paramount importance that the following activities are completed before the project(s) commence:

- Sufficient budget is made available by the Government to all beneficiary institutions before the start of the project.

- Beneficiaries demonstrate strong ownership attitude towards the project.

- Organisation, selection and appointment of members of working groups, steering and coordination committees, training activities, seminars and study visits by the beneficiaries as per the project work plan.

- The Government has to remain dedicated to the devolution of powers, to development of professionalism in the administration and to its commitment to the process of European Integrations.

In the event that conditionalities are not met, suspension or cancellation of the project or specific activities may be considered.

3.6 Linked activities

The project builds-on the significant EC assistance for public administration reform in Kosovo.  In particular, the 2009 projects will follow-up, consolidate and draw lessons learned from the following on-going EC funded projects:

| Name of project (Amount EUR million) | Start End | Activities/Results |
| --- | --- | --- |
| Support to Local Government (EUR 1 million) | May 2007 -May 2009 | - The project aims to achieve a more efficient, effective and accountable local government (municipalities) with emphasis on better management (particularly financial); consistent service delivery and improved relations with citizens. |
| Municipal Infrastructure Development Projects (EUR 16 million) | Nov 2004- Dec 2007 | - Support to implementation of UN Standards for Kosovo in municipalities through provision of social and economic infrastructure. To date 44 projects were designed by the municipalities out of which 12 are road projects, 19 for improving water supply and sewage systems, 11 for building schools, one for a sports centre and one for an archive building. |
| Support to Local Government (EUR 3.4 million) | January 2009 – January 2011 | - Assessment of implementation of new legislation deriving from decentralisation and complete missing secondary legislation. - Benchmarking system and a set of indicators established for regular assessment of performance and reports are published for an increased transparency and confidence of public. - Public enabled to have access to information and participation in municipal activities and decision making. - Each municipality developed at least 5 project proposals in line with municipal development plans. - Procedures, structures and capacities of municipal inspectorates reviewed and improved and cooperation agreements signed between Inspectorates, Kosovo Police Service and Courts to enhance enforcement mechanisms. - The three best performing municipalities received awards. - At least five Inter-municipal cooperation agreements signed and implemented. |
| Ministry of the Local Government Administration (EUR 1 million) | April 2009 – April 2011 | - Assist the MLGA in implementation of the Local Government Reform Strategy. - Support MLGA in implementing the municipal performance assessment system and institutionalising the incentive measures. - Improve the coordination role of MLGA within the government and with donors for more effective service delivery. |
| 'Support Kosovo municipalities and MESP for the implementation of environmental Laws at municipal level' (EUR 1 million) | Jan 2008 – Jan 2010 | To strengthen the institutional capacity of Kosovo’s municipalities and MESP and to improve enforcement of environmental laws and regulations and to ensure better communication and cooperation between the central (MESP) and local level (5 regional offices/inspectorates, municipalities, local councils, mayors’ offices). |

The project will built upon the significant US assistance for local government/decentralization in Kosovo.  In particular, this project will follow-up, consolidate, built upon and draw lessons learned from the USAID-Emi project (running until 2010) and will coordinate with the potential US funded projects in the filed of local government.

3.7 Lessons learned

Although impact realised through the previous assistance overall is satisfactory, a number of challenges remain:

- Staffing: Often project implementation is hampered by either insufficient staff and resources or insufficient funds available in the institution budget to allow for appropriate implementation of the mandate.

- Cross-cutting issues: There is more need to institute formal checks that cross cutting themes are respected in all dimensions of project activities to enhance relevance and impact.

- Flexibility: Recurring reference is made to the importance of creating flexibility in planning and projects to accommodate the needs at the time; and the importance of avoiding duplication.

- Coordination: Close consultation among the many stakeholders involved in the project and a collaborative approach are essential to ensure that all these stakeholders are fully informed, and are supportive of the project to be carried out. The project shall in particular coordinate the efforts with other projects supporting local government reform, especially related to performance benchmarking such as IPA 2007 and USAID projects and ensure clear division of tasks (either territorially or functionally).

4. Indicative Budget  (amounts in EUR million)

|  |  |  |  | SOURCES OF FUNDING |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | TOTAL EXP.RE | IPA COMMUNITY CONTRIBUTION |  | NATIONAL CONTRIBUTION |  |  |  |  | PRIVATE CONTRIBUTION |  |
| ACTIVITIES | IB (1) | INV (1) | EUR (a)=(b)+(c)+(d) | EUR (b) | %(2) | Total EUR (c)=(x)+(y)+(z) | % (2) | Central EUR (x) | Regional/ Local EUR (y) | IFIs EUR (z) | EUR (d) | % (2) |
| Activity 1 | x |  | 5.0 | 5.0 | 100 |  |  |  |  |  |  |  |
| contract 1 (Twinning) |  |  | 5.0 | 5.0 | 100 |  |  |  |  |  |  |  |
| TOTAL IB |  |  | 5.0 | 5.0 | 100 |  |  |  |  |  |  |  |
| TOTAL INV |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT |  |  | 5.0 | 5.0 | 100 |  |  |  |  |  |  |  |

Note:

Amounts net of VAT

(1)	In the Activity row "X" is used to identify whether IB or INV

(2)	Expressed in % of the Total Expenditure (column (a))

5.  Indicative Implementation Schedule (periods broken down per quarter)

| Contracts | Start of Tendering | Signature of contract | Project Completion |
| --- | --- | --- | --- |
| Contract 1 (EUR 5.0 million) (Twinning) | Q42009 | Q3 2010 | Q3 2012 |

All projects should in principle be ready for tendering in the 1ST Quarter following the signature of the FA.

6. Cross cutting issues (where applicable)

6.1	Equal Opportunity

In the implementation of the Project, specific attention will be given to the need to reflecting gender balance and equal opportunities for all communities in the selection process.

The project will actively liaise with gender officers in the ministries and municipalities and the Office of Gender Equality in the OPM in order to get their participation in planned activities. This dimension is also reinforced in the IPA, European Partnership Action Plan and the draft Kosovo Development and Strategy Plan.

Terms of reference will identify the impact of the project on women and minorities including the employment opportunities and will encourage compliance by the beneficiary with Kosovo law on employment of women and minorities.

6.2	Environment

Result 2 of the project is expected to have serious impact on the environment as one of the targets of the project is also environment improvement. The Project will be consistent with environmental implications as set out in relevant legislative acts. When and if appropriate environmental impact assessment will be carried out.

6.3	Minorities

Minority representation will be pursued across the civil service and in all aspects of project activities. Active steps will be needed to encourage adequate minority participation in selection procedures of the programme.

The equitable treatment of Minorities has formed a fundamental element in the implementation of the EPAP and is reflected in the Draft Kosovo Civil Service Law and Anti Discrimination Laws. The Comprehensive Proposal for the Status Settlement of Kosovo also underlines a multi ethnic society in its General principles and Annexes 2 and 3. Formal recognition of these key issues will form a compulsory part of any planning process.

Improvement in water and waste management can improve the quality of life for all communities particularly those living in the most deprived and/or unsanitary conditions.  The programme will ensure that the needs of all members of the population receive proportionate benefit and that no sector is discriminated against and will identify means to ensure positive benefits to minority communities.

- ANNEXES

Annex 1	Log frame in Standard Format

Annex 2    	Amounts contracted and Disbursed per Quarter over the full duration of Programme

Annex 3	Description of Institutional Framework

Annex 4	Reference to laws, regulations and strategic documents

- Annex 5 	Details per EU funded contract

- ANNEX 1:	Logical framework matrix in standard format

| LOGFRAME PLANNING MATRIX FOR Project Fiche |  | Programme name: Strengthening the human resources and the institutional capacity of the Kosovo Local Public Administration |  |
| --- | --- | --- | --- |
|  |  | Contracting period expires three years after the date of conclusion of the Financing Agreement between the European Commission and the Kosovo Authorities | Disbursement period expires one year after the final date for the execution of contracts |
|  |  | Total budget : EUR 5.0 million | IPA budget: EUR 5.0 million |
| Overall objective | Objectively verifiable indicators | Sources of Verification |  |
| Contribute to the development of public administration that can better meet the demands of a functioning society in a transparent and accountable manner. | - Progress in contractual relationships between Kosovo and EU. | - Contractor’s regular reports. - Reports of the STM meetings. - EC progress reports on Kosovo. |  |
| - Project purpose | - Objectively verifiable indicators | - Sources of Verification | - Assumptions |
| Support in developing a professional administrative capacity for implementation of the EPAP towards a more effective and efficient service delivery and dialogue with citizens | - EPAP implemented - Action Plan on decentralisation implemented - Municipal performance in all respective municipalities improved | - Performance assessment reports - Contractor’s regular reports - Reports of the STM meetings - EC progress reports on Kosovo - Reports of MLGA and municipalities | Commitment from the Government to implement reforms. Competencies from central to local government delegated |

| Result 1 (Completed Planning Framework) – All Kosovo municipalities exercise their competences in accordance with a comprehensive set of municipal plans fully integrated with the municipal budget . | Capacity and Capability Assessment Reports prepared for all municipalities All municipalities have published their core planning documents in accordance with legal planning requirements The municipal policy framework is improved allowing for increased decentralization in decision making, appropriate fiscal disciplines, and clearer definition of responsibilities between the local and central level The planning framework embraces European values and includes priorities derived from the European Partnership Municipal officials and their staff have a greater focus and clarification to their tasks | Assessment reports Contactor's reports Central government approval of policies MLGA reports | Commitment from municipalities to implement the project |
| --- | --- | --- | --- |
| Result 2 (Implementation of Municipal Plans) – Citizens receive municipal social and regulatory services in accordance with the stated planning intentions of the municipality | Assembly, Director and Management meetings of the municipality are focused around the delivery of the municipal plans Performance indicators are developed that track in implementation of service plans A selection of municipalities, chosen according to weaker planning capabilities, commit to improvement in planning and the delivery of services Improved efficiency and financial management of the respective municipal staff Expenditure of the municipalities is incurred in support of the planning intentions and in a manner that is sustainable | Contractor’s regular reports Reports from the MLGA Citizen's opinions | The policy framework shall be improved and implemented to allow for increased decentralization in decision making and clearer distinction of responsibilities between local and central level |
| Result 3 (Improvement Cycle) – Municipal services are improved | Mid-year and end of year reports are presented to Municipal Assemblies and to citizens Municipalities that have improved performance receive public recognition of service quality (including financial incentives) Government approves legal, institutional and fiscal reforms necessary to promote decentralized service delivery The policy framework allows for decentralized power in decision making and local exercise of fiscal controls Components of the European Partnership Action Plan are identified as complete | Contractor’s regular reports Guidelines and Reporting Manuals | Mayors will be an important part of the policy making process Municipalities will be able to effectively advocate collectively for legislative and administrative changes |

| Activities | Means | Costs | Assumptions |
| --- | --- | --- | --- |
| Activities for achieving Result 1 A baseline analysis is conducted through all Kosovo municipalities identifying the current level of preparation of municipal plans and identifying the gaps in plans preparation Consultation workshops take place between local and central levels to increase dialogue and understanding of the legal planning requirements in all areas of municipal service The European Partnership and the Action Plan for implementation of the partnership are fully analyzed to identify actions required by the municipalities Training is provided, as identified as necessary, to improve the knowledge and value of service planning The financial control environment is critically analyzed and recommendations are made for the local exercise of sustainable fiscal disciplines Activities for achieving Result 2: Management audits of municipalities are undertaken in order to verify the extent to which internal municipal processes support the implementation of service plans Existing performance data is collected and used, and further performance indication processes are developed, as necessary, in order to report on the quantity and quality of municipal services and barriers to municipal performance Twinning arrangements are deployed to exemplify, develop, encourage and implement European practice in planning and delivery of municipal services Financial management reports are developed that accurately report the level of municipal expenditure incurred to implement municipal plans Activities for achieving Result 3: Assistance is given to municipalities to assist the transparency of public reporting Competitive mechanisms are developed that identify and reward municipalities for consistent high performance and significant improvement in performance Consultative processes are developed that allow municipal performance to be reflected into local and central-local policy and in the setting of future year plans including fiscal policy Municipal are engaged in activities linked to European integration | One Twinning | 5.0 mill | All municipalities cooperate and provide sufficient human and financial resources Citizens' participate in consultation process |

Pre-conditions:

Sufficient staff and budget is made available to all beneficiary institutions by the Government before the start of the project

Beneficiaries demonstrate strong ownership attitude towards the project.

- ANNEX 2:	Amounts (in EUR million) contracted and disbursed by quarter for the project

|  | 2010 |  |  | 2011 |  |  |  | 2012 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contracted | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Contract 1 |  | 5 |  |  |  |  |  |  |  |  |  |
| Cumulated |  | 5.0 |  |  |  |  |  |  |  |  |  |
| Disbursed | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Contract 1 |  | 1.5 |  | 1 |  | 1 |  | 1 |  | 0.5 |  |
| Cumulated |  | 1.5 |  | 2.5 |  | 3.5 |  | 4.5 |  | 5.0 |  |

Annex 3:	Description of Institutional Framework

The Ministry of Local Government Administration (MLGA)

The Ministry of Local Government Administration was established with UNMIK Regulation 2004/50 of 04 December 2004. The responsibilities of MLGA are determined with the UNMIK Regulation 2001/9 on the Constitutional Framework for Provisional Self-Government in Kosova, Chapter 5, item 2 and UNMIK Regulation 2005/15 of 16 March 2005 amending UNMIK Regulation 2001/19 on the Executive Branch of PISG in Kosova.

Mission of MLGA:

To promote local government through coordination, empowerment, supporting of municipalities for the purpose of ensuring efficient services as well as bringing services closer to citizens.

Relevant MLGA aims,

- Inter-ministerial coordination to ensure sufficient resources for realization of municipal competences;

- Supporting, monitoring and supervising the competences of municipalities to ensure implementation of legality;

- Coordination of activities with donors’ community and non-governmental organizations;

- Continual improvement of the quality of municipal services, through professional capacity building of human resources

Relevant MLGA responsibilities

- Supporting inter-municipal co-operation;

- Assisting the municipalities in the development of their own budgets and financial management systems;

- Monitoring the quality of municipal services,

- Identifying the ways and means for training activities for the municipalities;

- Assisting the municipalities in making their activities transparent to the public;

- Coordinating the activities of international agencies and non-governmental organizations pertaining to the municipalities;

- Overseeing compliance of municipalities with responsibilities and powers delegated to the municipalities;

- Coordinate with other ministries to meet the needs for and ensure the access of all communities to essential basic goods and services;

- Coordinate with the Ministry of Finance to ensure that municipal administrations receive the financial allocations to exercise their own responsibilities, including public investment.

- Allocates adequate financial and human resources for supporting Municipal Gender Officers, address gender inequalities and integrate a gender perspective in local governance policy-making and delivery of services.

Organizational structure of MLGA

At the political level the Ministry is headed by a Minister assisted by two Deputy Ministers (one D/minister belongs to minority community) as well as advisors.  The civil staff is headed by the Permanent Secretary. In the hierarchy structure, following Permanent Secretary the ministry is composed of departments   (divisions and sectors) and Offices. 
Departments and Offices

Legal Department - Department for Planning of Resources - Department for Monitoring, Efficiency and Reform of Municipalities - Department for Administration and Finances - Department of Procurement - Office for European Integrations - Office for Planning and Development -  Office for Information

- ANNEX 4:	Reference to laws, regulations and strategic documents:

Reference list of relevant laws and regulations:

- UNMIK Regulation on Civil Service

- Draft Law on Civil Service

- UNMIK Regulation on establishment of PISG

- Law on Local Self Government

- Law on Spatial Planning

- Law on Environmental Impact Assessment

- The Environmental Protection Law

- The Construction Law

- The Administrative Instruction n9/2004 concerning Environmental Impact Assessment

Reference to AP /NPAA / EP / SAA:

- European Partnership Action Plan 2008

- EC Progress Report on Kosovo - 2008

Reference to MIPD:

- The project links with MIPD main priorities and objectives for the period 2008 – 2010, namely Economic criteria and European Standards.

Reference to National Development Plan

- Both KDSP and MTEF highlight the needs for public administration reform and advance the EU Integration process.

Reference to national / sectoral investment plans

The project is in line with the priority actions identified in:

- PAR Strategy

- Plan on European Integration 2008 – 2010

- Strategy for the environment sector (2007 -2013)

- Kosovo Environmental Action Plan 2006 – 2010

ANNEX 5:	Details per EU funded contract (*) where applicable:

The instrument of twinning will be used to implement this activity.  Standard twinning procedures are to be used.  There will be two Resident Twinning Advisors (RTA), who are expected to be a senior civil servant from similar institutions of member states (i.e. Municipalities). RTAs provide technical advice and assists the administration or other public sector bodies in the beneficiary country in the context of a predetermined work plan. He/she is in charge of the day-to-day implementation of the project in the BC. All rights to any work done by RTA in the performance of his/her duties become the property of the beneficiary country in question. The MS and the Commission will be permitted to use the results of the work elsewhere by permission of the beneficiary country. RTA is made available by Member States’ administrations and mandated bodies to counterparts in beneficiary countries through EU funding. RTA must in principle be nationals of a Member State of the EU. The RTAs will be based in Prishtina, for the period of 27 months.

The RTAs will be assisted by EU MS short and medium-term experts. The specific knowledge, skills and competencies required from the RTA are:

RTA Profile:

- Experience in working with local government institutions and experience in decentralisation;

- Experience in the transition countries

- Experience in the development and implementation of decentralisation/

- deconcentration initiatives;

- Experience in supporting and working with high level groups

- Knowledge of governance and accountability frameworks, including

- monitoring and evaluation arrangements, suitable for decentralised service

- delivery

- Excellent project management, team building and communication skills –

- specific competency in mentoring the work of multi-disciplined inter-ministry

- groups and the sector working groups;

- Prior knowledge of the Kosovo related to the actual stage of the fiscal and financial decentralization would also be an advantage.

The main activities of the twinning covenant will be:

- Assessment carried out in all municipalities across Kosovo

- Map out the existing situation in beneficiary municipalities with regard to Municipal Plans

- Preparation of the memoranda to be signed with municipalities

- Support to respective municipal staff responsible for implementation of municipal plans

- Work with respective actors  to ensure update of municipality ordinances

- Assist respective local and national authorities in ensuring that sufficient budget is made available for future fiscal years in improving service delivery gaps.

- Assist respective municipal directorates in planning of the budgets

- Design and implement training targeting gaps in knowledge of both local and national authorities

- Assist local government institutions in identifying and implementing performance benchmarks for a more targeted delivery of services to citizens

- Transfer of experience, skills and best practice to the management and staff of the municipalities on strategic planning, hands on preparation of plans and their implementation, through an open consultation process with citizens

- Organise a study visit for national and municipal authorities to know organization and implementation of the service delivery in the member states

ANNEX 6:  Law Nr. 03/L-040 ON LOCAL SELF GOVERNMENT

Article 17

Own Competencies

17.1 Municipalities shall have full and exclusive powers, insofar as they concern the local interest,

while respecting the standards set forth in the applicable legislation in the following areas:

a) local economic development;

b) urban and rural planning;

c) land use and development;

d) implementation of building regulations and building control standards;

e) local environmental protection;

f) provision and maintenance of public services and utilities, including water supply, sewers and

drains, sewage treatment, waste management, local roads, local transport, and local heating

schemes;

g) local emergency response;

h) provision of public pre-primary, primary and secondary education, including registration and

licensing of educational institutions, recruitment, payment of salaries and training of education

instructors and administrators;

i) promotion and protection of human rights;

j) provision of public primary health care;

k) provision of family and other social welfare services, such as care for the vulnerable, foster care,

child care, elderly care, including registration and licensing of these care centres, recruitment,

payment of salaries and training of social welfare professionals;

l) public housing;

m) public health;

n) licensing of local services and facilities, including those related to entertainment, cultural and

leisure activities, food, lodging, markets, street vendors, local public transportation and taxis;

o) naming of roads, streets and other public places;

p) provision and maintenance of public parks and spaces;

q) tourism;

r) cultural and leisure activities;

s) any matter which is not explicitly excluded from their competence nor assigned to any other

authority.

Article 18

Delegated Competencies

18.1 Central authorities in Republic of Kosova shall delegate responsibility over the following

competencies to municipalities, in accordance with the law:

a) cadastral records;

b) civil registries;

c) voter registration;

d) business registration and licensing;

e) distribution of social assistance payments (excluding pensions); and

f) forestry protection on the municipal territory within the authority delegated by the central

authority, including the granting of licenses for the felling of trees on the basis of rules adopted by

the Government;

18.2. Central authorities in Republic of Kosova may delegate other competencies to municipalities,

as appropriate, in accordance with the law.

18.3. Delegated competencies must in all cases be accompanied by the necessary funding in

compliance with objectives, standards and requests determined by the Government of Kosova.

Article 19

Enhanced Municipal Competencies

19.1. Certain municipalities explained below shall have their own competencies enhanced in the

areas of health, education and cultural affairs and shall have participatory right in selecting local

station police commanders as set forth in the subsequent articles.

19.2. Central authorities of Republic of Kosova shall monitor the exercise of enhanced

competencies, in accordance with the central legislation providing for equal access to public

services; minimum quality and quantity standards in the provision of public services; minimum

qualifications of personnel and training facilities; general principles on licensing and accreditation

of public service providers.

19.3. Municipalities exercising enhanced municipal competencies may cooperate with any other

municipality in providing services.

Article 20

Enhanced Competencies in Secondary Health Care

The municipalities of Mitrovicë/Mitrovica North, Graçanicë/Gracanica, Shtërpcë / Štrpce shall

have the competence for provision of secondary health care, including registration and licensing of

health care institutions, recruitment, payment of salaries and training of health care personnel and

administrators;

Article 21

Enhanced Competencies in the University Education

21.1. The municipality of Mitrovicë/ Mitrovica North shall have competence for the provision of

higher education, including registration and licensing of educational institutions, recruitment,

payment of salaries and training of education instructors and administrators.

Article 22

Enhanced Competencies in the Area of Culture

22.1 All municipalities in which the Kosova Serb Community is in the majority shall have

authority to exercise responsibility for cultural affairs, including, protection and promotion of

Serbian and other religious and cultural heritage within the municipal territory as well as support

for local religious communities in accordance with the applicable law.

22.2. Municipalities may cooperate with any other municipality in cultural affairs.

Article 23

Enhanced Participatory Rights in Selection of the Local Police Station Commanders

Municipalities in which Kosova Serb community is in a majority shall exercise enhanced

participatory rights in the selection of the local station police commanders in accordance with law

on police.

The total cost of the project should be net of VAT and/or other taxes. Should this not be the case, the amount of VAT and the reasons why it should be considered eligible should be clearly indicated (see Section 7.6).

Planning in the context of this fiche is a reference to ‘service planning’ and is not restricted to the concept of spatial planning, it includes, but is not restricted to, spatial planning (land use and urban plans), environmental planning (waste, air, noise, water), built infrastructure planning (roads, pavements, public places), budget planning.

All municipalities have approved their documents according the law on spatial planning (Municipal development plan; municipal urban development plan and municipal urban regulatory plan)

Planning in the context of this fiche is a reference to ‘service planning’ and is not restricted to the concept of spatial planning, it includes, but is not restricted to, spatial planning (land use and urban plans), environmental planning (waste, air, noise, water), built infrastructure planning (roads, pavements, public places), budget planning.

All municipalities have approved their documents according the law on spatial planning (Municipal development plan; municipal urban development plan and municipal urban regulatory plan)