STANDARD TWINNING PROJECT FICHE

- Basic Information

- Programme:		IPA National Programme 2011for BiH

- Twinning Number:	BA11-IB-OT-02

- Title:			Strengthening Institutional Capacity for Quality Assurance

- Sector:			Education

- Beneficiary country:	Bosnia and Herzegovina

2. Objectives

2.1	Overall Objective(s):

To contribute to increased mobility and employability of labour force through improvement of quality work of higher education institutions in line with Bologna process

2.2	Project purpose:

To improve and develop human resources and institutional capacities for quality assurance in higher education

2.3	Contribution to National Development Plan/Cooperation agreement/Association Agreement/Action Plan

Stabilisation and Association Agreement

Article 100: "A priority for the higher education systems shall be the achievement of the objectives of the Bologna Declaration in the intergovernmental Bologna process."

Progress Report

2010: "Some progress has been made in the field of education. The Agency for Development of Higher Education and Quality Assurance is an associate member of the European Association for Quality Assurance in Higher Education." 2012: "The process of accreditation of higher education institutions has begun."

The Strategic Directions for Development of Education in BIH with the Implementation Plan for 2008-2015

Chapter 4.7. Quality Assurance - Support to the Development of Education HEA

To introduce the Standards and Guidelines for Quality Assurance in the European Higher Education Area in accordance with the Bologna process, the Agency for the development of higher education and quality assurance shall be established. The agency would, among other things, be responsible for:

- Establishing criteria for the accreditation of higher education institutions and the adoption of standards of minimum standards in higher education, and to review the accreditation decision on compliance with established accreditation criteria and standards;

- Giving recommendations on criteria and standards for the establishment or termination of higher education institutions and study programs restructuring, as well as for the licensing of higher education institutions and study programs;

- Maintaining a state register of accredited higher education institutions;

- Set quality standards, quality analyses, give recommendations for removal of shortcomings in the quality of studies and higher education institutions;

- Establishing a on the format and general content of Diploma and Diploma Supplement;

- Represent Bosnia and Herzegovina in international organizations for quality in higher education.

Chapter 5. Plan of Development of Education in Bosnia and Herzegovina by 2015

5.5. Higher Education

"The objectives of the development of higher education are:... the establishment and development of monitoring and quality assurance in higher education";

"In accordance with the Bologna Process, the Lisbon Convention and other relevant international instruments in the area of higher education: ... will be established and developed a system for monitoring and quality assurance and support European cooperation in this field";

Short term goals: "Process of implementation of the Framework Law on Higher Education (FLHE) in Bosnia and Herzegovina; Designed and compulsory Diploma Supplement"

Mid-term goals: "Agency for Development of Higher Education and Quality Assurance established, as well as quality assurance systems in higher education developed; Carried out evaluation of the quality of higher education programs and institutions"

Decision on Adoption of Documents for Further Implementation of the Bologna Process in Bosnia and Herzegovina – Council of Ministers of BiH, 2007, Official Gazette of BiH No 13/08

Standards and Guidelines for Quality Assurance in Higher Education in Bosnia and Herzegovina

The development of quality assurance systems are in the best interests of the higher education institutions in Bosnia and Herzegovina. Quality assurance generates quality-related information on education and degrees, which benefits employers, society at large, as well as academics, students and applicants. The analytical description and systematic evaluation of quality and its assurance make it easier for higher education institutions to convince their national and international partners of the quality of their education provision and to make higher education in BiH more attractive for students.

The purpose of this work is to provide explicit standards and guidelines both internal and external - for quality assurance in higher education in BiH, for the use by universities, ministries and quality assurance agencies through their work to support the fundamental reform processes which are taking place in higher education. These BiH standards and guidelines are designed to meet the requirements of the ESG.

Recommendations for Implementing Quality Assurance in Higher Education in Bosnia and Herzegovina

- Raise awareness on quality issues and the use of the standards and guidelines for quality assurance in higher education in BiH;

- Enhance capacities for self-evaluation, quality assurance and improvement activities within higher education institutions;

- Seek approval for the proposed BiH Standards and Guidelines for Quality Assurance in Higher Education from the relevant governmental authorities at various levels;

- Pilot the BiH Standards and Guidelines for internal quality assurance across a number of similar Faculties or disciplines or administrative divisions/domains;

- Develop a National Quality Assurance Framework;

- Conduct an external evaluation of BiH universities, carried out by an external quality assurance agency, on the basis of the BiH Standards and Guidelines for Quality assurance in Higher Education;

- Revise the BiH Standards and Guidelines for Quality Assurance in Higher Education;

3.	Description

3.1	Background and justification:

By signing the Bologna Declaration (2003), ratifying the Lisbon Convention (2003), and embarking on the overall development process in the European Higher Education Area (EHEA), Bosnia and Herzegovina has committed to confirm its higher education to the common European policy in this field that was established by the Bologna process.

Bosnia and Herzegovina is a complex country, consisted by two entities (Federation BiH and Republika Srpska) and a District (Brčko). In Republika Srpska and Brcko District, constitutional responsibility for all levels of education (including higher education) lies on the entity and District level, while for Federation BiH (consisted by 10 cantons), it lies on canton level.  So, there are 12 responsible higher education authorities (ministries) responsible for higher education. By the Framework Law on Higher Education in Bosnia and Herzegovina (2007), under which the Agency for Development of Higher Education and Quality Assurance (Agency, www.hea.gov.ba) was established, additional provisions were made for higher education reforms and development of new institutional capacities. Framework Law on Higher Education in Bosnia and Herzegovina (FLHE) stipulates joint implementation of Bologna Process, but ministries are authorized to adopted policies and priorities that they find as appropriate. Ministry of Civil Affairs at the State level has a coordination role as well as the Conference of Educational Ministers (composed by all educational ministers). Coordination of educational policies has been the most challenging task in the implementation of reforms.

According to the data provided by the Agency for Statistics of Bosnia and Herzegovina, in Bosnia and Herzegovina, in 2011, there were 124.036 students pursuing their degrees in 37 higher education institutions (number of institutions for 2012 is 44).  According to the Framework law, higher education institutions are universities and colleges. Eight public universities and two public colleges account for the largest number of students. Besides the 10 public HEIs, there are 14 private universities and 13 private colleges operating in Bosnia and Herzegovina. It is estimated that 15 % of students study at private higher education institutions. According to the data the Agency for Development of Higher Education and Quality Assurance collected from both official and public sources, in the current academic year there are 620 study programs of the first cycle, 427 study programs of the second cycle and 61 doctoral degrees being offered at 37 higher education institutions. In 2010, 18.177 students obtained their bachelor's degree (completed the first cycle of study), 1.298 students obtained their master's degree and the Master of Science degree, and 205 PhD students received their doctoral degrees. In Bosnia and Herzegovina there are totally 8.643  teachers and external associates employed in higher education institutions (The Agency for Statistics of B&H: ''Given that teachers and external associates can teach at two or more higher education institutions, the given number as full-time equivalent is merely an approximation'').

Competences of the Agency are provided for in Article 48, 49 and 50 of the FLHE. In the field of development of higher education the competences of the Agency refers to the adoption of criteria for accreditation of higher education institutions and norms for determining minimum standards in higher education, recommendations to the Ministry of Republika Srpska, cantonal ministries and Brčko District of Bosnia and Herzegovina on criteria and standards for establishment and closure of higher education institutions and restructuring of study programs, provision of advice to competent ministries on issues relating to work and development policies, determining standards of quality, quality analysis, giving recommendations on the remedy of shortcomings in the quality of studies and higher education institutions, representing Bosnia and Herzegovina in international organizations for quality in higher education, and other competences laid down by the FLHE. In the field of accreditation the Agency is empowered to set criteria for selection and establishment of the list of national and international experts that conduct quality assessment and review and give recommendations on accreditation of higher education institutions and study programs, appoint panels for accreditation of higher education institutions and study programs, select experts from the list of experts, give recommendations on each conducted accreditation, review compliance of the decision on accreditation with criteria and norms for determining minimum standards in higher education and keep a National register of accredited higher education institutions. Article 50 lays down that the Agency shall elaborate a manual on the model and content of diploma and diploma supplement issued by accredited higher education institutions.

The Agency is fully governmental, even though it was established as an “independent public organization”. Top management of the Agency is Director and two Deputies, appointed by Council of Ministries of BiH after the public procedure. Agency has a Steering Board, consisted by 10 members, appointed by the Parliament of BiH after the public procedure. The half of Steering Board members, in accordance to FLHE, has to be full professors. Agency has 20 employees: Director, two Deputies, 9 in the status of “civil servant” and 8 supporting staff. Agency is fully operational.

From the very beginning and within the limits of its authority, the Agency has been actively involved in the implementation of higher education reforms. The Agency has made continuous efforts to raise awareness about the importance of quality assurance in higher education through a wide range of communication activities, targeting in particular the academic community that has the primary responsibility for quality assurance in higher education. Fully aware of the fact that quality assurance mechanisms, either external or internal, would be merely mechanical processes if they did not imply development of culture of quality as well, the Agency dedicated part of its activities to promoting this vital element. The Agency has established an excellent cooperation with quality assurance agencies from the Southeast Europe and EU as well, and has until now signed four memoranda of understanding with agencies from Germany, Austria, Bulgaria and Russia. The Agency has become a full member of the International Network for Quality Assurance Agencies in Higher Education (INQAAHE), the Central and Eastern European Network of Quality Assurance Agencies in Higher Education (CEENQA), and has been granted the associate membership of the European Association for Quality Assurance (ENQA).

So far, Agency adopted documents which could be found at the following link:

(http://hea.gov.ba/Dokumenti/dokumenti_agencije/Archive.aspx?template_id=52&pageIndex=1&langTag=en-US ).

List of domestic and international experts to provide assessment and conduct quality reviews and give recommendation on accreditation of higher education institutions and study programs in BiH is created in the public procedures. Totally 334 experts divided in four categories (academic community, students, labor market and international experts) are on the list. Trainings within the experts were conducted. Trainings of quality managers at the all 44 higher education institutions were conducted as well. All higher education institutions have established their internal system of QA and have working on the self-evaluations in sense of preparation for the process of accreditation.

Process of accreditation of higher education institutions against the Criteria for Accreditation has recently started. Five of 44 institutions have applied for accreditation and external panels have been appointed. Through the EU Tempus Project “EU standards for accreditation of study programs on BH universities – ESABIH”  project Criteria for the Accreditation of Study Programs are developed and pilot accreditation of the 33 study programs is conducted.

However, the Agency still needs further strengthening. Dividing the responsibilities among the Agency and different higher education authorities in the country in the process of external quality assurance, as well as running the appropriate strategy of quality assurance of higher education institutions and study programs (institutional vs. programs accreditation) are very challenging topics.  The Project will strengthen the capacity of Agency’s staff and all stakeholders such as higher education institutions, ministries and other governmental structures to ultimately contribute to achievements through transfer of experience from an agency from the European Union. Although the proposed twinning methodology, which the first of all includes close connections between two similar public institutions (QA agencies), the Project has to involve stakeholders deeply. The ultimate goal of the Agency is to apply Standards and Guidelines for Quality Assurance in European Higher Education Area and to become a full member of European Association of Quality Assurance (ENQA) and to be listed in the European QA Register.

3.2	Linked activities

Project ''Support to establishment and functioning of the Agency for Development of Higher Education and Quality Assurance''

Project ''Support to establishment and functioning of the Agency for Development of Higher Education and Quality Assurance'' (2009 – 2012) is financed by the Austrian Development Agency and is fully implemented by the Agency for Development of Higher Education and Quality Assurance. The main objective of the project is establishment and implementation of a functional and efficient policy development system of quality assurance in higher education.Through this project, the Agency for Development of Higher Education and Quality Assurance of BiH has received technical equipment (including 2 vehicles, eDMS system, IP telephony system, servers and other ITC equipment), and key staff of relevant ministries, academic institutions and the Agency acquired necessary skills to conduct quality assurance in accordance with European standards.The project lasted 32 months, from 1st October 2009 to 31st May 2012. The total project budget was € 362,848.51, of which € 310,000.00 was donation of the Austrian Development Agency while the Agency's participation was € 52,848.51.

ENQA Project „Implementing the ESG in the Balkan Region“

Regional cooperation and exchange of experiences have been increased through the new project of UNESCO and the Global Initiative on Quality Assurance Capacity of the World Bank (GIQAC) on the theme of „Implementing the ESG in the Balkan Region“. The Project aims to support the regional quality assurance agencies to comply with internationally accepted standards such as the Standards and Guidelines for Quality Assurance in the European Higher Education Area (ESG) and to create a shared pool of experts for quality assurance in higher education.  Project was implemented by ENQA and its duration was 14 month.

Tempus projects

The Agency has actively participated in five EU Tempus projects related to quality assurance.  By those projects a special policy making system has been developed:

- Strengthening Quality Assurance System within Western Balkan HEIs in Support of National and Regional Planning – CUBRIK – the co-ordinator being the University of Alicante, Spain. The aim of this project is to strengthen capacities of higher education institutions toward establishing adequate internal quality system, to strengthen quality assurance agencies and increase regional cooperation. The project is entirely based on consistent implementation of ESG. Duration of the Project is 36 months (2009 – 2012), total budget is 656,323.00 €.

- EU standards for accreditation of study programs on BH universities – ESABIH – the co-ordinator being Katholieke Hogeschool Sint-Lieven, Belgium. Through this project Criteria for accreditation of study programmes have been developed based on which the pilot accreditation of 33 study programmes from 8 public universities was conducted. Duration of the Project is 36 months (2009 – 2012), total budget is 864,470.00 €.

- Strategic Management of Higher Education Institutions Based on Integrated Quality Assurance System – SHEQA. The project leader is Katholieke Hogeschool Sint-Lieven from Belgium, and the partner from Bosnia and Herzegovina is the University of Mostar. The aim of this project is to develop key performance indicators (KPI) for higher education institutions to help an institution follow progress indicators, and to support ministries and agencies in decision-making related to institutions. Through this project information system will be developed to support KPIs. Duration of the Project is 36 months (2010 – 2013), total budget is 951,350.50 €.

- Building Capacity for Structural Reform in Higher Education of Western Balkan Countries – STREW. The project leader is the University of Novi Sad. This regional Tempus project is focused on developing the institutional system of Western Balkan countries to support and increase reforms in and development of higher education. Duration of the Project is 36 months (2010 – 2013), total budget is 729,120.06 €.

- Embedding Quality Assurance in Doctoral Education – project leader is WUS Austria and Medical Faculty of the University of Heidelberg, Germany. Duration of the Project is 36 months (2011 – 2014), total budget is 876,755.05 €.

IPA Projects

The Agency has so far been involved in four IPA projects:

- A joint project of the European Commission and the Council of Europe "Strengthening Higher Education III" –main benefiunts for HEA

- "Support to Reform of Higher Education in Bosnia and Herzegovina"

And is still particapting in:

- "The Reform of Financing of the Higher Education in Bosnia and Herzegovina"

- "Stgrenghtening Capacity Building in BiH for Human Resources Devlopment "

The agency has a bilateral Memorandums of Understanding with the following agencies:

- Austrian Accreditation Council ÖAR,

- Germany Agency EVELAG,

- Bulgarian National Evaluation and Accreditation Agency NEAA,

- National Centre for Public Accreditation Russia.

3.3	Results:

Mandatory results

- Standards and Guidelines for QA in European Higher Education Area (ESG) implemented on all levels (higher education institutions, higher education authorities and QA agencies);

- All HEIs have internal QA system developed, upgraded and in implementation;

- First cycle of accreditation of all BiH Higher Education institutions (HEIs) and selected number of study programs in BiH is done in accordance with ESG, conducted quality analyse with recommendations for removal of shortcomings in the quality of studies and higher education institutions, after the first cycle of institutional accreditation;

- Accreditation Criteria were revised;

- The provisions in laws as well as procedures of the higher educational authorities related to the quality assurance of higher education were analysed.

Specific results

      - Institutional Development

- An internal quality system of the Agency developed

- A system of strategic planning of the Agency developed

- Self-evaluation and external evaluation of the Agency conducted

      - Study Tour

- Links with two similar Agencies in EU  established

3. Staff Capacity Building

- Institutional and HR capacities strengthened

- Joint trainings for all stakeholders (QA managers at higher education institutions, training of civil servants in ministries, experts and Agency’s staff) organised.

- Activities:

- Run workshop about introducing and developing proper internal QA system at HEIs as to enable HEIs to conduct self-evaluation reports

- Conduct accreditation of 37 HEIs and activities leading to establishment of Register of accredited HEIs

- Analyse all HEIs external reports in sense of fulfilment of criteria for institutional accreditation and recommendations given by external panels

- Elaborate recommendations for improvement of QA system

- Develop the internal QA procedures and make a quality manual of the Agency

- Develop the mid-term strategy of the Agency

- Prepare the self-evaluation report and conduct external evaluation of the Agency against ESG, within the ENQA (External Report of the Agency submitted to the ENQA Board and EQAR Register Committee)

- Legislation review and review of procedures of higher education authorities regarding the quality assurance in higher education

- Review of Accreditation Criteria

- Organize two study visits to foreign accreditation and QA Agencies

- Inform on good practices in EU countries

- Organize events and promotional material on the project’s results to the academic community and general public

- Support the set up and regular working meetings of a working group of national and international experts for the review and reform of legislation relevant to QA in HE.

- Means/ Input from the MS Partner Administration:

Project Management

The scope of the Twinning Project will require clear project management to ensure that the Project achieves the Mandatory Results and in particular that the activities are well coordinated. Within their proposals Member States should detail the project management systems they would implement, as well as the previous project management experience of the proposed Project Leader and Resident Twinning Advisors, which will be taken into consideration during the evaluation and selection process. The emphasis will be put on:

- Project management, reporting, presentation and communication skills;

- Experience in human resource development.

For the purpose of efficient project coordination, the Steering Committee will be established by representatives of the Agency, Delegation of the European Union, Ministry of Civil Affairs, entity/cantonal ministries of education, and the twinning partner. Final composition of the Steering Committee will be defined in the initial phase of project implementation. Both partners shall be responsible for holding a meeting of the Steering Committee. The Steering Committee shall meet on a quarterly basis in order to discuss and approve reports presented by the project partners and decide about the schedule of planned activities in the project and achievement of project objectives.

- Profile and tasks of the Project Leader

Compliance with the profile is not however a strict requirement and Member State institutions may propose Project leader with other profiles so long as they have proven experience and expertise in the tasks required to be conducted by the Project Leader.

The profile of the Project Leader should be as follows:

  - university degree (preferable master or PhD degree);

  - minimum 5 years but preferably 10 years of professional experience in fields of quality assurance in higher education and/or reform of higher education;

  - Specific experience in Twining projects,

  - at list as an expert in Higher Education/QA, preferably in Western Balkans Region;

  - preferably experience as high level civil servant positioned in Government, including managerial positions at the QA agency or body which is listed in EQAR and/or full-member of ENQA;

  - experience in external QA activities (preferably in revision of QA Agencies)

  - familiar with Standards and Guidelines for Quality Assurance in European Higher Education Area (ESG) and with ENQA rules and policies;

  - good knowledge of EU systems and higher education policies and Bologna process, as well as management of complex projects;

  - good communication skills;

  - preferable experience in the Western Balkans Region;

  - fluency in English.

The Project Leader will be responsible for:

- management of the project including reports in accordance with the project plan;

- preparation of project implementation process;

- coordination of the short-term experts;

- supervision of the training programs;

- the quality of printed materials;

- rational use of all resources available.

- Profile and tasks of the RTA

The following profile is provided to give an indication of the types of skills, qualifications and expertise that it is expected would be required for the post.  Compliance with the profile is not however a strict requirement and Member State institutions may propose Resident Twinning Advisors with other profiles so long as they have proven experience and expertise in the tasks required to be conducted by this RTA.

The profile of the RTA should be as follows:

Qualifications:

- university degree and/or postgraduate

General experience:

- Proven experience in quality assurance in higher education;

- Preferably  experience in a managerial position in ENQA and/or EQAR recognized QA agency in an EU member state;

- Proven specific experience in Twining projects,

- at list as an expert in Higher Education/QA;

- Demonstrable experience in the transposition and/or enforcement of higher education policies related to the Bologna process in similar agencies;

- Experience in project management;

- Experience in human resources development;

- Experienced in planning and delivering of training;

- Excellent communication and information technology skills;

- Preferable experience in the Western Balkans Region.

Specific experience:

- Work experience in organizational management and planning at a senior level within higher education in EU Member state or accession country;

- Specific experience in  at least one of these domains: quality assurance, development of QA standards, internal QA procedures;

- Work experience in similar Agencies;

- Experienced in the design and implementation of public awareness programs.

The RTA will be responsible for:

- Review existing capacity level of the Agency;

- Review existing documents developed by the Agency;

- Conduct training needs assessment in relevant institutions;

- Coordinate and participate in the review of existing strategic plans of the Agency;

- Provide on-the-job training;

- Assist with conducting of comparative analysis of guidelines developed by the Agency with EU practise;

- Assist in the coordination of the training delivered by short-term experts;

- Evaluate training results and propose improvements;

- Regular co-ordination and cooperation with counterparts in the beneficiary country;

- Supervise all activities and assisting short-term advisers and experts.

The duration of the assignment of the Resident Twinning Advisor will be 24 calendar months.

- Profile and tasks of the medium/short-term experts:

The following profile is provided to give an indication of the types of skills, qualifications and expertise that it is expected would be required for the post.  Compliance with the profile is not however a strict requirement and Member State institutions may propose experts with other profiles so long as they have proven experience and expertise in the tasks required to be conducted by these experts.

The profile of the medium/short-term experts should be as follows:

Qualifications:

- university degree and/or postgraduate degree

General experience:

- Proven experience in quality assurance in higher education and/or higher education policies;

- Proven experience in external QA activities (preferably in revision of QA Agencies)

- Proven experience in work within the ENQA and/or EQAR recognized QA agency in an EU member state;

- Demonstrable experience in the transposition and/or enforcement of higher education policies related to the Bologna process in similar agencies;

- Experience in human resources development;

- Experienced in planning and delivering of training;

- Excellent communication and information technology skills;

- Preferable experience in the Western Balkans Region.

Specific experience:

- Work experience in organizational management and planning at a senior level within higher education in EU Member state or accession country;

- Specific experience in  at least one of these domains: quality assurance, development of QA standards, internal QA procedures;

- Work experience in similar Agencies;

- Experienced in the design and implementation of public awareness programs.

The areas of expertise will include:

- Development of QA standards in higher education;

- Development of Criteria for Accreditation;

- Development of internal QA system of the Agency;

- Preparation of self-evaluation report of the Agency,

- Analysing the impact of accreditation;

- Legislation review, development of legislation/normative acts and EU harmonization;

- Design of training needs;

- Preparation and delivery of training;

- Strategic and business planning;

- IT expertise;

- PR activities;

- Statistics;

- Establishment of links between education and social partners.

Tasks for Medium/Short-term Experts

It is expected that medium/short-term experts will provide inputs in the following areas:

- Analysis of existing practices related to QA;

- Assist in development of all elements of QA in higher education;

- Drafting of relevant reports and other relevant documents;

- Development of training plan and human resources development plan;

- Conduct training within all stakeholders;

- Definition of the internal QA structure;

- Development of the midterm strategy;

- Development of business plan and human resources development plan for the Agency;

- Legislation review;

- Assistance in improvement of existing practices and introduction of new methods of PR activities;

- Providing trainings in relevant issues;

The number, tasks and duration of short term experts will be defined in the work plan.

- Institutional Framework

The implementation of the program requires the full commitment and participation of the senior management of the Agency, the Ministry of Civil Affairs of Bosnia and Herzegovina, Agency for Accreditation of Higher Education Institutions of Republika Srpska, in coordination with entity and cantonal Ministries of Education and the Department for Education in Brcko District, and 44 higher education institutions.

They must be fully informed and consulted in the development and implementation of the institutional changes and policies required to deliver the project results. The senior management of the Agency must ensure the creation of Working Groups as agreed with the project SC to facilitate the implementation of the respective activities of the twinning project.

The BIH twinning partner will ensure adequate support and basic equipment for the work of experts. This includes administrative support, office space, phone and fax (communication within the BIH) in Banja Luka, and provision of other necessary conditions. The contribution should also include logistical support for the various training activities, including selection of trainees (in consultation with the EU experts), as well as providing the EU experts with legislation and any other documents necessary for the implementation of the project.

The BIH twinning partner shall ensure that appropriate staff is made available to work alongside the EU twinning partner(s). In particular the Senior Management of the Agency will assist with nomination of members of working groups from the Agency.

It will also appoint chairmen and participants for the Working Groups.

The BIH twinning partner shall in addition provide all possible assistance to solve unforeseen problems that the EU MS twinning partner(s) may face.

- Budget

1.000.000 EUR + 50.000 EUR (co-financing)

Co-financing will be separately contracted and it will be contribution in running costs and one part of administrative costs (paper, printing costs)

- Implementation Arrangements

- Implementing Agency responsible for tendering, contracting and accounting including contact person and full contact details

EUD to Bosnia and Herzegovina

Ms Jadranka Mihic,

Programme Manger

Skenderija 3a, Sarajevo

- Main counterpart in the BC, including contact person and contact details. Also include RTA counterpart and the BC Project leader

Agency for Development of Higher Education and Quality Assurance

Blvd. vojvode Stepe Stepanovića 11

BA – 78000 Banja Luka

www.hea.gov.ba

Tel: +387 51 430 510

Fax: +387 51 462 302

Contact person:

Mr. Boris Ćurković, Deputy Director

e-mail: Boris.Curkovic@hea.gov.ba

BC Project leader:

Mr. Husein Nanić, Director

e-mail: Husein.Nanic@hea.gov.ba

Deputy Senior Programme Officer:

Mr. Jugoslav Vuk Tepić

e-mail: Jugoslav.Vuk.Tepic@hea.gov.ba

RTA counterpart:

Mr. Boris Ćurković, Deputy Director

e-mail: Boris.Curkovic@hea.gov.ba

Other beneficiaries and partners are as follows:

- Ministry for Civil Affairs,  Sector for education;

- Entity and cantonal ministries of education and of BIH;

- Education department of the Government of Brčko district of B&H;

- Agency for Accreditation of Higher Education Institutions of Republika Srpska;

- Higher education institutions in Bosnia and Herzegovina.

- Contracts

One Twinning contract (Institutional building is envisaged: for organization, development and implementation.

7 Implementation Schedule (indicative)

- Launching of the call for proposals (Date)

October  2012

- Start of project activities (Date)

September 2013

- Project completion (Date)

September  2015

- Duration of the implementation period (number of months)

24 months + 3 months for start-up and closing phase

8.	Sustainability

Population of BiH will have more benefits if the Project results are achieved as planned. Project will certainly contribute to higher education sector reform having catalytic effects to reducing public expenditures. It will enable better quality of higher education and its recognisability in the European Higher Education Area.

The successful development of the BiH Agency will ensure implementation of relevant policies and strategic documents in its related fields. It will indirectly contribute to coherency and harmonization of reforms of higher education and free movement of students through education system in BIH and abroad.  It will contribute to development of better links between the higher education sector and partners. The Agency will be involved in international activities, and will be a partner to similar Agencies in region and in EU.

This project is aiming at providing assistance for the proper start-up and proper functioning of a quite new institution in BIH. This is a new type of institution and the legal basis for its operation is also totally new for the country. The twinning project will have to seek for sustainable solutions and approaches, which shall ensure adoption of best practices and thus prepare grounds for BIH full compliance with the EU standards.

- Crosscutting issues

The Project activities will cover the needs of all relevant population groups without any kind of discrimination. It will pay special attention in addressing gender equity. It will contribute to equal access to the higher education by insuring equal access to education op in whole country.

- Conditionality and sequencing

This project has been prepared and planned for in cooperation with the Agency for Development of Higher Education and Quality Assurance as well as responsible Ministries of the Beneficiary country. All conditions should be well prepared for a start-up of the implementation of this project.

Annexes to project Fiche

- Logical framework matrix in standard format (compulsory)

- Annual Report of the Agency for 2011

# ANNEX I: 	Logical framework matrix

| LOGFRAME PLANNING MATRIX FOR Project Fiche |  | Programme name: IPA National Programme 2011 – BiH - "Education" |  |  |
| --- | --- | --- | --- | --- |
| Project title: Strengthening Institutional Capacity of the Agency for Development of Higher Education and Quality Assurance for implementing the Standards and Guidelines for Quality Assurance in European Higher Education Area |  | Contracting period expires: |  | Disbursement period expires: |
| CRIS Number: |  | Total budget : 1 050 000 | IPA budget: 1 000 000 |  |
| Overall objective | Objectively verifiable indicators | Sources of Verification |  |  |
| To contribute to increased mobility and employability of labour force through improvement of work quality of higher education insitutions in line with Bologna process | - Increased number of employed graduates - Number of students spending study periods in different Universities in BiH and out of the country | - Annual EU progress report on BiH - Development reports on BiH |  |  |
| Project purpose | Objectively verifiable indicators | Sources of Verification |  | Assumptions |
| To improve and develop human resources and institutional capacities for quality assurance in higher education. | Agency for Development of Higher Education and Quality Assurance is full member of ENQA and listed in EQAR | - Decisions of ENQA Board and EQAR Register Committee, web page of ENQA and EQAR (section Register of QA agencies) - Published external QA reports - Relevant documents adopted by responsible authorities. |  | - All parties (twinning implementing agency and beneficiary) mobilize appropriate human and financial resources - Stable political and economic climate - Relevant institutions committed to cooperate |
| Results | Objectively verifiable indicators | Sources of Verification |  | Assumptions |
| Mandatory results: - Standards and Guidelines for QA in European Higher Education Area (ESG) implemented on all levels (higher education institutions, higher education authorities and QA agencies); - All HEIs have internal QA system developed, upgraded and in implementation; - First cycle of accreditation of all BiH Higher Education institutions (HEIs) and selected number of study programs in BiH is done in accordance with ESG, conducted quality analyse with recommendations for removal of shortcomings in the quality of studies and higher education institutions, after the first cycle of institutional accreditation; - Accreditation Criteria were revised; - The provisions in laws as well as procedures of the higher educational authorities related to the quality assurance of higher education were analysed. Specific results: - An internal quality system of the Agency developed - A system of strategic planning of the Agency developed - Self-evaluation and external evaluation of the Agency conducted - Links with two similar Agencies in EU established - Institutional and HR capacities strengthened - Joint trainings for all stakeholders (QA managers at higher education institutions, training of civil servants in ministries, experts and Agency’s staff) organised | - Agency is full member of ENQA and listed in EQAR - 30 HEIs which have proper internal QA procedure introduced - 100% of HEIs and 25% (out of ca. 1,200) of study programs accredited - 30 HEIs listed into the Register of accredited HEIs - Report on analysis submitted to Council of Ministers and Conference of BiH Education Ministers - New Criteria drafted - Report on analysis submitted to Council of Ministers and/or Conference of BiH Education Ministers - Agency’s quality manual published - Agency’s Strategy Developed and submitted to the Steering Board - Self-evaluation and external evaluation of HEA conducted - 25 Agency’s employees as well as at least 15 employees from all relevant ministries and at least 40 employees at HEIs and 230 external QA expert well trained about all aspects of accreditation and QA in HE - All HEIs have received information about the project’s results, including total of approx. 1,000 individuals (academics, university administrations, ministries, social partners, etc.) | - Decisions of ENQA Board and EQAR Register Committee, web page of ENQA and EQAR (section Register of QA agencies) - Project Report - Agency’s documentation about internal QA (policies, procedures, strategy), Agency’s annual reports -Institutional self-evaluation reports of HEIs - Decisions on accreditation, web page of the Agency – section external reports, section Register - Conclusion of the Council of the Ministers of B&H and Conference of BiH Education Ministers - Decision of Agency’s Steering Board - Conclusion of the Council of the Ministers of B&H and Conference of BiH Education Ministers - Web page of the Agency - Conclusion of the Steering Board - Reports of HEIs- Project Reports, training reports, WS reports, evaluation sheets, lists of contacts, minutes of Meetings, study visit reports |  | - Political commitment and follow-up by the relevant authorities particularly on the establishment, mandate and scope of the independent QA bodies. - Successful implementation of the ESABIH and SHEQA TEMPUS projects - Institutional accreditation is started at least at one canton/entity |
| Activities | Means | Costs |  | Assumptions |
| - Run workshop about introducing and developing proper internal QA system at HEIs as to enable HEIs to conduct self-evaluation reports - Conduct accreditation of 37 HEIs and activities leading to establishment of Register of accredited HEIs - Analyse all HEIs external reports in sense of fulfilment of criteria for institutional accreditation and recommendations given by external panels - Elaborate recommendations for improvement of QA system - Develop the internal QA procedures and make a quality manual of the Agency - Develop the mid-term strategy of the Agency - Prepare the self-evaluation report and conduct external evaluation of the Agency against ESG, within the ENQA (External Report of the Agency submitted to the ENQA Board and EQAR Register Committee) - Legislation review and review of procedures of higher education authorities regarding the quality assurance in higher education - Review of Accreditation Criteria - Organize two study visits to foreign accreditation and QA Agencies - Inform on good practices in EU countries - Organize events and promotional material on the project’s results to the academic community and general public - Support the set up and regular working meetings of a working group of national and international experts for the review and reform of legislation relevant to QA in HE. | Twinning contract | Total: EUR 1 050 000 IPA contribution: EUR 1 000 000 |  |  |