The "ACHIEVING ADVANCED STATUS" Program

(Programme: "Réussir le StatutAvancé")

Project no. ENPI/2011/022-778

Supporting the creation of the monitoring and observation system for social protection indicators MA/33 Beneficiary Authority: Ministry of Labour and Social Affairs Kingdom of Morocco

ABSTRACT TWINNING PROJECT

The global objective of this project is to provide the government with precise, reliable and up-to-date information and with a better knowledge of the social protection system, enabling design and implementation of a more effective social policy.

The specific objectives of this twinning project are:

- Setting-up an information system to collect data on social protection;

- Implement a monitoring and observation system for social protection indicators and publication of studies.

The legal and institutional framework of social security is provided by the Law 1-72-184 of 27 July 1972 concerning the social security system, modified on 23 August 1972. It includes health care, protection against professional accidents, professional sickness and pension for employees of the public and private sector.

Moroccan social security is generally linked to personal contribution and does not benefit all the population. Furthermore, it is not equally shared according to the risks. Services relating to health care represent the most important expenditure but they concern just 30 % of the employed population.This regards:

- The ad hoc health care system created for craftsmen, businesses and self-employed has not given positive results;

- Insurance contracts placed on the market do cover just a limited number of social services and are not always in line with the legal framework;

- Principles of equality, solidarity and mutualisation of risks, even if promoted at governmental level, represent the principal challenge for the implementation of a social security system in favour of vulnerable groups.

Even if the current social security system does not cover all potential risks, there is a positive trend in favour of students, self-employed workers, workers in the transportation sector and workers of the private sector, providing them aredundancy pay-off in case of job loss. Furthermore, a global reform of the pension scheme should soon be enacted.

Many reforms have begun in order to improve social security, namely in the field of global health care, but despite these attempts, current social assistance does not allow enough cover for employees and their families. Workers and actors of the informal economy are totally excluded from social and health care schemes.

Legal and institutional frameworks relating to social security are very diversified and articulated, combining public and private actors, intervening in different areas of the social security and providing specific assistance. Because of these elements, social security system appears to be neither coherent nor efficient. Therefore, data relating to social security are produced by different actors having a narrow perspective, and there is no central processing system of data and no indicators are yet identified.

In the near future, the beneficiary authority should publish a national strategy for social security

The components, the mandatory results and the specific activities under each component are presented below:

- Component 1:Design and setting up of an information, processing and monitoring system for social protection indicators

Mandatory result:

- A reliable database, shared between social protection stakeholders, is operational ;

Including inter alia the following activities:

1.1: Support to the mapping of the current situation in Morocco in the field of social protection system, stakeholders and data;

1.2: Experience sharing as regards building up of a database for social protection data through a study visit in two EU countries;

1.3: Drafting of a training plan for teams in other administrations (other than the beneficiary administration) in charge of producing data and for teams in the beneficiary administration of processing data and in charge of the deliverables in order to for building up the database;

#### 1.4:Implementing the training plan for teams in other administrations (other than the beneficiary administration) producing data and for beneficiary administration in charge of processing this data;

1.5: Audit of the database by a European expert;

- Component 2: Support to mobilisation and coordination of social protection stakeholders

Mandatory results:

- Relationships between the Ministry of Labor and Social Affairs and bodies in charge of the production of data and social indicators are defined and institutionalised;

Including inter alia the following activities:

2.1: Support to the definition of an institutional hierarchy of relationships between stakeholders in the field of social protection;

2.2: Audit of the legal and regulatory framework for data transfer for statistical purposes;

2.3: Support to registration with data producing administrations;

2.4: Support to the first work plan on statistical studies using social protection indicators;

- Component 3: Provision of a clear vision of existing indicators in the EU and in selected countries, to build up a network of experts in statistics, to train teams on processing statistics and supporting the publication of studies

Mandatory results:

- Reference indicators for Morocco are selected and used in published studies ;

Including inter alia the following activities:

#### 3.1: Study visit in an EU member State and to the EU Social Protection Committee;

#### 3.2: Workshop for the presentation of EU and selected countries’ indicators;

#### 3.3: Drafting a training plan on social indicators and studies for teams in charge of statistics in the Ministry of Labor and Social Affairs and in other institutions and administrations dealing with social protection;

#### 3.4: Implementation of the training plan for teams in charge of statistics in the Ministry of Labor and Social Affairs and in other institutions and administrations dealing with social protection;

3.5: Support to communication on reference social protection indicators selected by and for Morocco;

#### 3.6: Support to the development of a quality audit system for indicators.

This project is expected to start in February/March2015. Its duration is 24 months and the budget allocated is around 1.050.000 Eur.