Annex 1:

Logical Framework Matrix for Capacity Building of the Employment Support Services (ESS) of Georgia

| Capacity Building of the Employment Support Services (ESS) of Georgia |  | Programme name and number | EaPIC 2013 |
| --- | --- | --- | --- |
| Employment Support Services |  | Contracting period expires: | Disbursement period expires: |
|  |  | Total budget: EUR 1 100 000 |  |
| Overall objective | Objectively Verifiable Indicators | Sources of Verification |  |
| To reduce poverty and enhance social cohesion in Georgia through the introduction of measures designed to stimulate employment, and to ensure synergy between the demands of the labour market and the skills and qualifications offered by the vocational education and training system. | - Reduction in numbers of citizens living on or below the poverty line - Reduction in numbers of unemployed - Increase in total active labour population | - EC Regular Report on progress by Georgia in implementation of the AA - GEOSTAT reports - MoLHSA Annual Reports | Not applicable at project level |
| Project purpose | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| To strengthen the institutional and human resource capacities of the Employment Support Services of Georgia to deliver well-targeted, high-quality, gender-sensitive and cost-effective services to job seekers | - Enhanced management and administrative arrangements within the ESS - Institutional reorganisation has been completed - Operational guidelines for the full range of services offered by the ESS have been prepared and codified - Comprehensive quality assurance plan designed and implemented - Labour Market Information Management System (WorkNet Information System) upgraded and providing quantitative and qualitative data on current state of Georgian labour market - Staff are well-trained - ESS has developed the tools and techniques for preparing and delivering well-targeted and user-friendly communications and awareness raising campaigns | - EC Regular Reports on progress by Georgia in implementation of the AA - MoLHSA and ESS Annual Reports - Progress Reports delivered by the Partner Country in Twinning Project Evaluation reports - Satisfaction of job-seekers and employers with the quality and range of services provided by ESS | - Continued commitment to an interventionist labour market policy - MoLHSA continues to develop and implement coherent labour market policies, notably linked to active employment initiatives - Adequate budgetary resource allocation to the ESS permitting it to extend the range and quality of its services - Sufficient capacity within the ESS to absorb the assistance provided by Twinning partner. |

| 3.3. Results | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| --- | --- | --- | --- |
| Result 1: Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annex XXX of the Association Agreement | - Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annex XXX of the Association Agreement - Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annex XXX of the Association Agreement - Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annex XXX of the Association Agreement - Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence - Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation | - Official Journal of the Georgian Parliament (Indicator 1.1, 1.2 & 1.3) - EU Regular Reports on the implementation of the AA (Indicator 1.1, 1.2 & 1.3) - MoLHSA/ESS Regulations (Indicator 1.4 & 1.5) | - Adequate legal and regulatory drafting capacity within the MoLHSA and ESS - Continued commitment to an interventionist labour market policy - MoLHSA continues to develop and implement coherent labour market policies, notably linked to active employment initiatives - Adequate budgetary resource allocation to the ESS permitting it to extend the range and quality of its services - Sufficient capacity within the ESS to absorb the assistance provided by Twinning partner - Sufficient financial resources within the MoLHSA to develop the Labour Market Information System |
| Result 2: The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced, the internal management and administrative processes have been clearly codified | 2.1 Functional Review of the SSA/ESS 2.2 Support to drafting of an Institutional Reform Plan for the SSA/ESS 2.3 Support to the implementation of institutional reforms within the SSA/ESS 2.4 Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities 2.5 Introduction of new services within the ESS 2.6 Support to the further development of job-seeker counselling services 2.7 Development of a Procedures Manual 2.8 Development of a Quality Assurance Plan 2.9 Study Visit to MS to examine the range of services provided to job-seekers and employers through employment offices | - STEs reports (Indicator2.1, 2.2, 2.3,2.4, 2.5, 2.6, 2.7& 2.8) - Functional Review document (Indicator 2.1) - Institutional reforms – ESS & MoLHSA Annual Reports (Indicator s 2.1, 2.2& 2.3 ) - Revised registration procedures - ESS & MoLHSA Annual Reports (Indicator 2.4) - Number of new services introduced - ESS & MoLHSA Annual Reports (Indicator 2.5) - Revised methodology for counselling services - ESS & MoLHSA Annual Reports (Indicator 2.6) - Procedures Manual (Indicator 2.7) - Quality Assurance Plan (Indicator 2.8) - Study visit report (Indicator 2.9) - Project reports |  |
| Result 3: A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and is fully operational | 3.1 Review of the WorkNet Information System 3.2 Elaboration of a Concept Paper for upgrading the WorkNet Information System 3.3 Preparation of Terms of Reference/Technical Specifications for upgrading the WorkNet Information System 3.4 Development of methodology and tools for the preparation of monthly/quarterly and annual labour market reports 3.5 Study Visit to MS to examine the collection, collation and analyses of Labour market data by the employment services | - STE report (All indicators) - Concept Paper (Indicator 3.2) - Terms of Reference/Technical Specifications (Indicator 3.3) - Methodology and tools for labour market reports (Indicator 3.4) - Study visit report (Indicator 3.5) - Project reports |  |
| Result 4: Modern human resource management techniques have been introduced, the staff have acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established | 4.1 Review of current HRD policy 4.2 Drafting of an HRD Manual 4.3 Conduct Training Needs Analysis 4.4 Development of Training Programme and Training Materials 4.5 Conduct Formal and in-service trainings for the ESS staff 4.6 Development of the Training manual 4.7 Training/retraining platform (Train the trainers) | - STE reports (All indicators) - Review Paper (Indicator 4.1) - HRD Manual(Indicator 4.2) - Training Needs Analysis (Indicator 4.3) - (Indicator 4.1 - Training programme and training materials (Indicator 4.4) - Feedback evaluation sheets (training) (Indicator 4.5.) - Training Manual (Indicator 4.6) - ToT feedback evaluation sheets (Indicator 4.7) Project reports |  |

| Result 5: The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients | 5.1 Review of current communications policies and recommendations for upgrading 5.2 Support to the establishment of a Communications Unit within the ESS 5.3 Elaboration of communications and awareness raising strategy and Action Plan 5.4 Development and application of communications tools and materials 5.5. Study Visit to MS to experience practical use of the promotion and marketing of services to job-seekers and employers | - STE report (Indicator5.1) - Communications and Awareness Raising Strategy and Action plan (Indicator 5.2) - Communications materials, updated website, awareness events (Indicator 5.2 - Study visit report (Indicator 5.4) - Project reports |  |
| --- | --- | --- | --- |

| 3.4. Activities | Means (indicative) | Costs | Assumptions |
| --- | --- | --- | --- |
| General: | Twinning project: 18 months; STEs | EUR 1.100.000 |  |
| Organise Kick-off Conference and Steering Committee |  | RTA + PL Interpretation + Translation + Conference Equipment + Refreshments | Good cooperation between the Twinning Team and the ESS Interest on the part of other Government agencies, development partners, civil society organisations and the mass media |
| Organise final “Closing conference” |  | RTA, PL, STEs Interpretation + Conference Equipment + Refreshments |  |
| 3.4.1 Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annex XXX of the Association Agreement |  |  |  |
| 3.4.1.1 Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annex XXX of the Association Agreement | A short-term legal/regulatory drafting expert will conduct a review of Georgian Equal Opportunities legislation and related to employment in order to determine the measure of compliance with the EU Equal Opportunities Directives identified in Annex XXX of the Association Agreement. | STE in legal drafting with specific knowledge of the acquis related to Equal Opportunities – 10 wd translation | - The ESS assigns appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues - The ESS releases members of staff to participate in Project activities (e.g. training workshops, study tours, communications actions) - The ESS ensures that the results of the project are fully integrated into the work routine of the ESS - The ESS provides access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the Project - The ESS facilitates access to regional offices of the ESS, and to decision-makers at national, regional and local levels - The ESS provides suitable venues for training workshops/ presentations/ meetings held within the framework of the Project |
| 3.4.1.2 Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annex XXX of the Association Agreement | On the basis of the review (1.1), the short-term legal/regulatory drafting expert will draft a Concordance Report. The Report will highlight where there are gaps in the legislation related to employment or where the current provisions are not aligned with the EU Equal Opportunities Directives identified in Annex XXX of the Association Agreement. The STE will append to the Report a series of recommendations for closing the gaps and ensuring harmonisation with the relevant EU Directives. | STE in legal drafting with specific knowledge of the acquis related to Equal Opportunities – 10 wd Translation |  |
| 3.4.1.3 Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annex XXX of the Association Agreement | In accordance with the recommendations appended to the Concordance Report, the short-term legal/regulatory drafting expert will assist staff within the MoLHSA to draft/amend Georgian legislation to ensure that it is harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services. | STE in legal drafting with specific knowledge of the acquis related to Equal Opportunities – 50 wd Interpretation Translation |  |

| 3.4.1.4 Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence |  | The short-term legal/regulatory drafting expert will carry out a Gap Analysis to ensure that the regulations for which the ESS has competence are consistent with Georgian legislation that should be harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services. Appended to the Gap Analysis will be a series of recommendations for revising the regulations in order to ensure compliance. | STE in legal drafting with specific knowledge of the acquis related to Equal Opportunities – 10 wd Interpretation Translation Interpretation |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 3.4.1.5 Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation |  | Based upon the conclusions of the Gap Analysis and in accordance with the recommendations appended thereto, the short-term legal/regulatory drafting expert will assist the staff of ESS to revise those regulations for which it has competence ensuring that the revised regulations are consistent with Georgian legislation that should be harmonised with Council Directives Nº2000/43/EC, Nº2000/78/EC, and Nº2006/54/EC related to the principles of equal treatment and non-discrimination in employment supporting services. | STE in legal drafting with specific knowledge of the acquis related to Equal Opportunities – 20 wd Interpretation Translation |  |  |  |
| 3.4.2 The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced, the internal management and administrative processes have been clearly codified |  |  |  |  |  |  |
| 3.4.2.1 Functional Review of the SSA/ESS | An STE specialised in strengthening institutional and service delivery capacities of employment agencies will review the SSA’s/ESS’s Charter and Mission Statement and carry out a functional analysis of the management structure of the SSA/ESS, the range of services offered, and the distribution of tasks and staffing, and will recommend management/administrative and operational changes as appropriate. |  | STE in strengthening institutional and service delivery capacities of employment agencies – 15 wd Interpretation Translation Transport |  |  | - The ESS assigns appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues - The ESS releases members of staff to participate in Project activities (e.g. training workshops, study tours, communications actions) - The ESS ensures that the results of the project are fully integrated into the work routine of the ESS - The ESS provides access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the Project - The ESS facilitates access to regional offices of the ESS, and to decision-makers at national, regional and local levels - The ESS provides suitable venues for training workshops/ presentations/ meetings held within the framework of the Project |
| 3.4.2.2 Support to drafting an Institutional Reform Plan for the SSA/ESS | Based on the outcomes of Functional Review, the STE will assist management of SSA/ESS to prepare an Institutional Reform Plan for the SSA/ESS. |  | STE in strengthening institutional and service delivery capacities of employment agencies – 10 wd Interpretation Translation |  |  |  |
| 3.4.2.3 Support to the implementation of the Institutional reform of the SSA/ESS | The STE will assist the management of the SSA/ESS to implement the Institutional Reform Plan. At this juncture it is anticipated that this will entail revisions to the ESS’s Charter, Mission Statement and Regulations, a redefinition of the range of services offered, and a scheme ensuring a more efficient distribution of tasks and staff implemented. |  | STE in strengthening institutional and service delivery capacities of employment agencies – 55 wd Interpretation Translation Transport |  |  |  |
| 3.4.2.4 Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities | The STE will assist the ESS to review its operating procedures and methodologies for the registration of job-seekers and job opportunities, and the provision of matching services to clients to ensure that the current procedures allow for the profiling and tracking of job seekers and job opportunities, thereby assisting the ESS to develop a more sensitive understanding of the needs of the labour market and the available skills. On the basis of the review the STE will make recommendations to the ESS for strengthening its registration procedures as appropriate. |  | STE in strengthening institutional and service delivery capacities of employment agencies – 20wd Interpretation Translation |  |  |  |
| 3.4.2.5 Introduction of new services within the ESS | In line with the recommendations of the Functional Review, the STE will assist the management of the ESS to introduce new services as appropriate. Inter alia, this will involve developing the guidelines, methodologies, and tools for each of the new services introduced. |  | STE in development of counselling and related advisory services for job seekers -30 wd Interpretation Translation |  |  |  |
| 3.4.2.6 Support to the further development of job-seeker counselling services | The STE will work closely with the ESS, MoLHSA and MoES to further develop counselling services for job-seekers. The counselling services should cover such diverse issues as career guidance, opportunities for skilling/re-skilling, job interviewing techniques, and the preparation of job applications/curriculum vitae. The piloting of the enhanced counselling services will be done in at list 30% of the total ESS offices and revised according to the outcomes of the piloting. |  | STE in development of counselling and related advisory services for job seekers – 20 wd Interpretation Translation Transport |  |  |  |
| 3.4.2.7 Development of a Procedures Manual | On the basis of the above work, the RTA and STEs will draft an internal Procedures Manual for use by Head Office and Regional Office staff. |  | STE in development of counselling and related advisory services for job seekers – 15 wd Interpretation Translation |  |  |  |
| 3.4.2.8 Development of a Quality Assurance Plan | The MS will assist the management of the ESS to elaborate a Quality Assurance Plan and to install quality controls for use by Head Office and District Office staff |  | MS – 15 wd Interpretation Translation |  |  |  |
| 3.4.2.9 Study Visit to MS to examine the range of services provided to job-seekers and employers through employment offices. | The PL and the RTA will organise a Study Visit for a minimum of 5 working days for 7 persons (including RTA Assistant/translator as a member of the group) drawn from the MoLHSA and the ESS central and regional to an EU Member State, and in particular to the national and regional offices of the employment support services. The Study Tour will focus upon the range of services provided to job-seekers and employers through employment offices. |  | Study visit: 7 flights, 7 x 5 per diems |  |  |  |
| 3.4.3 A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and is fully operational |  |  |  |  |  |  |
| 3.4.3.1 Review of the WorkNet Information System | A short-term expert, specialised in the design and implementation of automated Labour Market Information Management systems, will carry out a review of the WorkNet Information System. The purpose of this Review is two-fold: to ensure that the WorkNet Information System is compatible with the wider Labour Market Information System being developed by the MoLHSA and to identify what methodologies and tools would be required to enable the ESS to develop a comprehensive overview of the current labour market, using the data gathered through the WorkNet Information System. |  | STE in Information and Communication Technologies – 10 wd Interpretation Translation |  |  | - The ESS assigns appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues - The ESS releases members of staff to participate in Project activities (e.g. training workshops, study tours, communications actions) - The ESS ensures that the results of the project are fully integrated into the work routine of the ESS - The ESS provides access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the Project - The ESS facilitates access to regional offices of the ESS, and to decision-makers at national, regional and local levels - The ESS provides suitable venues for training workshops/ presentations/ meetings held within the framework of the Project |
| 3.4.3.2 Elaboration of a Concept Paper for upgrading the WorkNet Information System | The STE will elaborate a Concept Paper, which will address three core areas: - Recommendations for refining the functionalities of the current WorkNet Information System to ensure interoperability and interconnectivity with the wider Labour Market Information System and for ensuring that the data collected and functionalities of the operating system enable the ESS to model and report upon the current labour market; - Identify upgrades in hardware and software that would be needed to ensure that the ESS possessed the technical capacities to implement recommendations under (a) above; - Suggest the approach, methodology, tools and templates that would be required to permit the ESS to develop monthly/quarterly and annual reports on the current state of the Georgian labour market |  | STE in Information and Communication Technologies – 25 wd Interpretation Translation |  |  |  |
| 3.4.3.3 Preparation of Terms of Reference/Technical Specifications for upgrading the WorkNet Information System | In line with the recommendations contained in Section (b) of the above Concept Paper, the STE will support the ESS to prepare the Terms of Reference and Technical Specifications for the procurement of off-the-shelf or tailor-made software and hardware. |  | STE in Information and Communication Technologies – 15 wd Interpretation Translation |  |  |  |
| 3.4.3.4 Development of methodology and tools for the preparation of monthly and annual labour market reports | In line with the recommendations contained in Section (c) of the above Concept Paper, the STE will support the ESS to design and develop the methodology, tools and templates that would permit the ESS to develop consolidated monthly/quarterly and annual reports on the current state of the Georgian labour market, and provide accurate data on supply and demand in the labour market, disaggregated by region/age/gender as a minimum. |  | STE in Information and Communication Technologies – 20 wd Interpretation Translation |  |  |  |
| 3.4.3.5 Study Visit to MS to examine the collection, collation and analysis of labour market data by the employment services | The PL and the RTA will organise a Study Visit for a minimum of 5 working days for 7 persons (including RTA assistant/interpreter as a member of the group) drawn from the MoLHSA and the ESS central and regional offices. to an EU Member State, and in particular to the national and regional offices of the employment support services. The Study Tour will focus upon the collection, collation and analysis of labour market data. |  | Study visit: 7 flights, 7 x 5 per diems |  |  |  |
| 3.4.4 Modern human resource management techniques have been introduced, the staff have acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established; |  |  |  |  |  |  |
| 3.4.4.1 Review of current HRD policy | An STE in HRD/training will be provided, who will carry out a review of the current HRD policy together with the management of the ESS. In particular, the review will focus upon the recruitment system, terms and conditions of employment, career development and promotions’ policy, in-service training, and performance appraisal. Based upon the results of the review, the STE will suggest revisions to the current HRD policy to the ESS management. |  |  | STE in Human Resource Development and training –10 wd Interpretation Translation | - The ESS assigns appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues - The ESS releases members of staff to participate in Project activities (e.g. training workshops, study tours, communications actions) - The ESS ensures that the results of the project are fully integrated into the work routine of the ESS - The ESS provides access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the Project - The ESS facilitates access to regional offices of the ESS, and to decision-makers at national, regional and local levels - The ESS provides suitable venues for training workshops/ presentations/ meetings held within the framework of the Project |  |
| 3.4.4.2 Drafting of an HRD Manual | On the basis of the above review and subsequent agreement with the ESS management, the STE in HRD/training will implement revisions to the HRD policy. Inter alia, this is expected to include: developing transparent recruitment, career development and promotions procedures; elaborating standard contracts; defining templates and methodology for performance assessment; identifying standard induction and in-service training modules. The new HRD policy will be consolidated into a HRD Manual. |  |  | STE in Human Resource Development and training – 20 wd Interpretation Translation |  |  |
| 3.4.4.3 Conduct Training Needs Analysis | The STE in HRD/training will carry out a comprehensive training needs analysis of the staff of the ESS (Headquarters and District Offices) |  |  | STE in Human Resource Development and training – 5 wd Interpretation Translation Transport |  |  |
| 3.4.4.4 Development of Training Programme and Training Materials | On the basis of the Training Needs Analysis the STE in HRD/training will draft a Training Programme for the Headquarters and District staff. The programme will be divided between formal and in-service training, and mentoring of senior management. In addition the STE will prepare and organise the translation of the training materials. |  |  | STE in Human Resource Development and training – 15 wd Interpretation Translation |  |  |
| 3.4.4.5 Conduct Formal and in-service trainings for the ESS staff | The STE in HRD and training will implement the formal training programme through a series of workshops at national and district levels. A minimum of 10 formal workshops for 1-2 days per each on different topics for 140 persons in total will be provided and at least 75 hours of in-service training. Series of trainings will be also conducted in three main regional centres: Kakheti, Imereti and Ajara. In addition, the STE will provide in-service training to ESS Headquarters staff and will mentor the Director and Deputy Director. |  |  | STE in Human Resource Development and training – 35 wd Interpretation Translation Transport |  |  |
| 3.4.4.6 Development of the Training manual | In the final three months of the project, the STE in HRD/training will consolidate the training materials into a Training Manual |  |  | STE in Human Resource Development and training – 5 wd Translation |  |  |
| 3.4.4.5 Training/retraining platform (Train the trainers) | The STE in HRD and training will provide further training to the existing cadre of 5 trainers. The objective is to strengthen capacity within the ESS to train and re-train staff. The training will cover pedagogic methods, the design and implementation of induction training for new members of staff, as well as the content of the Training Manual. |  |  | STE in Human Resource Development and training – 5 wd Interpretation Translation |  |  |
| 3.4.5 The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients |  |  |  |  |  |  |
| 3.4.5.1 Review of current communications policies and recommendations for upgrading | A short-term communications expert will be recruited to support the ESS to review its current communications policies and provisions and to help the Service to establish a dedicated communications unit. In the first instance, the communications expert and the ESS, together with the STE in strengthening institutional and service delivery capacities of employment agencies, will assess the Service’s communications needs and provide recommendations for upgrading the approach, messages, target groups, and communications tools. |  |  | STE in communications and awareness – 5 wd Interpretation Translation | - The ESS assigns appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues - The ESS releases members of staff to participate in Project activities (e.g. training workshops, study tours, communications actions) - The ESS ensures that the results of the project are fully integrated into the work routine of the ESS - The ESS provides access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the Project - The ESS facilitates access to regional offices of the ESS, and to decision-makers at national, regional and local levels - The ESS provides suitable venues for training workshops/ presentations/meetings held within the framework of the Project |  |
| 3.4.5.2 Support to the establishment of a Communications Unit within the ESS | On the basis of the above review (5.1), the STE and the management of the ESS will draft and agree on the mission statement, functions and optimum staffing level of the communications unit. Thereafter, the communications expert will provide in-service mentoring to the staff of the Communications Unit. |  |  | STE in communications and awareness – 10 wd Interpretation |  |  |
| 3.4.5.3 Elaboration of communications and awareness raising strategy and Action Plan | Based upon the results of the above review, the STE and the ESS will prepare a communications and awareness strategy and associated Action Plan. As a minimum the strategy will identify the priorities, objectives and anticipated results, and will define the approach, messages, target groups, and communications tools to be used. The associated Action Plan will include clear timeframes, indicators of achievement and sources of verification. |  |  | STE in communications and awareness – 20 wd Interpretation Translation |  |  |
| 3.4.5.4 Development and application of communications tools and materials | The STE in Communications and the ESS, together with support from the STE in Information and Communications Technologies will develop communications tools and materials. Inter alia, this will entail the establishment of consultative mechanisms with employers, the further development of the ESS’s interactive web-site, www.worknet.gov.ge, the elaboration of information materials for job-seekers and employers, and the organisation of promotional events. |  |  | STE in communications and awareness – 20 wd STE in Information and Communications Technologies – 10 wd Interpretation Translation |  |  |
| 3.4.5.5 Study Visit to MS to experience practical use of the promotion and marketing of services to job-seekers and employers | The PL and the RTA will organise a Study Visit to an EU Member State for a minimum of 5 working days for 7 persons (including RTA Assistant/interpreter as a member of the group) drawn from the MoLHSA and the ESS central and regional offices, and in particular to the national and regional offices of the employment support services. The Study Tour will focus upon the promotion and marketing of services to job-seekers and employers |  |  | Study visit: 7 flights, 7x 5 per diems |  |  |