| Nº | ACTIVITY | STE DAYS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | RTA Mobilisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Kick-off event | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 | Activities linked to Results 1: Revision of the Georgian Legal Framework of equal opportunities legislation and related to employment in line with the EU acquis and in accordance with the provisions of Annex XXX of the Association Agreement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.1 | Review of Georgian Equal Opportunities legislation related to employment and measure of concordance with EU Equal Opportunities legislation identified in Annex XXX of the Association Agreement | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.2 | Drafting a Concordance Report and recommendations for harmonisation of the Georgian legislation related to employment with the EU Equal Opportunities Directives identified in Annex XXX of the Association Agreement | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.3 | Support to legal drafting with regard to the Equal Opportunities legislation related to the employment service identified in the relevant Annex XXX of the Association Agreement | 50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.4 | Gap analysis of the equal treatment and non-discrimination sections of the regulations for which the ESS has competence | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1.5 | Support to regulatory drafting with regard to Equal Opportunities legislation identified in Annex XXX of the AA Regulatory drafting support to the ESS in order to ensure compliance of the regulations for which it has competence with the revised Georgian Equal Opportunities legislation harmonised with EU Equal Opportunities legislation | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 | Activities linked to Result 2: The structure and functions of the ESS have been revised to reflect it expanded role in the labour market management processes, the range and quality of services provided to job-seekers have been piloted and enhanced, the internal management and administrative processes have been clearly codified |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.1 | Functional Review of the SSA/ESS | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.2 | Support to drafting an Institutional Reform Plan for the SSA/ESS | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.3 | Support to the implementation of institutional reforms within the SSA/ESS | 55 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.4 | Review and revision (if required) of the current procedures for registration of job-seekers and job opportunities | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.5 | Introduction of new services within the ESS | 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.6 | Support to the further development of job-seeker counselling services | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.7 | Development of a Procedures Manual | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.8 | Development of a Quality Assurance Plan | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2.9 | Study Visit to MS to examine the range of services provided to job-seekers and employers through employment offices | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 | Activities linked to Result 3: A comprehensive Labour Market Information Management System (WorkNet Information System) has been established and is fully operational |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.1 | Review of the WorkNet Information System | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.2 | Elaboration of a Concept Paper for Up-grading the WorkNet Information System | 25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.3 | Preparation of the Terms of Reference/Technical Specifications for upgrading the WorkNet Information System | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.4 | Development of methodology and tools for the preparation of monthly/quarterly and annual labour market reports | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3.5 | Study Visit to MS to examine the collection, collation and analysis of labour market data by the employment services | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4 | Activities linked to Result 4: Modern human resource management techniques have been introduced, the staff have acquired the necessary skills and experience to provide high quality services to job-seekers, and an in-house training and retraining platform has been established; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.1 | Review of current HRD Policy | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.2 | Drafting of an HRD Manual | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.3 | Conduct Training Needs Analysis | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.4 | Development of Training Programme and Training Materials | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.5 | Conduct Formal and in-service trainings for ESS staff | 35 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.6 | Development of the Training Manual | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.4.7 | Training/retraining platform (Train the Trainers) | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5 | Activities linked to Result 5: The ESS has acquired the necessary tools and materials to communicate effectively its range of services to clients and potential clients |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.1 | Review of current communications policies and recommendations for upgrading | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.2 | Support to the establishment of a Communications Unit within the ESS | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.3 | Elaboration of a communications and awareness raising strategy and Action Plan | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.4 | Development and application of communications tools and materials | 20 + 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.5.5 | Study Visit to MS to experience practical use of the promotion and marketing of services to job-seekers and employers | 0 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Closing Conference | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |