| REPUBLIC OF CROATIA MINISTRY OF ECONOMY, LABOUR AND ENTREPRENEURSHIP |  |
| --- | --- |

Programme: IPA 2009

Partner Country: Croatia

Area of Cooperation: Free movement of workers

# IPA TWINNING PROJECT FICHE

## “Strengthening the administrative capacity of competent authorities and implementation agencies for co-ordination of social security schemes”

Project budget: € 1.000.000

IPA 2009 TWINNING PROJECT FICHE

1.	Basic Information

1.1	Programme:			 IPA 2009

1.2	Twinning Number:		 HR 09 IB SO 01

1.3    Title:	Strengthening the administrative capacity of competent authorities and implementation agencies for co-ordination of social security schemes

1.4   Sector:				 Free movement of workers

1.5   Beneficiary country:	Croatia

- Objectives

  - Overall Objective:

The overall objective is to strengthen the administrative capacities of Croatian competent authorities and implementation agencies to implement acquis, in the field of free movement of workers and co-ordination of social security schemes.

2.2	Project purpose:

Project purpose is to increase the institutional and administrative capacity of competent authorities and implementation agencies (liaison bodies) to effectively coordinate social security schemes upon EU accession.

2.3    Contribution to Accession Partnership/ Stabilization and Association Agreement/

National Programme for Integration of the Republic of Croatia into the EU (NPIEU)

The project is in line with:

Accession Partnership (www.mvpei.hr/ei), New Council Decision of February 2008, which in the area of free movement of workers puts requirement to “Abolish any discriminatory measures towards EU migrant workers and EU citizens  and to reinforce administrative structures for the co-ordination of social security schemes”. This project will contribute to the fulfillment of both requirements, especially to the latter through the extensive training of the staff, application of the EU regulations and recommendations for better functioning of all the institutions in charge of the co-ordination of the social security schemes.

Stabilisation and Association Agreement (Croatian Official Gazette - International Agreements № 14/2001; www.mvpei.hr/ei), which envisages the possibility of establishing “the rules for the co-ordination of social security systems for workers with Croatian nationality, legally employed in the territory of Member state, and for the members of their families legally resident there”, in the article 47. This project will contribute to the aforementioned through the improvement of administrative procedures on implementation and application of co-ordination rules.

National Programme for the Adoption of the Acquis 2009 (NPAA 2009), which is an integral part of the National Programme for the Integration of the Republic of Croatia into the European Union (NPIEU -   www.mvpei.hr/ei ) in the area of free movement of workers, underlines the importance to ensure necessary administrative capacity for the correct application of the acquis on co-ordination of social security systems as from the date of accession. It states that “the principle task in the forthcoming period will be strengthening the administrative structures for the co-ordination of social security systems”. Adequate administrative capacities should be especially developed and enforced in the competent authorities with supervisory competence (ministries). “This will entail the training of existing staff and the development of the skills necessary to take part in the preparation of regulations, as well as for familiarisation with the regulations of the European social acquis communautaire, which will be transposed into Croatian legislation”. The same is also stated in the Program of the Government of the Republic of Croatia for assumption and implementation of the acquis communautaire published in the 2010. Tasks and objectives stated in the document will be met with the planned trainings of the staff in charge of the co-ordination of the social security schemes as well as with the improvement of existing administrative procedures.

EU Common Position (AD 18/08, 16 June 2008, AD 18/08, LIMITE CONF-HR 12) which states that Chapter 2. Freedom of Movement of Workers may only be provisionally closed once it is agreed by the EU that the following benchmark is met: Croatia demonstrates that adequate administrative structures and enforcement capacity will be in place to implement correctly the acquis on freedom of movement for workers, particularly in the field of co-ordination of social security systems, by the time of accession. According to revised Common position (AD 3/09, 2 Jully 2009, AD 3/09, CONF-HR 23/07) and positive Commission assessment of the benchmark related to the co-ordination of social security capacities, Croatia has reached a good level of alignement with the acquis on freedom of movement for workers. In the field of co-ordination of social security schemes measures have been taken, with the goal to develop adequate administrative structures and enforcement capacity to implement correctly the acquis in this field. According to EU Common Position (AD 13/09, 30 September 2009, LIMITE CONF-HR 8, Revision of  CONF-HR 12/8) the EU underlines the importance for Croatia to ensure that the necessary administrative capacity is developed in view of correct application of the acquis on co-ordination of social security systems as from date of accession. The EU also noted that the requirements of the closing benchmark set out in the EU Common position (CONF_HR 12/8) have beed fulfiled after the Government of the Republic of Croatia submitted the Report on fulfillment of the obligations in the Chapter 2 as well as the Document on fulfillment of the closing benchmark in relation to adequate administrative structures and enforcement capacity. This Document comprises Croatian plan for organizational adjustments and introduction of the appropriate measures for increasing the administrative capacity and efficiency of administrative strucutures. On the base of these documents Chapter 2. was provisionaly closed on the Inter-governmental Conference held on 3 October 2009. The need for continuation to adopt the current administrative capacities for carrying out a potentially wider range of tasks, still exists, which means that there is still a need for further increase in the number of civil servants, structural reorganisation and carrying out further professional training. Results of further professional training should be reached  through this TW project.

3.	Description

3.1	Background and justification:

The free movement of workers is a fundamental expression of the free movement of persons, which represents one of the four pillars of the EU single market. Article 42 (ex Art. 51) of the EC Treaty requires that the Council adopt measures in the field of social security that would render possible the free movement of workers. Co-ordination of social security schemes is a cornerstone of the European internal market, allowing workers from one EU member state to work in another member state and still claim their full social security rights. Participation in this co-ordination mechanisms in EU requires not only the strict application of all principles according to its legal meaning, but also setting up adapted structures for its effective implementation, setting up a sufficiently reliable analytical and statistical tools with respect to the control mechanisms implemented to monitor EU co-ordination rules. The achievement of such important accession goals by the Republic of Croatia requires further strengthening of administration capacities of the competent authorities as well as of the implementation agencies. The EU legislation in the area of social security systems is represented by the Regulation (EEC) 1408/71 of the Council of 14 June 1971 on the application of social security schemes to employed persons and their families moving within the Community and Regulation (EEC) 574/72 of the Council of the 21 March 1972 establishing the procedure for implementing Regulation (EEC) 1408/71. In 2004 a new Regulation (EC) 883/2004 of the European Parliament and the Council of the 29 April 2004 on the co-ordination of social security systems has been approved, in order to replace the Regulation 1408/71, and in October 2009 the new implementing Regulation 987/09 was adopted. The application of these rules implies preparedness of all competent administrative structures for the application of these rules. It means well trained and educated civil servants/public servants who would be able to apply and to monitor the application of the co-ordination rules. It also means the preparation of analytical studies on impact of free movement of workers on Croatian administrative system, including impact study to the scheme of family benefits under the EU co-ordination rules. These studies should comprise also the financial study on the impact of free movement of workers, including estimation of additional costs for the Croatian health system with regards to the application of the co-ordination rules. The project is expected to influence raising of the public awareness on free movement of workers along with the development of the communication strategy for migrant workers.

3.2 Linked activities:

Ministry of Economy, Labour and Entrepreneurship applied for TAIEX Expert Mission and for TAIEX Study Visit, and the application forms have been approved by the European Commission. Objective of the TAIEX Expert Mission (held in Zagreb, from 31 August to 4 September 2009) was to familiarize the participants to the social security system for migrant workers and to provide support to Croatian administrative authorities and implementation agencies which will be competent for application of the EU co-ordination Regulations. Objective of the TAIEX Study Visit (held in Helsinki, from 21 to 24 April 2009) was to familiarize the participants with the organization of units in the administrative authorities which are responsible for applying EU regulations for co-ordination, as well as to provide general information regarding preparational activities for the administrative authorities related to applying of co-ordination rules. Croatian Institute for Health Insurance applied for TAIEX Study Visit and which was also approved by the European Commission. Study Visit was held in Prague, in May 2009. The objective of the Study Visit was to familiarize the participants with the organisational structure within liaison bodies for applying of the co-ordination rules in the area of disease risks, maternity and cost calculation, and also information related to the needs in IT system support for co-ordination. Croatian Pension Insurance Institute participated at the TAIEX Study Visit as well. The objective of this Study Visit was gathering information about the organisational structure within liaison bodies for  application of the co-ordination rules in the area of pension insurance as well as information related to the needs in IT system support . Study Visit was held from 25 to 27 January 2010, in the National Institute for Social Security of Spain, Central Service in Madrid.

Ministry of Economy, Labour and Entrepreneurship is also a counterpart and submitter of the Project “Further modernisation of the social security administration of Croatia”, within the MATRA Pre-accession Project Programme (MPAP) the implementation of which started at the beginning of 2009 and will finish at the end of 2010. (this project is follow-up of the previous MATRA project “Possibility for Abolishment of the Work Book System”, organized during 2007 and 2008 which aimed to reform the administrative and legislative framework of the work book system and consider the possibility to abolish the system of the work book). The aim of the current MATRA project is further modernisation of the Croatian social security administration in regard to the participation of Croatia in the EU social security co-ordination system. The project aims to assist the Croatian authorities responsible for the social security system in the process of developing the set up for a modern social security system and administration, which will facilitate the exchange of information with the European Commission and other EU member states, as well as simplify the communication with insured persons. Having in mind the possibility of entering into force the Regulation 883/2004, and its implementing Regulation 987/2009, before the time of Croatian accession to EU, which implies the introduction of electronic exchange of data, Croatian Ministry of Economy, Labour and Entrepreneurship requested for MPAP assistance with the design of a new institutional set up for recording data on social security benefits and pensions in conformity with EU requirements. One of the activities in the project will be detailed social security data survey. The results of the data survey will be used for drafting of a report with policy recommendations and an implementation plan in order to modernise and reorganise the Croatian social security administration. Some of the elements of the report will be defining of a reliable identification data set and set up for electronic data exchange in a so called e-Government system including the establishment of Access Points (per domain) or one Access Point. The results of the project will provide useful input for further development of the IT structure and further technical implementation. MATRA Project will explore all possibilities for connecting data basis in all institutions involved and will give recommendations about the most certain way of data exchanging. This Project will prepare Croatian administration for implementing the Regulation 883/2004. Existing data basis should be adjusted to the new conditions, but number of data that Croatian institutions collect in this moment, quality of data, availability and reliability of data are more or less on the satisfied level. The result of the Project will be recommendation on the secure way of data exchange and expert opinion on establishing one or more Access Point/Points connected to the EC Access Point. The Regulation 883/2004 and its implementing Regulation 987/2009 entered into force on May 1, 2010, with two years of transitional period, which is, in our opinion, enough time for Croatian administration to implement these recommendations and for final connecting with EU Member state's administrations.

And finally, the same Ministry is a counterpart of the IPA 2008 Regional Programme on “Social Security Co-ordination and Social Security Reforms in the South East Europe” follow-up of the previous “Social Security Support Programme”, also for the South East Europe (held from 2005 to 2007). The aim of both projects was/is to present the social security standards and principles of co-ordination of social security systems but for restricted territorial area – South East Europe, and prepare the administration of beneficiary countries for future EU membership, with presenting the legislative and institutional framework to the administration in South East Europe countries (three of them are candidate countries – Croatia, Turkey and Former Yugoslav Republic of Macedonia). This proposal for the project in the area of social security co-ordination should be complement with all other projects and at the same time it should not overlap with mentioned activities. In relation to proposed TAIEX activities, we consider the proposed project as a medium-term activity related to several beneficiaries, while TAIEX activities are short-term and restricted to small number of civil servants from the competent authorities. In relation to ongoing project in the area of co-ordination “Social Security Co-ordination and Social Security Reforms in the South East Europe” we consider that there will not be overlapping of the activities, because this project is focused to the restricted territorial area. And in relation to the MATRA/MPAP project, we consider that this will be an occasion to combine two projects with similar purpose, but at the same time with different ways of resumption of the results.

3.3 Results:

Component 1. Strengthening of institutional and administrative capacity of competent authorities and implementation agencies

Result 1.1:

- Overall co-operation and functioning of all institutions in charge of co-ordination of social security issues improved.

- Indicators of achievement:

- Analysis of the current level of co-operation and functioning of all relevant institutions, identifying existing shortcomings conducted and corresponding report produced;

- Recommendations for improvement of co-operation and more efficient functioning of all involved institutions prepared;

- Support and advice to the Inter-institutional Working Group provided and minutes of the meetings prepared;

- Recommendations and advice for functioning of the established units provided through roundtable discussions and minutes of the meetings prepared;

- Competent authorities’ staff prepared for active participation at the meetings in the EU institutions.

- Result 1.2:

- Capacity of the relevant institutions directly applying the co-ordination rules on the social security schemes enhanced, their expertise in this field upgraded and transfer of knowledge ensured through the trainings of future trainers.

- Indicators of achievement:

- Analysis of training needs conducted and training needs report produced;

- Training programmes for general and in-depth trainings prepared;

- At least 180 employees trained, each group of employees educated in the area related to their work;

- Train the trainers programme developed and continuous education ensured through the Train the trainers programme;

- At least 40 future trainers trained, in groups according to the area related to their field of work;

- Two (2) study visits (one to an old MS, one to a new MS; each for 8 civil servants) lasting 4 days conducted and report on the findings of the study visits drafted.

- Result 1.3:

Administrative procedures on implementation and direct application of the co-ordination rules harmonized with the EU co-ordination regulations.

- Indicators of achievement:

- Analysis of existing administrative procedures conducted and corresponding report on existing gaps and needs produced;

- Manuals and administrative procedures on implementation and application of the co-ordination rules prepared in line with the EU co-ordination regulations and approved by all institutions involved;

- Summary of the most important co-ordination rules and of the consolidated version of relevant EU regulations in English and Croatian prepared and distributed.

- Component 2. Analyses of impact of free movement of workers on Croatian social security administration system

- Result 2.1:

Comprehensive analytical and financial study of the impact of free movement of workers between Croatia and EU member states on the Croatian social security administrative system prepared.

- Indicators of achievement:

- Existing administrative system in charge of co-ordination of social security schemes analysed;

- Analytical study including modality of statistical monitoring of posted workers/frontier workers/migrant workers prepared;

- Financial study on the impact of free movement of workers comprising estimation of additional costs for the Croatian health system with regards to the application of the co-ordination rules and impact study to the scheme of family benefits regarding co-ordination rules prepared.

Component 3. Raising of public awareness on right of free movement of workers

Result 3.1:

Awareness raising strategy and communication system established and functioning.

Indicators of achievement:

- Awareness raising strategy and communication strategy developed;

- Plan for dissemination of information related to the free movement of workers prepared.

Result 3.2:

Information related to the free movement of workers disseminated to the general public.

Indicators of achievement:

- Information on right of free movement of workers on the EU Internal market published on the web sites of relevant institutions;

- Newsletter prepared,  Brochures prepared and disseminated

- At least 2 awareness raising events organized for general public.

  - Activities:

- Component 1: . Strengthening of institutional and administrative capacity of competent authorities and implementation agencies

- 1.1.1. Conducting analysis of the current level of co-operation and functioning of all institutions involved in social security issues. The analysis should identify shortcomings in cooperation and functioning of these institutions.;

- 1.1.2. Preparation of recommendations for improvement of co-operation and more efficient functioning of these institutions on the basis of the analysis conducted under activity no. 1.1.1.;

- 1.1.3. Providing support and advice to the Inter-institutional Working Group in charge of co-ordination of the social security schemes by holding roundtable discussions;

- 1.1.4. Providing recommendations and advice for functioning of the established units for coordination in the relevant institutions and for its mutual cooperation (advice should be provided by holding roundtable discussions);

- 1.1.5. Providing advice to the authorities involved in social security issues on the functioning of the relevant EU bodies by holding roundtable discussions. The purpose of this activity is to prepare the staff of the competent authorities for participation at the procedural and technical meetings in the EU institutions;

- 1.2.1. Conducting training needs analysis of the staff working in the competent authorities and implementation agencies on the social security matters and preparing training programmes for general and in depth trainings;

1.2.2. Conducting trainings for at least 180 employees on pension rights for migrant workers/frontier workers, health protection and reimbursement of health care costs and conditions for establishing European Health Insurance Card, family benefits and rights based on unemployment. The relevant staff should be organized in different groups which will receive the training in one or more of the aforementioned fields depending on their job description.;

1.2.3. On the basis of the analyses of training needs performed, developing train the trainers programme that will ensure continuous education;

1.2.4. Conducting training for at least 40 future trainers on pension rights for migrant/frontier workers, health protection and reimbursement of health care costs, family benefits and rights based on unemployment;

1.2.5. Organizing 2 study visits (one study visit to an old MS and one study visit to a new MS, each for 8 civil servants from the relevant institutions to counterpart institutions in the EU Member States), each lasting 4 days, in order to get an insight into the way coordination is ensured in the practice.;

1.3.1. Conducting analysis of existing administrative procedures related to the area of social security and identification of existing gaps related to the EU co-ordination regulations; preparation of report on gaps and needs;

1.3.2. Preparation of Manuals and administrative procedures on implementation and application of the co-ordination rules in line with the EU co-ordination regulations and on the basis of the analysis conducted under activity 1.3.1.;

1.3.3. Summarizing the most important co-ordination rules and existing consolidated versions of relevant EU regulations and preparation of printed version of aforementioned rules and regulations in English and Croatian for internal use in relevant institutions (each institution should receive at least one copy).

- Component 2:. Analyses of impact of free movement of workers on Croatian social security administration system

- 2.1.1. Conducting analysis of the existing administrative system in charge of co-ordination of social security schemes in Croatia.;

- 2.1.2. On the basis of the analysis conducted, drafting the Analytical Study on the impact of free movement of workers between Croatia and EU Member States on the Croatian administrative system. Speacial focus should be put on the administrative capacities of all institutions involved. Additionaly, the Study should include modality of statistical monitoring of posted workers/frontier workers/migrant workers.;

- 2.1.3. Conducting financial analysis and preparing Financial study on the impact of free movement of workers, including estimation of additional costs for the Croatian health system with regards to the application of the co-ordination rules as well as impact study to the scheme of family benefits under the EU co-ordination rules.

Component 3: Raising of public awareness on right of free movement of workers

3.1.1. Development of awareness raising strategy on right of free movement of workers and communication strategy for migrant workers;

3.1.2. Preparation of strategic work plan for dissemination of information related to the free movement of workers for general public;

3.2.1. Preparation of information on social security rights of migrant workers and their families as well as conditions of posting and national employment conditions in the Republic of Croatia and different EU Member States. Aforementioned information should be published on the web sites of the competent authorities and implementation agencies in order to inform Croatian citizens on right of free movement of workers on the EU Internal market;

3.2.2. Preparation of a newsletter to be regularly updated and used by the Beneficiary institution and preparation /dissemination of brochures for general public;

3.2.3. Organizing of at least 2 Awareness raising events for general public. The form of the events will be subject to agreement between the twinning partners and based on the conclusions of the awareness raising strategy developed under activity 3.1.1.;

Two visibility events will be organized in the course of the implementation of the project; Kick-off meeting at the start of the implementation and the Final meeting at the end of the implementation of the project activities.

3.5 Means /Input from the MS Partner Administration

3.5.1 Profile and tasks of the Project Leader

Profile of the Project Leader

Requirements:

- University level education or equivalent professional experience of 15 years in the area of  social welfare

- 8 years of experience in the area of social security

- Working level of English language

- Computer literacy

- High ranking official

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2.

- Experience in project management

Assets:

- Experience on at least 1 project in the field of co-ordination of social security schemes

- Experience in the area of co-ordination of social security schemes in the EU Candidate Country

Tasks of the Project Leader:

- Organization of study visits

- Participation in Steering Committee meetings

- Project reporting

- Ensuring backstopping and financial management of the project in the MS

- MS side project management and coordination of the project according to the project plan

- Overall co-ordination of MS expert’s work

- Mobilization and deployment of STEs for the project

3.5.2	Profile and tasks of the RTA

Profile of the Resident Twining Adviser

Requirements:

- University level education or equivalent professional experience of 13 years in the area of social welfare

- 6 years of experience in the area of social security

- Working level of English language

- Computer literacy

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2.

- Experience in project management

- 2 years of experience in the application of EU Regulations for Co-ordination of social security schemes

Assets:

- Experience in the area of co-ordination of social security schemes in the EU Candidate Country

- Experience in EU assistance programmes

- Experience in drafting laws/regulations/national policies and strategies

Tasks of the Resident Twining Adviser:

- Day to day management of the project in the BC

- Support and coordination of all activities in the BC

- Organization of visibility events (kick-off and final event)

- Networking with stakeholders of the project in Croatia and in MS.

- Advising on related EU polices and best practices, legislation and regulations

- Ensuring the continuity of project implementation, quality management of STE inputs

Duration of RTA secondment is 15 months.

3.5.3 Profile and tasks of the short-term experts

Profile of the Short-term experts

Short-term expert 1

Requirements:

- University level education or equivalent professional experience of 10 years in the area of social security

- 5 years of experience in the area of pension insurance

- Working level of English language

- Computer literacy

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2.

Assets:

- Experience in implementation of EU standards in Candidate Countries;

- Experience in PAY-AS-YOU-GO scheme and private capitalized schemes

- Experience in preparation and delivery of trainings

Tasks of the Short-term expert:

- Providing analysis of the current level of co-operation among all institutions in-charge of the co-ordination of social security scheme

- Providing recommendations for effective co-operations and functioning of aforementioned institutions

- Performing analysis of the training needs, organizing and providing the training

- Revising and improving training programmes and materials based on feedback

- Analysis of the existing administrative procedures and recommendation for improvement in the area of pension insurance as well as preparation of Manuals on implementation and application of co-ordination rules

Short-term expert 2

Requirements:

- University level education or equivalent professional experience of 10 years in the area of social security

- 5 years of experience in the area of family benefits and health insurance including basic insurance (health care and cash benefits) and/or additional insurance (mixed public-private and private insurance)

- Experience in preparation of analytical study

- Working level of English language

- Computer literacy

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2.

Assets:

- Experience in implementation of EU standards in Candidate Countries;

- Experience in preparation and delivery of trainings

Tasks of the Short-term expert:

- Performing analysis of the training needs, organizing and providing the training

- Revising and improving training programmes and materials based on feedback

- Analysis of the existing administrative procedures and recommendation for improvement in the area of health insurance as well as preparation of Manuals on implementation and application of co-ordination rules

- Conducting analyses;

- Preparation of Analitical study on the impact of free movement of workers on the Croatian administrative system

Short-term expert 3

Requirements:

- University level education or equivalent professional experience of 10 years in the area of social security

- 5 years of experience in the area of social security - unemployment insurance

- Experience in preparation of financial analyses

- Working level of English language

- Computer literacy

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2.

Assets:

- Experience in implementation of EU standards in Candidate Countries;

- Experience in preparation and delivery of trainings

Tasks of the Short-term expert:

- Performing analysis of the training needs, organizing and providing the training

- Revising and improving training programmes and materials based on feedback

- Analysis of the existing administrative procedures and recommendation for improvement in the area of unemployment insurance and family benefits as well as preparation of Manuals on implementation and application of co-ordination rules

- Conducting analyses;

- Preparation of Financial study on the impact of free movement of workers including estimation of additional costs for the Croatian health system

Short-term expert 4

Requirements:

- University level education or equivalent professional experience of 10 years in public relations

- 3 years of experience in organizing awareness raising activities

- Working level of English language

- Computer literacy

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2.

Assets:

- Experience in implementation of EU standards in Candidate Countries;

Tasks of the Short-term expert:

- Preparation of awareness raising and communication strategy

- Development of the work plan for dissemination of information on the right of free movement of workers

- Preparation and publishing of relevant infromation on the web sites of institutions involved in the project

- Conducting awareness campaign with the cooperation of stakeholders, including preparation of brochures and newsletters

- Institutional Framework

Concerning the project purpose the following institutions (competent authorities and implementation agencies) need to be involved in project implementation:

- Ministry of Economy, Labour and Entrepreneurship, Pension Insurance Directorate is responsible for monitoring of the whole pension system development and for recommendations regarding the legislative framework and additional measures with the aim to improve pension system. It is responsible also for making the pension policy. This Ministry is supervising authority for Croatian Pension Insurance Institute, in the matters of providing public pension system, PAY-AS-YOU-GO system. Department for Bilateral Cooperation in the Area of Social Security is now responsible for bilateral negotiations and signing of bilateral Agreements on Social Security, but in the future this unit will be responsible for monitoring of applying the EU co-ordination rules.

- Croatian Pension Insurance Institute is implementation agency responsible for implementation of PAY-AS-YOU-GO pension system. It keeps the register of insured persons, of persons liable to pay contributions and of pension beneficiaries, in accordance to the Act on Pension Insurance. CPII is a public institution which has the status of a legal person and which exercises public powers in relation to issuing decisions on pension insurance entitlements (in the I. pension pillar, solidarity based) in the proceedings conducted following the claims that have been filed (general supervision:  Ministry of Economy, Labour and Entrepreneurship). Croatian Pension Insurance Institute is also the competent agency for the implementation of the Children Allowance Scheme (general supervision: Ministry of Family, Veterans' Affairs and Intergenerational Solidarity)

- Croatian Employment Service is a public institution responsible for defining rights and benefits for unemployed persons, based on their work history.

- Ministry of Health and Social Welfare is responsible for developing policy for health and social welfare. Part of the Ministry which is going to be the unit responsible for co-ordination issues is Department for European Integrations, which will be in the future responsible for monitoring and applying the EU Co-ordination rules.

- Croatian Institute for Health Insurance is implementation agency responsible for implementation of the rules related to basic health insurance and implementation on bilateral agreement on social security. It also implements the additional insurance, although private insurance companies are also included in the implementation of the additional insurance.

- Croatian Institute for Health Insurance of Health Protection at Work is implementation agency responsible for execution of rules and polices concerning development and improvement of health protection regarding work injuries and professional diseases, and diseases related to work, for monitoring and performing measures for preventing injuries at work as well as measures for preventing and detecting professional disease (specific health protection of workers) and for regulation of workers' rights regarding work injuries and professional diseases. Croatian Institute for Health Insurance of Health Protection at Work is included in the Project as a beneficiary, although this institution will include itself step by step to the co-ordination affairs.

- Ministry of Family, Veterans' Affairs and Intergenerational Solidarity in whole is responsible for developing policy for family, veterans and intergenerational solidarity. Directorate for Family is responsible for family issues.

All mentioned competent authorities and implementation agencies will be involved in the project. The reason for that is the wide range of social security matters. Social security comprises pension insurance, health insurance, insurance against unemployment and family benefits. In Croatia social security matters are encompassed by different institutions. Every implementation agency is responsible for just one area, and every competent authority (Ministry) is responsible for monitoring of one of the mentioned implementation agency. There are also some exceptions, e.g. Ministry of Economy, Labour and Entrepreneurship is responsible for supervising of the Croatian Pension Insurance Institute in the area of pension insurance, and also Croatian Employment Service in the area of implementation of the employment policy. Ministry of Family, Veterans' Affairs and Intergenerational Solidarity is responsible for supervising  of the Croatian Pension Insurance Institute in the area of children allowance, as well as of the Croatian Institute for Health Insurance in the area of maternal and parental benefits. However, responsible institutions for applying the rules are Croatian Pension Insurance Institute and Croatian Institute for Health Insurance.

The beneficiary institution will dedicate all necessary human and financial resources in order to guarantee an effective implementation of the respective project. In particular, the main beneficiary institution Ministry of Economy, Labor and Entrepreneurship will ensure the availability of the following provisions:

- Adequately equipped office space for the RTA and the RTA assistant for the entire duration of his/her secondment (in particular a desk, a telephone line, PC with e-mail account and internet access, possibility to use fax & copy services);

- Adequate conditions for the STEs to perform their work while on mission to the BC;

- Training and conference venues as well as presentation and interpretation equipment; Costs for travel by BC participants from their capitals to a MS or between MS (study visits) will be insured on behalf of each beneficiary institution for their participants.

- Its active involvement in preparation of the PIU and Steering Committee meetings and participation of its members on the same;

- The availability of the BC human resources (BC experts) during the implementation of the activities;

In order for the coordination of activities to be ensured and due to the fact that there are several institutions involved in the project, Inter-institutional Working Group will act as coordinating body. Inter-institutional Working Group was established on temporary basis as a relevant body for providing the activities related to co-ordination matters before the Chapter 2. was provisionally closed and after that, in the February 2010 on the permanent basis according to the Governmental Decision. Inter-institutional Working Group includes two participants from each beneficiary institution and it works through monthly meetings, or more often meetings if needed and is running by the Secretariat organized within the Ministry of Economy, Labour and Entrepreneurship If it is necessary it could be extended with more experts from the same institutions, especially with those who participated in the process of the project proposal making.

- Budget

| Strengthening the administrative capacity of competent authorities and implementation agencies for co-ordination of social security schemes | IPA Contribution | National Co-financing | TOTAL |
| --- | --- | --- | --- |
| Twinning Contract | 95% | 5% | € 1.000.000 |

Interpretation costs will be reimbursed from the budget only for the purposes of workshops and seminars, up to 7% of the budget can be used for translation and interpretation purposes.

In addition to the above-mentioned, provisions with the maximum total amount of 10.000€ should be included in the budget for the following purposes:

- Publishing of brochures for public - minimum 50.000 copies with translation to Croatian language

6.	Implementation Arrangements

6.1 Implementing Agency responsible for tendering, contracting and accounting

Central Finance and Contracting Agency (CFCA)

Ulica grada Vukovara 284

HR – 10000 Zagreb

Mrs. Marija Tufekčić, Director of the CFCA

Phone:+ 385 1 4591 245

Fax: +385 1 4591 075

E-mail: procurement@safu.hr

Twinning Administrative Office

Central Finance and Contracting Agency

Ulica grada Vukovara 284

HR - 10000 Zagreb

Contact: Mr Domagoj Šimunović

Phone: +385 1 4591 213

Fax: + 385 1 4591 075

E-mail: twinning@safu.hr

6.2 Main counterpart in the BC

Ministry of Economy, Labour and Entrepreneurship

Pension Insurance Directorate

Senior Programme Officer (SPO):

Mr Robert Markt, state secretary

Address and contact details:

Ulica grada Vukovara 78

HR - 10000 Zagreb

Phone: +385 1 6106 548

Fax:     +385 1 6109 921

E-mail: robert.markt@mingorp.hr

BC Project Leader (PL)

Ms. Snježana Baloković, head of Departement

Pension Insurance Directorate

Ministry of Economy, Labour and Entrepreneurship

Address and contact details:

Ulica grada Vukovara 78

HR - 10000 Zagreb

Phone: +385 1 6106 377

Fax:     +385 1 6109 905

E-mail: snjezana.balokovic@mingorp.hr

RTA counterpart 1

Ms. Mirsada Hujdur, expert advisor

Pension Insurance Directorate

Ministry of Economy, Labour and Entrepreneurship

Address and contact details:

Ulica grada Vukovara 78

HR - 10000 Zagreb

Phone: +385 1 6106 837

Fax:     +385 1 6109 905

E-mail: mirsada.hujdur@mingorp.hr

RTA counterpart 2

Ms Kristina Ognjenović

Department for European Integrations

Ministry of Health and Social Welfare

Ksaver 200a

HR – 10000 Zagreb

Phone: +385 1 4607 629

Fax: +385 1 4677 008

E-mail: kristina.ognjenovic@mzss.hr

6.3 Contracts

It is envisaged that the Project will be implemented through one twinning contract, with the indicative amount of 1 000 000 €.

7.	Implementation Schedule (indicative)

7.1	Launching of the call for proposals

Start of tendering – 2nd quarter 2010

7.2	 Start of project activities

Start of twinning activities – 2nd quarter 2011

7.3	Project completion

End of twinning activities – 2nd quarter 2012

7.4	Duration of the implementation period (number of months)

18 months; 15 months for the implementation of the activities and 3 months for the starting up and closure of the Action.

8. Sustainability

The achievement of the project should be establishing of a modern Croatian social security administration, which will be an important step forward on the way of accession to the EU, as all EU social security systems will have to communicate and work with each other, in order to make it possible for EU citizens to practise their right to move within the EU. Sustainability will be insured with maintaining and improving of this achievement. Also, sustainability will be insured with the possibility of transferring the knowledge from civil/public servants who had passed the training courses for trainers. Manuals and Procedures published under the project should stay available for all current and future administration.

- Crosscutting issues

- 9.1 Equal Opportunity

Based on the fundamental principles of promoting equality and combating discrimination, participation in the Project will be guaranteed on the basis of equal access regardless of sex, racial or ethnic origin, religion or belief, disability, age or sexual orientation. The institutions involved in the project execution will observe equal opportunities in the recruitment process and human resources development. The beneficiary will insure equal access for all categories of persons to the project activities and results. Anti-discrimination on all grounds (gender, race, sexual identity, expression of orientation) is guaranteed by the Croatian's Constitution and through the comprehensive Anti –discrimination Law, adopted in 2008.

- Conditionality and sequencing

The conclusion of the contract resulting from this call for proposals is subject to the fulfillment of the following condition:

- Entry into force of a Financing Agreement implementing the National Programme for 2009 under the Instrument for Pre-accession Assistance (“Transition Assistance and Institution Building” Component, Part 1), concluded between the European Union and Croatia.

ANNEXES TO PROJECT FICHE

1.   Logical framework matrix in standard format

2.   Detailed implementation chart

3.   Contracting  and  disbursement  schedule  by  quarter  for  full  duration  of  programme  (including disbursement period)

4.   List of relevant Laws and Regulation

- ANNEX 1: Logical framework matrix in standard format

| STRENGTHENING THE ADMINISTRATIVE CAPACITY OF COMPETENT AUTHORITIES AND IMPLEMENTATION AGENCIES FOR CO-ORDINATION OF SOCIAL SECURITY SCHEMES |  | Programme name and number: IPA 2009 |  |  |
| --- | --- | --- | --- | --- |
|  |  | Contracting period expires 2 years following the date of conclusion of the Financing Agreement |  | Disbursement period expires 3 years following the end date for contracting |
| MINISTRY OF ECONOMY, LABOUR AND ENTREPRENEURSHIP |  | Total budget : 1 000 000 € |  | IPA budget: 95% |
| Overall objective | Objectively verifiable indicators | Sources of Verification |  |  |
| To strengthen the administrative capacity of Croatian competent authorities and implementation agencies to implement acquis in the field of free movement of workers and co-ordination of social security schemes | Croatian competent authorities and implementation agencies ready to apply EU acquis in the field of free movement of workers and co-ordination of social security | Regular European Commission Reports Records of the Ministry of Economy, Labour and Entrepreneurship and of Ministry for Health and Social Welfare Conclusion of the Inter-institutional Working Group on sufficient horizontal cooperation between institutions involved in co-ordination of social security schemes |  |  |
| Project purpose | Objectively verifiable indicators | Sources of Verification |  | Assumptions |
| To increase the institutional and administrative capacity of the competent authorities and implementation agencies (liaison bodies) to effectively coordinate social security schemes upon EU accession | Staff trained and ability to apply EU acquis in the field of free movement of workers and co-ordination of social security schemes improved Appropriate co-ordination infrastructure for co-ordination of social security established and ready to apply EU co-ordination rules Management staff in the competent authorities trained and well prepared for implementation of the co-ordination rules Increased public awareness on EU social security co-ordination legislation | Project reports Records of the Ministry of Economy, Labour and Entrepreneurship and Ministry for Health and Social Welfare Records of the Steering Committee on self assessment Official statistics on trained and educated staff, prepared for implementing the co-ordination rules |  | Efficient structures for social security co-ordination |
| Results | Objectively verifiable indicators | Sources of Verification |  | Assumptions |
| Result 1.1: Overall co-operation and functioning of all institutions in charge of co-ordination of social security issues improved. Result 1.2: Capacity of the relevant institutions directly applying the co-ordination rules on the social security schemes enhanced, their expertise in this field upgraded and transfer of knowledge ensured through the trainings of future trainers. Result 1.3: Administrative procedures on implementation and direct application of the co-ordination rules harmonized with the EU co-ordination regulations. Result 2.1: Comprehensive analytical and financial study of the impact of free movement of workers between Croatia and EU member states on the Croatian social security administrative system prepared. Result 3.1: Awareness raising strategy and communication system established and functioning Result 3.2: Information related to the free movement of workers disseminated to the general public |  Analysis of the current level of co-operation and functioning of all relevant institutions, identifying existing shortcomings conducted and corresponding report produced;  Recommendations for improvement of co-operation and more efficient functioning of all involved institutions prepared;  Support and advice to the Inter-institutional Working Group provided and minutes of the meetings prepared;  Recommendations and advice for functioning of the established units provided through roundtable discussions and minutes of the meetings prepared;  Competent authorities’ staff prepared for active participation at the meetings in the EU institutions. Analysis of training needs conducted and training needs report produced;  Training programmes for general and in-depth trainings prepared;  At least 180 employees trained, each group of employees educated in the area related to their work;  Train the trainers programme developed and continuous education ensured through the Train the trainers programme;  At least 40 future trainers trained, in groups according to the area related to their field of work;  Two (2) study visits (one to an old MS, one to a new MS; each for 8 civil servants) lasting 4 days conducted and report on the findings of the study visits drafted.  Analysis of existing administrative procedures conducted and corresponding report on existing gaps and needs produced;  Manuals and administrative procedures on implementation and application of the co-ordination rules prepared in line with the EU co-ordination regulations and approved by all institutions involved;  Summary of the most important co-ordination rules and of the consolidated version of relevant EU regulations in English and Croatian prepared and distributed. Existing administrative system in charge of co-ordination of social security schemes analysed; Analytical study including modality of statistical monitoring of posted workers/frontier workers/migrant workers prepared; Financial study on the impact of free movement of workers comprising estimation of additional costs for the Croatian health system with regards to the application of the co-ordination rules and impact study to the scheme of family benefits regarding co-ordination rules prepared. Awareness raising strategy and communication strategy developed;  Plan for dissemination of information related to the free movement of workers prepared. - Information on right of free movement of workers on the EU Internal market published on the web site of relevant institutions; - Newsletter prepared, Brochures prepared and disseminated; - At least 2 awareness raising events organized for general public | Project reports Monitoring reports Records of the competent authorities - Records of Steering Committee on assesment of the project Report on training needs - List of participants on trainings Reports on findings on study visits - Twinning report on project implementation. Reports on implemented training courses - Twinning report on project implementation. - Manual on application and implementation - Twinning report on project implementation - Summarized the most important co-ordination rules as well as consolidated version version of relevant EU regulations - Twinning report on project implementation - Analytical Study and Financial study on the impact of free movement of workers between Croatia and EU Member States on Croatian administrative system - Twinning report on project implementation - Twinning report on project implementation - Overview of European best practices on co-ordination, conditions of posting and national employment conditions of the Republic of Croatia and different EU Member States, information on co-ordination rules available on the web sites of the competent authorities; prepared and published information materials |  | - Government commitment for ensuring inter-institutional structure for horizontal cooperation between institutions involved - Commitment of all stakeholders for ensuring adequate institutional structures (units) within itselves as well as commitment for future mutual cooperation Government commitment for providing co-ordination rules without any obstacles, quality retaintion policy related to the trained staff The appropriate staff is made available for training Financial background allocated - Adequate participation of appointed and selected employees during trainings. - Timely and adequate availability of data necessary for proper conducting of the analysis. - Availability of necessary data - Channels for dissemination of the outputs of the campaign established |
| Activities | Means | Costs |  | Assumptions |
| Component 1: . Strengthening of institutional and administrative capacity of competent authorities and implementation agencies 1.1.1. Conducting analysis of the current level of co-operation and functioning of all institutions involved in social security issues. The analysis should identify shortcomings in cooperation and functioning of these institutions.; 1.1.2. Preparation of recommendations for improvement of co-operation and more efficient functioning of these institutions on the basis of the analysis conducted under activity no. 1.1.1.; 1.1.3. Providing support and advice to the Inter-institutional Working Group in charge of co-ordination of the social security schemes by holding roundtable discussions; 1.1.4. Providing recommendations and advice for functioning of the established units for coordination in the relevant institutions and for its mutual cooperation (advice should be provided by holding roundtable discussions); 1.1.5. Providing advice to the authorities involved in social security issues on the functioning of the relevant EU bodies by holding roundtable discussions. The purpose of this activity is to prepare the staff of the competent authorities for participation at the procedural and technical meetings in the EU institutions; 1.2.1. Conducting training needs analysis of the staff working in the competent authorities and implementation agencies on the social security matters and preparing training programmes for general and in depth trainings; 1.2.2. Conducting trainings for at least 180 employees on pension rights for migrant workers/frontier workers, health protection and reimbursement of health care costs and conditions for establishing European Health Insurance Card, family benefits and rights based on unemployment. The relevant staff should be organized in different groups which will receive the training in one or more of the aforementioned fields depending on their job description.; 1.2.3. On the basis of the analyses of training needs performed, developing train the trainers programme that will ensure continuous education; 1.2.4. Conducting training for at least 40 future trainers on pension rights for migrant/frontier workers, health protection and reimbursement of health care costs, family benefits and rights based on unemployment; 1.2.5. Organizing 2 study visits (one study visit to an old MS and one study visit to a new MS, each for 8 civil servants from the relevant institutions to counterpart institutions in the EU Member States), each lasting 4 days, in order to get an insight into the way coordination is ensured in the practice.; 1.3.1. Conducting analysis of existing administrative procedures related to the area of social security and identification of existing gaps related to the EU co-ordination regulations; preparation of report on gaps and needs; 1.3.2. Preparation of Manuals and administrative procedures on implementation and application of the co-ordination rules in line with the EU co-ordination regulations and on the basis of the analysis conducted under activity 1.3.1.; 1.3.3. Summarizing the most important co-ordination rules and existing consolidated versions of relevant EU regulations and preparation of printed version of aforementioned rules and regulations in English and Croatian for internal use in relevant institutions (each institution should receive at least one copy). Component 2:. Analyses of impact of free movement of workers on Croatian social security administration system 2.1.1. Conducting analysis of the existing administrative system in charge of co-ordination of social security schemes in Croatia.; 2.1.2. On the basis of the analysis conducted, drafting the Analytical Study on the impact of free movement of workers between Croatia and EU Member States on the Croatian administrative system. Speacial focus should be put on the administrative capacities of all institutions involved. Additionaly, the Study should include modality of statistical monitoring of posted workers/frontier workers/migrant workers.; 2.1.3. Conducting financial analysis and preparing Financial study on the impact of free movement of workers, including estimation of additional costs for the Croatian health system with regards to the application of the co-ordination rules as well as impact study to the scheme of family benefits under the EU co-ordination rules. Component 3: Raising of public awareness on right of free movement of workers 3.1.1. Development of awareness raising strategy on right of free movement of workers and communication strategy for migrant workers; 3.1.2. Preparation of strategic work plan for dissemination of information related to the free movement of workers for general public; 3.2.1. Preparation of information on social security rights of migrant workers and their families as well as conditions of posting and national employment conditions in the Republic of Croatia and different EU Member States. Aforementioned information should be published on the web sites of the competent authorities and implementation agencies in order to inform Croatian citizens on right of free movement of workers on the EU Internal market; 3.2.2. Preparation of a newsletter to be regularly updated and used by the Beneficiary institution and preparation /dissemination of brochures for general public; 3.2.3. Organizing of at least 2 Awareness raising events for general public. The form of the events will be subject to agreement between the twinning partners and based on the conclusions of the awareness raising strategy developed under activity 3.1.1. | - Analysis, Consultancy - Recommendations - Consultations, preparation of documentation , Roundtable discussion - Analysis, Reccommendations, Roundtable discussion - Consultancy, Roundtable discussion - Analysis, - Trainings - Preparation of documentation - Trainings - Study visits - Analysis, Preparation of documentation - Analysis, Preparation of documentation - Preparation of documentation - Analysis, Roundtable disscussions - Roundtable discussion, Consultations, Preparation of documentation - Analysis, Preparation of documentation - Analysis - Preparation of documentation - Preparation and dissemination of Awareness raising materials - Preparation of documentation - Awareness raising events | 1 000 000 € |  |  Adequate and timely technical assistance is provided by twinning partners  Support of the Government, as well as support of the Ministry of Economy, Labour and Entrepreneurship and Ministry for Health, and Social Welfare's senior management  Prepared adequate language trainings in order to increase the level of communication between the competent institutions in Croatia and the Member States |
|  |  |  | Pre conditions The conclusion of the contract resulting from this call for proposals is subject to the fulfillment of the following condition: - Entry into force of a Financing Agreement implementing the National Programme for 2009 under the Instrument for Pre-accession Assistance (“Transition Assistance and Institution Building” Component, Part 1), concluded between the European Union and Croatia. |  |

- Annex 2. Detailed implementation chart

| - “Strengthening the administrative capacity of competent authorities and implementation agencies for co-ordination of social security schemes” | - 2010 |  |  |  |  |  |  |  |  |  |  |  | - 2011 |  |  |  |  |  |  |  |  |  |  |  | - 2012 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Month | - J | - F | - M | - A | - M | - J | - J | - A | - S | - O | - N | - D | - J | - F | - M | - A | - M | - J | - J | - A | - S | - O | - N | - D | - J | - F | - M | - A | - M | - J | - J | - A | - S | - O | - N | - D |
| - Twinning |  |  |  |  | - T | - T | - T | - T | - C | - C | - C | - C | - C | - C | - S | - I | - I | - I | - I | - I | - I | - I | - I | - I | - I | - I | - I | - I | - I | - I | - R | - R |  |  |  |  |

- T – Call for proposals and evaluation

- C- Contracting

- S- Starting up

- I –  Implementation of activities

- R – Report

- Annex 3. Contracting  and  disbursement  schedule  by  quarter  for  full  duration  of  programme  (including disbursement period)

| - Strengthening the administrative capacity of competent authorities and implementation agencies for co-ordination of social security schemes | - Cumulative contracting schedule by quarters in EUR (provisional) |  |  |  |
| --- | --- | --- | --- | --- |
|  | - 2011 |  |  |  |
|  | - I | - II | - III | - IV |
| - Twinning | - 1.000.000 |  |  |  |
| - TOTAL (EUR): | - 1.000.000 |  |  |  |

| - “Strengthening the administrative capacity of competent authorities and implementation agencies for co-ordination of social security schemes” |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | - 2011 |  |  |  | - 2012 |  |  |  |
|  | - I | - II | - III | - IV | - I | - II | - III | - IV |
| - Twinning | - 640.000 |  |  | - 260.000 |  |  | - 100.000 |  |
| - TOTAL (EUR): | - 640.000 |  |  | - 900.000 |  |  | - 1.000.000 |  |

- ANNEX 4: List of the relevant Laws and Regulations

List of he relevant regulations regarding the proposed project:

- The free movement of services and workers, article 39 and 42 of the Treaty

- Stabilisation and Association Agreement, article 47

- Accession Partnership, New Council Decision of February 2008

- Regulation (EEC) 1408/71 of the Council of 14 June 1971 on the application of social security schemes to employed persons and their families moving within the Community Regulation

- Regulation (EEC) 574/72 of the Council of the 21 March 1972 establishing the procedure for implementing Regulation (EEC) 1408/71

- Regulation (EC) 883/2004 of the European Parliament and the Council of the 29 April 2004 on the co-ordination of social security systems has been approved, in order to change the Regulation 1408/71

- Decisions and recommendation on (electronic) data exchange of the Administrative Commission on Migrant Workers and its working groups

- Multi-Annual Indicative Planning Document 2008 – 2010

According to EU Regulations on co-ordination of social security schemes, competent authority means the Minister, Ministers or other equivalent authority responsible for social security schemes. Expression implementation agency comprises all competent institutions according to EU Regulations and stands instead of institution, competent institution, institution of the place of residence and institution of the place of stay, which are bodies or authorities responsible for applying the legislation. These competente authorities and implementation agencies are:

Ministry of Economy, Labour and Entrepreneurship

Ministry of Health and Social Welfare

Ministry of Family, Veterans' Affairs and Intergeneration Solidarity

Croatian Pension Insurance Institute

Croatian Institute for Health Insurance

Croatian Institute for Health Insurance of Health Protection at Work

Croatian Employment Service

Study Visits to competent authorities and relevant institutions in one old Member State and one new Member State should be organized with the aim to gather information about organizing of work on co-ordination of the social security schemes as well as information on co-operation of all institutions in one Member State which apply or supervise applying of co-ordination rules and on comprehensive co-operation with relevant EU institutions. Exchange of experience with civil/public servants who deal with the co-ordination rules and advising on the preparation for the future activities in relation to EU institutions will be of a great value for Croatian civil/public servants

Member States submitting proposals for Twinning projects implemented in Croatia, as well as the beneficiary institutions, will be requested to finalise drafting of the contracts in maximum six months regardless of the period of the year during which the drafting will take place.