- Twinning Number: TR 08 IB SO 01

- Promoting Gender Equality in Working Life

- Note for the information of future Twinning partners:

- The indicative budget for the Twinning is € 1.0 million (see paragraph 4)

- The indicative duration of the Twinning project is 21 months (see paragraph 5)

Standard Summary Project Fiche – IPA decentralised National programmes

(maximum 12/15 pages without the annexes)

1. Basic information

1.1   CRIS Number: TR080218

1.2   Title  	       : Promoting Gender Equality in Working Life.

1.3   Sector            : 19-Social Policy and Employment

1.4   Location        : Turkey

Implementing arrangements:

1.5   Implementing Agency:

The CFCU will be the implementing agency and will be responsible for all procedural aspects of the tendering process, contracting matters and financial management, including payment of project activities. The director of the CFCU will act as Programme Authorizing Officer (PAO) of the project. His contact details are:

Mr. Muhsin ALTUN (PAO-CFCU Director)

Central Finance and Contracting Unit

Tel:  +90 312 295 49 00

Fax: +90 312 286 70 72

E-mail: muhsin.altun@cfcu.gov.tr

Address: Eskişehir Yolu 4.Km. 2.Cad. (Halkbank Kampüsü) No:63 C-Blok 06580  Söğütözü/Ankara Türkiye

  - Beneficiary (including details of Project Leader and RTA counterpart):

Ministry of Labour and Social Security (MoLSS) General Directorate of Labour will be the beneficiary. The project will be implemented under the supervision of the project leaders who will be responsible for the proper and timely implementation of activities. The beneficiary country project leader will be:

Mr. Fikret SOHRET, General Director of Labour

Ministry of Labour and Social Security

General Directorate of Labour

Adress: İnönü Bulvarı No: 42 B Blok Kat:9 06100 Emek/Ankara Türkiye

Tel: +90 312 296 63 33

Fax: +90 312 212 0781

E-Mail: fsohret@csgb.gov.tr

RTA Counterpart will be:

Sadettin AKYIL, Deputy Director of Labour

Ministry of Labour and Social Security

General Directorate of Labour

Adress: İnönü Bulvarı No: 42 B Blok Kat:9 06100 Emek/Ankara Türkiye

Tel: +90 312 296 63 18

Fax: +90 312 212 0781

E-Mail: sadettin@akyil.com.tr    sakyil@csgb.gov.tr

1.7   Overall cost:  € 1,000,000

1.8   EU contribution: € 950,000

1.9   Final date for contracting: 2 years after the signature of the Financing Agreement

1.10 Final date for execution of contracts: 2 years following the end date for contracting

1.11 Final date for disbursements: 3 years following the end date for contracting.

2.   Overall Objective and Project Purpose

2.1 Overall Objective: To ensure gender equality in working life.

2.2 Project purpose: To align Turkish legislation with EU gender equality acquis and improve capacity of institutions responsible for the implementation of the said acquis.

2.3. Link with AP/NPAA / EP/ SAA:

In the Accession Partnership (2007), in subheading  “Women’s Rights”  under heading Economic and Social Rights of Political Criteria, “increasing  the awareness of the general public , and of men in particular, concerning  gender issues, and promoting  the role of women in society , including through their education  and participation  in the labour market  and  in political  and social  life; supporting  the development  of women’s  organisations to fulfill these goals” are given as priorities.

In 2007 Progress Report, in political criteria, economic and social rights section , it is stated that  in general, women's participation in the labour market remains low, although women occupy some high-profile positions. Although, the legal framework guaranteeing gender equality is in place, further efforts are needed to translate it into social reality. The gap between men and women in economic participation and opportunity, educational attainment, health and survival, and political empowerment remains significant. In the social policy and employment section, it is mentioned that , as regards anti-discrimination and equal opportunities, limited progress was achieved and further alignment is required. Low participation of women in the labour market and access to education remain points of concern. Gender equality should be improved in all economic and social life. In general, there is a need to increase administrative capacity for the effective implementation of the acquis.

In this context, project outputs including recommendations and proposals for draft legislation related to the EU gender equality acquis to be transposed to Turkish legislation will facilitate the harmonisation process. Training sessions will pave the way for increasing understanding of gender equality issues in the public administration as well as for increasing public awareness on these issues.

2.4.Link with MIPD (2008-2010):

In the “Equal opportunities for men and women” section of the document, it is stated that the status of women in Turkish society is matter of continuing concern for the European institutions.  Despite formal equality before the law and the commitment of state institutions to egalitarian principles, the empowerment of Turkish women and their participation in economic life remains inadequate. Potential measures to address gender issues include: under Component I, harmonisation of the Turkish legal framework with the gender equality acquis and support to state institutions and NGO dealing with gender issues.

2.5 Link with National Development Plan (where applicable)

Ninth Development Plan (2007-2013) in subheading 7.2.1 improving the labour market of main heading 7.2 increasing employment, it is mentioned that “equal opportunities will be provided for the women, the young, and the longterm unemployed, the disabled and former convicts, who encounter difficulties in the labor market. With the aim of increasing the participation of women in the labor force and employment, their access to childcare and other similar services will be facilitated.”

  - Link with national/ sectoral investment plans(where applicable)

According to the one of the opening benchmarks of chapter 19 Social Policy and Employment for accession negotiations is the preperation and submission of an action plan for transposition, implementation, enforcement throughout the country of the  acquis covered by the chapter for the benefit of entire workforce. Gender equality acquis that is the subject the present project is also covered by this chapter. Furthermore, while preparing the action plan, gender mainstreaming approach will be adopted with particular attention given to women’s participation into labour market.

One of the outputs of the “Promoting Gender Equality Project” implemented by the DG on Status of Women is the “National Action Plan for Promotion of Gender Equality”. Under Component 4,  a Mapping Exercise and a Gender mainstreaming Policy Report were prepared under the scope of activities concerning designing a Draft National Action Plan. Under the scope of the Mapping Exercise, in total 62 interviews were made with public institutions and organizations and NGOs in various provinces. The "Mapping Exercise Report" was prepared after interviews with relevant stakeholders. Activities for forming working groups and preparing policy documents for the preparation of the draft of the National Action Plan are ongoing. Six working group meetings were organised. In these meetings 8 main critical areas of concern from Beijing Platform for Action will be addressed. These areas are education and training of women, women and health, women and economy, women in authorization and decision-making process, institutional mechanisms in the womens’ promotion, women and media, women and environment. Especially, women and economy part is very much related to the theme of this project.

3. Description of project

3.1 Background and justification:

In the European Union, equal treatment of men and women is one of the main purposes of EC social policy.  In Acquis Communitaire, gender equality is taken account not only in social policy, but also in gender mainstreaming area. Also, one of four dimensions of EU Employment Strategy is gender equality.

The EU's gender equality acquis includes the directives stated below:

1. Council Directive 96/34/EC on the framework agreement on parental leave concluded by UNICE, CEEP and the ETUC;

2. Council Directive 92/85/EEC on the introduction of measures to encourage improvements in the safety and health at work of pregnant workers and workers who have recently given birth or are breastfeeding;

3. Council Directive 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security;

4.Council Directive 86/613/EEC on the application of the principle of equal treatment between men and women engaged in an activity, including agriculture, in a self-employed capacity, and on the protection of self-employed women during pregnancy and motherhood;

5. Council Directive 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services;

6. Council Directive 2006/54/EC on the implementation of the principle of equal opportunities and equal treatment of men and women in matters of employment and occupation (recast)

Although, other directives have been in force, Council Directive 2006/54/EC which is composed of relevant directives on gender equality will come into force by 2009.

Since gender equality is an important theme in the EU, during the harmonisation process with the EU acquis, special attention was given to this area in Turkey, as summarised below:

As stated in the National Programme of Turkey (2003), under heading “Social Policy and Employment”, directives related to gender equality were taken into consideration when arrangements were made Labour Law No. 4857. During the sub committee and screening meetings, the obvious gaps  in the Turkish legislation regarding the gender equality acquis have been stated..

Nevertheless, in conjunction with the Labour Law No.4857, various regulations and a Prime Minister circular were put into force, such as “Implementing Regulation Concerning the working conditions of Pregnant or Breastfeeding Mothers, Breastfeeding rooms and Children Nursing Homes”, “Implementing Regulation Concerning the working conditions of Female Workers at Night Shifts” and PM Circular on “Acting in accordance with the principle of gender equality in the recruitment of civil servants”. So far, no feedback regarding difficulties in implementation of the said regulations have been communicated to the Ministry.

Turkey also participated to the Gender Equality Community Programme (2003-2006). Within the framework of the Programme, seminars concerning awareness and sensitivity raising were organised by the Ministry of Labour and Social Security.

Under the heading “Strengthening Social Structure” of the 60th Government Programme, a general action is determined in the area of gender equality. The action of  “Ensuring women taking more part in every field of social life” include development of social policies strengthening the status of women, development of training programmes for policy maker to ensure they implement gender mainstreaming policies, organisation of awareness-raising seminars and preparation of Gender Equality National Action Plan.

Furthermore, Turkey aims to complete the harmonization for the EU gender equality acquis in 2008-2013 period, as it will soon to be clarified in the upcoming National Programme for the Adoption of the EU Acquis. This project will enable proper transposition of EU gender equality acquis, so that harmonisation work will be completed on time as planned in the draft National Programme.

Within the scope of the project, it is planned that, in addition to the EU Directives on gender equality, related case-law of the European Court of Justice and CoE standards and texts such as ECHR will be analysed by twinning experts, since court jurisdiction enlarges and clarifies the scope of implementation of the Directives. In this respect, existing discrepancies between Turkish legislation and EU Acquis will be determined by twinning experts. These experts will determine existing gaps between EU Acquis and Labour Law No 4857, Law on Civil Servants No 657 and Law on Social Security No 5510 (including secondary legislation of labour and social security related with equal treatment and implementation in practice). (The legal position of employers has been regulated according to the Labour Law numbered 4857 and the legal position of workers has been regulated according to Civil Servant Law numbered 657 so that there are two different structures.) As a result of this work, twinning experts will prepare a report including amendment proposal related to the diverging provisions on the afore-mentioned laws with close collaboration of experts of Ministry and Social Security Institution. By taking into account of the related directives and judgment of the Court of Justice, a report is to be prepared, which includes recommendations of experts and amendment proposals on the current relevant legislation, that will play an important role in the harmonization process of relevant legislation. Hence, social partners and relevant public institutions will take the report into consideration in preparing draft legislation, which will amend diverging provisions of the existing laws, rather than preparing completely a new law.

Second output of the project is the strengthening of human resources capacity in the Ministry of Labour and Social Security (MoLSS), the Social Security Institution (SSI) which is related institution of MoLSS and State Personnel Presidency (SPP). These institutions are primarily responsible for the alignment of the relevant acquis and hence will play very important role in legislative studies on promoting gender equality in working life. Therefore, strengthening their institutional capacity is critically important, which will be ensured by implementation of training programmes for staff of relevant institutions, as well as for social partners and NGOs.

325 personnel will be trained in Ankara. More specificly, the institutions which will attend the trainings are State Personnel Presidency (SPP), Social Security Institution (SSI), Turkish Employment Organization, Center for Labour and Social Security Training and Research (ÇASGEM), Labour Inspection Board,  Labour District Offices which are affiliated institutions of MoLSS, General Directorate on the Status of Women and, members of women NGOs and representatives of social partners. The project aims to provide attendance of NGOs which are dealing with women's issues, and in particular with women's employment.

DG Labour informed the related institutions (State Personnel Presidency, Social Security Institution, Turkish Employment Organisation, Labour and Social Security Research and Training Center, DG on the Status of Women, Turkish Confederation of Employer Associations, Confederation of Turkish Trade Unions, Confederation of Progressive Trade Unions of  Turkey, Confederation of Turkish Real Trade Unions) by an official letter that highlights the importance of coordination between related institutions and active participation of them. The draft project fiche was attached to the mentioned official letter. Information on the project will be delivered to the women NGOs through the DG on the Status of Women. Besides, PCU members communicated with potential contact persons of mentioned institutions and social partners by e-mail and phone calls. The draft project fiche was evaluated by social partners and relevant public institutions. Social partners declared their positive opinions about the project.

Furthermore, social partners and women NGOs will also participate to to meetings and conference in İstanbul and Ankara. Seminars will be organised to draw out the public and related bodies' attention and disseminate the project activities in local level. A closing conference will be organised to announce the project activities and results to the related organizations and media.

The public institutions mentioned above are going to be involved in both legislation and implementation process, therefore, their relevance to the scope of the project is clarified further below:

Social Security Institution is established with the administrative restructuring component of the Social Security Reform which took place in 2006 and which unified the older social security institutions (SSK, Bag-Kur and ES) under a single framework. Social Security Institution is affiliated with the Ministry of Labor and Social Security and is autonomous administratively and financially. According to current legislation, the Institution is responsible for regulation and monitoring of mandatory social security scheme (I Pillar). In the context of this project, it has a direct responsibility for acquis harmonization in the field of Directives 79/7/EEC ve 86/613/EEC and still interested in equal treatment in regard to occupational social security schemes regulated with 2006/54/EC.

State Personnel Presidency is entitled with the duties and responsibility of determining the legal and financial status of the civil servants, performing studies for the regulation of the said status and preparing the required legislation on the basis of the Decree Law No. 217. State Personnel Presidency has duties, authorities and responsibilities for preparing the legislation or application of the present legislation on the subjects which are essential to provide the harmonization with the acquis on equal opportunities (equality between men and women) such as admission in the civil service, training of the civil servants candidates, in service training and promotion of civil servants. Within this scope, state personnel experts need to be informed about the EU gender equality acquis and their implementation. They also require to observe EU implementation on this issue.

Due to complex nature of problem and so many institutions to handle various parts of gender equality policy in Turkey, the Twinning Counterpart Institution may opt to form consortiums with other Institutions in domestic or in another member states in order to cover all the mentioned Directives and their implications for Turkey. And yet, the Twinning Counterpart will have to guarantee the participation of skillful experts for acquis harmonization and trainings about the unknown expertise areas (but still covered by Directives) to it in case the Project will be implemented by just that institution.

In addition to legal alignment of gender equality acquis, their implementation and inspection of the implementation raising awareness and sensivity about gender equality is another focal point of the project, where preparation of brochures will help people grasp what will change in women’s life with the implementation of gender equality acquis.

As a result of succesful implementation of this project, harmonisation studies on gender equality acquis will be completed timely. Furthermore, staff in the relevant institutions performing legislation alignment studies will become more qualified.  As a result of the study visits, difficulties at the implementation stage and solutions will be taken into consideration in the legislation alignment studies. Moreover, pariticipation of all relevant partners into the project process will minimize lack of coordination between institutions in the progress of legislation alignment studies.

3.2 Assessment of project impact, catalytic effect, sustainability and cross border impact (where applicable)

The training of trainers about gender equality will be arranged, because the number of people attending the training will be limited. Thus, there will be training opportunities for other institutions’ personnel. By means of the activities of the project, capacity improvement of staff in relevant instiutions, especially who will work in harmonization studies of the acquis will contribute to gender mainstreaming in legislation studies and implementations. Moreover, the social dialogue provided through the participation of social partners and NGOs to the project activities, will improve the cooperation between them. The cooperation will contribute to the studies of stakeholders. As a result, the project will provide a fresh impetus for the development of more visible, inclusive and sustainable gender equality mainstreaming.

The project will contribute to step up and complete the legislative hormonization process on gender equality in working life. The advantages of the harmonization will lead to awareness raising of employers, workers, (both men and women). It can be expected to reflect the working conditions and labour participation of women positively.

3.3 Results and measurable indicators:

Results expected from this project are:

1. Draft bill prepared related to the expert report on the legislation alignment between national legislation and EU acquis regarding working life.

2. The human resources capacity in central and provincial bodies of MoLSS and other institutions strengthened.

3 Increased sensitivity on gender equality in working life among NGOs and social partners.

Indicators of achievements of the above-mentioned results are:

1. Draft bill was put on the agenda of the Tripartite Advisory Board by the end of the Project

2. Minimum 3 meetings on draft bill were organised with social partners by the end of the Project.

3. Increased awareness and sensitivity of trained staff of public sector and social partners on gender equality in EU Acquis and Turkish legislation, to be measured through surveys to be conducted at the beginning and end of the project.

8. The project web link was clicked at least 100 times a month by the end of the Project.

3.4 Activities:

National co-financing of the project will be provided from the budget of MoLSS. An 18 months duration twinning project is envisaged. These are the activities which will be done in this process:

1.1 Analysis of Turkish legal texts compared to the EU gender equality acquis (Directives) and relevant case-law of the Court of Justice.

1.2 A report including amendment proposal related to the diverging provisions on the Labour Law no 4857, Law on Civil Servants no 657, Law on Social Security no 5510 (including secondary legislation of labour and social security related with equal treatment and implementation in practice) regarding the gender equality issues in close collaboration with experts of Ministry and Social Security Institution were prepared by twinning experts.

1.3 The report of identifying gaps in the legislation published on the web.

1.4 Draft bill studies are made together with social partners by taking the report including recommendations into consideration.

2.1 Training the related staff of the MoLSS and other relevant institutions. Below is the specific training needs (subject to change after negotiations with the Twinning Counterpart Institution) which should be satisfied at utmost at the end of the Project:

2.1.1 Training on The Equal Treatment of Men and Women. In this trainings issues: generally relevant EU directives about gender equality (96/34/EC, 92/85/EEC, 79/7/EEC, 86/613/EEC, 2004/113/EC, 2006/54/EC); examples of the judgment of the Court of Justice of the European Communities (CJEC), best practices, difficulties which have been faced with in the implementation process, experiences of foreign experts, gained from their own countries..etc. In this training programme, 200 staff will be participating from MoLSS, the other beneficiary institutions and social partners.

2.1.2   Inspector (for MoLSS ve SSI) Training on Practical Inspection Issues Related to Gender Equality in working life for 40 inspectors.

2.1.3 Lawyer and Expert Training on Judicial Issues of Equal Treatment in the   area of social security (case law included) for 20 staff.

2.1.4   Training of 20 State Personnel Expert especially in the field of their expertise area enriched with the experiences of different countries

2.1.5 For 25 experts of MoLSS, SSI and SPP training of trainers concerning EU directives

2.1.6 Training on project management for 20 experts. (There is a requirement in the improvement of staff qualification because project team needs to improve its experiences and knowledge about project implementation process.)

2.2 Arrangements of four study visits of eight persons to the public institutions in EU countries in order to analyze gender equality mechanisms.(160 man/day) The study visit will be arranged with the consideration of following focal points: the sensitivity points taken into consideration in harmonization period by new member states, the institutional structure formed on gender equality, difficulties which are faced with in the implementation process.

2.3 Study visit reports were sent to the related institutions and published in the web.

2.4 Arrangement of 3 traineeships for the experts of Ministry and 2 traineeships for the experts of SSI for one month short terms. These experts will closely observe the policy making and implementatiton of equal treatment in the Twinning Counterpart Institution so that they will prepare a detailed report on how the issues are dealt and their views of relevance of the Member State’s policies with Turkish policy making. They may also inform about feasibility to transfer those policies into the Turkish working life.

2.5 Questionnaires was taken to the personnel attending to the training in order to determine their knowledge level on gender equality in working life at the beginning and at the end of the Project.

3.1 Developing appropriate materials. (Brochure, booklet…) for raising awareness and sensivity about gender equality

3.2 3 seminars and 1 conference (at the end of the project) were held in Ankara and İstanbul.

3.3 Organizing awareness-raising campaigns for public opinion. (By the print media and visual media)

3.4 Forming a web link for the project on Ministry webpage.

3.5 Conditionality and sequencing:

The conditionality for the signature of contracts under the project is that the beneficiary provides sufficient human and material resources for the implementation of the project. The precondition of the project is  to form project implementation unit and to activate this unit.

3.6 Linked activities

"Promoting Gender Equality" Project is implemented jointly by the Prime Ministry, General Directorate on the Status of Women. The aim of this project is to promote gender equality and to protect Womens’ Human Right in Turkey. Twinning Project "Promoting Gender Equality" was launched in March 2007 and it will be completed in November 2008.

Aims of the Project are:

- To promote gender equality in Turkey through communication, training and other tools,

- To strengthen the institutional capacity of the General Directorate on the Status of Women in order to promote gender equality in Turkey,

- To ensure that the gender equality principle is incorporated into all public policies,

- To support the implementation of gender equality related laws through support and involvement of central government, local administrations and non-governmental organisations,

- To contribute to design a draft model for a Gender Equality Body in line with EU practices and the acquis.

UNFPA, an international development establishment, UNFPA’s Fourth National Programme will continue between 2006-2010. One of UNFPA’s aims to support the Turkish Republic Government is to promote the social gender equality.  UNFPA’s National Programme has three components, namely, “Reproductive Health”, “Gender Equality” and “Population and Development Strategies”.  In Gender Equality component, Directorate General on the Status of Women (DGSW) is the implementing institution.

Social Security Institution is going to start implementing the “Capacity Building of Social Security Institution Project” which is financed within the 2007 Financial Programming of the first component of the IPA by the beginning of 2009. The Project has components for training and awareness-raising activities related to social security legislation. In this context, a seminar for 20 people will be organised to introduce EU gender equality acquis related to the social security matter, namely, Directives 96/97/EC, 79/7/EEC and 86/613/EEC.

One of the priority axes of Human Resources Development Operational Program Strategy of Turkey is employment. Priority axes of employment is to increase labour force participation of women and decrease unemployment especially for women and young by supporting public employment services.

Based on the importanace of the necessity to improve women employment, İŞKUR takes active employment measures such as providing vocational trainings, consultancy and guidance services. Due to the participation of ISKUR staff to the project activities, their qualification will improve. Thus, the quality of services mentioned will be enhanced.

3.7 Lessons learned

The project of “Strengthening Gender Equality In Employment” that is prepared by the Turkish Ministry of Labour and Social Security (MoLSS) and the Dutch Ministry of Social Affairs and Employment started on 1 October 2005. Project purpose is to analyse of legal procedures and the implementations of the Netherlands regarding gender equality and unregistered labour with respect to women and to design and develop appropriate administrative and legal measures in Turkey.  There are two results of the project. First result is to increase the capacity of MoLSS in terms of gender equality and unregistered labour and second result is to enhance training and monitoring capability of MoLSS. First result includes following items:

- The establishment of a shared awareness and knowledge of EU directives regarding gender equality.

- The promotion gender equality both in the public and private sectors.

- The demonstration of decisiveness in ensuring of gender equality in working life.

It is stated that Turkish government does not have any holistic approach to establish “Gender Equality” in the conclusion report of MATRA Project which is aimed at advising on the flexibility of labour force in Turkey. Furthermore, it is suggested that it is necessary to develop alternative targets with a view to improving of equality for continuation of the modernization of labour market.

Gender equality working group was constituted within the Social Dialogue Project implemented by the European Union Co-ordination Department of the Ministry. One of the important outputs of this working group is to pinpoint the importance of widening day-care and nursing home facilities, in order to   increase female employment. In Gender Equality Working Group, it was emphasized that most of the important complications are child and elderly care in the harmonization of womens’ work and private life. Thus, it was stated that child and elderly care services should have priority in the social policy field. For institutionalizing child care services social dialogue mechanisms should be strengthened.

By the projects mentioned above, the capacity of MoLSS has been improved. The improved capacity and gained experience will let the Ministry to behave consciously in the project activities.

4. Indicative Budget (amounts in EUR)

|  |  |  |  | SOURCES OF FUNDING |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | TOTAL EXP.RE | TOTAL PUBLIC EXP.RE | IPA COMMUNITY CONTRIBUTION |  | NATIONAL PUBLIC CONTRIBUTION |  |  |  |  | PRIVATE CONTRIBUTION |  |
| ACTIVITIES | IB (1) | INV (1) | EUR (a)=(b)+(e) | EUR (b)=(c)+(d) | EUR (c) | % (2) | Total EUR (d)=(x)+(y)+(z) | % (2) | Central EUR (x) | Regional/ Local EUR (y) | IFIs EUR (z) | EUR (e) | % (3) |
| Activity 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Twinning contract 1.1 | – | – | 1 000 000 | 1 000 000 | 950 000 | 95 | 50 000 | 5 | 50 000 |  |  |  | – |
| TOTAL IB |  |  | 1 000 000 |  |  | 95 |  | 5 |  |  |  |  |  |
| TOTAL INV |  |  | - |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT |  |  | 1 000 000 | 1 000 000 | 950 000 | 95 | 50 000 | 5 |  |  |  |  |  |

NOTE: DO NOT MIX IB AND INV IN THE SAME ACTIVITY ROW. USE SEPARATE ROW

Amounts net of VAT

(1)	In the Activity row use "X" to identify whether IB or INV

(2)	Expressed in % of the Public Expenditure (column (b))

(3) 	Expressed in % of the Total Expenditure (column (a))

5. Indicative Implementation Schedule (periods broken down per quarter)

| Contracts | Start of Tendering | Signature of contract | Contract Completion |
| --- | --- | --- | --- |
| TWINNING Contract 1.1 | First Quarter of 2009 | Forth Quarter of 2009 | Second Quarter of 2011 |

Duration of the project : 18+3  months

All projects should in principle be ready for tendering in the 1st Quarter following the signature of the FA.

6. Cross cutting issues (where applicable)

  - Equal Opportunity

To promote gender equality in working life is the main aim of this project. Therefore, the project will make a direct contribution to provide equal opportunities for men and women.

6.2	Environment

N/A

6.3	Minority and vulnerable groups

According to the Turkish Constitutional System, the word minorities encompass only groups of persons defined and recognized as such on the basis of multilateral or bilateral instruments to which Turkey is a party.

ANNEXES

1-	Log frame in Standard Format

2-	Amounts contracted and Disbursed per Quarter over the full duration of Programme

3- 	Institutional Framework

* Role and responsibilities of the SPO

* frequency of project management meetings,

* who chairs, who attends and in what role

* coordination mechanisms for multi-beneficiary projects

*  monitoring (roles, responsibilities of all actors)

4 -	Reference to laws, regulations and strategic documents:

Reference list of relevant laws and regulations

Reference to AP /NPAA / EP / SAA

Reference to MIPD

Reference to National Development Plan

Reference to national / sector investment plans

5-	Details per EU funded contract (*) where applicable:

For TA contracts: account of tasks expected from the contractor

For twinning covenants:  account of tasks expected from the team leader, 	resident twinning advisor and short term experts

For grants schemes:  account of components of the schemes

For investment contracts: reference list of feasibility study as well as technical specifications and cost price schedule + section to be filled in on investment criteria (**)

For works contracts: reference list of feasibility study for the constructing works part of the contract as well as a section on investment criteria (**); account of services to be carried out for the service part of the contract

(*) non standard aspects (in case of derogation to PRAG) 	also to be specified

(**) section on investment criteria (applicable to all infrastructure contracts and constructing works):

Rate of return

Co financing

compliance with state aids provisions

Ownership of assets (current and after project completion)

ANNEX 1: Logical framework matrix in standard format

| LOGFRAME PLANNING MATRIX FOR Project Fiche Promoting Gender Equality in Working Life |  | Programme name and number |  |
| --- | --- | --- | --- |
|  |  | Contracting period ) expires 2 years after the signature of the Financing Agreement | Disbursement period expires in 3 years following the end date for contracting. |
|  |  | Total budget : € 1,000,000 | IPA budget: 950,000 € |
| Overall objective | Objectively verifiable indicators | Sources of Verification |  |
| To ensure gender equality in working life. | To make progress about gender equality in working life | Accession Partnership Priority and Regular Report Comments |  |
| Project purpose | Objectively verifiable indicators | Sources of Verification | Assumptions |
| To align Turkish legislation with EU gender equality acquis and improve capacity of institutions responsible for the implementation of the said acquis | The draft bill in line with the EU acquis is put on the agenda of the Tripartite Advisory Board by the end of the Project As a result of seminars and trainings on gender equalityknowledge and awareness of relevant staff is increased by 25%. | The draft bill in line with the EU acquis Results of quastionnaries made at the beginning and at the end of the Project. (Base Line Study) | During the implementation of the project, continuing political stabiliy related to the integration with EU, both in EU and in Turkey. The willingness of the target group. To be open coordination of relevant public institutions |
| Results | Objectively verifiable indicators | Sources of Verification | Assumptions |
| 1. Draft bill prepared related to the expert report on the legislation alignment between national legislation and EU acquis regarding working life. 2. The human resources capacity in central and provincial bodies of MoLSS and other institutions strengthened. 3. Increased sensitivity on gender equality in working life among NGOs and social partners. | Draft bill was put on the agenda of the Tripartite Advisory Board by the end of the Project Minimum 3 meetings on draft bill were organised with social partners by the end of the Project. Increased awareness and sensitivity of trained staff of public sector and social partners on gender equality in EU Acquis and Turkish legislation The project web link was clicked at least 100 times a month by the end of the Project. | CEDAW reports Project reports Draft bill Baseline survey | Political authorities taking into account expert report Persons attended to training are sensitive on gender equality. Persons joining the baseline survey reply the questions correctly. |
| Activities | Means | Costs | Assumptions |
| 1.1 Analysis of Turkish legal texts compared to the EU gender equality acquis (Directives) and relevant case-law of the Court of Justice, case-law of ECHR and the other relevant on gender equality CoE standards and texts. 1.2 A report including amendment proposal related to the diverging provisions on the Labour Law no 4857, Law on Civil Servants no 657, Law on Social Security no 5510 including secondary legislation of labour and social security related with equal treatment and implementation in practice in close collaboration with experts of Ministry and Social Security Institution were prepared by twinning medium term experts. 1.3 The report of identified gaps in the legislation published on the web. 1.4 Draft bill studies are made together with social partners by taking the report including recommendations into consideration. 2.1 Training the related staff of the MoLSS and other beneficiary instituions. Below is the specific training needs (subject to change after negotiations with the Twinning Counterpart Institution) which should be satisfied at utmost at the end of the Project: 2.1.1 Training on The Equal Treatment of Men and Women. In this trainings issues: generally relevant EU directives about gender equality (96/34/EC, 92/85/EEC, 79/7/EEC, 86/613/EEC, 2004/113/EC, 2006/54/EC); examples of the judgment of the Court of Justice of the European Communities (CJEC), best practices, difficulties which have been faced with in the implementation process, experiences of foreign experts, gained from their own countries..etc.In this training programme, 200 staff will be participating from MoLSS, other relevant institutions and social partners 2.1.2 Inspector (for MoLSS ve SSI) Training on Practical Inspection Issues Related to Gender Equality in working life for 40 inspectors. 2.1.3 Lawyer and Expert Training on Judicial Issues of Equal Treatment in the area of social security (case law included) for 20 staff. 2.1.4 Training of 20 State Personnel Expert especially in the field of their expertise area enriched with the experiences of different countries 2.1.5 For 25 experts of MoLSS, SSI and SPP training of trainers concerning directives 2.1.6 Training on project management for 20 experts. 2.2.Arrangements of four study visits of eight persons to the public institutions in EU countries in order to analyze gender equality mechanisms.(160 man/day) The study visit will be arranged with the consideration of following focal points: the sensitivity points taken into consideration in harmonization period by new member states, the institutional structure formed on gender equality, difficulties which are faced with in the implementation process..etc. 2.3.Study visit reports were sent to the related institutions and published on the web. 2.4 Arrangement of 3 traineeships for the experts of Ministry and 2 traineeships for the experts of SSI for one month short terms 2.5.Questionnaire was filled in by the personnel attending to the training in order to determine their knowledge level on gender equality in working life at the beginning and at the end of the Project. 3.1. Developing appropriate materials. (brochure, booklet…) 3.2. 3 seminars and 1 conferences (at the end of the project) were held in Ankara and İstanbul. 3.3 Organizing awareness-raising campaigns for public opinion. (By the print media and visual media). 3.4 Forming a web link for the project on Ministry webpage | Contract 1: TWINNING | € 1,000,000 | Effective coordination among the all stakeholders regarding adoption of the EU acquis. Provide appropriate human resources, to support the project activities and to keep Stakeholders’ willingness |

Precondition:

Provision of sufficient human and material resources for the implementation of the project by the beneficiaries.Establishment and operation of project implementation unit.

ANNEX II:	amounts (in €) contracted and disbursed by quarter for the project

(IPA contribution only)

| Contracted | 2009/Q4 |  | 2010/Q1 | 2010/Q2 |  | 2010/Q3 | 2010/Q4 | 2011/Q1 |  | 2011/Q2 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contract 1.1 TWINNING | 950,000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cumulated | 950,000 | 950,000 |  | 950,000 | 950,000 |  | 950,000 |  | 950,000 | 950,000 |  |  |  |  |  |  |  |  |
| Disbursed | 2009/Q4 | 2010/Q1 |  | 2010/Q2 | 2010/Q3 |  | 2010/Q4 |  | 2011/Q1 | 2011/Q2 |  |  |  |  |  |  |  |  |
| Contract 1.1 TWINNING | 427,500 |  |  |  |  |  | 427,500 |  |  | 95,000 |  |  |  |  |  |  |  |  |
| Cumulated | 427,500 | 427,500 |  | 427,500 | 427,500 |  | 855,000 |  | 855,000 | 950,000 |  |  |  |  |  |  |  |  |

INDICATIVE    BUDGET

TWINNING

|  | Budget Summary | Units | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
| 1 | RTA | 18 Month | 15 000/month* | 270 000 |
| 2 | RTA Assistant | 18 Month (×2) | 2 000/month | 72 000 |
| 3 | Project Leadership | 54 days | 1 000/day* | 54 000 |
| 4 | Mid / Short Term Expert | 350 days | 750 / day* | 262 500 |
| 5 | Activities (trainings, seminers, conferences ) | 77 days | 1 700 / day* | 130 900 |
| 6 | Study Visit | 160 manday (8 men×20 days) | 275 /day** | 44 000 |
| 7 | Operational Costs (interpretation during meetings, trainings etc., translation of the documents, training materials including CDs, pens, papers, published documents etc..) |  |  | 60 000 |
| 8 | Traineeships (5 person) | 150 days | 225/ day** | 33 750 |
| 9 | Sub-Total |  |  | 927 75 150 |
| 10 | Contengencies |  |  | 22 850 |
| 11 | Total |  |  | 1 000 000 |

* It includes estimated average costs of per diem, flight, fee, project management costs

** It includes estimated average costs of per diem, accomodation, meals etc.

ANNEX III: Institutional Framework

ORGANİSATIONAL  CHART

Technical Assistance

Resident Twinning Adviser (RTA)

Project Coordination Unit

(PCU)

Project Implementatiom Unit

STEERING COMMITTEE

Central Finance and Contracting Unit (CFCU)

EU DELEGATION

Institutional Framework

The main beneficiary of the project is the Directorate General of Labour of the Ministry of Labour and Social Security. The co-beneficiary is EU and Foreign Affairs Department of Social Security Institution. A Project Coordination Unit (PCU) will be established by MoLSS which will closely liaise with the twinning partner. The other beneficiary institutions will provide experts to work within or for the PCU in case need arises for the specific expertise areas of those institutions.  The MoLSS will establish a Project Co-ordination Unit (PCU) headed by RTA counterpart. The PCU will be adequately staffed and will provide the use of all necessary premises and logistical support (office space, access to telephone, fax, etc. The Beneficiary institution (MoLSS) will work together with the Twinning Partner that will be determined at the end of the selection process regarding implementation of the project activities indicated in the subsequent sections. Existence of a professional and stable structure for PCU staff is a crucial factor for the timely and proper implementation of the programme.

A Steering Committee (SC) will be established for the project. Steering Committee (SC) is the decision-making body of the project. The quarterly meetings of the SC will provide a platform for monitoring project implementation at the national level. The SC will provide policy guidance to improve project implementation. It will also discuss the strategy and/or policy documents prepared within the framework of the project, and make recommendations based on such strategies and policies. It will review all the activities and analyses the achievement of project outputs and objectives. It discusses problems which arise during the implementation of the project and makes recommendations.

The SC will be composed of RTA, RTA Counterpart, representatives from the main institutions dealing with gender equality in working life in Turkey, namely, MoLSS,  Social Security Institution, State Personnel Presidency, Turkish Employment Organisation (İŞKUR), General Directorate on the Status of Women, CFCU and ECD.

The SC will be co-chaired by two project leaders. SC will meet to discuss at quarterly intervals. The Twinning Project Steering Committee will also discuss the draft of the quarterly report submitted to it beforehand and recommend corrections.

While all administrative and technical responsibility rests with the MOLSS, the project will create and make extensive use of links with other ministries and government institutions, universities, international agencies and civil society organisations operating in the field of gender equality.

ANNEX IV: Reference to laws, regulations and strategic documents

EU LEGISLATION:

1. Council Directive 96/34/EC on the framework agreement on parental leave concluded by UNICE, CEEP and the ETUC;

2. Council Directive 92/85/EEC on the introduction of measures to encourage improvements in the safety and health at work of pregnant workers and workers who have recently given birth or are breastfeeding;

3. Council Directive 79/7/EEC on the progressive implementation of the principle of equal treatment for men and women in matters of social security;

4.Council Directive 86/613/EEC on the application of the principle of equal treatment between men and women engaged in an activity, including agriculture, in a self-employed capacity, and on the protection of self-employed women during pregnancy and motherhood;

5. Councıl Directive 2004/113/EC implementing the principle of equal treatment between men and women in the access to and supply of goods and services;

6. Council Directive 2006/54/EC on the implementation of the principle of equal opportunities and equal treatment of men and women in matters of employment and occupation (recast)

7. Case-law of the European Court of Justice regarding to gender equality

8. CoE standards and texts (ECHR and its case-law and selected monitoring reports)

TURKISH LEGISLATION:

- Labour law No. 4857

- Civil Servants Law No. 657

- Law on Trade Unions No 2821

- Social Security and Universal Health Insurance Law No. 5510

- Implementing regulation  concerning the working conditions of pregnant or breastfeeding mothers, breastfeeding rooms and children nursing homes.(Official Gazette No.25522)

- Implementing regulation for hard and dangerous work (Official Gazette No. 25494)

- Implementing regulation concerning labour law  for overtime and work for extra duration (Official Gazette No. 25425)

- Implementing regulation concerning  the working conditions of female workers at night shifts.( Official Gazette No. 25548)

- Implementing regulation for minimum wage (Official Gazette No. 25540)

- Implementing regulation for short term working short  term  working  allocation. (Official Gazette No.25419)

- Implementing regulation for special methods and principles concerning the work executed through shift workers. (Official Gazette No.25426)

ANNEX V: Details per EU funded contract (*) where applicable:

For twinning covenants:  account of tasks expected from the team leader, resident twinning advisor and short term experts

TWINNING:

The MoLSS Directorate General of Labour will be the main beneficiary of the project. The project will be implemented in the form of a Twinning contract between Turkey and a Member State/Member States. Close cooperation and communication between the twinning partner and beneficiary is crucial during the implementation of the project. The EU Twinning partner will be a Member State institution directly involved in gender equality issues. The Twinning Team will be located at the MOLSS.

For the twinning component, MoLSS will appoint a project leader and an RTA counterpart. Project leader will have the overall responsibility for all issues concerning the management and monitoring of the project. The Project leader from the Turkish side will be will be the General Director of Labour.

The Twinning partner(s) will provide a Resident Twinning Advisor (RTA) and also secure a pool of medium and short- term experts, who will be called upon whenever necessary to contribute to the achievement of the results according to the work plan that will be prepared as part of the corresponding contract. MOLSS will provide office space, internet and fax access for the twinning partner.

PROJECT LEADER:

The PL should be a high-ranking official with broad knowledge of gender equality issues who will continue to work at his/her Member State administration but devote some of his/her time to conceive, supervise and coordinate the overall thrust of the Twinning Project.

He/she should also have international experience. He/she will be responsible for overall implementation of the project. Furthermore, project leader will manage financial issues and coordination with RTA and also beneficiary project leader and SPO.

The PL will allocate a minimum of 3 days per month and including one visit every 3 months to Turkey as long as the project lasts.

Qualifications:

- Broad long-term knowledge of all processes in the area of gender equality;

- High-ranking official with ability to call on short and medium-term experts in support of the efficient implementation of the project;

- Capable of unblocking any problems at highest level;

- Good leadership skills.

Tasks:

- Overall project coordination;

- Co-chairing with the Turkish PL the regular project implementation steering committee meetings;

- Mobilizing short and medium-term experts;

- Executing administrative issues.

RESIDENT TWINNING ADVISER (RTA)

The RTA, who will reside 18 months in Turkey, will be responsible for overall management and coordination of project activities. RTA will work together with the staff of the beneficiary institution under the overall direction of the beneficiary institution and the Steering Committee. He is expected to carry out the following tasks during his full-time working period. The duration of the assignment of the RTA will be 18 calendar months.

Qualifications:

- At least 5 years of experience in gender equality related acquis and gender policies of the European Union,

- Experience in a gender equality related department of the government of a member state,

- Have access to specialist personnel who are able to provide the detailed and relevant information or other skills required,

- Play the key role in the management of the twinning project and should have the necessary managerial skills,

- Sound communication skills and previous experience of working in a multi-disciplinary and multi-national team,

- Good knowledge of English.

Tasks:

- Play the key role in the management of the twinning project,

- Monitor the project implementation and propose corrective management actions,

- Monitor the disbursement of funds of the project,

- To plan and coordinate on training programmes and outputs,

- To nominate and supervise the medium and short term experts,

- To coordinate and organise study visits, training activities, seminars, conferences and public awareness activities,

- As a result of  seminars and conferences, to prepare reports.

- To ensure proper quality of outputs,

- To provide detailed reports on the impact of the project,

- To assist the Turkish experts and short term experts in the preparation of all strategic project documents [inception study, quarterly monitoring reports, final project report, training manuals etc.]

- To prepare quarterly meetings.

MID / SHORT-TERM EXPERTS

The experts will work in close co-operation with the RTA and the PCU staff in order to meet specific objectives as set above.

Qualifications:

The experts will be qualified in the particular fields in which they are being utilised, either through formal qualifications or through practical experience. The experts should have the following knowledge and experience:

- Sound background in the fields of law and policy making concerning EU policies on gender equality, gender mainstreaming, equality bodies, project management and best practices of Member States. Minimum of 5 years Professional experience in the gender equality field and its application

- Sound and broad knowledge on implementation of EU gender equality acquis in the EU Member States, including case law of European Court of Justice

- Broad professional experience in the gender equality field and its application

- Skills in policy development,

- Designing training curriculum as well as implementing training of trainers,

- “Consultancy” experience in an international context,

- Strong communication skills and having ability to train.

- Good comment of written and spoken English.

Tasks:

Each expert in his/her scope of expertise should make an analysis of the current situation and develop a concept together with the experts of Turkey as to further implement an efficient reorganisation of the service. The short terms experts will be responsible for the execution of the following tasks:

- To contribute to the project with specialist knowledge in the area of gender equality.

- To analyse Turkish legal texts and compare with EU gender equality acquis, case-law of the ECJ, case-law of ECHR and the other relevant on gender equality CoE standards and texts.

- To prepare a comprehensive report including recommendations and determining discrepancies between relevant provisions in Turkish legislation and  EU gender equality acquis, case-law of the ECJ, case-law of ECHR and the other relevant on gender equality CoE standards and texts.

- To assist MoLLS  drafting of legislation concerning gender equality in compliance with the relevant EU legislation.

- To prepare questionnares for training  staff at the beginning and end of the Project.

- To prepare the context of the brochures and handbooks related to gender equality

- To provide specialist support and advice services.

- To prepare training curriculum in coordination with the RTA.

- To prepare the necessary training documentations.

- To prepare the reports for the end of the trainings

- To train on EU Acquis related to gender equality and best practices of Member States, training of trainers.

The expert visits to carry out project activities will be organised by the RTA together with the project leader. RTA will provide all relevant documentation and information on the situation in Turkey to the experts and their contribution will be expected. Each expert will write a ‘mission report’ upon completion of his/her visit to Turkey. This will give a brief appraisal of the situation upon arrival, the work done (developments achieved, meetings attended, people met) during the stay, recommendations for future action including specific tasks to be mandated to the Turkish specialists, and difficulties encountered during the visit.