|  | THE REPUBLIC OF CROATIA MINISTRY OF ENVIRONMENTAL PROTECTION, PHYSICAL PLANNING AND CONSTRUCTION |
| --- | --- |

Programme: IPA 2008 – component I

Partner Country: Croatia

Area of Cooperation: Environment

IPA: STANDARD TWINNING PROJECT FICHE

Enforcement of the new Environmental Protection Act harmonized with EU legislation in cases of criminal offences against the environment

Project budget: 1.100.000 €

STANDARD TWINNING PROJECT FICHE

1. 	Basic Information

1.1 	Programme: IPA TAIB 2008

1.2 	Twinning Number: HR/2008/IB/EN/01

1.3 	Title: Enforcement of the new Environmental Protection Act harmonized with EU legislation in cases of criminal offences against the environment

1.4 	Sector: Environment

1.5 	Beneficiary country: Croatia

2. 	Objectives

2.1 	Overall Objective(s):

Support to environmental protection in Croatia through the enforcement of provisions of the new Environmental Protection Act.

2.2 	Project purpose:

To build up capacity for enforcement of the provisions of the new Environmental Protection Act (EPA) in cases of criminal offences against the environment.

  - Contribution to Accession Partnership / the Stabilization and Association Agreement / the National Programme for Integration of the Republic of Croatia into the EU (NPIEU)

1. Stabilization and Association Agreement, COM (2001) - 371 final, Article 103: Environment

„The Parties shall develop and strengthen their co-operation in the vital task of combating environmental degradation, with the view to promoting environmental sustainability.”

Having in mind the overall objective and project purpose and most importantly - all defined stakeholders of this project, it is expected that this project will contribute greatly to the abovementioned combat with environmental degradation through the strengthened co-operation and enhanced capacity for enforcement of new environmental legislation.

2. European Partnership (Council Decision, COM (2004) 275, Brussels 20 April 2004)

One of the chapters’ 3.1 short term priorities was to strengthen the capacity of national and regional inspection services and enable them to effectively enforce environmental legislation.

In Chapter 3.2 Medium term priorities, such as „assurance the integration of environmental protection requirements into the definition and implementation of other sectoral policies with a view to promoting sustainable development and implementation of horizontal legislation“ are defined, also refer to this project purpose which is the enforcement of provisions of the new Environmental Protection Act with the view of supporting environmental protection in Croatia.

3. National Programme for the Integration of the Republic of Croatia into the European Union 2008.

Chapter 3.27.1: Environment Horizontal legislation, B) Key Priorities

The environmental inspection will work intensively on bringing its working methods into line with new legislation, continuing to upgrade its working methods and co-ordination during inspectional supervision.

Pursuant to the Act on Environmental Protection (OG 110/2007) the adoption of subordinate legislation regarding environmental liability is foreseen in 2008, with the purpose of further alignment with Directive 2004/35/EC.

Cooperation with Interpol and ECENA and INECE network will be furthermore enhanced through the activities foreseen in ECENA’s Cluster 3 „Protection of Environment through Enforcement of the Criminal Law” as well as the close cooperation and trainings of inspectors for environmental protection, police officers, custom officers and public prosecutors in Interpol headquarters. Inspectors for environmental protection will be trained in cooperation with Interpol for reporting and for collection of evidences in case of criminal offences against the environment.

4. Council Decision on the principles priorities and conditions contained in the Accession partnership with Croatia and repealing Council Decision 2006/145/EC Brussels, 05.02.2008., 5122/2008; Chapter 27: Environment

This project will also contribute to realization of several stated priorities such as continuation of work on transposition and implementation of the EU acquis, with particular emphasis on waste management, water quality, air quality, nature protection and integrated pollution prevention and control, as well as ensuring the integration of environmental protection requirements into the definition and implementation of other sectoral policies and promote sustainable development, since it's main goal is to facilitate Croatian bodies to enforce more efficiently the provisions of the new Environmental Protection Act (EPA) in cases of criminal offences against the environment.

5.  Link with MIPD 2008-2010

Under Component I, 3rd area of intervention - Ability to assume the obligations of membership, the project will focus for chapter 27 – Environment, where the proposed Accession Partnership identifies some priorities notably to support the Croatian authorities by measures aimed at adopting or completing the transposition of the acquis. Therefore this project will directly contribute towards achieving the “Ability to assume the obligation of membership”.

3. 	Description

3.1 	Background and justification:

The implementation of the EU environmental acquis is a demanding but necessary requirement for each country that is seeking membership of the EU. Alignment with the environmental acquis is a necessary but not the only requirement to meet the obligations of EU membership. The Republic of Croatia must also take all measures to establish efficient implementation structures, to bring administrative as well as judicial capacities up to the required level and to ensure effective enforcement of the environmental law.

Area of the protection of the environment and all it’s components within the environmental protection regulations and acts related to the criminal offences against environment is recognized within EU as the very important but also as the one that needs to be improved. In order to strengthen environmental protection through criminal law, the European Commission adopted on December, 6th 2008 a Directive 2008/99/EC of the European Parliament and of the Council of 19 November 2008 on the protection of the environment through criminal law, Official Journal L 328. The Directive obliges Member States to treat serious offences against the environment as criminal offences and to ensure that they are effectively sanctioned. Since the definition of environmental crimes varies greatly from one Member State to another in many Member States the new Directive will ensure a minimum level of protection of the environment under criminal law throughout the European Union.

At this moment, in the Republic of Croatia the issue of criminal offences against environment is tackled by the new Environmental Protection Act (Official Gazette No 110/2007) which is in line with the EU legislation in force. EPA defines the main principle regarding the role of environmental protection inspectors and their duties and responsibilities in the procedures in case of misdemeanour or criminal charges. The Article 213 of the Environmental Protection Act states:

“If during inspectional supervision, it is established that this Act and/or regulations passed on the basis thereof have been violated, the inspector has the right and obligation to immediately:

- issue a misdemeanour order in accordance with a special act,

- file criminal charges for a criminal act to the competent body,

- undertake other measures and perform other actions for which he is authorised pursuant to this Act and special regulation.”

The same rights and obligations are in force also according the provisions of, Waste Act (Official Gazette No 178/04,111/06) or Air Protection Act (Official Gazette No 178/04) and/or regulations passed on the basis of these acts. If during inspectional supervision, it is established that these acts are violated the inspector has the right and the obligation to immediately file criminal charges to the competent body. In case that there is a suspicion of violation of the provisions of the Environmental Protection Act the principles and articles of Criminal Procedures Act (OG No 152/08) should apply.

Croatian Criminal Act (Amended text) (OG No 110/97, 27/98, 129/00, 51/01, 111/03) in chapter XIX in articles 250, 251, 252, 253, 254 prescribes criminal offences against the environment as well as Serious Criminal Offences Against the Environment in the article 262.:

“(1) If, by the criminal offence referred to in Article 250, paragraphs 1 and 2, Article

251, paragraph 1, Article 252, paragraphs 1 and 2, Article 253, paragraphs 1 and 2 and Article 254, paragraph 1 of this Code, serious bodily injury or severe impairment to the health of a number of persons is caused, or the death of one or more persons is caused, or if the changes caused by the pollution cannot be eliminated for a considerable period of time, or if an ecological catastrophe is caused, the perpetrator shall be punished by imprisonment for one to ten years.

(2) If, by the criminal offence referred to in Article 250, paragraph 3, Article 251,

paragraph 2, Article 252, paragraph 3 and Article 254, paragraph 2 of this Code, the death of one or more persons is caused, or serious bodily injury or severe impairment to the health of a number of persons is caused, or if the changes caused by the pollution cannot be eliminated for a considerable period of time, or if the quality of the environment is substantially diminished, the perpetrator shall be punished by imprisonment for one to five years.

(3) If, by the criminal offence referred to in Article 255, paragraph 1, Article 256,

paragraph 1 and Article 257, paragraph 1, Article 258, paragraph 1 and Article 259, paragraph 1of this Code, extensive material damage is caused, the perpetrator shall be punished by imprisonment for one to five years.

(4) If, by the criminal offence referred to in Article 255, paragraph 2 and Article 257,

Section 2 of this Code, extensive material damage is caused, the perpetrator shall be punished by imprisonment for one to three years.“

The New Environmental Protection Act also deals in section ten with the environmental liability regarding environmentally dangerous activities and environmental liability, liabilities in general, exemptions, obligation to determine which company caused environmental damage and/or damage to protected species, obligation to assess the significance of the damage and the imminent threat of damage, compensation for expenses and damages, claim for compensation of costs and damages, compensation for other damages which occurred during environmental damage and obligation of undertaking measures and notification.

Having in mind the obligation for openness and free access to environmental information, in December 2006 the Croatian Parliament has ratified The Convention on Access to Information, Public Participation in Decision making and Access to Justice in Environmental Matters (so called “Aarhus Convention”). Provisions of the convention haves been integrated in new EPA.

Therefore existing “Right to Access Information Act” (Official Gazette No 172/2003) and the new Environmental Protection Act create coherent legal framework for providing the access of public to environmental information, which is fully in line with the principles of Aarhus Convention. The provisions must also be respected through inspection procedures including also the criminal offences procedures.

Republic of Croatia till now can not report about large number of successfully finished cases in relation with criminal offences against the environment as well as serious criminal offences against the environment. It indicates that we have to bring and enhance capacities up to the required level and to ensure effective enforcement of the environmental law. Improvement of the knowledge and skills in order to establish the effective measures for the protection of the environment in Republic of Croatia is necessary to ensure the efficient implementation of Croatian environmental protection policy. Environmental protection inspection needs to improve the knowledge and skills together with police officers, custom officers, public prosecutor officers, judiciary, courts experts and expert witnesses in order to recognize criminal offences against the environment as well as serious criminal offences against the environment. Appart from this, they need to improve their knowledge and skills on how to react immediately and how to coordinate all relevant staff in order to protect the evidences on the ground.

Therefore the main reason for proposing this project is to improve protection of environment through enforcement of the new Environmental Protection Act harmonised with EU legislation and it’s provision regarding filling criminal charges for a criminal offences to the competent body.

The project results will be applicable in recognitions of the violations against environment and in the process of collecting the evidences for the purpose of the prosecution in front of the Criminal Court. We expect that the results will be measurable and visible on the long term period and will help Republic of Croatia in required level to ensure effective enforcement of the environmental law as a future member of EU Community.

3.2 	Linked activities:

3) CARDS 2003 regional project „Establishment of an Independent, Reliable and Functioning Judiciary and the Enhancing of the Judicial Co-operation in the Western Balkans“, Module 4 „Introduction to EC Law and EU judicial system“, Chapter 6 „Introduction to other EU Policies (Public Procurement, Consumer Protection and Environment Law)“, Activity 4.6.6., Regional Roundtable Ohrid (The Former Yugoslav Republic of Macedonia), July 13 – 14, 2006.

The main issues which were addressed within this project module were ways of strengthening the regional cooperation between judges, prosecutors and inspectors in the implementation of EU Environmental Law and strengthening the judicial protection of the citizens according to the EU acquis and the European Convention for Human Rights.

In the course of the abovementioned Regional Roundtable the following critical issues related to environmental protection inspection procedures were identified:

- Need to inform environmental inspectors about the outcome, within the judicial phase, of their investigations and to clarify the discretion upon prosecutors related to the decision to proceed against environmental alleged violations.

- Difficulties for environmental inspectors in the collection of evidences and in reporting to public prosecutors often due to the lack of know-how and training of inspectors on procedural and substantive rules and mechanisms in this field. For instance sampling procedures often are left to third parties and inspectors do not have powers on sites; no guidelines available relating to the collection of samples (i.e. distance from pollution sources – how does it affect assessment of liability and quantification of damages).

- Lack of adequate involvement of citizens and non governmental organizations in judicial and administrative proceedings on environmental matters.

The recommendations reflecting on these issues and at the same time most relevant regarding this project proposal are the following:

- To promote the dialogue between inspectors, prosecutors and judges (seminars, workshops etc.) at national and regional level in view of sharing best practices and eventually adopting standards of cooperation (i.e. Investigation Protocols), developing strategies in non-compliance response and code of conduct, related to investigations conducted by inspectors and public prosecutors. Because of their regional programmes in this field, this should be done in coordination or in cooperation with the Regional Environmental Centre, including the Secretariat of the Environmental Compliance and Enforcement Network for Accession (ECENA). This would help to improve structured compliance monitoring, consistent non compliance response, and enforcement procedures that would stand in Court.

- To develop means of cooperation between inspectors and public prosecutors and judges in the adoption of preventive and interim measures.

- To promote the assistance from inspectors to prosecutors and judges in identifying the most appropriate remedy measures (i.e. restoring as it was quo ante the contaminate site).

- To improve exchange of data and information between inspectors and public prosecutors regarding pending procedures and their outcome.

- To improve legal training of inspectors.

1) Phare 2005 project - Enhanced Environmental Inspection for Enforcement of the New Environmental Legislation

MEPPPC is currently implementing project „Enhanced Environmental Inspection for Enforcement of the New Environmental Legislation“ financed through Phare 2005 programme, which started with implementation in January 2008 and is to be completed by the November 2009, enshuring that there are no overlapping with IPA 2008 project.  The objective of this project is to increase environmental protection's capacities for enforcement of new environmental acquis and it's Component 3 is the most relevant for IPA 2008 project proposal. Table developed below is showing all linkages between the two projects:

| Phare 2005 project - Enhanced Environmental Inspection for Enforcement of the New Environmental Legislation | Link to IPA 2008 -Enforcement of the new Environmental Protection Act harmonized with EU legislation in cases of criminal offences against the environment |
| --- | --- |
| Component 1: Analysis of the environmental and other related inspections and Proposal for the structure of environmental inspection. | IPA 2008 will be built upon Phare 2005 outputs, however will consist of the analysis of all the bodies engaged in cases of criminal actions against the environment and not only environmental inspections as well as proposing a Manual for coordinated enforcement of stipulations of the EPA in Croatia for all involved bodies (env.prot.inspection, customs, public prosecutors, police, courts experts, expert witnesses). |
| Component 2: Definition of skills and qualifications, training and education for Inspectors involve in environmental inspections (Phase1: Training of the trainers group for MEPPPC inspectors; Phase2A: National Training Program for environmental inspectors and inspectors from line bodies; Phase2B: Education about EU Legislation on Environmental Protection for broader group). | Training in the framework of IPA 2008 is conceived for all the bodies engaged in cases of criminal offences against the environment in order to establish efficient cooperation between them. As it plans to establish core trainers which are environmental inspectors it will profit from the knowledge they gained in the framework of Phare 2005. Also the involvement of all bodies in IPA 2008 training will be facilitated thanks to ownership built in Phare 2005 project. |
| Component 3: Proposal for the structure of the pilot team and development of common criteria for the work of the team. | This (IPA) project proposal is planned to be mainly a continuation of the Phare 2005 Component 3. Defined ways of cooperation and standards for proceeding in cases of environmental damage as well as criteria and recommendations for the future work of the team will be the starting point for developing procedures in cases of criminal offences against environment and making the Manual for coordinated enforcement of stipulations of the EPA in Croatia. |
| Component 4: Development and introduction of software application which will enable the improvement of the existing reporting system trough electronic and other media, both in English and Croatian. | Developed, tested and operational software application and functioning reporting system will be used as supporting tool for the proposed IPA project and vice-versa, since the application should have possibility of managing and demonstrating data, pictures and movies in a multimedia video room; be linked to other useful databases of relevant line institutions, projects and networks (ECENA, IMPEL, IMPEL TFS, INECE; REPIN, Interpol, …). Each regular inspection, or on site visit in case of emergency should be stored in database together with photos, videos and other media, while it will also contain relevant legislation, procedures in urgent situations etc. One of the aims is to make certain data available for the exchange with relevant databases as well as to the public in order to improve reporting system. |

Phare 2005 project will end with its activities by November 2009, while start of activities within IPA 2008 project is expected in 2nd quarter of 2010, which leaves enough time period in-between to enable the start of IPA project activities on the strong basis of the Phare 2005 outputs.

2) Phare 2006 multi-country programme on Environment and Enlargement – project “Developing capacity in implementation and enforcement of environmental law through ECENA and IMPEL”

In the framework of the PHARE 2006 multi-country programme on Environment and Enlargement, the Commission has signed a contract with Eptisa International (and their partner RPS Advies) for the Project "Developing capacity in implementation and enforcement of environmental law through ECENA and IMPEL".

The Environmental Compliance and Enforcement Network for Accession (ECENA) is an informal network of environmental authorities from the pre-candidate countries, candidate countries and Bulgaria and Romania as new EU member states (http://www.rec.org/REC/Programs/REREP/ECENA/Default.html). The general objective of ECENA is to improve the ability of the pre-candidate, candidate and acceding countries to implement and enforce the environmental acquis. The network needs to closely cooperate with the European Union Network for the Implementation and Enforcement of Environmental Law (IMPEL) and seek its involvement in the network’s activities.

The activities of the project "Developing capacity in implementation and enforcement of environmental law through ECENA and IMPEL" are divided in the following three clusters:

Cluster 1: Participation in IMPEL;

Cluster 2: Participation in ECENA; and

Cluster 3: Specific activities linked to ECENA and IMPEL

This project started with implementation in November 2007 and is planned to be finished by November 2009 so it will not overlapping with IPA 2008 project.

The IPA project proposal will mostly build on results achieved within one particular activity of ECENA network: Protection of Environment through Enforcement of Criminal Law. In response to the International Network for Environmental Compliance and Enforcement (INECE) and INTERPOL initiatives, this activity aims to improve capacity of environmental inspectors in combating environmental crime by capacity building and increasing the cooperation among different stakeholders such as police, customs and prosecutors. Related to this trainings will be organised in co-operation with INTERPOL, in period from November 2008 till November 2009.

The main focus will be oriented to: criminal penalties in pre-candidate, candidate and acceding countries; inspection investigations and preparing law suits; trans-border shipment of hazardous waste with emphasis on Basel Convention and Waste shipment regulations, especially in less developed countries, illegal dumping of oil in seas; illegal shipment of ozone-depleting substances; and illegal discharge of waste into rivers and lakes; reporting environmental crime to INTERPOL.

All activities of the project “Developing capacity in implementation and enforcement of environmental law through ECENA and IMPEL” are carefully taken into account and will be respected as well during all phases of the IPA project, particularly cooperation regarding issues of protection of environment through enforcement of Criminal Law. IPA project will also build on all related previous ECENA experience gained and is planned as an upgrade of it.

  - Results:

Component 1.

Development of procedures for coordinated enforcement of the Environmental Protection Act in Croatia.

Result 1.1 - Assessment of current situation regarding enforcement of the Environmental Protection Act in the cases of criminal offences against environment conducted and recommendations for coordinated procedures created.

Result 1.2 - Standard Operating Procedures for cooperation between environmental protection inspectors and other stakeholders in cases of criminal offences against environment produced.

Result 1.3 - Manual for coordinated enforcement of the Environmental Protection Act in Croatia for all involved stakeholders produced, translated into Croatian, published and disseminated.

Component 2

Strengthening the capacity of all institutions involved

Result 2.1 – Training needs analysis conducted and training programme designed.

- Result 2.2 – Capacity of environmental protection inspectors and other stakeholders (customs, public prosecutors, judiciary, courts experts, expert witnesses, police) increased through providing education and trainings for coordinating relevant activities in Croatia as well as in transboundary movement and impact.

3.4 	Activities:

Component 1.

Development of procedures for coordinated enforcement of the Environmental Protection Act in Croatia.

1.1.1 Activity - Assessment of current situation regarding enforcement of the Environmental Protection Act in the cases of criminal offences against environment.

Assessment will be made by reviewing and bringing into correlation relevant competencies, procedures and practices performed by all included stakeholders: environmental protection inspection, police, customs, public prosecutors, judiciary, courts experts, expert witnesses as well as all others according to RTA / Project Leader's recommendations and experience/expertise based on the best EU MS practice in this field.

The Assessment should take into account all the assessments already made, different reports regarding status of misdemeanour or criminal/serious criminal offences against environment especially taking into account successfully finished cases, to be able to analyse the level of cooperation and coordination in various situations regarding enforcement of criminal law in sector environment.

1.1.2 Activity – Preparation of comprehensive Assessment Report with recommendations on enforcement of the Environmental Protection Act in the cases of criminal offences against environment in Croatia. The report should include relevant competencies, procedures and practices of all stakeholders compared with European Practices.

1.2.1. Activity – Preparation of draft Standard Operating Procedures (SOPs) for cooperation between environmental protection inspectors and other relevant stakeholders in cases of misdemeanour or criminal/serious criminal offences against environment taking into consideration provisions of the Criminal Procedures Act and Misdemeanour Act, and based on results achieved through Activity 1.1.1.

Although Criminal Procedures Act prescribes all legislative provisions regarding procedures and must be followed by all involved parties, the clear procedures/SOPs (Standard Operational Procedures) which will be established/developed in this project will clearly define steps to ensure avoidance of possible overlapping or misunderstandings in procedures with numerous stakeholders.

SOPs are to be very detailed and comprehensive, based on the best EU MS practice, and translated in Croatian language.

1.3.1. Activity - Preparation of manual (with approximately 200 pages and in minimum 200 copies), for coordinated enforcement of the Environmental Protection Act in Croatia for all involved stakeholders. The manual will be based on SOPs and also deal with procedures in cases of illegal transboundary shipments of waste and hazardous waste and ozone depleting substances (ODS) with neighbouring countries and other countries.

Furthermore, additional contribution to this manual will be comprehensive overview of MS partner practical experience and procedures in cases of violations of environmental legislation. The manual should be translated into Croatian language.

Component 2.

Strengthening the capacity of all institutions involved

2.1.1. Activity – Analysis of training needs for all the stakeholders including definition of necessary inputs to be provided to the participants of training programmes.

2.1.2. Activity – Designing training programme for all involved stakeholders, including case studies and supporting training materials for efficient cooperation between included stakeholders.

2.1.3. Activity – Preparation of training materials and handbook (with approximately 300 pages and in minimum 110 copies), based on the training programme and manual for coordinated enforcement of the Environmental Protection Act in Croatia, including translation of handbook into Croatian.

2.2.1. Activity – Conducting training of trainers.

Trainers will be educated through two groups: group A and group B.

GROUP A:

This group will be made of 25 environmental protection inspectors. Training should be conducted through workshops which should provide trainees with practical experience gained by Member States (MS) that posses desirable structure and level of efficiency in related matters, and also the knowledge of optimal procedures in continental and maritime locations.

GROUP B:

This group will be made of 12 representatives from Ministry of Interior – the police, Ministry of Finance – customs, public prosecution offices, judiciary, court experts, expert witnesses. Trainings should be conducted through workshops and practical work in the field held in Zagreb.

All documentation will be used to sustain knowledge gained in the framework of this project by means of implementing further trainings.

2.2.2. Activity – Conducting 2 study visits for up to 10 participants per study visit, in duration of 5 days each, in EU member state for the environmental inspectors with the purpose to acquire on-the-spot knowledge experience of  procedures and structures in MS counterpart administration,

2.2.3. Activity – Conducting training for environmental protection inspectors not included in training of trainers programme.

Participants that are to be trained are 60 environmental protection inspectors, and should be trained in the following way:

twinning partners will hold the training in all 20 Branch units of environmental protection inspection, to inspectors that were not participating in “Train the trainers” programme from the Activity 2.2.1. (group A).

The training will include workshops with emphasis on practical exercises, case studies and site visits to different locations where they could gain practical experience regarding covered training topics.

Two visibility events will be organized in the course of the implementation of the project, kick off meeting at the beginning of the implementation and Final meeting at the end of implementation.

3.5 	Means/ Input from the MS Partner Administration:

3.5.1 Profile and tasks of the Project Leader

Profile of the Project Leader

Requirements:

- University degree

- 8 years of relevant experience in a MS public administration in the field of environmental acquis implementation and/or enforcement

- High-ranking official commensurate with the requirement for an operational dialogue and backing at political level

- Experience in project management

- Active knowledge of English language

- Fully computer literate

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2.

Assets:

- Experience with international networks and projects on environmental compliance and enforcement

- Previous experience in the area of capacity building

Task of the Project Leader:

- Overall responsibility, coordination and direction of the MS TW partner inputs

- Directing towards introducing EU best practice in connection with acquis communautaire  and assuring compatibility with EU requirements

- Supervising and coordinating implementation of the project

- Project reporting

- Ensuring backstopping and financial management of the project in the MS

3.5.2 Profile and tasks of the Resident Twining Adviser

Profile of the Resident Twining Adviser

Requirements:

- University degree

- 8 years of experience in MS administration operationally enforcing environmental legislation

- Experience in project management

- Active knowledge of English language

- Fully computer literate

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2.

Assets:

- Comparative knowledge of environmental inspection systems in other MS

- Experience in developing training programmes

Tasks of the Resident Twinning Adviser

- Working on a daily basis with the BC staff on the implementation of the project

- Support and coordination of all activities in Croatia

- Day-to-day implementation of the project

- Provide technical advice and assist Croatian administration in the context of project working plan.

- Organization of visibility events (kick-off and final event) and study visits

- Networking with institutions relevant in this project in Croatia and in MS

Duration of RTA secondment will be 18 months.

3.5.3 Profile of the short-term experts

Profile of the Short-term experts

Requirements:

- University degree

- 5 years of experience in a relevant administrative structure of a MS in implementation of environmental aquis

- Experience in organizing and providing training

- Fluency both in written and spoken English

- Computer literate

- Proven contractual relation to public administration or mandated body, as defined under Twinning manual 5.3.2.

Assets:

- Previous experience in international co-operation and in international projects

Tasks of the Short-term experts

- Support the RTA in the implementation of all project activities

- Preparation of assessment report with recommendations

- Preparation of SOPs

- Preparation of manual and handbook

- Performing training needs analysis

- Design of training programmes and supporting materials

- Organizing and conducting trainings

4. 	Institutional Framework

Ministry of Environmental Protection, Physical Planning and Construction (MEPPPC) in Republic of Croatia has overall responsibility for environmental protection and implementation of sustainable development principles throughout the Republic of Croatia. This overall responsibility includes protection of all aspects of the environment and protection against environmental burdening, implementation of the environmental protection regulatory framework, environmental monitoring, environmental information systems, ensuring access to environmental information, public participation in environmental matters, access to justice, liability for damage, financing and instruments of general environmental policy, administrative and inspection supervision.

The environmental inspection of the MEPPPC undertakes inspection control in the area of environmental protection, waste management, air protection, emergency plans, quality of fuels, ozone depleting substances, EIA prescribed measures. It also participates in procedures for the removal of consequences of accidents/incidents as well as matters related to liability for damage.

Organigrams of Inspection Directorate

Inspection Directorate within MEPPPC will be the main beneficiary (“owner” of the project). Other involved stakeholders will be judiciary, customs, public prosecutors, police, courts experts, and expert witnesses.

- The head office of the Inspection Directorate is responsible for this project with support from other departments within MEPPPC. Criminal acts against environment as a whole are defined with articles 250 – 262 of Croatian Criminal Act and particularly with articles 250, 252, and 262 for the scope of inspection of environmental inspectors in MEPPPC.

The beneficiary institution will dedicate all necessary human and financial resources in order to guarantee an effective implementation of the respective project. In particular, the beneficiary institution will insure the availability of the following provisions:

Adequately equipped office space for the RTA and the RTA assistant for the entire duration of their secondment (in particular a desk, a telephone line, PC with e-mail account and internet access, possibility to use fax & copy services).

Adequate conditions for the STEs to perform their work while on mission to the BC.

Training and conference venues as well as presentation and interpretation equipment.

Costs for travel by BC participants from their capitals to a MS or between MS (study visits).

Its active involvement in preparation of the PIU and Steering Committee meetings and participation of its members on the same.

The availability of the BC human resources (BC experts) during the implementation of the activities.

5. 	Budget

|  | IPA SUPPORT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Investment support (I) | Institutional Building (IB) | IPA Community Contribution | National Co-financing | IFI | Total |
| Contract 1 Twinning | / | € 1.100.000 | € 1.045.000 | € 55.000 |  | € 1.100.000 |
| TOTAL | / | € 1.100.000 | € 1.045.000 | € 55.000 |  | € 1.100.000 |

Interpretation costs will be reimbursed from the budget only for the purpose of workshops and seminars, up to 7% of the budget can be used for translation and interpretation purposes.

In addition to the above-mentioned, provisions in the maximum amount of 10.000€ should be included in the budget for the following purposes:

Translation, design, preparation and printing of the:

-Manual for coordinated enforcement of the Environmental Protection Act (200 copies with approximately 200 pages with translation in Croatian language)

-Training materials and Handbook (110 copies with approximately 300 pages with translation in Croatian language)

6. 	Implementation Arrangements

6.1 	Implementing Agency responsible for tendering, contracting and accounting

Central Finance and Contracting Agency

Ulica grada Vukovara 284

HR - 10000 Zagreb

Mrs Marija Tufekčić, Director of the CFCA

Phone: +385 1 4591 245

Fax: +385 1 4591 075

E-mail: procurement@safu.hr

Twinning Administrative Office

Central Finance and Contracting Agency

Ulica grada Vukovara 284

HR- 10000 Zagreb

Ms Štefica Belčić, National Contact Point

Phone: +385 1 4591 060

Fax: +385 1 4591 075

E-mail: twinning@safu.hr

6.2 	Main counterpart in the BC

Ministry of Environmental Protection, Physical Planning and Construction

Directorate for Inspection

Vinogradska 25

10000, Croatia

Senior Programme Officer - SPO

Mrs Josipa Blažević – Perušić, State Secretary

Ministry of Environmental Protection, Physical Planning and Construction

Directorate for Inspection

Vinogradska 25

10000 Zagreb, Croatia

Phone: +385 1 3712 714

Fax: +385 1 3712 713

E-mail: josipa.blazevic-perusic@mzopu.hr

BC Project Leader

Mrs Anita Pokrovac Patekar, Head of Section for International Co-operation

Ministry of Environmental Protection, Physical Planning and Construction

Directorate for Inspection

Vinogradska 25

10000 Zagreb, Croatia

Phone: +385 1 3712 797

Fax: +385 1 3712 713

E-mail: anita.pokrovac.patekar@mzopu.hr

RTA counterpart

Mrs Vlasta Pašalić

Ministry of Environmental Protection, Physical Planning and Construction

Directorate for Inspection

Vinogradska 25

10000 Zagreb, Croatia

Phone: +385 1 3712 786

Fax: +385 1 3712 713

E-mail: vlasta.pasalic@mzopu.hr

6. 3 	Contracts

One twinning contract is foreseen with an indicative amount of 1.100.000 EUR

7. 	Implementation Schedule (indicative)

7.1 	Launching of the call for proposals: 2nd quarter 2009

7.2 	Start of project activities: 2nd quarter 2010

7.3 	Project completion: 4th quarter 2011

7.4 	Duration of the implementation period: 21 months; 18 months for the implementation of the activities and 3 months for the starting up and closure of the Action.

8. 	Sustainability

Sustainability of this project will be ensured through continuation of training, by forming of training programme with trained trainers. In this way, participants trained to become trainers in this particular field, would be able to educate other colleagues in future and maintain the flow of information and knowledge gained through this project. Furthermore, outputs of Results 1.1., 1.2. and 1.3. will be greatly used and of benefit for future work of environmental protection inspectors and all other included stakeholders, since it will contain recommendations and standard operating procedures for their work.

9. 	Crosscutting issues

Equal Opportunity:

Based on the fundamental principles of promoting equality and combating discrimination, participation in the project will be guaranteed on the basis of equal access regardless of sex, racial or ethnic origin, religion or belief, disability, age or sexual orientation.

Environment:

The programme has no negative effect on environment. The project will implement a part of the European environmental policy. It will provide the basis for more efficient work of Croatian environmental inspection.

10. 	Conditionality and sequencing

The conclusion of the contract resulting from this call for proposals is subject to the fulfillment of the following condition:

Entry into force of a Financing Agreement implementing the National Programme for 2008 under the Instrument for Pre-accession Assistance (“Transition Assistance and Institution Building” Component, Part 1), concluded between the Commission and Croatia.

Involved stakeholders are ready to provide adequate and permanent staff to be trained in the framework of this project.

Sequencing: Relevant activities from the 2nd component need to be implemented upon completion of activities under the Component No. 1.

ANNEXES TO PROJECT FICHE

1. 	Logical framework matrix in standard format

2. 	Detailed implementation chart

3. 	Contracting and disbursement schedule by quarter for full duration of programme

4. 	List of relevant Laws and Regulations

5. 	Reference to relevant Government Strategic plans and studies

- ANNEX 1: Logical framework matrix in standard format

| Enforcement of the new Environmental Protection Act harmonized with EU legislation in cases of criminal offences against the environment |  | Programme name and number # IPA 2008 |  |
| --- | --- | --- | --- |
| Ministry of Environmental Protection, Physical Planning and Construction |  | Contracting period expires: 2 years following the date of conclusion of the Financing Agreement | Disbursement period expires: 3 years after the end date for contracting |
|  |  | Total budget: € 1.100.000 | IPA budget: € 1.045.000 |
| Overall objective | Objectively Verifiable Indicators | Sources of Verification |  |
| Support to environmental protection in Croatia through the enforcement of provisions of the new Environmental Protection Act | - Decrease of the rate of violations against environment, compared to baseline data of year 2008 | - National report on the state of environment - Reports for various networks of environmental protection inspectors which Croatia is a member of - Other reports by relevant authorities |  |
| - Project purpose | - Objectively Verifiable Indicators | - Sources of Verification | - Assumptions |
| To build up capacity for enforcement of the provisions of the new Environmental Protection Act (EPA) in cases of criminal offences against the environment | - Increase in number of cases subject to investigation, compared to baseline data of year 2008 - Increase in number of case brought before the courts, compared to baseline data of year 2008 - Increase in number of prosecutions, compared to baseline data of year 2008 | - Report by Directorate for Inspection - Joint annual reports on co-ordinated inspection controls undertaken - Reports of other relevant bodies and authorities - Guidelines for cooperation of all relevant bodies | - Harmonization of secondary national environmental legislation with EU legislation - Capacity of courts to deal with environmental cases |
| - Results | - Objectively Verifiable Indicators | - Sources of Verification | Assumptions |
| Result 1.1 - Assessment of current situation regarding enforcement of the Environmental Protection Act in the cases of criminal offences against environment conducted and recommendations for coordinated procedures created. Result 1.2 - Standard Operating Procedures for cooperation between environmental protection inspectors and other stakeholders in cases of criminal offences against environment produced. Result 1.3 - Manual for coordinated enforcement of the Environmental Protection Act in Croatia for all involved stakeholders produced, translated into Croatian, published and disseminated. Result 2.1 – Training needs analysis conducted and training programme designed. - Result 2.2 – Capacity of environmental protection inspectors and other stakeholders (customs, public prosecutors, judiciary, courts experts, expert witnesses, police) increased through providing education and trainings for coordinating relevant activities in Croatia as well as in transboundary movement and impact. | - Assessment Report prepared - Recommendations created - Standard Operating procedures produced - Manual for coordinated enforcement of EPA produced in minimum 200 copies - 23 workshops, 2 study tours and 1 field work held - 37 trainers for conducting education trained - 60 environmental inspectors trained - Training materials produced - Training handbook created and published in 110 copies | - Assessment document of current situation regarding enforcement of the Environmental Protection Act in the cases of criminal offences against environment - Proposal document for procedures in cases of criminal offences against environment - Project final and progress reports - Periodic and annual reports by the environmental protection inspection and other stakeholders - Training materials | - Permanent cooperation of Ministry of Environmental Protection, Physical Planning and Construction with all stakeholders |
| Activities | Means | Specification of costs | Assumptions |
| 1.1.1 Activity - Assessment of current situation regarding enforcement of the Environmental Protection Act in the cases of criminal offences against environment. 1.1.2 Activity – Preparation of comprehensive Assessment Report with recommendations on enforcement of the Environmental Protection Act in the cases of criminal offences against environment in Croatia. 1.2.1. Activity – Preparation of draft Standard Operating Procedures (SOPs) for cooperation between environmental protection inspectors and other relevant stakeholders in cases of misdemeanour or criminal/serious criminal offences against environment taking into consideration provisions of the Criminal Procedures Act and Misdemeanour Act, and based on results achieved through Activity 1.1.1. 1.3.1. Activity - Preparation of manual (with approximately 200 pages and in minimum 200 copies), for coordinated enforcement of the Environmental Protection Act in Croatia for all involved stakeholders. 2.1.1. Activity – Analysis of training needs for all the stakeholders including definition of necessary inputs to be provided to the participants of training programmes. 2.1.2. Activity – Designing training programme for all involved stakeholders, including case studies and supporting training materials for efficient cooperation between included stakeholders. 2.1.3. Activity – Preparation of training materials and handbook (with approximately 300 pages and in minimum 110 copies), based on the training programme and manual for coordinated enforcement of the Environmental Protection Act in Croatia, including translation of handbook into Croatian. 2.2.1. Activity – Conducting training of trainers. Trainers will be educated through two groups: group A and group B. 2.2.2. Activity – Conducting 2 study visits for up to 10 participants per study visit, in duration of 5 days each, in EU member state for the environmental inspectors with the purpose to acquire on-the-spot knowledge experience of procedures and structures in MS counterpart administration 2.2.3. Activity – Conducting training for environmental protection inspectors not included in training of trainers programme. | - Analysis, round table discussions - Consultations, Preparation of documentation - Consultations, Preparation of documentation - Consultations, Preparation of documentation, round table discussions - Analysis, Consultations - Analysis, Consultations, Preparation of documentation - Preparation of documentation - Trainings, workshops - Study visits - Trainings, workshops | € 1.100.000 | - Implementation of Phare 2005 project “Enhanced Environmental Inspection of New Environmental Legislation” |
|  |  |  | Preconditions 1. The conclusion of the contract resulting from this call for proposals is subject to the fulfillment of the following condition: Entry into force of a Financing Agreement implementing the National Programme for 2008 under the Instrument for Pre-accession Assistance (“Transition Assistance and Institution Building” Component, Part 1), concluded between the Commission and Croatia. |

ANNEX 2: Detailed implementation chart

| Project Title: Enforcement of the new Environmental Protection Act harmonized with EU legislation in cases of criminal offences against the environment | 2009 |  |  |  |  |  |  |  |  |  |  |  | 2010 |  |  |  |  |  |  |  |  |  |  |  | 2011 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Month | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D |
| Twinning |  |  |  |  |  | T | T | T | T | C | C | C | C | C | C | S | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I | R | R |

T – Call for proposals and evaluation

C- Contracting

S- Starting up

I –  Implementation of activities

R – Report

ANNEX 3: Contracting and disbursement schedule by quarter

| Contracted | 2009 Q4 | 2010 Q1 | 2010 Q2 | 2010 Q3 | 2010 Q4 | 2011 Q1 | 2011 Q2 | 2011 Q3 | 2011 Q4 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contract 1 (EUR) |  | 1.100.000 |  |  |  |  |  |  |  |
| Total (EUR) |  | 1.100.000 |  |  |  |  |  |  |  |
| Disbursed | 2009 Q4 | 2010 Q1 | 2010 Q2 | 2010 Q3 | 2010 Q4 | 2011 Q1 | 2011 Q2 | 2011 Q3 | 2011 Q4 |
| Contract 1 (EUR) |  | 586.666,67 |  |  |  | 403.333,33 |  |  | 110.000,00 |
| Total (EUR) |  | 586.666,67 |  |  |  | 990.000 |  |  | 1.100.000 |

ANNEX 4: List of relevant Laws and Regulations

Reference list of relevant Croatian laws and regulations:

- Environmental Protection Act (OG No. 110/07)

- Criminal procedure act (OG No. 62/03)

- Criminal Act (OG No. 110/07)

- Misdemeanour Act (OG No. 107/07)

- Instructions on the form, the tenor and the manner of keeping records of  inspections performed by environmental inspectors (OG No. 79/95)

- Ordinance on environmental emission inventory (OG No.36/96)

- Regulation on conditions for issuing permits for performing professional environmental activities (OG No. 7/97)

- Contingency plan for accidental marine pollution in the Republic of Croatia (OG No. 8/97)

- Regulation on environmental information system (OG No.74/99, 79/99)

- Environmental protection emergency plan (OG No. 82/99, 86/99, 12/01)

- Ordinance on environmental impact assessment (OG No. 59/00, 136/04, 85/06)

- Ordinance on the official identity card of inspectors of the urban-planning inspection of the Ministry of Environmental Protection, Physical Planning and Construction (OG No. 1/05)

- Regulation on the quality of biofuels (OG No. 141/05)

- Regulation on unit charges, corrective coefficients and detailed criteria and benchmarks for determination of the charge for emission into the environment of carbon dioxide (OG No. 73/07)

- Regulation on the establishment of the Croatian Environment Agency (OG No. 75/02)

- Act on the Environmental Protection and Energy Efficiency Fund (OG No. 107/03)

- Regulation on unit charges, corrective coefficients and detailed criteria and benchmarks for determination of the charge for emission into the environment of sulphur oxides, in the form of sulphur dioxide, and nitric oxides, in the form of nitric dioxide (OG No. 71/04)

- Regulation on unit charges, corrective coefficients and detailed criteria and benchmarks for determination of charges for burdening the environment with waste (OG No. 71/04)

- Air Protection Act (OG No. 178/04)

- Regulation on siting of national network stations for continuous air quality monitoring (OG No. 4/02)

- Regulation on substances that deplete the ozone layer (OG No. 120/05)

- Regulation on limit values of pollutants in air (OG No. 133/05)

- Regulation on alert thresholds for pollutants in air (OG No. 133/05)

- Regulation on the quality of petroleum-derived liquid fuels (OG No. 53/06)

- Ordinance on issuing of licence or approval for performing the activities of monitoring air quality and emissions into the air from stationary sources (OG No. 79/06)

- Ordinance on information exchange of data from the network for continuous air quality monitoring (OG No. 135/06)

- Regulation on technical standards of environmental protection from volatile organic compound emissions by storage of petrol and its distribution (OG No. 135/06)

- Regulation on the monitoring of greenhouse gas emissions in the Republic of Croatia (OG No. 01/07)

- Regulation on limit values for pollutant emissions from stationary sources into the air (OG No. 21/07)

- Regulation on limit values of the content of volatile organic compounds in certain paints and varnishes and vehicle refinishing products (OG No. 94/07)

- Waste Act (OG No. 178/04, 111/06)

- Ordinance on waste types (OG No. 27/96)

- Ordinance on requirements for handling waste (OG No. 123/97, 112/01)

- Regulation on requirements  for handling hazardous waste (OG No. 32/98)

- Regulation on categories, types and classification of waste with a waste catalogue and list of hazardous waste (OG No. 50/05)

- Ordinance on packaging and packaging waste (OG No. 97/05, 115/05)

- Ordinance on waste tyre management (OG No. 40/06)

- Regulation on supervision of transboundary movement of waste (OG No. 69/06, 17/07)

- Ordinance on waste oil management (OG No. 124/06)

- Ordinance on waste batteries and accumulators management (OG No. 133/06)

- Ordinance on the management of end-of-life vehicles (OG No. 136/06)

- Ordinance on waste management (OG No. 23/07, 111/07)

- Ordinance on the method and procedures for managing waste containing asbestos (OG No. 42/07)

- Ordinance on methods and requirements for thermal treatment of waste (OG No. 45/07)

- Ordinance on medical waste management (OG No. 72/07)

- Ordinance on the management of waste electrical and electronic appliances and equipment (OG No. 74/07)

- Ordinance on the methods and conditions for the landfill of waste, categories and operational requirements for waste landfills (OG No. 117/07)

Reference to acquis:

- Recommendation 2001/331/EC providing for minimum criteria for environmental inspections (RMCEI)

Reference to international strategic documents:

- Aarhus Convention, Convention on Access to Information, Public Participation in Decision-making and Access to Justice in Environmental Matters, adopted on June 25, 1998

ANNEX 5: Reference to relevant Government Strategic plans and studies

- National Environmental Strategy (OG No. 46/02)

- National Environmental Action Plan (NEAP) (OG No. 46/02)

- Waste Management Strategy of the Republic of Croatia (OG No. 130/05)

- Waste Management Plan of the Republic of Croatia for 2007-2015 (OG No. 85/07)

- National Programme for the Integration of the Republic of Croatia into the European Union 2008 (www.mvpei.hr)