- Twinning Number: TR 08 IB EN 02

Improving Emissions Control

- Note for the information of future Twinning partners:

- Please note that this fiche contains a Twinning and a Technical Assistance contract for in total 16 different activities: of these, 10 activities take the form of a Twinning (activities 1.1, 1.2, 2.3, 2.4, 2.5, 4.1, 4.2, 5.1, 5.2 and 5.3 see paragraph 3.4)

- The indicative budget for the Twinning contract is € 1.3 million (see paragraph 4)

- The indicative duration of the Twinning project is 24 months (see paragraph 5)

- Please see Annex V on page 47 for further details on the Twinning component

- Standard Summary Project Fiche – IPA decentralised National  programmes

(maximum 12/15 pages without the annexes)

1. Basic information

1.1   CRIS Number: 	 TR080203

1.2   Title: 		Improving Emissions Control

1.3   Sector: 	 	27- Environment

1.4   Location:  	Turkey/ Ankara

Implementing arrangements:

1.5   Implementing Agency:

The CFCU will be Implementing Agency and will be responsible for all procedural aspects of the tendering process, contracting matters and financial management, including payment of project activities. The director of the CFCU will act as Programme Authorizing Officer (PAO) of the project.

Mr. Muhsin ALTUN (PAO-CFCU Director)

Central Finance and Contracting Unit

Tel:  +90 312 295 49 00

Fax: +90 312 286 70 72

E-mail: muhsin.altun@cfcu.gov.tr

Address: Eskişehir Yolu 4.Km. 2.Cadde  (Halkbank Kampüsü) No:63 C-Blok 06580  Söğütözü/Ankara Türkiye

1.6   Beneficiary (including details of SPO):

Official Contact Details of SPO:

Sedat KADIOĞLU

Deputy Undersecretary

Ministry of Environment and Forestry

Söğütözü Cad. No:14/E Beştepe/ANKARA /TURKEY

Tel:+ 90 312 207  62 83

Fax: + 90 312 207 65 35

e-mail:sedatkad@yahoo.gov.tr

1.7   Overall cost:     	2,050 M Euro

1.8   EU contribution:  1,910  M Euro

1.9   Final date for contracting: 2 years after the signature of the Financing Agreement

1.10 Final date for execution of contracts: 2 years following the end date for contracting

1.11 Final date for disbursements: 3 years following the end date for contracting

2.   Overall Objective and Project Purpose

2.1  Overall Objective:

The overall objective of the project is to improve the environmental conditions in Turkey by implementation and enforcement of the EU environmental acquis in the frame of ambient air quality.

2.2  Project purpose:

The project purpose is to establish the necessary capacity within Ministry of Environment and Forestry to transpose and implement National Emission Ceilings Directive (2001/81/EC) in Turkey.

2.3  Link with AP/NPAA / EP/ SAA

The Accession Partnership(AP);

Council Decision of 18 February 2008 on the principles, priorities and conditions contained in the Accession Partnership with Republic of Turkey and repealing Decision 2006/35/EC.

(2008/157/EC)

In the short term those priorities for environment  are:

- Adopt a comprehensive strategy for the gradual transposition, implementation and enforcement of the acquis, including plans for building up the necessary administrative capacity at national, regional and local level and required financial resources, with an indication of milestones and timetables

- Continue transposition, implementation and enforcement of the acquis, in particular horizontal and framework legislation, such as the environmental impact assessment, including transboundary aspects, as well as strengthening of administrative capacity

In the medium- term the priorities for Environment are;

- Continue to transpose and implement the acquis related to the framework legislation, international environmental conventions and legislation on nature protection, water quality, chemicals, industrial pollution and risk management and waste management

- pursue integration of environmental requirements into other sectoral policies,

The National Programme (NP);

In the National Programme for the Adoption of the Acquis dated July 2003, Under Environment Chapter Priority 22.3. “Improving Air Quality” title, it is stated that;“Air Quality has been designated as a priority. Considering that beginning to transpose and implement  the   acquis   is a   short   term   priority  and completing the transposition   of the   acquis and strengthening institutional, administrative, and monitoring capacity, including data collection, to ensure   environmental protection   are medium term priorities in the 2003 Accession Partnership Document.

There   is   a need for   eliminating   the differences between Turkish   and the   EU air quality legislation.  In this framework, The Ministry of Health (MoH) contributes   to   harmonization efforts   carried out by the Ministry of Environment and Forestry (MoEF)”.

Regarding to this priority, project entitled “Support to Turkey in the Field of Air Quality, Chemicals and Waste Management Project TR03-IB-EN-01 Component-1 Air Quality” has been   initiated   in   2004 and completed at the end of 2006 to strength of the administrative capacity for harmonizing and implementing Air Quality Directive (96/62/EC) (ANNEX-4-3). Furthermore, in the scope of the support to Turkey in the field of Air Quality “Institution Building on Air Quality in The Marmara Region” was submitted to 2007 Financial Cooperation Programme, for strengthening of administrative capacity for harmonizing and implementing Air Quality will be studied.

  - Link with MIPD

“Main Priorities” under headline “Transposition and implementation of the acquis” for Environment includes that “Adoption of a revised programme for transposition and implementation of the acquis; Transposition of framework legislation, international environmental conventions, and legislation on nature protection, water quality, air quality, Integrated Pollution Prevention Control and waste management, environmental impact and strategic impact assessment, chemicals and GMOs, climate change.”

  - Link with National Development Plan (where applicable)

The Ninth Five-Year Development Plan Strategy has been prepared within the framework of the Long-term Strategy and is the basic document setting out Turkey’s approach for the solution of its main medium-term economic and social problems. Thus, the main objectives and priorities of Turkey are based on the medium-term strategy set forth by the Ninth Five-Year Development Plan Strategy.

The European Commission also requested from Turkey in October 2001, as with other candidate countries, to prepare a Preliminary National Development Plan (pNDP) covering the period 2004-2006 which would be treated as an annex to the NPAA and would establish a strategic framework for programming pre-accession financial assistance for Turkey’s economic and social cohesion with the EU. Subsequently, this has also been underlined in the Regular Reports on Turkey’s Progress Towards Accession in 2002 and 2003. In these documents, it was stated that the pNDP would be a step in the process of preparing the development plan as required for Objective 1 regions in the EU member states. Moreover, it was indicated that the pNDP would need to be in conformity with the planning and programming documents and should be applicable in the EU and should be updated in line with the developments in Turkey’s strategy for economic and social cohesion with the EU.

Turkey’s first pNDP is prepared to form the basis for the use of the financial assistance towards economic and social cohesion to be provided by the EU within the framework of Turkey-EU relations, during the 2004-2006 period. The legal bases of the preaccession financial assistance for Turkey are Council Regulation (EC) No 390/2001 of 26 February 2001 and Council Regulation (EC) No 2500/2001 of 17 December 2001.

It is aimed that during the pNDP period, pre-accession financial assistance shall be used in an effective way and establishment of the necessary infrastructure shall be initiated for the utilization of structural funds after accession. The pNDP attempts to set out a strategic framework towards formulating an economic and social cohesion policy for the country and achieving convergence to the EU, taking into account, inter alia, the issues put forward in Regular Reports on Turkey’s Progress Towards Accession and Accession Partnerships.

In this context/frame work, regarding “Air Quality” under in pNDP Strategy, it is defined as;  “The feasibility study dated 2002 revealed that the majority of existing air quality measurement stations need to be supported in terms of infrastructure, equipment, measurement methods and personnel”.

  - Link with national/ sectoral investment plans(where applicable)

EU Integrated Environmental Approximation Strategy (UÇES) covering the period 2007-2023 contains the information on pertaining to the technical and institutional infrastructure, the environmental improvements that are required to be performed as well as the mandatory arrangements which are necessary to establish complete harmonization for compliance with EU Environmental Acquis Communautaire and the effective implementation of the legislation which are the two pre-conditions for Turkey to join European Union. This main strategy document is the basic source of the project proposal named as “Strengthening the Capacity Building in NEC Directive”.

In the preparation of UÇES, outputs from the following documents were made use of; “National Environmental Strategy and Action Plan” that was prepared as a basis beforehand and the “Integrated Approximation Strategy Project” that was realized with the EC funds and the “Environmental Heavy Cost Investment Planning Project”. Furthermore, care was taken to make sure that the strategy paper was prepared in line with the Development Plan, Annual Programs, and the strategies and policies of the National Program.

Under the Air Quality title of UÇES (ANNEX 4-4), it is mentioned that on National Emission Ceilings (2001/81/EC) technical studies and infrastructural investments are needed in order to strengthen technical capacity. It is also mentioned as the directive on National Emission Ceiling has not yet been reflected into our legislation yet.

The main responsible institution on the subject is the Ministry of Environment and Forestry. But Turkish Statistical Institute and Ministry of Energy and Natural Resources and Electricity Generation Corporation (EÜAŞ) will be the beneficiaries in the collection of the data.

- Description of project

3.1 Background and justification:

Background:

Increase in population has resulted in urbanization, industrialization and inconvenient city planning according to the topographical and meteorological conditions causing air pollution in Turkey. Although various factors are involved, causes of air pollution can be divided into three main categories:  urbanization, industrialization and motor vehicles. In urban areas in Turkey, industrial emissions and traffic combine with emissions from residential heating and power generation to cause major air pollution episodes. There is little information on air quality in industrial areas though some major environmental impacts have been observed. It is known that areas where road traffic is intense and there are large stationary combustion facilities (such as power stations and refineries) are properly affected by photochemical pollution, However, due to the absence of air quality data relating to NOx, VOCs and ozone, the scale of the problem is not known. According to the research carried out in metropolitan areas, the harmful exhaust gases released by the ever increasing motor vehicles play an important role and air pollutants originated from motor vehicles have already exceeded all combined emissions that the overall resultant concentrations of pollutants are above limits. Motor vehicles are estimated to contribute about 46% of NOx emissions and undoubtedly a significant source of lead, CO, HC and PM.

In the past, some indicative air quality measurements and investigations were already done in Turkey. A national network system has been built up for measuring SO2 and PM10 parameters by the MoEF and Refik Saydam Hygiene Centre (RSHC). The fully automated air quality measurement stations were established in 81 provinces by the Ministry of Environment and Forestry in 2006. The national network of the MoEF measures only two parameters, namely the components of sulphur dioxide (SO2) and particulate matter (PM10). Gölbaşı Reference Laboratory as a related institution of the MoEF, is responsible for the evaluation of the air quality data and management of the National Air Quality Network. In addition, Turkish Statistical Institute has responsibility in collection of emission data.

At legal bases, an amended Environment Law has passed in the Parliament in May 2006, in which the responsibilities of ministries and institutions involved in air quality were redefined. The Environment Law introduces methods about the determination, monitoring and measurement of air quality and air quality limit values and measures to be taken to prevent exceeding of limit values. Also, the Environment Law determines the MoEF as the primary responsible authority for environmental issues, such as increasing public awareness and providing access to related information.With the purpose of harmonization of EC legislation on air quality to national legislation, a Twinning Project named “Support to Turkey in the field of Air Quality, Chemicals and Waste Management’’ was started in the year 2004, and with the first component of this project, the Air Quality, it is aimed to transpose  Air Quality Framework Directive into Turkey’s National Air Quality Legislation and into the activities for measuring the air quality and the transposition of the provisions of the Large Combustion Plants Directive to our legislation.  The project is completed in 2006. Draft By-law on Air Quality Assessment and Management (BAQAM) and Draft By-Law on Large Combustion Plant, to limit emissions arising from large combustion plants, were prepared. Those drafts were submitted for approval to the related authorities of Turkey.

The Draft By-law on Air Quality Assessment and Management  covers four daughter directives (99/30/EC, 2000/69/EC, 2002/3/EC and 2004/107/EC) besides Air Quality Framework Directive, 96/62/EC. The new draft by-law sets the implementation calendar for the implementation and harmonization of 13 pollutants that are defined under the framework directive and the daughter directives. By-law also aims to strengthen the monitoring, sanctioning and institutionalization in the area of controlling the pollution and air quality. BAQAM is planned to be taken into force in the year of 2008.

After the transposition of the Air Quality Framework Directive and its daughters into the national legislation, the implementation of these directives is the second step that should be taken.  Therefore, it is necessary to strengthen the institutional capacity for the implementation of other directives about air quality. Furthermore, in case the new air quality limit values which are indicated in BAQAM, are exceeded, a strategy is required to reduce ambient air pollution concentrations. In this framework, Strategy For the Implementation and Enforcement of the By-Law on Air Quality Assessment and Management requires a new structure both at the national and regional level. Some new working units are needed to fulfill the new tasks. In this regard, the capacity of MoEF should be increased for the implementation of the Air Quality Framework Directive and daughter directives as a first step. Within this context, the establishment of the necessary technical infrastructure, its operation and inspection and the training of the personnel to be employed in these areas carry great importance for the effective implementation of the directives generally in the country. Measurement devices are required for both effective monitoring of the air quality and for reaching the necessary standards. The establishment of the monitoring systems is also considered to be important for full implementation of Air Quality Framework Directive and the other directives on air quality such as the Fuel Quality, the Emissions Arising from the Vehicles and NEC Directive.

Because of the needs stated above and all these studies on air quality addressed a new project which will give opportunity to establish necessary capacity for the implementation of EU Acquis on air quality in a region. Particularly, Strategy Paper prepared under Twinning Project has revealed the necessities of Turkey in field of air quality and determined related technical and financial requirements on regional base. Results of the project will be the example and experience and this region will serve as a model region for the other regions to implement the EU Air Quality Framework and Daughter Directives.

As a result, the project concerning “Institutional Building on Air Quality in Marmara region” was taken under the IPA 2007 Programme. This project will carried out under the supervision and patronage of the MoEF as the main administrative body for the air quality issues. However, this work will be carried out in cooperation with the municipalities of the selected region (Istanbul/Bursa for the Marmara region), the RSHC, the Gölbaşı Reference Laboratory and TUBITAK. The Provincial Directorates of the MoEF in the region, metropolitan municipalities, universities, chambers etc. are the other beneficiaries of the project. Such a project will be started in the third quarter of 2008 and be ended at latest in 2012 in order to provide for the implementation of its results (Clean air plans, action plans) in the remaining zones and agglomerations of Turkey by 2014. In the framework of this project, there is a supply component regarding the procurement of software for emission data base and modeling. In order to conduct an emission inventory, all data relating the air quality in the region will be collected with the help of the stakeholders of the project and these data will be used for the modeling purposes.

In addition, the gaps in this rather incomplete system need to be filled in Marmara region. The system should be built in the region fulfilling all the technical and administrative requirements of the AQFD and the reporting requirements of the LCPD. In this regard, the “Marmara Air Quality Project” is a good model for monitoring of all sources of air pollution such as industry, traffic and heating. In this framework, it is essential to establish a comprehensive air quality-monitoring network for defining the scale of the air pollution problem and minimizing the problem. The project will bring a new assessment and management approach in line with EU Ambient Air Quality Directives for solving air pollution problem and its potential effects on human health.

This project would also enable the decision makers and local authorities to evaluate the effectiveness of air pollution minimization strategies and clean air plans / action plans. For this purpose Regional Centre for Clean Air includes Regional Ambient Air Network, Regional Calibration Laboratory (RCL), Regional Data Centre (RDC) and Regional Maintenance Centre(RMC). RCL should ensure the use of the national calibration standard in the respective regional network. RDC also need to be established in the region, which transmits the data to the National Data Centre. RMC should be established for maintenance of equipment and to provide system operating properly.

In Regional Ambient Air Monitoring Center, 23 Turkish technical experts from different disciplines will take responsibility in monitoring network operation, regional calibration laboratory, regional data center, analytical laboratory, regional unit for analysis and modeling action. The project enables to fulfill the AQFD in the region and will be a model for the other regions. In addition to the administrative requirements; in order to increase the technical capacity of the ambient air quality monitoring system in the Marmara region, 39 air quality measurement stations have to be installed and to ensure the fulfilment of the Framework Directive 96/62/EC and its daughter directives. From these stations 19 of them will be established in intensive residential areas, 7 will be established in the areas where the industry is intensive, 9 will be established in the areas where the traffic is intense and 4 will be located in the rural areas.

EU IPPC Directive (2008/1/EC), which has been referred to in NEC Directive is also being studied in Turkey. So far two bi-lateral projects have been successfully done between 2003 and 2008 in order to assist Turkish Ministry of Environment and Forestry with implementation of the Integrated Pollution Prevention Control (IPPC) Directive. Project outputs include a roadmap towards full implementation of the IPPC Directive in Turkey. Implementation of IPPC Directive in Turkey will lead to significant reduction in emissions of acidifying, eutrophying and ozone forming substances. Two Directives also are interrelated in information exchange and reporting. This project is intended to facilitate implementation of IPPC while IPPC studies serve Turkey in achieving targets set out in NEC Directive.

At international area for controlling air pollution, Turkey has ratified the Convention on Long Range Transboundary Air Pollution (CLRTAP) in 1979 and EMEP Finance Protocol in 1984. Turkey has fulfilled responsibility in terms of financial contribution regularly under the Convention. Turkey could not to be a party to the various UN-ECE Protocols aimed at limiting emissions of SO2 , NOx and VOCs  due to several reasons. Full implementation of UN/ECE Protocols necessitates modification of technologies applied in a number of sectors, establishment of new treatment plants, use of new technologies and upgrading the fuel quality etc. Turkey is doing her utmost to convert into clean technologies that would enable her meet the targets specified in the mentioned protocols.  Although Turkey fully associates herself with the objectives of Protocols, because of the limitations in technological transformation, bottlenecks in financing such transformation as well as the inadequacy of its environmental monitoring infrastructure and lack of proper emission inventories, she was not be able to sign the Protocols. As known, NEC Directive and Gothenburg Protocol of The Long-Range Transboundary Air Pollution Convention (CLRTAP) have same policies and principles for controlling emissions of SO2, NOx, VOCs and ammonia. The implementation of the NEC Directive will facilitate application the Gothenburg Protocol Provisions. Furthermore, this project will provide capacity increase in the Ministry.

Justification;

Turkey is not yet a member of the European Union (EU), but has formally been accepted as an candidate country to join the EU and has begun a process of screening and approximation to establish the readiness of its legislation.  The Long-Range Transboundary Air Pollution Convention (CLRTAP), Gothenburg Protocol, Air Quality Framework Directive and its daughter directives, and IPPC Directive are parts of the EU’s acquis communautaire and the adoption of those is a part of the approximation process.Turkey has ratified the CLRTAP, but it has not adopted any of the protocols that impose limitations on emissions on transboundary pollutants.  The NEC Directive (2001/81/EC) and the Gothenburg Protocol of CLRTAP set specific national ceilings for emissions for four air pollutants (SO2, NOx, VOC and ammonia) that cause acidification and the formation of ground-level ozone. According to the NEC Directive, Member States must prepare and annually update national emission inventories and emission projections for SO2, NOx, VOC, NH3 and draw up programmes.

In this scope, Turkey, as a candidate country, infrastructural investment and technical study in order to strengthen technical capacity are needed. In UÇES, which defines comprehensive coordination role for the MoEF on Air Quality for adaptation and implementation of EU Directives, NEC Directive has taken into consideration under the air quality sector.  Detailed and thorough strategies for the implementation and enforcement of NEC Directive, with institutional strengthening and methodological support are necessary to establish infrastructure for providing and assuring the protection of environment and improving the air quality in Turkey. This situation addresses the needs for the transposition of NEC Directive, besides other directives under air quality sector. The transposition of NEC Directive is necessary to set out emissions data base (especially focused on SO2, NOx, VOC, NH3 which are stated in NEC), to develop a national emission inventory which should be sectoral and pollutant based, and to include information on the spatial distribution of the emissions all over Turkey and in the further stages, to develop abatement strategies.

There is currently no capability (in the form of trained staff and methodology) in the MoEF to transpose and implement NEC Directive except for the software programme for air quality dispersion modelling. It is not easy to transpose NEC Directive and prepare emission inventory for Turkey without EU expertise. In this view, EU support is needed in order to initialize the related studies in this field. By using methodologies referred in the NEC Directive, emission inventories for the pollutants defined in the directive were prepared and from the data obtained from the project, air quality model should be used to determine the dispersion of pollutants NH3, VOC, SOx and NOx in Turkey.

This project will be the determining factor for the overall national air quality policy of Turkey in line with EU air quality policies. The main output of this project will affect the investment plans of Turkey considering all air pollution sources namely industrial, motor vehicles, domestic heating etc. Also This project will bring a new assessment and management approach in line with EU air quality policies for solving air pollution problem and its potential effects on human health. In addition, it would enable the decision makers and local authorities to evaluate the effectiveness of air pollution minimization strategies and action plans/programs drawing emission reduction roadmap. The UÇES Document defines comprehensive coordination role for the MoEF in Air Quality field for adaptation and implementation of EU Directives. Furthermore, UÇES and other EU funded projects on, Air Quality, addresses a new project proposal which will give opportunity to strength  the capacity for the implementation and enforcement of National Emission Ceilings Directive.

The staff from the departments of the MoEF that are responsible from control, management and monitoring of air quality, will attend whole steps of the project activities  with full time support. The proposed project for “Strengthening the Capacity Building on NEC Directive” should be carried out under the supervision and patronage of the MoEF as the main administrative body for the air quality issues. This work needs to be carried out in cooperation with the Ministry of Energy and Natural Resources and Turkish Statistical Institute. Furthermore, universities, chambers and NGOs are the other stakeholders of the project.

Such a project would need to be started in 2009 and be ended at latest in 2011 in order to establish a baseline for the national emission ceilings of mentioned pollutants for Turkey. The total budget of the Project is estimated to be 2,050  M Euro, of which 140,000 Euro will be supported by Turkish Government.  Furthermore, expenses related with the software of modeling programme will be financed within the MoEF.

Regarding Directive on National Emission Ceilings 2001/81/EC, infrastructural investment and technical study in order to strengthen technical capacity, are needed. Enforcement date will be designated by the legislation prepared according to the result of the technical studies.

Furthermore, it is the initial step that the Directive on National Emission Ceiling Limits should be reflected on our national legislation. However, for Turkey, it is not easy to overcome bottlenecks both in the transposition and implementation of NEC Directive requirements in Turkey without EU expertise.

The most crucial reason to propose such a project is to gradually improve, through a stepwise reduction of the four pollutants, the protection both of human health and the environment throughout the Turkey. By means of specific strategies to combat acidification and ground-level ozone, it is important to establish interim environmental quality targets that are to be attained. These targets constitute the first step towards the achievement of the long-term objectives of not exceeding the critical loads and of effective protection of human health against risks from air pollution. It is well known that NEC directive is the key legislation for the achievement of those environmental objectives, as well as for attaining the EU air quality standards for a number of pollutants, including SO2, NO2, fine particles (PM10), and ozone.

Total budget of the Project is 2,050 Million Euro, out of which 750,000 Euro will be expended in Technical Assistance for the preparation of emission inventory, cost benefit analysis and preparation of Regulatory Impact Assessment Report  and .workshop arrangements .   Detailed budget calculation could be followed from Annex 5-2

3.2 Assessment of project impact, catalytic effect, sustainability and cross border impact (where applicable):

Project Impact:

The project is expected to produce mainly five outcomes:

- Transposition of NEC Directive into Turkish Air Quality Legislation

- Development of national emission inventory and emission projections for SO2, NOx, VOC and NH3

- Preparation of Regulatory Impact Assessment for the implementation of NEC Directive

- Adoption of an agreed long-term comprehensive strategy for the improvement of air quality in line with the NEC Directive

- Establishment of institutional structure, technical capacity and related procedural arrangements

Catalytic Effect:

This project will bring long-term catalytic effects in terms of estimating emission projections, identifying technical measures and possible financial instruments to reduce emissions. This project will also enhance the selection of possible additional measures into the national strategic plan, the adaptation of clean technologies into industrial sectors and use of better fuel quality both in transportation and heating.

Sustainability:

Since the NEC Directive enforces the emission projections for four certain pollutants, in case of whole consistency with the directive, it would be obligatory to obey the ceilings via an acceptable emission reduction plan through the years. The fact that the average age of trainers is below 40, will ensure long-term commitment to their career and availability of their services to the Government. Furthermore, the development of the emission inventory would readily be available for the usage of decision-makers in the reporting to the EU and other international authorities.

Cross-border impact:

This Project will determine long range transboundary effect of the pollutants that defined in the NEC Directive.  According to the result of the scientific research, the pollutants that have an effect on air quality ,  transported from Europe to Turkey . This project will give a chance to make an analysis  in determination of sources pollutants and their tansboundary effects.

3.3 Results and measurable indicators:

The results expected from the project are as follows;

| Results | Objectively Verifiable Indicators |
| --- | --- |
| 1. Legal transposition of National Emission Ceilings Directive was fulfilled. 2. National emission inventory and emission projections with various scenarios for four pollutants (SO2, NOx, VOC, NH3) were developed. 3-Regulatory Impact assessments for the implementation of different NE Ceilings were done. 4- An agreed long-term comprehensive strategy to improve the air quality for pollutants defined in NEC directive was developed. 5- Required institutional structure, technical capacity and procedural arrangements defined and developed to implement NEC Directive | 1.1- Legal gap analysis in the framework of other international agreements was studied by the end of 2011. 1.2- A Draft Agreed By-Law on National Emission Ceilings was prepared by the end of 2011. 2.1- National emissions inventory for four pollutants on the basis of sources namely industrial, heating and motor vehicle was used within EMEP’s integrated assessment modelling by the end of 2011. 2.2- National emission projections prepared according to at least 2 different ceiling values for four pollutants were reported by the end of 2011. 2.3- 35 staff from MoEF, MoENR and Turkish Statistical Institude were trained on data analysis, source analysis, modelling, emission data base, reporting by the end of 2011 2.4- 20 MoEF staffs were trained in air quality modeling by the end of 2011. 2.5- At least 4 Workshops were done with all stakeholders to share emission inventory until the end of 2011. 2.6- Web-site of the project was prepared within three months after the project started. 3.1- Regulatory Impact assessment was prepared in coordination with related sectors in order to increase the public/sectoral awareness by the end of 2011. 3.2- Cost-benefit analysis from implementation of NEC directive, prepared in sectoral basis by the end of 2011 3.3- 3 seminars were done together with related sectors. 4.1- Strategic action plans and programmes drawing an emission reduction roadmap were developed and adopted by the end of 2011. 5.1- Roles and responsibilities of related institutions are agreed and clearly defined in the Draft legislation at the end of the project. 5.2- 35 Turkish Experts were technically trained for the application of NEC Directive by the end of 2011. 5.3- At least 4 workshops and 8 seminars were done together with all stakeholders until the end of 2011. |

Legal Transposition of National Emission Ceilings Directive was fulfilled: Adoption of a draft by-law on NEC Directive is the main core of the legal transposition of the NEC Directive, of which the indicator 1.1 covers. Moreover, all international agreements related with Turkey should be screened by means of NEC Directive.

National emission inventory and emission projections with various scenarios for four pollutants (SO2, NOx, VOC, NH3) were developed.  In order to determine the national emission ceiling values for four pollutants, at first stage it is necessary to have an emission inventory.  National emissions inventory on the basis of sources namely industrial, heating and motor vehicles was used within EMEP’s integrated assessment modelling by the end of 2011. After the determination of the present situation, on the bases of possible emission ceilings, emission reduction strategies and national emission projections which are prepared according to at least 2 different ceiling values for four pollutants on the basis of sources namely industrial, heating and motor vehicles were reported by the end of 2011. Emission inventory and projections can be verified from Modelling Outputs and National Emission Projection Reports respectively. Because of the reason that national emission inventories and emission projections should be prepared and annually updated, related staff was trained. Sharing of emission inventory and project activities, workshops between stakeholders were arranged and web-site of the project was developed.

Regulatory Impact assessments for the implementation of different National Emissions Ceilings were done: Regulatory Impact assessments which were developed according to different national emission ceilings were prepared in order to increase the public/sectoral awareness. Related sectors were informed via seminars. Cost-benefit analysis was done in order to set a basis for regulatory impact assessments.

An agreed long-term comprehensive strategy to improve the air quality for pollutants defined in NEC directive was developed.In order to reach the emission ceilings, required emission reduction roadmap including strategic action  plans and programmes were erected.

Required institutional structure, technical capacity and procedural arrangements defined and developed to implement NEC Directive.To enhance the sustainability of the project, intuitional building was developed by means of Directive specific training programmes and workshops. In addition, the roles and responsibilities of related institutions are defined and clearly stated in the Draft legislation at the end of the project.

3.4 Activities:

Under one Twinning and one TA Contract, five main results should be achieved, for which  the main activities are listed below. Cofinancing source for all activities is the MoEF budget. This budget will be available once it is nominated for the fiscal year, in which the activities are executed.

1.1-Identification of present situation for the Implementation of the NEC Directive: In order to evaluate the institutional and technical capacity (existing structure/equipment) and to make the legal gap analysis, related studies were done for the implementation of the NEC Directive. This activity will be covered by Twinning

1.2- Investigation of roles and responsibilities of Turkey due to International Agreements such as Convention on Climate Change, Convention on Long Range Transboundary Air Pollution particularly Gothenburg Protocol and EU Directives on fuel quality: In order to implement the EU and other international legislation properly, the roles and responsibilites of the institutions and authorities of Turkey should be clearly defined in the national legislation. Therefore, the requirements of all agreements and conventions should be investigated and transposed. This actitity will be covered by Twinning

2.1- Workshop arrangements in order to develop coordination and cooperation among stakeholders for the preparation of emission inventory: Since that the emission inventory and projections required for the implementation of the NEC Directive, the procedure for the preparation of emission inventory and for making projections should be learned by organizing workshops and seminars. In addition, these workshops and seminars should be arranged in order to develop coordination and cooperation among the stakeholders. This will be done by Technical Assistance.

2.2 – Preparation of emission inventory Using methodologies that are defined in the NEC Directive for the determination of emissions from point and area sources of Turkey:

In order to make projections on the air quality and determine the emissions from point and area sources, methodologies that are defined in the NEC Directive should be used. This will be done by Technical Assistance.

2.3- Comprehensive training of related personnel of MoEF, and Turkish Statistics Institute both in Turkey and in the Member States for the strengthening  of personnel capacity and for the preparation of emission inventory and reporting: Because of the reason that the emission inventory and projections required for the implementation of the NEC Directive should be annually updated, the training of the personnel is vitally important for the sustainability of the project. This activity will be covered by Twinning

2.4- Sharing experiences by workshops, seminars, published papers, brochures, etc.  Since the awareness of the decision makers should be raised to establish air quality policies, sharing experiences by workshops, seminars, published papers etc. for the implementation of the NEC Directive is necessary. This activity will be covered by Twinning

2.5- Preparation of Website: Website of the project should work in order to inform the stakeholders and the public about the activities and results of the project within three months after the project started. This activity will be covered by Twinning

3.1- Preparation of cost benefit analysis: Cost-benefit analysis for the implementation of NEC directive should be prepared on sectoral basis and for different possible emission ceilings by the end of 2011. This activity will be covered by TA

3.2- Preparation of Regulatory Impact Assessment Report: After the determination of the present situation, on the bases of emission reduction strategies and national emission projections which are prepared according to at least 2 different ceiling values for four pollutants on the basis of sources namely industrial, heating and motor vehicles were reported by the end of 2011. Using the results of cost-benefit analysis, the regulatory impact assessment should be prepared. This activity will be carry out by TA

3.3. Workshop arrangements in order to develop coordination and cooperation among stakeholders for the preparation of impact assessment analysis for the implementation of NEC Directive:  Since that the preparation of impact analysis required for the implementation of the NEC Directive, the impact analysis should be prepared by organizing workshops and seminars. In addition, these workshops and seminars should be arranged in order to develop coordination and cooperation among the stakeholders. This activity will be covered by TA

4.1- Preparation of an agreed Strategic Action Plan for the achievement of National Emission Ceilings: After the determination of the present situation, the strategic action plan for the achievement of national emission ceilings should be developed according to the project results. An agreed long-term comprehensive strategy to improve the air quality for pollutants defined in NEC directive and strategic action plans and programmes drawing an emission reduction roadmap should be developed and adopted by the end of 2011. This activity will be covered by Twinning

4.2 – Preparation of emission abatement road map for four pollutants in sectoral basis (SO2, NOx, VOC, NH3): To improve the air quality and the consistency with the NEC Directive, emission abatement road map should be drawn up on sectoral basis according to the national emission ceilings stated in the directive. This activity will be covered by Twinning

4.3- Preparation of guidelines for the effective usage of methodologies and models for the inventory and the projections : Because of the reason that the air quality projections required for the implementation of the NEC Directive should be annually updated, the guideline is needed for the usage of methodologies for the inventory and the projections for the sustainability of the projections. This will be done by Technical Assistance.

5.1 Evaluation of the institutional and technical capacity for the implementation of NEC Directive in Turkey: In order to evaluate the institutional and technical capacity (existing structure/equipment), the present situation of Turkey should be evaluated for the implementation of the NEC Directive. This activity will be covered by Twinning

5.2. A comprehensive training programme implemented covering trainings both in Turkey and Member States: Training of the personnel is important for the sustainability of the project. 55 Turkish Experts were technically trained for the application of NEC Directive by the end of 2011 and at least 4 workshops and 8 seminars were done together with all stakeholders until the end of 2011. This activity will be covered by Twinning

5.3 Dissemination workshops on the implementation of NEC Directive in Turkey:For the implementation of the NEC Directive in Turkey, the workshop and seminar organizations are important for the involvement of all stakeholders by means of coordination, cooperation and sharing experiences. This activity will be covered by Twinning

3.5 Conditionality and sequencing:

N/A

3.6 Linked activities

There is a need for strengthening of the institutional

structure to ensure the full and effective implementation, monitoring and inspection of the existing legislation as well as the related EC Directives.  Many of the EU funded projects have been completed in Ministry of Environment and Forestry. These projects provided a base for improving at institutional level.

“Air Pollution Measurement and Monitoring Systems”: It is a national project, which has been finalized in 2002. In this project, generally, locations and number of measurement stations were determined in 81 cities, and financial analysis was made according to EU requirements.

“Analysis of Environmental Legislation in Turkey”: This project was completed in 2002. An analysis of Turkish environmental legislation and the gaps according to EU legislation were given.

Within the framework of the MATRA Pre-Accession Projects Program (MAT02/TR/9/2), “Strengthening of the implementation of the Council Directive 96/62/EC and Council Decision 97/101/EC on ambient air quality assessment and management, and reciprocal information exchange in the RSCH, MoH, Turkey” Project has been carried out in the period of January 2003-December 2004. This project consists of the preparation for reporting of Turkish air quality information to EU, the development at institutional level of RSCH and MoEF in air quality, the preparation of preliminary assessment and basis air quality monitoring and policy, introduction of a quality system according to ISO17025 in the RSCH-air quality and research laboratory

“Capacity Building (Human Resources Aspect) on the adoption of Integrated Pollution Prevention and Control Directive (IPPC-96/61/EC)”: The project was supported by the Dutch PSO Program. The objective of the project was to develop in-depth understanding of the IPPC Directive and design an action plan for adoption and implementation in Turkey. The project was finalised in 2004.

”Integrated Harmonisation Strategy Project” project defined the programme through which the necessary changes in legislation and implementation will be achieved in Turkey. The strategy covers a period of 20 years, starting in 2003, in order to ensure that all long term investment needs are included. The strategy covers all nine sectors of the environmental acquis. The environmental approximation strategy was prepared at three levels: Firstly, a series of Directive Specific Implementation Plans (DSIP) was prepared. Secondly, a Sector Approximation Strategy (SAS) was prepared for each of the nine sectors including air sector. Finally, a single Integrated Approximation Strategy (IAS) for Turkey was prepared based on the nine sectors’ Approximation strategies. This project was completed in April 2004.

“Environmental Heavy Cost Investment Planning Project” The project was launched in the framework of 2002 European Union Financial Cooperation Programme and finished by the end of 2005. Among others, the consequences of implementation of the air quality framework directive were evaluated and estimated in terms of necessary investment costs. The inception report for the project has already been prepared.

EU-Twinning Project Air Quality, Chemicals, Waste, Component 1: “Air Quality” was completed in 2006. The main aims of the project were reached. The transpositions of the Council-Directive 96/62/EC (Air Quality Framework Directive) including the 4 Daughter Directives and the Directive 2001/80/ EC (Large Combustion Plant Directive) into Turkish Legislation were drafted and agreed. Under the Project the following studies were completed. Preparation of Draft regulation on ambient air quality assessment and management;          Preparation of Draft regulation on large combustion plants, Designation of zones and agglomerations with a view of the ambient air quality assessment, Determination of the number of stations necessary and regional network structure, Preparation of a Strategy for the implementation and enforcement of the regulation on air quality assessment and management in Turkey, Preparation of a Strategy paper on the implementation of the large combustion plant directive, Calculating the cost of ambient air quality monitoring and use of EURAD model for air quality forecast

The MATRA programme “IPPC Implementation in Turkey” was started in January 2006. The project purpose is to assist the Turkish Ministry of Environment and Forestry with the implementation of the IPPC Directive. More specifically, the project should lead to the preparation of a roadmap towards full implementation of the IPPC Directive in Turkey. The project will end in January 2008.

3.7 Lessons learned

All projects mentioned above have highlighted a number of weaknesses such as;

- Weakness in collection of data and the transformation of data into an inventory,

- Absence of adequate planning system and sectoral strategies,

- Weakness in demands analysis,

- Absence of methodology for data collection and use of this data in a correct manner,

Currently, it is clear that effective implementation of the air quality strategy and legal programme will require;

- Reliable data collection system,

- Effective system and institutions for monitoring and reporting of emissions and             environmental quality and inspection,

- Procedures and tools for raising environmental awareness of industry and public in order to secure understanding, cooperation and support of environmental measures,

- Institution procedures facilitating public participation and environmental management,

- Administrative and judicial resource relation to (actual and threatened),

- Violation and Environment Law accompanied by appropriate systems of adequate and dissuasive fines and penalties including provision for liability  under criminal jurisdiction for serious violations ,

- Training of staff and susceptible sector of society,

- Adequate funding of implementing and enforcement institutions

All the above remedial actions to avoid identified problems have been addressed in the project design and need to be addressed during the project implementation.

4. Indicative Budget (amounts in €) (Detailed budget calculations in Annex 5)

|  |  | SOURCES OF FUNDING |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | TOTAL PUBLIC COST | EU CONTRIBUTION |  |  |  |  |  | NATIONAL PUBLIC CONTRIBUTION |  |  |  |  |  |  |  |  |  | PRIVATE |
| Activities |  | Total | % * |  | IB |  | INV | Total |  | Type of cofinancing (J / P) ** | % * |  | Central |  | Regional | IFIs |  |  |
| Activity 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Twinning | 1,300,000 | 1,235.000 | %95 |  | 1,235.000 |  |  | 65,000 |  |  | %5 |  | 65,000 |  |  |  |  |  |
| Technical Assistance | 750,000 | 675,000 | % 90 |  |  |  |  | 75,000 |  |  | %10 |  | 75,000 |  |  |  |  |  |
| TOTAL | 2,050.000 | 1,910,000 |  |  |  |  |  | 140,000 |  |  |  |  | 140,000 |  |  |  |  |  |
| ** compulsory for INV (minimum of 25 % of total EU + national public contribution) : Joint cofinancing (J) as the rule, parallel |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| co financing (P) per exception |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| * expressed in % of the Total Public Cost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

5. Indicative Implementation Schedule (periods broken down per quarter)

| Contracts | Start of Tendering | Signature of contract | Contract Completion |
| --- | --- | --- | --- |
| Twinning | QR1 2009 | QR4 2009 | QR1 2012 |
| Technical Assistance | QR2 2009 | QR1 2010 | QR2 2011 |
| …… |  |  |  |

Duration of the project : 24 months

All projects should in principle be ready for tendering in the 1ST Quarter following the signature of the FA

6. Cross cutting issues (where applicable)

6.1	Equal Opportunity

The project is running on the environmental field, rehabilitation of which increases life standards, and chance of every party for taking part in the society. Environmental administration in Turkey is one of the sectors with the highest rate of women employed. Thus, the project is believed to have quite a positive impact on equal opportunity creation.

6.2	Environment

The project itself is focused on the achievement of long-term improvements in Turkey in the environment sector. It will improve the environmental conditions in Turkey and some activities like transportation can also be improved in terms of environmental standards.

There are important cross-cutting issues with implementation of other relevant air pollution legislation (not just LCP and fuel quality, but also By-Law on Air Quality Assessment and Management ….) which need to be properly addressed, as these legislation is taken in by TK in the following years. In addition, climate change which is an important EU policy is partly covered in the integrated “clean air” programme (if we understood properly one of the pillars of this activity), almost as a side-issue to the air quality and fuel quality measures.

6.3	Minority and vulnerable groups

According to the Turkish Constitutional System, the word minority encompasses only groups of persons defined and recognized as such on the basis of multilateral or bilateral instruments to which Turkey is a party. This project has no negative impact on minority and vulnerable groups.

- ANNEXES

1-	Log frame in Standard Format

2-	Amounts contracted and Disbursed per Quarter over the full duration of Programme

3- 	Institutional Framework

* Role and responsibilities of the SPO

* frequency of project management meetings,

* who chairs, who attends and in what role

* coordination mechanisms for multi-beneficiary projects

*  monitoring (roles, responsibilities of all actors)

- 4 -	Reference to laws, regulations and strategic documents:

Reference list of relevant laws and regulations

Reference to AP /NPAA / EP / SAA

The Latest Acession Partnership  18.02.2008 ( 2008/157/EC)

Reference to MIPD

Reference to National Development Plan

Reference to national / sector investment plans

5-	Details per EU funded contract (*) where applicable:

For TA contracts: account of tasks expected from the contractor

For twinning covenants:  account of tasks expected from the team leader, 	resident twinning advisor and short term experts

For grants schemes:  account of components of the schemes

For investment contracts: reference list of feasibility study as well as technical specifications and cost price schedule + section to be filled in on investment criteria (**)

For works contracts: reference list of feasibility study for the constructing works part of the contract as well as a section on investment criteria (**); account of services to be carried out for the service part of the contract

(*) non standard aspects (in case of derogation to PRAG) 	also to be specified

(**) section on investment criteria (applicable to all infrastructure contracts and constructing works):

- Rate of return

- Co financing

- compliance with state aids provisions

  - Ownership of assets (current and after project completion)

ABBREVIATIONS BAQAM By-Law on Air Quality Assessment and Management CFCU Central Finance and Contracting Unit CLRTAP Convention on Long-Range Transboundary Air Pollution EC European Commission EU European Union IPPC Integrated Pollution Prevention and Control LCP Large Combustion Plant MATRA Funding Program of the Government of the Netherlands for Candidate Countries MoEF MoENR MoARA Ministry of Environment and Forestry Minisrty f Energy and Natural Resources Ministry of Agriculture and Rural Affairs MoH Ministry of Health NOx VOCs Nitrogen Oxide Volatile Organic Compounds PM Particulate matter RSHC Refik Saydam Hygiene Centre TÜBİTAK The Scientific and Technological Research Council of Turkey TUIK Turkish Statistical Institute UÇES TOBB EU Integrated Environmental Approximation Strategy The Union Chambers And Commodity Exchanges of Turkey EUAS DSIP SAS IAS Electricity Generation Corporation Directive Specific Implementation Plan Sector Approximation Strategy Integrated Approximation Strategy

- ANNEX 1: Logical framework matrix in standard format

| # ANNEX 1: Logical framework matrix in standard format |  |  |  |
| --- | --- | --- | --- |
| LOGFRAME PLANNING MATRIX FOR STRENGTHENING THE CAPACIY BUILDING ON NATIONAL EMISSION CEILINGS DIRECTIVE |  | Programme name and number: | EU IPA – Component I – 2008 Programming |
|  |  | Contracting period expires : 2 years after the DATE signature of the Financing Agreement | Disbursement period expires: 3 years following the end date for contracting |
|  |  | Total Budget: 2,050 M Euro | IPA budget: 1,910 M Euro |
| Overall Objective | Objectively verifiable indicators | Sources of Verification |  |
| To improve the environmental conditions in Turkey by the implementation and enforcement of the EU environmental acquis in the frame of ambient air quality. | Turkey will improve the capacity to meet the requirements of the environmental acquis in air quality by 2011. | - Accession Partnership Document Chapter Environment - National Program for the Adoption of the Acquis - EU Regular Progress Reports for 2008, 2009, 2010 and 2011. - State of Environmental reports for 2009, 2010,2011 |  |
| Project Purpose | Objectively verifiable indicators | ## Sources of Verification | Assumptions |
| To establish the necessary capacity within the Ministry of Environment and Forestry to transpose and implement the National Emission Ceilings Directive ( 2001/81/EC) | Draft By-Law for the transposition of the NEC Directive was prepared by the end of 2011. National emission inventory and emission projections were prepared. MoEF staff trained in data quality management and air quality modelling by the end of the project. | - EU Regular Reports - State of the Environment reports - Turkish National statistics - Annual reports of MoEF - Monitoring reports of the project | - By law on Air Quality will come into force - Governmental interest on reducing and controlling air pollution |
| Results | Objectively verifiable indicators | Sources of Verification | Assumptions |
| 1. Legal transposition of National Emission Ceilings Directive was fulfilled. 2. National emission inventory and emission projections with various scenarios for four pollutants (SO2, NOx, VOC, NH3) were developed. 3-Regulatory Impact assessments for the implementation of different National Emissions Ceilings were done. 4- An agreed long-term comprehensive strategy to improve the air quality was developed. 5- Required institutional structure, technical capacity and procedural arrangements defined and developed to implement NEC Directive | 1.1- Legal gap analysis in the framework of other international agreements was studied by the end of 2011. 1.2- A Draft Agreed By-Law on National Emission Ceilings was prepared by the end of 2011. 2.1- National emissions inventory for four pollutants on the basis of sources namely industrial, heating and motor vehicle was used within EMEP’s integrated assessment modelling by the end of 2011. 2.2- National emission projections prepared according to at least 2 different ceiling values for four pollutants were reported by the end of 2011. 2.3- 35 staff from MoEF, MoENR and Turkish Statistical Institude were trained on data analysis, source analysis for the pollutants that are covered under NEC Directive, modelling, emission database in the member states reporting by the end of 2011 2.4- 20 MoEF staff was trained in air quality modeling by the end of 2011. 2.5- At least 4 Workshops were done with all stakeholders to share emission inventory until the end of 2011. 2.6- Web-site of the project was prepared within three months after the project started. 3.1- Regulatory Impact assessment was prepared in coordination with related sectors in order to increase the public/sectoral awareness by the end of 2011. 3.2- Cost-benefit analysis from implementation of NEC directive, prepared in sectoral basis by the end of 2011. 3.3- 3 seminars were done together with related sectors. 4.1- Strategic action (alarm) plans and programmes drawing an emission reduction roadmap were developed and adopted by the end of 2011. 5.1- Roles and responsibilities of related institutions are agreed and clearly defined in the Draft legislation at the end of the project. 5.2- 35 Turkish Experts were technically trained for the application of NEC Directive by the end of 2011. 5.3- At least 4 workshops and 8 seminars were done together with all stakeholders until the end of 2011. | - Inception Report - Quarterly Report, Mission Reports, Final Report. - Certificates of training issued by supplier (education evaluation forms) - Statistical data base on emissions. - Spatial distribution of the air emissions. - National emission projection reports. - Clean air plans, action (alarm) plans for emission reduction - Website, published reports. | - Good cooperation and coordination among MoEF and other institutions. |

| Activities | Means | Cost | Assumptions |
| --- | --- | --- | --- |
| 1.1-Identification of the present situation for the implementation of the NEC Directive. 1.2- Investigation of roles and responsibilities of Turkey due to International Agreements such as Convention on Climate Change, Convention on Long Range Transboundary Air Pollution particularly Gothenburg Protocol and EU Directives on fuel quality 2.1- Workshop arrangements in order to develop coordination and cooperation among stakeholders for the preparation of emission inventory. 2.2 –Preparation of emission inventory Using methodologies that are defined in the NEC Directive for the determination of emissions from point and area sources of Turkey. 2.3- Comprehensive training of related personnel of MoEF, and Turkish Statistics Institute both in Turkey and in the Member States for the strengthening of personnel capacity and for the preparation of emission inventory and reporting 2.4- Sharing experiences by workshops, seminars, published papers, brochures, etc. 2.5- Preparation of Website 3.1- Preparation of cost benefit analysis 3.2- Preparation of Regulatory Impact Assessment Report 3.3. Workshop arrangements in order to develop coordination and cooperation among stakeholders for the preparation of impact assessment analysis for the implementation of NEC Directive. 4.1- Preparation of an agreed Strategic Action Plan for the achievement of National Emission Ceilings. 4.2 – Preparation of emission abatement road map for four pollutants in sectoral bases (SO2, NOx, VOC, NH3 ) 4.3- Preparation of guidelines for the effective usage of methodologies and models for the inventory and the projections 5.1 Evaluation of the institutional and technical capacity for the implementation of NEC Directive in Turkey 5.2. A comprehensive training programme implemented covering trainings both in Turkey and Member States 5.3 Dissemination workshops on the implementation of NEC Directive in Turkey | Twinning Technical Assistance | 1.300.000 EUR 750.000 EUR | - Preparation of proper working conditions and supplying the necessary equipments (building, room, computers etc.) for the success of the project - Good cooperation among MoEF , Turkish Statistical Institute and Ministry of Energy and Natural Resources. - Good cooperation and training activities among working groups - Good cooperation among stakeholders in terms of collection of data (e.g Chambers, NGO etc. ) - Elaboration of qualified and willing staff - Training and study tours regarded as key learning opportunities by the participants. |

- Pre conditions

- ANNEX II:	amounts (in €) Contracted and disbursed by quarter for the project

- (IPA contribution only)

| Contracted | III-2009 | IV-2009 | I-2010 | II-2010 | III-2010 | IV-2010 | I-2011 | II-2011 | III- 2011 | IV-2011 | I-2012 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Twinning |  | 1,235,000 |  |  |  |  |  |  |  |  |  | 1,235,000 |
| Technical Assistance |  |  | 675,000 |  |  |  |  |  |  |  |  | 675,000 |
| Cumulated |  | 1,910,000 | 1,910,000 | 1,910,000 | 1,910,000 | 1,910,000 | 1,910,000 | 1,910,000 | 1,910,000 | 1,910,000 | 1,910,000 | 1,910,000 |
| Disbursed | III-2009 | IV-2009 | I-2010 | II-2010 | III-2010 | IV-2010 | I-2011 | II-2011 | III- 2011 | IV-2011 | I-2012 | Total |
| Twinning |  | 555,700 |  | 277,900 |  |  |  | 277,900 |  |  | 123,500 | 1,235,000 |
| Technical Assistance |  |  | 202,500 |  | 135,000 |  | 135,000 |  | 135,000 |  | 67,500 | 675,000 |
| Cumulated |  | 555,700 | 758,200 | 1,036,100 | 1,171,100 | 1,171,100 | 1,306,100 | 1,584,000 | 1,719,000 | 1,719,000 | 1,910,000 | 1,910,000 |

ANNEX-3

INSTITUTIONAL FRAMEWORK

All activities depend fundamentally on close and effective co-ordination, co-operation and good lines of communication with and between the various stakeholders at managerial and technical level.  The main beneficiary will be the MoEF.

Figure-1: Institutional Framework in project management

CFCU

Administrative Issues

MoEF

Main Beneficiary

Turkish Project Leader

RTA Counterpart/Technical Assistance Team

Project Leader

RTA

Project Steering Committee

International and local short term experts pool

Provincial Directorates of MoEF

Coordination with

Metropolitan Municipality/ Municipalities/SPO/MoH, Chamber of Indusrty/

TOBB/stakeholders

Other Beneficiaries: Turkish Statistical Institute

Ministry of Energy and Natural Resources

,

Ministry of Agriculture and Rural Affair

Roles and responsibilities:

Senior Programme Officer (SPO) is responsible for the preparation, technical implementation and follow-up of the EU funded projects. SPO also provides regular information and monitoring reports on on-going projects and authorizations to undertake financial commitments or disbursement in relation to projects.  SPO will participate during the project activities in ad-hoc basis.

The Project Leader (PL) should be a high ranking official with broad knowledge of all processes in the area of the acquis that the project deals with, who will continue to work at his/her Member State administration but devote some of his/her time to conceive, supervise and coordinate the overall thrust of the Twinning Project. The  PL will allocate a minimum of three(3)  days per month including one visit every 3 months (more for complex projects ) to Turkey as long the project lasts. His/Her task will be overall project coordination, Co-chairing with the Turkish Project Leader, the regular project implementation steering committee meetings, mobilizing short-end medium term experts, executing administrative issues (i.e. signing reports, side letters etc.) PL will participate during the project activities in ad-hoc basis.

Resident Twinning Adviser (RTA) :   The main responsibility of the RTA  is the project management and coordination of the activities of the team members in line with the agreed work programs to enable timely completion of project outputs and preparation of project progress reports and supervision of the preparation and production of task reports. RTA will work during the whole duration of Project.

Technical Assistance Team:  (TAT) Main responsibilities of the staff of TAT are to develop coordination and cooperation among stakeholders for the preparation of emission inventory, to prepare emission inventory using methodologies that are defined in the NEC Directive for the determination of emissions from point and area sources of Turkey and to prepare guidelines for the effective usage of methodologies and models for the inventory and the projections. TAT will be working in coordination with RTA.

Ministry of Environment and Forestry (MoEF) The beneficiaries of this project will be the General Directorate of Environmental Management of MoEF as the administrative body. MoEF will therefore assume complete responsibility for administration related to the preparation, technical control and implementation of the project components for efficient administration.

Central Finance and Contracting Unit (CFCU) : The Implementing Agency for this Project will be the Central Financing and Contracting Unit (CFCU), who will be responsible for all procedural aspects of the tendering processes, contracting matters and financial management (including payments) of the Project activities.  CFCU will be responsible for financial implementation of the project, ensuring full transparency in financial transactions, management and reporting and operating an appropriate administrative structure, including premises, sufficient qualified structure, and staff.

EC Delegation: will carry out ex-ante control over the financial assistance programme throughout the programme implementation.

The main stakeholders (and the summary basis of their involvement) will be

- MoEF, as - among other things - the national Competent Authority for Environment and Turkey’s official designated link with the European Environment Agency and including the MoEF’s Golbasi Reference Laboratory as the future National Reference Laboratory for Air Quality, auditing body and emissions monitoring body; (Ankara and 11 province offices)

- General Secretariat for EU Affairs (“EU Secretariat General”) (as a representative of a source of international funding)

- Undersecretariat of Treasury (as a representative of a source of national funding)

- The Ministry of Energy and National Resources, in relation to power plants and the LCPD;

- The Chamber of Industry (as a coordinating body for major industries including the refinery, chemical and cement industries);

- Ministry of Industry & Trade (for vehicle approval and vehicle emission issues);

- General Directorate of State Highways (vehicle emission measurements)

- Turkish Statistical Institute: responsible for the preparation of inventories and other statistical work

- the State Planning Organisation (as a source of approval for projects);

- the State Statistics Institute (as a holder, manager and distributor of air quality data);

- the Environmental Engineering Departments of (i) the Middle East Technical University and (ii) İstanbul Technical University, (iii)Marmara University (iv) Yıldız Technical University  etc. (as sources of national and international scientific expertise knowledge);

- TUBITAK (Turkish Scientific and Technical Research Council),

- NGOs

- The Turkish Regional Environmental Centre (REC).

PROJECT MANAGEMENT

In order to identify and invite the participants, elaborate the programme, share the experiences in practical implementations of the project activities, introduce the project purposes kick-off meeting will be hold at the beginning of the project period..

Steering Committee

For the purpose of this twinning component, a Steering Committee will be chaired by the Ministry of Environment and Forestry, consisting of representatives from the above organizations. At quarterly intervals or whenever deemed necessary by its members, the Project Leaders, the RTA and RTA counterpart and where applicable, representatives of the administrative office(CFCU), EUSG and the EC Delegation will meet to discuss the progress of the project, verify the achievement of the outputs and mandatory results and discuss actions to be undertaken in the following quarter . The Project Steering Committee will also discuss the draft of the quarterly report submitted to it beforehand, and recommend corrections. The responsibility for the organization of the project Steering Committee meeting lies with both Project Leaders. For the purpose of this twinning component, a Steering Committee will be chaired by the Ministry of Environment and Forestry, consisting of representatives of Resident  Twinning Adviser (RTA) of the Beneficiary Country and the Member State Partner, Project Leaders of the Member State and the Beneficiary Country, European Commission Turkish Delegation, Central Finance and Contracting Unit (CFCU), State Planning Organization, Refik Saydam Hıfzıssıhha Center of Hygiene , Ministry of Environment and Forestry . Steering Committee will meet quarterly .

In every week, RTA’s would come into together in order to analyze the studies held  under project activities, to assess of  the needs, to elaborate of the recommendations to manage  the project successfully and discuss weekly works.

For monitoring of Project management and activities, beneficiary will prepare the monitoring reports to be submitted to National Aid Coordinator (NAC)  besides in independent Interim Evaluation Team contracted by EC will also prepare Interim Evaluation Report for the evaluation of the project management implementation.

### ANNEX-4-1 RELATED PART OF NATIONAL PROGRAMME

### PRIORITY 22.3 Improving Air Quality

##### 1-Priority Description

Air quality has been designated as a priority, considering that beginning to transpose and implement the acquis is a short term priority, and completing the transposition of the acquis and strengthening institutional, administrative, and monitoring capacity, including data collection, to ensure environmental protection are medium term  priorities in the 2003 Accession Partnership Document.

There is a need for eliminating differences between Turkish and EU air quality legislation. The Ministry of Health contributes to harmonization efforts carried out by the Ministry of Environment and Forestry.

The project entitled “strengthening of the implementation of Council Decision 97/101/EC on ambient air quality assessment, management and reciprocal information exchange (as part of Air Quality Directive 96/62/EC) at the Refik Saydam Hygiene Centre, Ministry of Health, Turkey”, supported by bilateral cooperation with the Government of the Netherlands MATRA Programme, was initiated in 2003. In addition, in the scope of  the Support to Turkey in the Field of Air Quality, Chemicals and Waste Management Project, which was submitted to 2003 Financial Cooperation Programme, strengthening of administrative capacity for harmonizing and implementing Air Quality Directive 96/62/EC will be studied.

Secondary legislation promulgated in the field of air quality are listed in Annex 22.1.

##### 2- Schedule of  Necessary  Legislative Changes

Table 22.3.1

| No | Title and number of EU legislation | Title of Draft Turkish Legislation | Responsible Institution a) |  |  | Proposed Date of Approval of Minister/Council of Ministers | Proposed Date of 1- Adoption by the Parliament 2- Entry into force |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Council Directive 96/62/EC of 27 September 1996 on ambient air quality assessment and management | Implementing Regulation | Ministry of Environment and Forestry |  |  | 2005, IV. Quarter | b) |
| 2 | Council Directive 1999/30/EC of 22 April 1999 relating to limit values for sulphur dioxide, nitrogen dioxide and oxides of nitrogen, particulate matter and lead in ambient air (was amended by Directive 2001/744/EC)c) | Implementing Regulation | Ministry of Environment and Forestry |  |  | For preparation of the legislation 2005, IV. Quarter | b) |
| 3 | Directive 2002/3/EC of the European Parliament and of the Council of 12 February 2002 relating to ozone in ambient air | Implementing Regulation |  | Ministry of Environment and Forestry | For preparation of the legislation 2005, IV. Quarter |  | b) |

| 4 | Directive 2000/69/EC of the European Parliament and of the Council of 16 November 2000 relating to limit values for benzene and carbon monoxide in ambient air | Implementing Regulation | Ministry of Environment and Forestry | For preparation of the legislation 2005, IV. Quarter | b) |
| --- | --- | --- | --- | --- | --- |
| 5 | Council Directive 1999/32/EC of 26 April 1999 relating to a reduction in the sulphur content of certain liquid fuels and amending Directive 93/12/EEC | Secondary legislation | Ministry of Environment and Forestry |  | d) |
| 6 | Directive 98/70/EC of the European Parliament and of the Council of 13 October 1998 relating to the quality of petrol and diesel fuels and amending Council Directive 93/12/EEC | Implementing Regulation | Ministry of Environment and Forestry |  | d) |
| 7 | Directive 1999/94/EC of the European Parliament and of the Council of 13 December 1999 relating to the availability of consumer information on fuel economy and CO2 emissions in respect of the marketing of new passenger cars | Communiqué to inform the consumers on fuel economy and CO2 emissions of new passenger cars | Ministry of Industry and Trade | 2003, II. Quarter | 2- 2007, I. Quarterd) |

a)  The Ministry of Health will contribute to the studies.

b) As the implementation of the legislation under this priority requires heavy investment for both the public and private sector,  it is deemed necessary to make infrastructural investment and to strengthen technical capacity. Therefore, the implementation date will be determined during legislation preparation.

c) It will be taken into account together with the Directives 80/779/EEC, 82/884/EEC, 85/203/EEC concerning limits.

d) The attainment of the limits within the scope of this Directive depends on investment by the Turkish Petroleum Refineries Corporation (TÜPRAŞ). The preparation of the necessary legislation will be dealt with in parallel to the progress regarding the investments and/or the implementation dates will be determined depending on these investments.

3- Schedule of Necessary Institutional Changes

Table 22.3.2

| No | Necessary Institutional Changes - (Ministry of Environment and Forestry) | Period of Implementation |
| --- | --- | --- |
| Air Quality |  |  |
| 1 | Assignment of authorised institutions at the national, regional and local level | 2006 |

| 2 | Strengthening technical and administrative capacity of the Ministry of Environment and Forestry | 2006 |
| --- | --- | --- |
| 3 | Establishment of the air quality monitoring station network and measurement quality system and improvement of the laboratory infrastructure | As from 2006 |
| 4 | Evaluation of the air quality in all different areas (including monitoring and modelling) and setting up an inventory | 2010 |
| 5 | Preparation of plans to improve air quality for areas where good air quality cannot be achieved | 2010 |
| 6 | Implementation of the plans for improvement of air quality | 2010 |
| 7 | Establishment of monitoring systems for the greenhouse gases and transboundary transport of pollutants | 2010 |
| 8 | Training on legislation and technical issues for staff involved in air quality. | 2010 |
| Fuel Quality |  |  |
| 1 | Improvement of quality of diesel fuels | 2007 |
| 2 | Improvement of quality of petrol | 2007 |
| 3 | Improvement of the quality of the liquid fuel used for purposes other than automobiles | Investment by TÜPRAŞ is essential. |

Table 22.3.3

| No. | Necessary Institutional Changes - (Ministry of Health) | Period of Implementation |
| --- | --- | --- |
| 1 | Training on legislation and its implementation for the personnel of the Ministry of Health central office staff, staff of the Refik Saydam Hygiene Centre (RSHM), and Provincial Health Directorates | 2004-2006 |
| 2 | Elimination of the technical deficiencies in the infrastructure of the Refik Saydam Centre of Hygiene (RSHM) and Public Health Laboratory for the monitoring of the air quality | 2004-2006 |
| 3 | Strengthening of the system to inform the public on air quality | 2004-2006 |

##### 4-Financing Requirements and Sources of Financing

Table 22.3.4																		(Euro)

| Requirements - (Ministry of Environment and Forestry) | Year | National Budget | EU Resources | Other | Total |
| --- | --- | --- | --- | --- | --- |
| I-Investment a) |  |  |  |  |  |
| II- Harmonisation with the EU legislation and Implementation | 2004-2006 |  | (1) |  |  |
| Personnel |  |  |  |  |  |
| Training | 2004-2006 | 5,000 | (2)+50,000b) |  | 55,000 |
| Consultancy | 2004-2006 |  | (3)+200,000b) |  | 200,000 |
| Translation | 2004-2006 | 5,000 | 10,000 |  | 15,000 |
| Other TR-0302.03c) | 2004-2006 |  | (1)+(2)+(3) = 1,500,000 |  | 1,500,000 |
| Total |  | 10,000 | 1,760,000 |  | 1,770,000 |

a) The investment requirement will be determined once the Project on Integrated Environmental Harmonisation Strategy (2002-31739) is finalised. In addition, studies on priority environmental projects for accession and supporting the development of an efficient financial mechanism for financing EU environmental heavy-cost directives will be carried out in the context of the environmental heavy cost investments component of the Capacity Development in The Field Of Environment (TR-362.03) Project under the 2002 Pre-accession Financial Assistance Programme.

b) This amount is required for the activities related to EU legislation which is not included in the project (TR-0302.03) proposed  to the 2003 Pre-accession Financial Assistance Programme. The needs of the Ministry of Health will also be considered in this context.

c) Twinning  Support to Turkey in the field of Air Quality, Chemicals and Waste Management Project (TR-302.03), air quality component (including Directives 96/62/EC on air quality and Directive 2001/80/EC on large combustion plants), proposed to 2003 Pre-accession Financial Assistance Programme.

Table 22.3.5																		(Euro)

| Requirements - (Ministry of Health) | Year | National Budget | EU Resources | Other | Total |
| --- | --- | --- | --- | --- | --- |
| I-Investment a-TR-0302.03a) b-Other b) | 2004-2006 2004-2006 | a- 350,000 b- (1) | a- 1,050,000 b- (2) | b- (3) | a- 1,400,000 b- 2,000,000 – 4,000,000 |
| II- Harmonisation with the EU legislation and Implementation | 2004-2006 |  |  | (4) |  |
| Personnel | 2004-2006 | 160,000 |  |  | 160,000 |
| Training | 2004-2006 | 5,000 |  | (5) | 5,000 |
| Consultancy | 2004-2006 |  |  | (6) |  |
| Translation | 2004-2006 | 5,000 | 10,000 |  | 15,000 |
| Other |  |  |  | (4)+(5)+(6) = 403 000c) | 403,000 |
| Total |  | 520,000 | 1,060,000 | 403,000 | 3,983,000 - 5,983,000 |

a) Investment amount of Support to Turkey in the field of Air Quality, Chemicals and Waste Management Project (TR-302.03) proposed to 2003 Pre-accession Financial Assistance Programme, twinning amount was previously given in Table 22.3.4.

b) This amount is required for the EU legislation which is not included in the project (TR-0302.03) proposed  to the 2003 Programming of Pre-accession Financial Assistance.

c) The project “strengthening of the implementation Council Decision 97/101/EC on ambient air quality assessment, management and reciprocal information exchange (as part of the Air Quality Directive 96/62/EC) in the Refik Saydam Hygiene Centre, Ministry of Health, Turkey”, supported by the bilateral cooperation with the Government of Netherlands, the MATRA Programme (MAT02/TR/9/2)

### ANNEX-4.2 RELATED PART OF EU INTEGRATED ENVIRONMENTAL APPROXIMATION STRATEGY IN TURKEY

5.3. Air Sector

5.3.1. Present Situation

In Turkey especially during the months of winter air pollution makes itself felt due to the intensive urbanization, rapid population increase and industrialization, wrong placement of the cities according to the topographic and meteorological conditions. The main reasons for the pollution in winter that originates from heating is the utilization of low grade fuel without being subjected to the improvement processing, application of wrong burning techniques and the lack of maintenance on the furnaces that are used. However with the utilization of natural gas and other high grade fuel in heating, some improvement has been seen in the air pollution in the big cities compared to the 1990s. The wrong location selection by the industrial facilities in their establishment stage also contributes to the air pollution in the thermal power stations that are based on coal; the SO2 emissions originating from high sulphur content of domestic lignite constitute a risk. With respect to the air pollution that is faced with in the cities, the harmful exhaust gases released by the ever increasing motor vehicles play an important role and precautions must be taken in this area. Generally the 70-90 percent of carbon monoxide emissions (CO), 40-70 percent of nitrogen oxide, 50 percent of hydrocarbon (HC) emission, as well as 100 percent of lead emissions in the city centers are caused by the motorized vehicles.

The air quality in the country in general is measured by using the semi-automatic measurement devices that belong to the Ministry of Health and it is observed in 31 fully automated measurement stations that were established in 2005 by Ministry of Environment and Forestry, the fully automated air quality measurement stations are planned to be used widely in 81 provinces in year 2006. The work related with air quality is being carried out within the scope of By-law on Air Quality Control published on 02.11.1986 dated and 19269 numbered Official Gazette. However the following By-laws have been issued by the Ministry of Environment and Forestry and furthermore the air quality related provisions of By-law on Air Quality Control are still effective; By-laws on Control of Air Pollution Arising from Heating published on 13.01.2005 dated and 25699 numbered Official Gazette, By-law on Industrial Air Pollution Control published on 07.10.2004 dated and 25606 numbered Official Gazette*, By-law on The Control of Air Pollution Arising from Motor Vehicles In Traffic published on 08.07.2005 dated and 25869

Numbered Official Gazette, By-Law on the Quality of Petrol and Diesel Fuels published on 11 June 2004 dated and 25489 numbered Official Gazette. About making amendments on 09.08.1983 dated and 2872 numbered Environment Law at 26.04.2006 dated and 5491 numbered Law, “methods about the determination, monitoring and measurement of air quality and air quality limit values and measures taken to prevent limit exceeding, to make the public awareness and access to information and related jobs are determined by The Ministry of Environment and Forestry.

* Updated as By-law on  Regulation on Control of Industry Caused Air Pollution  published on  22.07.2006 dated and 26236 numbered Official Gazette

5.3.2. Legislative Compliance

Table 5.3.2 Timetable for Approximation

The main subjects where the responsibilities lie with respect to air pollution are the Air Quality Framework Directive and its daughter directives, Fuel Quality Directive, and Climate Change and Informing the Consumer Directive. With the purpose of harmonizing the legislation of EC on air quality to a framework legislation a Project named ‘’Support to Turkey in the field of Air Quality, Chemicals and Waste Management’’ was started in year 2004, and with the first component of this Project, Air Quality, it is aimed to reflect the contents of EC Framework Air Quality Directive on our National Air Quality Act and to the activities for measuring the air quality along with the reflection of the provisions of The Directive of Large Combustion Plants Directive on our domestic legislation. New draft regulations were prepared for limiting emissions arising from The Large Combustion Plants and to ensure air quality and these were submitted for

the approval of the related institutions. The Draft By-law on Air Quality Assessment and Management were prepared such that it covers four daughter directives (99/30/EC, 2000/69/EC, 2002/3/EC and 2004/107/EC) other than 96/62/EC numbered Air Quality Framework Directive. The new draft by-law sets the implementation calendar for implementation and harmonization for 13 pollutants that are defined under the framework directive and the daughter directives. By-law also aims to strengthen the monitoring, sanctioning and institutionalization in the area of controlling the pollution and air quality. Furthermore, one of the requirements of the directive that is air quality preliminary assessment study has started, and this study has already been completed in the provinces of Ankara, Karabük and Kütahya.

The Ministry of Environment and Forestry is determined as the responsible institution for the 98/70/EC numbered EU Directive under the heading of Turkish National Program Adoption of the Acquis. On this purpose, in the scope of harmonizing the Directive about the quality of fuel and diesel used at motor vehicles due to the 2/95 numbered Customs Union Agreement signed with EU, the 98/70/EC numbered EU Directive which came into force in 2000 in Europe, is prepared by The Ministry of Environment and Forestry by receiving approvals of related institutions and organizations, especially by taking the approval of TÜPRAS and it is transferred in Turkish laws as By-law on The Quality of Petrol and Diesel Fuels by being published on 11.06.2004 dated and 25489 numbered Official Gazette. Also, the duty to audit petroleum market is given to The Institution of Energy Market Regulatory Authority (EMRA) with the 04.12.2003 dated and 5015 numbered Petroleum Market Law. In this purpose EMRA has prepared the following By-laws: “Published on 30.12.2005 dated and 26039 numbered Official Gazette: Communiqué on The Production of Diesel Types, Obtaining Them In Or Out of The Country and

Presenting Them to The Market which was approved by the 08.12.2005 dated and 590/177 numbered Committee Decision of TS 3082 EN 590 Automotive Fuels-Diesel- Necessities and Testing Methods Standards.” “TS 228 EN 590 Automotive Fuels-unleaded gasoline- Necessities and Testing Methods Standards published on 05.01.2006 dated and 26044 numbered Official Newspaper as technical arrangement with Arrangement Notice on The Production of Gasoline Types, Obtaining Them In Or Out of The Country and Presenting Them to The Market approved by 29.12.2005 dated and 623/2 numbered Committee Decision The adaptation with respect to the Directive on the Sulphur Content in the fuel oil used in the Industry and Residents that takes place under the Air Sector Title (99/32/EC) will be commenced by considering TÜPRAS investments. The harmonization work on the Directive for Volatile Organic Compounds Emissions

Arising from Petrol Storage and its distribution from Terminals to Service Stations (94/63/EC) has not been started yet and furthermore the Directive on National Emission Ceiling Limits has not been reflected on our legislation yet. The work pertaining to carbon dioxide is still in progress.

5.3.3. Goals, Objectives and Strategies

The fundamental purpose is to define, and establish the air quality targets and evaluate the air quality in order to avoid, prevent and reduce the harmful effects that air pollution may have on human health as well as the environment.

1. Goal: The Air Quality targets will be defined and established.

Objective 1: With a by-law that will be issued the Air Quality targets will be defined and established.

2: Air Quality preliminary assessment studies will be completed until year 2012.

3: The air quality monitoring and measurement stations will be established until year 2012.

4: In relation with the air quality sector, the present institutional structure will be reviewed so that a more effective system can be established and the authority confusion among the institutions will be eliminated.

Strategy 1: Completion of Air Quality preliminary assessment studies will be completed.

2: Starting to the air quality monitoring and measurement stations will be established, and regular

and reliable data acquisition at this level that can be reported to EC will be started.

2. Goal: By taking the defined criteria and methods as the basis the air quality will be decided on.

Objective 1: Air Quality preliminary assessment studies will be completed until year 2012.

2: The air quality monitoring and measurement stations will be established until year 2012.

Strategy 1: Completion of Air Quality preliminary assessment studies will be completed.

2: Starting to the air quality monitoring and measurement stations will be established, and regular

and reliable data acquisition at third level that can be reported to EC will be started.

3: Establishment of Air Quality Monitoring Network Management Center.

4: Establishment of the National Data Center and forming of the reporting system.

5: Establishment of the regional calibration laboratories.

6: Establishment of the National Calibration Center.

7: Preparation of the emission inventory.

3. Goal: Sufficient information will be collected on the air quality and in case the thresholds are exceeded the public will be informed.

Objective 1: Air Quality preliminary assessment studies will be completed until year 2012.

2: The air quality monitoring and measurement stations will be established until year 2012.

3: In relation with the air quality sector, the present institutional structure will be reviewed so that a more effective system can be established and the conflict of competence among the institutions will be eliminated.

4: Clean air plans and action plans will be prepared to prevent the air pollution.

Strategy 1: Completion of Air Quality preliminary assessment studies will be completed.

2: The air quality monitoring and measurement stations will be established, and regular and reliable data acquisition at this level that can be reported to EC will be started.

3: Establishment of Air Quality Monitoring Network Management Center.

4: Establishment of the National Data Center and forming of the reporting system.

5: Establishment of the regional calibration laboratories.

6: Establishment of the National Calibration Center.

7: Preparation of the emission inventory.

8: Preparation and implementation of “Clean Air” plans for the improvement of the air quality.

9: Preparation of action plans for the prevention of the air pollution.

10: Informing the public on the causes and results of air pollution.

4.Goal: Living beings and the environment will be protected from the air pollution caused by the exhaust gases originating from the motor vehicles as well as the dangers associated with it.

Objective 1: Air Quality preliminary assessment studies will be completed until year 2012.

2: The air quality monitoring and measurement stations will be established until year 2012.

3: Clean Air Plans and action plans for the prevention of air pollution will be drown up.

4: To establish the policies that give incentives in the reduction of the pollution will be achieved.

5: For the improvement of air quality the work to improve the fuel quality will be carried on.

Strategy 1: Air Quality preliminary assessment studies will be completed.

2: The air quality monitoring and measurement stations will be established, and regular and reliable data acquisition at this level that can be reported to EC will be started.

3: Preparation of the emission inventory.

4: Drawing up and implementation of “Clean Air” plans for the improvement of the air quality.

5: Drawing up action plans for the prevention of the air pollution.

6: Informing the public on the causes and results of air pollution.

7: The coordinated working of the sectors such as energy, industry and transportation in ensuring

the limit values are achieved.

5. Goal: The fuel quality will be improved.

Objective: For the improvement of air quality the work to improve the fuel quality will be carried on

Strategy 1: The coordinated working of the sectors such as energy, industry and transportation in ensuring the limit values are achieved.

2: In the implementation of the requirements of air quality sector, utilization of the best techniques in the industrial facilities and changing of the manufacturing processes.

6. Goal: The implementation of action plans for improving air quality and the usage of environment friendly clean technologies will be ensured.

Objective 1: Drawing up “Clean Air” plans and action plans for the prevention of air pollution.

2: The creation and implementation of encouraging policies to decrease pollution will be ensured.

3: For the improvement of air quality the work to improve the fuel quality will be carried on.

4: The plans will be prepared for the implementation of the changes in the fuel quality and for the

reduction of carbon dioxide (CO2) and other greenhouse gas emissions.

Strategy 1: Air Quality preliminary assessment studies will be completed.

2: Starting to receive proper and secure data at a level to be reported to EU by establishing air

quality monitoring and measurement stations.

3: Establishment of Air Quality Monitoring Network Management Center.

4: Establishment of the National Data Center and forming of the reporting system.

5: Establishment of the regional calibration laboratories.

6: Establishment of the National Calibration Center

7: Preparation of the emission inventory

8: Drawing up and implementation of Clean Air Plans for the improvement of the air quality

9: Drawing up action plans for the prevention of the air pollution.

10: The coordinated working of the sectors such as energy, industry and transportation in ensuring the limit values are achieved.

11: In the implementation of the requirements of air quality sector, utilization of the best techniques in the industrial facilities and changing of the manufacturing processes.

5.3.4. Strengthening the Institutional Capacity

It is necessary to strengthen institutional capacity for the implementation of other directives about air quality, by taking The Directive of Air Quality Framework as first. Within this context, the establishment of the necessary technical infrastructure, its operation and inspection and the training of the personnel to be employed in these areas carry great importance for the effective implementation of the directives generally in the country.

Measurement devices are required for both effective monitoring of the air quality and for reaching the necessary standards. The establishment of the monitoring systems is considered important for full implementation of Air Quality Framework Directive and the other directives such as the Fuel Quality, and the Emissions Arising from the Vehicles.

5.3.5. Investment Needs

From the investments to be made in the public sector the costs necessary for the implementation and sanction of the directives is understood. The monitoring equipment, measurement systems and quality assurance systems must be installed for the implementation. In the investment stage Air Quality Framework Directive and its daughter directives have priority in this sector. The responsible institutions on this subject are the Ministry of Environment and Forestry and the Ministry of Health. To ensure approximation of the limit values, costs related for changing production periods by using all available best techniques to be implemented especially in industrial plants will be covered by the industrialists.

In accordance with the project for the planning on the Environmental Heavy Cost Investment Planning for Turkey, it is foreseen that in total 206 air quality measurement stations have to be installed in Turkey in general. From these stations 123 of them will be in intensive residential areas, 40 will be in the areas where the industry is intensive, 12 will be in the areas where the traffic is intense and 31 will be located in the rural areas. This number will be finalized as a result of the preliminary assessment studies to be conducted. Until year 2012 it is required for the preliminary assessment” studies for the whole of Turkey must be concluded and the monitoring system must be established. The total cost forecasted for the establishment of the monitoring system is 11 million Euro The maintenance and operating costs of all the stations will come up to 1.5 million Euros. On the other hand the maintenance and operating costs related with the measurement stations will continue after the establishment of the monitoring systems (2012) and the related cost for this will be an additional 1.5 million Euros every year. The total cost of the preliminary assessment studies for air quality is 6 million Euros.  Furthermore under Table 5.3.5 cost calculations for the following elements were made and these will be considered as additional costs; establishment of the calibration laboratories, establishment of the national calibration centre, establishment of the monitoring network management centre, national data centre, formation of the emission inventories, drawing up the clean air plans, drawing up the action plans, implementation of the plans and programs for the improvement of the air quality, informing the public, reporting and the related personnel costs. Also it is necessary to employ totally 243 personnel at the national centre and 8 regional centers for the evaluation system and air quality monitoring system in the scope of the “Support to Turkey in the Field of Air Quality, Chemicals and Waste Management” project, first component air quality. The cost of the personnel will be nearly 3 million euros/year. These costs are not reflected in Table 6.1.1 The implementation of the regulation about gasoline and diesel type fuels prepared as adapted with EU legislation and fuel specifications will be performed gradually in the years of 2007 and 2009. The implementation date for the Directive on the reduction of sulphur rate in some of the liquid fuel that is used in heating and industry (99/32/EC) will be determined due to the investments of TÜPRAS. The implementation date for Carbon dioxide emissions and Fuel consumption directive is determined as 2008. The implementation date of the Directive on Volatile Organic Components originating from petroleum stations (94/63/EC) is not known yet. TUPRAS has completed the majority of the investments in relation with the implementation of the Directive on the quality of gasoline and diesel, and it is known that TÜPRAS is targeting the rest of its investments in the year of 2007.

The implementation cost for 99/32/EC numbered Council Directive on the reduction of sulphur rate in some of the liquid fuel is related with TUPRAS which is the manufacturer of the fuel and the investments to be made in the large combustion plants. The investment cost related with the de-sulphurization that is defined in large combustion plants directive has been evaluated in the industrial pollution sector. However, according to the study results conducted to determine the feasibility of a reduction of sulphur rates in fuel oil, the investment needed to be made in four refineries of TUPRAS to be made is between 885 million – 1.135 million Euros. As TUPRAS is being privatized, there are no evaluations on Table 5.3.5 about fuel quality.

In the Project for planning on the Environmental Heavy Cost Investment Planning for Turkey, the

investment costs related with air quality framework directive and the daughter directives as well as the fuel quality directive were worked out partially. Work on other directives has not been conducted.

ANNEX 4-3  ACCESSION PARTNERSHIP  ( 2008/157/ EC)

Council Decision of 18 February 2008 on the principles, priorities and conditions contained in the Accession Partnership with Republic of Turkey and repealing Decision 2006/35/EC.

(2008/157/EC)

In the short term those priorities for environment  are:

- Adopt a comprehensive strategy for the gradual transposition, implementation and enforcement of the acquis, including plans for building up the necessary administrative capacity at national, regional and local level and required financial resources, with an indication of milestones and timetables

- Continue transposition, implementation and enforcement of the acquis, in particular horizontal and framework legislation, such as the environmental impact assessment, including transboundary aspects, as well as strengthening of administrative capacity

In the medium- term the priorities for Environment are;

- Continue to transpose and implement the acquis related to the framework legislation, international environmental conventions and legislation on nature protection, water quality, chemicals, industrial pollution and risk management and waste management

- pursue integration of environmental requirements into other sectoral policies,

ANNEX-5

ANNEX-5-1 DETAILS OF TASKS EXPECTED FROM THE TEAM LEADER, RESIDENT TWINNING ADVISOR AND SHORT TERM EXPERTS

Resident Twinning Adviser (24 working months)

Tasks:

- Project management and coordination of the activities of the team members in line with the agreed work programs to enable timely completion of project outputs

- Preparation of project progress reports and supervision of the preparation and production of tasks reports

- Analysis of Turkey’s capacity to implement National Emission Ceilings Directive ( 2001/81/EC) setting up a Community Framework for cooperation in the field of air pollution.

- Analysis of Turkey’s capacity to implement Council Directive 2001/80/EC establishing a Community mechanism to facilitate reinforced cooperation in the field of Emission.

Profile:

- Strong project management skills and experience

- Excellent computer literacy (Word, Excel, Power Point)

- Very good command of English (oral and written)

- Experience in the field of air quality and emission

- Wide knowledge of related EC legislation

- Appropriate university qualification in environmental sciences or other

related disciplines

RTA assistant (24 working months) – contracted by CFCU

Tasks:

- Assisting the RTA and project experts in project implementation, production of project reports and preparation of meetings, workshops and training courses

- Liaison between project experts and local authorities as well as NGO-s

- Assisting in preparation and translation of project documents and reports from

English to Turkish and from Turkish to English

- Editing of project documents

Profile:

- Very good computer literacy (Word, Excel, Power Point)

- Excellent English and Turkish (oral and written)

- Translation, editing and interpretation experience

- Good communication and organization skills

- Full  university degree-

MS Project Leader (24 working days in Turkey over 24 consecutive months)

Tasks:

- Overall co-ordination of the project;

- Leading the project activities.

Profile:

- Long-term civil servant from an EU Member State administration;

- Educated and experienced in the field of management and organization

- At least 3 years working experience in a leading management

- Very good command of English (oral and written)

- Excellent computer skills (Word, Excel)

STE 1: Institutions and Legal Analyses ( 132 man days-indicative )

Tasks:

- Analysis of the tasks and responsibility areas assigned to competent authorities (Ministry of the Environment  , Ministry of  Energy and Natural Resources , Turkish Statistical Institute and the institutions in their field of governance

- Identification of missing/weak links in institutional set-up

- Elaboration of clear distribution of functions, development of information exchange systems, cooperation schemes and action plans between different parties responsible for air quality management, development of relevant guidelines

- Charting of obligations arising from relevant international treaties and EC legislation

- Assessment of current inspection system for emission and preparation of recommendations for optimum set up of joint inspection schemes

- Assessment of current measurement systems for air quality and preparation of recommendations for optimum set up

- Assessment of the capacity and preparedness of relevant public authorities to handle air quality and emission problems (location, experts, contracts)

- Preparation and publication of Task Report 1

Profile:

- Experience in assessing the set-up of public and technical administration and management

- Wide knowledge of EC legislation

- Excellent computer skills (Word, Excel)

- Very good command of English (oral and written)

STE 2: Emission data base ( 110 man days- indicative)

Tasks:

- Analysis of existing emission data bases

- Review on different sources and capacities

- Assistance in the preparation of Technical specifications for Supply Tender

- Coordination of the work from private sector input (preparing data for the emission file, creating the emission data base using the soft- and hardware from the investment including the training for both)

- Making suggestions for improving the collection of the data and the update of the newly created data base

- Preparation of Task Report 2

Profile:

- Excellent computer skills (Word, Excel, Power Point)

- Very good command of English (oral and written)

- Proven knowledge of building up emission data bases

- Wide knowledge of relevant EC legislation

- University degree in technical sciences or other environmental related subjects

STE 3: Models (110 man days-indicative )

Tasks:

- Analysis of existing data bases for air dispersion models

- Review on different sources and capacities

- Assistance in the preparation of Technical specifications for Supply Tender

- Assistance in the buildup of a basic wind field data base; Assistance in the preparation of Technical specifications for Supply Tender

- Coordination of the work from private sector input (preparing input data for the modeling, creating the model results using the soft- and hardware from the investment including the training for both)

- Making suggestions for improving the collection of the input data and the update of the model results

- Preparation of Task Report 4

Profile:

- Excellent computer skills (Word, Excel, Power Point)

- Very good command of English (oral and written)

- Proven knowledge of building up modeling capacities

- Wide knowledge of relevant EC legislation

- University degree in technical sciences or other environmental related subjects

STE 4: Human Resources and Training ( 132 man day -indicative)

Tasks:

- Assessment of human resources

- Provision of recommendations for optimisation of human resources

- Training on technical running of a network, on instruments, on reporting, on clean air plans, on action plans etc.

- Site visits to monitoring sites

- Preparation and conduct of a study tour to 1 EU country to get a strong personal touch with the arrangement of air quality management in EU Member States. The study will focus on giving extra expertises to the key personnel in air quality management, getting to know the systems established in other member states

- Preparation of recommendations for follow up training system

- Preparation of Task Report 5

Profile:

- Excellent computer skills (Word, Excel, Power Point)

- Very good command of English (oral and written)

- Experience in organizing similar training courses

- University degree or other relevant education

STE 5 . Public information (44 man day –indicative )

Tasks:

- Assessment of current public information schemes (regional/national level)

- Provision of a optimum mechanisms and schemes for public information

- Elaboration of a detailed systems describing the mechanisms for

different target groups for action plans, clean air plans and regular information on air pollution

- Elaboration of Task Report 8

Profile

- Excellent computer skills (Word, Excel, Power Point)

- Very good command of English (oral and written)

- Knowledge of implementing similar public information systems in other Member States

- University degree

DETAILS OF TASKS EXPECTED FROM TECHNICAL ASSISTANCE CONTRACTOR:

Tasks:

-Preparation of a comprehensive emission inventory meeting the quality and resolution standards of the NECD

- Preparation of cost benefit analysis

-Preparation of Regulatory Impact Assessment Report

-Make use of Corinair Methodology and tools

-Data collection and compilation (from n various sources)

-Communication and cooperation with data sources and related institutions

-Bring data and the inventory into acceptable NECD format and standard.

-Manage a team of experts to fulfil the contract requirements.

Project Fiche – decentralised

Indicative Budget (amounts in EUR)

|  |  |  |  |  | SOURCES OF FUNDING |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | TOTAL EXP.RE | TOTAL PUBLIC EXP.RE | IPA COMMUNITY CONTRIBUTION |  | NATIONAL PUBLIC CONTRIBUTION |  |  |  |  | PRIVATE CONTRIBUTION |  |
| ACTIVITIES | IB (1) | INV (1) | EUR (a)=(b)+(e) | EUR (b)=(c)+(d) | EUR (c) | % (2) | Total EUR (d)=(x)+(y)+(z) | % (2) | Central EUR (x) | Regional/ Local EUR (y) | IFIs EUR (z) | EUR (e) | % (3) |
| Activity 1 | X |  | 308,800 | 308,800 | 293,360 |  | 15,440 |  | 15,440 |  |  |  |  |
| contract 1.1 | – | – | 308,800 | 308,800 | 293,360 | 95 | 15,440 | 5 | 15,440 | - | - | - | – |
| contract 1.2 | – | – | - | - | - |  | - |  | - | - | - | - | – |
| Activity 2 | X |  | 656,800 | 656,800 | 603,310 |  | 53,490 |  | 53,490 | - |  |  |  |
| contract 2.1 | – | – | 243,800 | 243,800 | 231,600 | 95 | 12,190 | 5 | 12,190 | - | - | - | – |
| contract 2.2 | – | – | 413,000 | 413,000 | 371,700 | 90 | 41,300 | 10 | 41,300 | - | - | - | – |
| Activity 3 | X |  | 250,000 | 250,000 | 225,000 |  | 25,000 |  | 25,000 |  |  |  |  |
| contract 3.1 | – | – | 250,000 | 250,000 | 225,000 | 90 | 25,000 | 10 | 25,000 | - | - | - | – |
| contract 3.2 | – | – | - | - | - |  | - |  | - | - | - | - | – |
| Activity 4 | X |  | 583,000 | 583,000 | 549,500 |  | 33,500 |  | 33,500 |  |  |  |  |
| contract 4.1 | – | – | 496,000 | 496,000 | 471,200 | 95 | 24,800 | 5 | 24,800 | - | - | - | – |
| contract 4.2 | – | – | 87,000 | 87,000 | 78,300 | 90 | 8,700 | 10 | 8,700 | - | - | - | – |
| Activity 5 | X |  | 251,400 | 251,400 | 238,800 |  | 12,570 |  | 12,570 | - | - | - |  |
| contract 5.1 | – | – | 251,400 | 251,400 | 238,800 | 95 | 12,570 | 5 | 12,570 | - | - | - | – |
| contract 5.2 | – | – |  |  |  |  |  |  |  |  |  |  | – |
| TOTAL IB |  |  | 2,050,000 |  |  |  |  |  |  |  |  |  |  |
| TOTAL INV |  |  | - |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT |  |  | 2,050,000 |  |  |  |  |  |  |  |  |  |  |

NOTE: DO NOT MIX IB AND INV IN THE SAME ACTIVITY ROW. USE SEPARATE ROW

Amounts net of VAT

(1)	In the Activity row use "X" to identify whether IB or INV

(2)	Expressed in % of the Public Expenditure (column (b))

(3) 	Expressed in % of the Total Expenditure (column (a))

I