- Twinning Number: TR 08 IB EN 01

Environment and Countryside under IPARD

- Note for the information of future Twinning partners:

- Please note that this fiche concerns 2 different activities, of which one takes the form of a Twinning (activity 1, see paragraph 3.4)

- The indicative budget for the Twinning component of activity 1 is € 1.0 million (see paragraph 4)

- The indicative duration of the Twinning project is 15 months (see paragraph 5)

- Please see Annex V on page 25 for further details on the Twinning component

- Standard Summary Project Fiche – IPA decentralised National programmes

1. Basic information

1.1   CRIS Number: TR080201

1.2   Title:  Environment and Countryside under IPARD

1.3   Sector: 11

1.4   Location: Turkey

Implementing arrangements:

1.5   Implementing Agency:

The CFCU will be Implementing Agency and will be responsible for all procedural aspects of the tendering process, contracting matters and financial management, including payment of project activities. The director of the CFCU will act as Programme Authorizing Officer (PAO) of the project.

Mr. Muhsin ALTUN (PAO-CFCU Director)

Central Finance and Contracting Unit

Tel:  +90 312 295 49 00

Fax: +90 312 286 70 72

E-mail: muhsin.altun@cfcu.gov.tr

Address: Eskişehir Yolu 4.Km. 2.Cadde (Halkbank Kampüsü) No:63 C-Blok 06580  Söğütözü/Ankara Türkiye

  - Beneficiary (including details of SPO):

Main Beneficiary: Ministry of Agriculture and Rural Affairs (MARA)

Candidate for the Senior Programme Officer of the Project: Mr. Enver AKSOY

Head of Internal Control Department

Strategy Development Board (Managing Authority)

Eskişehir Yolu. 9.km Lodumlu/ANKARA

Tel: +90 312 286 58 76

Fax: +90 312 285 69 40

E-Posta: enver.aksoy@tarim.gov.tr

Co-Beneficiary: Agriculture and Rural Development Support Institute (IPARD Agency)

Mr. Mevlüt ÖZEN

Eskişehir Yolu. 9 Km. Lodumlu /ANKARA

Contact: Mevlüt ÖZEN

Tel : + 90 312 285 35 80 / 2354

Fax: + 90 312 287 67 83

e.posta: mevlut.ozen@tarim.gov.tr

Eskişehir Yolu 9.km Lodumlu Ankara / Turkey

1.7   Overall cost: EUR 1, 140,000

1.8   EU contribution: EUR 1, 055,000

1.9   Final date for contracting: 2 years after the signature of the Financing Agreement

1.10 Final date for execution of contracts: 2 years following the end date for contracting

1.11 Final date for disbursements: 3 years following the end date for contracting.

2.   Overall Objective and Project Purpose

2.1 Overall Objective:

Strengthening the institutional capacity for alignment to EU Rural Development Policy.

2.2 Project purpose:

Institutional capacity building to implement preparatory actions for pilot agri-environmental measures under IPARD.

2.3 Link with AP/NPAA/EP/SAA

In 2005 Accession Partnership Document for Agriculture and Rural Development Chapter, it is stated as short term priority to

— To adopt the necessary legislative measures and set up suitable administrative structures to operate EU instruments related to rural development.

The IPARD funds will contribute to the   rural development by a set  of measures envisaged to be implemented in  IPARD Programme.  The envisaged measures includes the agri-environmental measures to be implemented in the second phase of  IPARD Programme (2010-2013)  which  are  also considered with importance in EU Member States’ Rural Development Programs.  In this regard, the implementation of agri-environmental measures in Turkey will help the adoption of the necessary legislative measures and set-up administrative structure to operate EU rural development instruments regarding agri-environmental applications.

The 2003 NPAA points out in Chapter 7.4 Preparation of a National Rural Development and Forestry Strategy;

The short term priority as; the preparation of a strategy for the introduction of the EC rural development policy and forestry strategy

The medium priority as, the setting up the administrative structures required for the implementation of EC rural development policy.

In this framework, the Rural Development Strategy was prepared and adopted by the High Planning Council Decision dated 25 January 2006. The strategy identifies the priorities of Turkey for   development of rural areas with regard to national policies and EU pre-accession works.  One of the priorities in the Strategy is the “Protection and improvement of rural environment including environmental friendly agricultural practices, protection of forest eco-systems and improvement of protected areas”. The implementation of environment related measures in the IPARD (which considers also NRDS priorities)   will contribute to the implementation of the EC rural development policy regarding the Axis 2 measures including the environment and land management measures.

In 2007 Accession Partnership Document for Agriculture and Rural Development it is stated as medium-term priority to;

- start  preparing the implementation of pilot  actions relating to environment and the countryside, in view of future implementation of agri-environmental measures.

In line with this priority, the preparation  for the implementation of  pilot actions relating to environment and countryside should be started.

2.4 Link with MIPD

In relation to axis 2 interventions of IPARD (one of the Axis 2 interventions is the preparatory actions for the implementation of agri-environmental measures), the MIPD (2007-2009) states that the capacity building for the preparation of the implementation of agri-environment measures will take considerable time. In this line the MIPD points out that; the actions regarding the implementation of this area should only be in the medium to long term and to be carried  out by preparatory actions.  Although a financial allocation is not indicated in the MIPD, it is stated   that  a financial allocation to preparatory actions  should as a consequence only be envisaged at a later stage. The MIPD emphasises that “the capacity building for this area to be supported under component I should start as soon as possible.”

As mentioned in the MIPD, one of the major areas of the IPARD intervention will be to take the form of preparatory actions for the implementation of agri-environmental measures and the potential key issue under this priority is the preparation for the implementation of actions designed to protect the environment and maintain the countryside.

2.5  Link with National Development Plan (where applicable)

In the Ninth Development Plan, the objectives and actions regarding the protection of the environment is defined under development axes “Increasing Competitiveness” as an action “Protecting the environment and improving the urban infrastructure”.

The objective of the action is to protect and utilize the natural resources by taking the needs of the future generations into consideration.

The strategy is to develop and extend production processes and technologies, which are productive and environmentally friendly, in order to increase the competitiveness and to ensure sustainable development in the context of directing consumer preferences to environmentally friendly goods and services.

The Plan points out that the agricultural, environmental and technological policies will be assessed in an integrated manner in order to minimize the risks related to bio-security and genetically modified organisms.

The Plan highlights the agriculture and tourism as the sensitive sectors to environment and the utilization of ecological potential by considering the protection-utilization balance.

2.6 Link with national/ sectoral investment plans(where applicable)

- The IPARD Programme of Republic of Turkey (2007-2013) was adopted by the Rural Development Committee on 19 December 2007 and the decision was approved by the Commission on 25 February 2008.  The measure “Actions to improve the environment and the countryside”  will be implemented in the second phase of the Programme (2010-2013).  In the Programme it is highlighted that; “The  implementation of actions relating to environment and countryside is planned to get started in the second phase of the programme (2010 – 2013) subsequent to an intensive prior capacity-building process. For this reason the measure currently represents only the basic approach and  a broad description of the concept which is to be followed  with  regard to the  measure without details. Pilot project areas and details of the actions will be designed, once the capacity-building process for this measure has taken place and the details of the measure have been elaborated”.

- In the IPARD Programme,   the implementation of actions relating to environment and countryside is planned to get started in the second phase of the programme (2010 – 2013) subsequent to an intensive prior capacity-building process. For this reason, in the Programme, the measure currently represents only the  basic approach and  a broad description of the concept which is to be followed  with  regard to the  measure without details.

Pilot project areas and details of the actions will be designed, once the capacity-building process for this measure has taken place and the details of the measure have been elaborated.

In line with the priorities of the Programme, this project will contribute to the setting up the legal, administrative and technical structures and capacity building for the implementation of actions relating to environment and the countryside envisaged to be implemented in the Second Phase of the IPARD Programme (2010-2013).

- Description of project

3.1 Background and justification:

In parallel with the recent developments in the agricultural technologies in Turkey, agricultural production has evolved into one aiming more yields per area of land by using more chemical fertilizers and pesticides as well as higher technology. Consequently, problems arising from agricultural activities and agriculture-environment interactions are faced. One of the results caused by these interactions is the pollution of water resources due to unconscious usage of chemical fertilizers and pesticides.

Erosion is among the most important environmental problems that Turkey is faced with. One of the factors causing erosion is the inappropriate agricultural practices. Moreover, the mismanagement of pasture lands by overgrazing has resulted in a reduction in the quality and quantity of the pastures which also results in erosion.

Regarding livestock production, irregular grazing (heavy, early, uncontrolled etc), especially on the hillsides, and cultivation are the major reasons of degradation of the rangelands. Overgrazing causes destruction of the botanical composition of the natural vegetation and also decreases rangeland efficiency leading to erosion.

Agriculture is  one of the important adverse effects of human influence to the biodiversity, Factors like inappropriate use of agricultural lands, use of chemicals and fertilizers adversely affect the biodiversity. During agricultural activities stubble burning or burning of weeds especially cause the extinction of the invertebrates. Besides, biological efficacy and activities are in a decreasing trend in the wetlands of whose water is to be used for irrigation purposes of agricultural lands. Another point to consider is that the increased use of chemical fertilizer and pesticides deteriorates the biodiversity.

The SWOT analysis of the Country with regard to agri-environmental issues is presented below table.

- Table 1. SWOT analysis for agri-environment sector

| Strengths | Weaknesses |
| --- | --- |
| Availability of agricultural land for a sustainable development. | Soil degradation due to different degrees of erosion. |
| Approximately 80% of farming is extensive, rainfed with low use of fertilizers and chemicals. | Waste of irrigation water. |
| Organic farming implemented since 1980s. Increasing domestic demand for organic products. | Moderate pollution of water in some areas of intensive farming. |
| Low pollution of soils, surface water and underground water. | Forest degradation. |
| Rich biodiversity of ecosystems and species | Loss of biodiversity through destruction of ecosystems, illegal hunting, fishing and inappropriate farming management |
| Important Nature Conservation areas. Among them 200 wetlands of international importance. | Inefficient protection of prime quality farm land, from urban and tourism pressure. |
| Many local crop varieties and indigenous farm animal breeds. | Small farms with split plots |
| Relatively young farmer population, more capable to understand and adopt environmental issues. | Low educational and vocational level of farmers. |
| Adoption and ratification by the government and the administration of all international conventions on environment and biodiversity. | Weak administrative structures and lack of experience to manage agri-environmental issues. |
| Action plans for combating erosion and protecting biodiversity. | Ineffective coordination between public, private and civil society institutions. |
| Legislation for organic farming similar to Council Regulation (EC) 2092/91 | Inadequacy of data needed to analyse environmental situation in rural areas. |
| Determination and designation of Natura 2000 sites and Nitrate vulnerable zones in progress. |  |
| Opportunities | Threats |
| Development of consumer awareness and increased demand for healthy, quality products. | Uncontrolled increase of the population. |
| Increasing interest in preserving and developing environment. | Abandonment of remote mountain areas with negative impact on landscape, biodiversity and land management. |
| Increasing demand for agri-environmental services from the tourist sector (maintenance of landscapes, ecotourism etc.). | Concentration of the population in the lowlands, coastal zones, urban areas with an accompanying pressure on the natural resources of these areas. |
| EU accession process and implementation of community acquis | Severe and irreversible soil erosion. |
| Access to international resources – funds | Scarcity of available water resources in the future. |
|  | Sealing of prime farm land in peri-urban and tourist zones. |

In line with the environmental issues rising in the recent years, the concern given to agri-environmental issues has been increased recently. There is a project called Protecting Agriculture Lands for Environmental Purposes (ÇATAK)   has been implemented on a pilot scale since 2005.

The regulation for voluntary good agricultural practices (Turkish code of good agricultural practices) was put into effect in 2004 which defines the criteria for good agricultural practices.

Agri-environmental payments are targeted to support the sustainable development of rural areas and to respond to society’s increasing demand for environmental services. The payments granted should encourage farmers and other land managers to serve society as a whole by introducing or continuing to apply agricultural production methods compatible with the protection and improvement of the environment, the landscape and its features, natural resources, the soil and genetic diversity.

The IPARD Programme which was adopted by the Rural Development Committee on 19 December 2007 and officially approved on 25 February 2008 includes pilot agri-environmental measures. The target is to contribute to the sustainable development of rural areas. By this way, the agri-environmental actions for the protection and improvement of the environment will be encouraged.

The planning of the implementation of agri-environmental measure is made in phase 2 (2010 – 2013) of IPARD. Because there needs to be established the necessary legal and procedural framework as well as the calculations in place and the needed administrative capacity building.

In the IPARD Programme the technical fiche of the agri-environmental measures are in the form of an outline. The technical fiche needs to be finalised with the capacity building by this project and the implementation to solve the  environmental problems of the selected areas (which will be determined during the finalisation of the  technical fiche)  will be carried out  by pilot actions. Consequently the strengthening of the administrative capacity is necessary to start and implement the agri-environmental measures. The project will provide the capacity building and will support the preparations of the Managing Authority and IPARD Agency for the implementation of the agri-environmental measures under IPARD Programme.

The agri-environmental supports will be paid  annually  after  the establishment of the amounts of payments which are based on;

- - Additional costs due to the commitment

- - Income forgone due to the commitment

- - Where necessary, they may also cover transaction costs.

- There is no capacity in the MA nor the IPARD Agency  on the amounts of the payments under the agri-environmental measures. The project will support on the establishment of the amounts of payments and elaborate the formula for the payments to beneficiaries. There is need to see the system for the calculations of the Member States  by visiting the institutions involved and their system  on these calculations.

The accreditation studies of the Managing Authority and the IPARD Agency has been carried  out for the measures  to be implemented in the first phase  (2007-2009) of the IPARD Programme. The agri-environmental measures are to be implemented in the second phase of the IPARD Programme, hence, there  needs to prepare  the accreditation preparations for the  agri-environmental  measures and to get the conferral of management decision from  the EC to  start implementation. The project will also support the accreditation process.

An IT system for the IPARD Agency is now under construction with the support of the project called              “Establishment of IPA Rural Development Agency (TR 050305)”.  The preparation of technical specifications of the software for implementation, payment, reporting and monitoring procedures of the Agency is under preparation. The software  that is under the preparation for the Agency, will  be used for the management of the Axis 1 and Axis 3 measures that were identified in the IPARD Programme (the measures to be implemented in the first phase 2007-2009).

Since the agri-environmental measures is planned to be implemented in the second phase of IPARD (2010-2013)   there will be needs for the improvement of the IT system of the Agency in that date and revision of the existing software. But it is important to make a comprehensive needs analysis, feasibility study and market study of the IT system required to manage and implement the agri-environmental measures. For this reason the project will also help for the identification of the needs for the IPARD Agency IT system.

3.2 Assessment of project impact, catalytic effect, sustainability and cross border impact (where applicable)

Project impact:

The project will provide the implementation of the agri-environmental measures and the harmonization with the EU rural development policy.

Catalytic Effect:

This project will contribute sound implementation of agri-environmental measures of IPARD. In this context it will provide the   structure necessary for the utilization of EU pre-accession assistance in the context of rural development.

Sustainability:

The IPARD Agency will start for the implementation of the agri-environmental measures under the  IPARD programme.

Managing Authority and IPARD Agency staff will have the necessary capacity for the implementation of  agri-environmental measure. With this project,  they will use the knowledge and skills  and also disseminate the information by means of meetings and seminars both in central and local level with regard to the agri-environmental measures.

Cross border impact: N/A

3.3 Results and measurable indicators:

Result 1. The Managing Authority and the IPARD Agency institutional capacities are ready for the implementation of the IPARD agri-environmental measures.

Measurable indicators of Result 1;

-The detailed measure fiche (finalised version) for inclusion in the IPARD Programme is ready by the second quarter of the project.

- Determined needs  (market analysis and feasibility study) for the improvement of IT system (and supporting elements) of the IPARD Agency by the third quarter of the project.

- The measure accreditation packages of Managing Authority and IPARD Agency  are ready   by the end of the project.

Result 2.   Strengthened institutional capacity of Managing Authority and IPARD Agency for the implementation of agri-environmental measures under IPARD.

Measurable indicators of Result 2;

-  Trained 30  staff of Managing Authority and IPARD Agency on the agri-environmental measures under IPARD for 21 working days by the third quarter of the project.

-  Self-assessment of IPARD Agency completed by the end of the project.

Result 3.  Raised awareness of related institutions and public on preparation and implementation of agri-environmental measures under IPARD.

Measurable indicators of Result 3;

-  Five workshops organized for raising the knowledge and awareness  about  the mandatory standards of agri-environmental measures and implementation procedures of the agri-environmental  measure for the central and local environmental public authorities, related NGOs and related stakeholders including farmers for 300 people in total by the fourth quarter of the project.

- 10 Meetings with central and local stakeholders, public authorities and NGOs on local areas organized in the fourth quarter of the   project.

3.4 Activities:

The project will be achieved by two activities; Twinning and technical assistance which will be carried out a comprehensive needs analysis for the IT system of the IPARD Agency.

- National co-financing source: The co-financing funding of the activities will be covered by the budget of MARA.

Activity 1: Twinning Project

- Within this activity, the institutional capacity of Managing Authority and the IPARD Agency will be strengthened in order to start for the implementation of preparatory actions for pilot agri-environmental measures  under IPARD.

- The activity consists of the following items;

- - The legal and institutional framework with regard to agri-environmental measures will be assessed and the required legislation and institutional arrangements will be identified.

- - The Turkish situation with regard to agri-environmental implementations in the Country will be evaluated in details and strengths and weaknesses   for the agri-environmental measure will be assessed to review the strategy of the measure.

- - The current guide of good agricultural practices will be assessed in parallel with the analysis of EU Member States experience and the changing needs of the legislation with minimum requirements will be determined. The Turkish Regulation on Good Agricultural Practices will be revised in terms of its compatibility with EU baseline for agri-environmental payments.

- -  The additionally required legislation on obligatory mandatory standards will be prepared

- -  The contacts will be established with the scientific institutes for the establishment of the amounts of payments for the selected actions.  The amounts of the payments for the measure will be established.

- - The pilot zones/sites   for the agri-environmental measures will be determined and the financial tables will be included for the measure and sub-measures.

- - The monitoring and evaluation indicators as well as baseline indicators (in line with Common Monitoring and Evaluation Framework)   will be elaborated.

- - The detailed measure fiche and sub-measure fiches for inclusion in the IPARD Programme will be prepared.

- -The accreditation package (preparation of project application forms,  guidelines and implementation manuals, operational manuals, sample grant contract, on the spot control principles etc…) for the implementation of the  measure will be prepared.

- - The training needs will be assessed and a training Plan will be prepared for the necessary training needs in order to establish the capacity of Managing Authority and IPARD Agency  staff as well as the related institutions (Ministry of Environment and Forestry)  on the agri-environmental measures   of the IPARD.

- - 30 staff of Managing Authority and IPARD Agency on the agri-environmental measures    under IPARD (EU legislation, agri-environmental measures programming and technical-fiche design, establishment of monitoring and evaluation indicators, establishment of the amounts of payments, implementation procedures, monitoring and evaluation procedures as well as on the training needs identified in the training plan) will be trained.

- - 20 project advisers will be trained on agri-environmental actions involved to help farmers to select suitable actions.

-  A Communication Strategy will be prepared for the publicity activities of the measure.

- - The awareness of the central and local public environmental authorities, related NGOs and related stakeholders including farmers on the mandatory standards and implementation procedures of the IPARD agri-environmental measure   will be raised by workshops and meetings.

- - Internship and study visits will be organised to EU Member States in order to see their implementation in their institutions and at local areas. Since the implementation of agri-environmental measures of the EU logic will be newly introduced and the capacity is low in Turkey, the study visits and particularly the internship will be critical to get the information and see the   implementation practices of the agri-environmental measures on site.  The agri-environmental measures are difficult to implement since, they are area based. For this reason, it is needed to see    the institutional and practical studies of the agri-environmental measure implemented countries (especially in experienced institutions with regard to IT system usage and on the spot controls).  With the capacity established under the project, the support has been taken for the preparation for accreditation of the measure   as well as the elaboration of the procedures guides for the operational management of agri-environmental measures.

- -The leaflets and manuals for the public awareness of the measure will be prepared.

- Activity 2: Technical Assistance

The inclusion of TA activity in the project can support the coordination with the Twinning Project. By this way, the tendering and contracting of TA activity can be in sequence with the Twinning activity.

The analysis of the available IT system of the IPARD Agency and the identification of the needs of the IT system to implement and monitor the agri-environmental measures will be carried out.

By this project, a comprehensive needs analysis of the IPARD Agency will be performed in order to improve the available IT system of the IPARD Agency for the implementation of the agri-environmental measures.  Moreover, the feasibility study and market survey of the needed investment will be carried out.

By this contract the technical specifications for the supply to improve the IT system of the Agency will be prepared.

3.5 Conditionality and sequencing:

Precondition: The tender for this project can be launched on the condition that, by submitting a formal Declaration of Assurance, showing that the beneficiary has sufficient staff in a list for technical implementation and monitoring of the contracts.

- The start for the implementation (conferral of management decision) of the  IPARD measures (the measures determined for the  first phase 2007-2009) and already established capacity for IPARD.

- The technical assistance project will start following the finalisation of the technical fiche for agri-environmental measures under the Twinning Project.

3.6 Linked activities

Some of the linked activities that have been carried out in Turkey are summarized below:

3.6.1. Environmentally Based Agricultural Land Protection Programme (ÇATAK)

The Environmentally Based Agricultural Land Protection Programme (ÇATAK) has been put into effect in 2005 as one of the components of the World Bank supported Agricultural Reform Implementation Project (ARIP).  The aim of the scheme is to reduce adverse effects of agricultural practices on environment, to prevent erosion, to sustain renewable natural resources, to protect the natural cover and the quality of soil and water in the vulnerable areas. (See Annex  6 for details)

Link with the Project: The ÇATAK project activities will be analysed and the coherence and overlaps with the IPARD will be determined. After the evaluation of the ÇATAK project,  the strategy of IPARD will be concluded.

3.6.2. Anatolia Watershed Rehabilitation Project

The aim of the project is to provide the management of natural resources and participatory planning by adoption of environment-friendly agricultural and forestry activities and by increasing institutional capacity and public awareness. (See Annex 6 for details)

Link with the Project: The Anatolia Watershed Rehabilitation Project activities will be analysed and the coherence and overlaps with the IPARD will be determined. After the evaluation of the ÇATAK project, the strategy of IPARD will be concluded.   Moreover, the capacity built with the project will be used.

3.6.3. Preparation for the Implementation of the EU Common Agricultural Policy (TR 04.02.08)

The Project of the Preparations for the Implementation of EU Common Agricultural Policy (TR 0402.08) consists of   two sub-projects. The project was completed in 2007.

Project 1: Designing a functioning Integrated Administration and Control System (IACS) and Land Parcel Identification System in Turkey

Project 2: Support for Preparation of Rural Development Plan and Strengthening Institutional Capacity for implementation of the Plan

Link with the Project:  The institutional capacity of MARA and other related institutions was strengthened for implementation of the IPARD Programme and the IPARD Programme was prepared with the Sub-project 2 of the project.

3.6.4. Establishment of IPA Rural Development Agency (TR 05 03 05);

The Project was started in 2007 and aims to support the establishment of an IPA Rural Development Agency and strengthen its administrative capacity to implement the IPARD programme. The Project consists of Technical Assistance, Twinning and investment support (IT and office equipments).

In the Technical assistance; the technical specifications and tender dossiers for the IT system and office equipment of the Agency was prepared.

In the Twinning Project: The project started in March 2007 and will be implemented for 19 months. The project supports the accreditation works of the Agency particularly to start to implement (conferral of management decision) the measures envisaged to be implemented in the first phase of the IPARD programme (2007-2009). Moreover, it supports the training of the staff of the Agency.

In the Supply component: The IT system (software and hardware) will   be established in order to implement the IPARD measures. Moreover the office equipment of the Agency will be purchased.

Link with the Project: The IPARD Agency project will establish a functional IPA Rural Development Agency and strengthen its capacity for the implementation of the IPARD measures. The Law for the establishment of the Agriculture and Rural Development Support Institute (IPARD Agency) was adopted in 2007 by the Turkish Parliament. The accreditation works of the Agency has been accelerated and the Project supports the first accreditation package of the IPARD Programme with particular emphasis for the measures to be implemented in the first phase of the IPARD Programme (2007-2009).  The Agency project will contribute to the project with the capacity developed for the accreditation works.

3.6.4. The Development of the Sustainable Pasture Management Methods in the Central Anatolian Region of Turkey (MATRA Pre-accession Projects Programme)

The objectives of the project are to diagnose the current pasture situation; vegetation and utilization patterns, to assess the pasture conditions and to map the vegetation, to develop sustainable pasture management models, conforming to the environmental concerns, to assess the position of land users in financial terms and to prepare a strategy on the national level.

The project   started in January 2008 and will be implemented in two pilot provinces (Kırıkkale and Sivas)  for one year.

Link with the Project: The experience gained and the capacity developed in this project will be used for the identification of the strategy for the IPARD agri-environmental measure.

3.7 Lessons learned

The EU funded Projects managed and completed previously by the Strategy Development Board   are;

- Twinning Project called ”Strengthening the Administrative Capacity for the effective Implementation of the Rural Development Plan TR/2004/IB/AG/01  and

- Technical assistance for the “Preparation of Rural Development Plan”.

The rural development programming process started with the Twinning Project TR/2004/IB/AG/01.   The twinning project has given a further push and accelerated the rural development process. The difficulty at the start of the project was the fair coordination and communication between the project partners. But with the implementation of the project, it was experienced how to make successful coordination and communication.

At the beginning the Strategy Development Board of MARA which was not familiar with the EU funded project preparation and  management has gained experience. Moreover, the Project has enabled the Strategy Development Board to learn the basic information with regard to   institutional and legal framework  of IPARD.

By the  technical assistance project,   MARA, not being very familiar with EU-TA  type projects, gained experience in this field as well as the effective coordination between the related institutions.  Moreover, the project  gave the substantial experience in IPARD Programming.

4. Indicative Budget  (amounts in EUR)

|  |  |  |  |  | SOURCES OF FUNDING |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | TOTAL EXP.RE | TOTAL PUBLIC EXP.RE | IPA COMMUNITY CONTRIBUTION |  | NATIONAL PUBLIC CONTRIBUTION |  |  |  |  | PRIVATE CONTRIBUTION |  |
| ACTIVITIES | IB (1) | INV (1) | EUR (a)= (b)+(e) | EUR (b)=(c)+(d) | EUR (c) | % (2) | Total EUR (d)= (x)+(y)+(z) | % (2) | Central EUR (x) | Regional/ Local EUR (y) | IFIs EUR (z) | EUR (e) | % (3) |
| Activity 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Twining | X | – | 1,000,000 | 1,000,000 | 950,000 | 95 | 50,000 | 5 | 50,000 | - | - | – | – |
| Activity 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TA for supply |  | X | 140,000 | 140,000 | 105,000 | 75 | 35,000 | 25 | 35,000 | - | - | – | – |
| …… |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL IB |  |  | 1,000,000 | 1,000,000 | 950,000 | 95 | 50,000 | 5 | 50,000 | - | - | – | – |
| TOTAL INV |  |  | 140,000 | 140,000 | 105,000 | 75 | 35,000 | 25 | 35,000 |  |  | – | – |
| TOTAL PROJECT |  |  | 1,140,000 | 1,140,000 | 1,055,000 | 92.5 | 85,000 | 7.5 | 85,000 |  |  |  |  |

NOTE: DO NOT MIX IB AND INV IN THE SAME ACTIVITY ROW. USE SEPARATE ROW    Amounts net of VAT

(1)	In the Activity row use "X" to identify whether IB or INV

(2)	Expressed in % of the Public Expenditure (column (b))

(3) Expressed in % of the Total Expenditure (column (a))

5. Indicative Implementation Schedule (periods broken down per quarter)

| Contracts | Start of Tendering | Signature of contract | Contract Completion |
| --- | --- | --- | --- |
| Twinning Contract | 1st quarter 2009 | 4th quarter 2009 | 4th quarter 2010 |
| TA | 4th quarter 2009 | 2nd quarter 2010 | 3rd quarter 2010 |

Duration of the project :  12 months

All projects should in principle be ready for tendering in the 1ST Quarter following the signature of the FA.

6. Cross cutting issues (where applicable)

6.1	Equal Opportunity

Equal opportunity between men and women will strictly be respected.

6.2	Environment

The project itself serves for the protection of the environment. By the end of the project, both public servants, personnel from relevant NGOs and some farmers will gain awareness and sense about the environment and the effect of agricultural activities on environment.

During the project, all environmental aspects will be respected.

  - Minority and vulnerable groups

According to the Turkish Constitutional System, the word minorities
encompasses only groups of persons defined and recognized as such on the
basis of multilateral or bilateral instruments to which Turkey is a party.
This project has no negative impact on minority and vulnerable groups.

The project will apply the policy of equal opportunities   for all groups including the vulnerable groups.

- ANNEXES

1-	Log frame in Standard Format

2-	Amounts contracted and Disbursed per Quarter over the full duration of Programme

3- 	Institutional Framework

* Role and responsibilities of the SPO

* frequency of project management meetings,

* who chairs, who attends and in what role

* coordination mechanisms for multi-beneficiary projects

*  monitoring (roles, responsibilities of all actors)

- 4 -	Reference to laws, regulations and strategic documents:

Reference list of relevant laws and regulations

Reference to AP /NPAA / EP / SAA

Reference to MIPD

Reference to National Development Plan

Reference to national / sector investment plans

5-	Details per EU funded contract (*) where applicable:

For TA contracts: account of tasks expected from the contractor

For twinning contracts:  account of tasks expected from the team leader, 	resident twinning advisor and short term experts

For grants schemes:  account of components of the schemes

For investment contracts: reference list of feasibility study as well as technical specifications and cost price schedule + section to be filled in on investment criteria (**)

For works contracts: reference list of feasibility study for the constructing works part of the contract as well as a section on investment criteria (**); account of services to be carried out for the service part of the contract

(*) non standard aspects (in case of derogation to PRAG) 	also to be specified

(**) section on investment criteria (applicable to all infrastructure contracts and constructing works):

- Rate of return

- Co financing

- compliance with state aids provisions

  - Ownership of assets (current and after project completion)

ANNEX 1: LOGICAL FRAMEWORK MATRIX IN STANDARD FORMAT

| ###### LOGFRAME PLANNING MATRIX FOR Project Fiche |  | Programme name and number | Environment and Countryside under IPARD- TR080201 |
| --- | --- | --- | --- |
|  |  | Contracting period expires: 2 years after the signature of the Financing Agreement | Disbursement period expires: 3 years following the end date for contracting. |
|  |  | Total budget : EUR 1,140,000 | IPA Budget: EUR 1,055,000 |
| Overall objective | Objectively verifiable indicators | Sources of Verification |  |
| - 1. Strengthening the institutional capacity for alignment to Rural Development Policy. | 1.1. Turkish institutions can carry out the rural development policy of EU with the membership 1.2. Positive assessment for the alignment to rural development policy of EU in the Country Progress Report in 2010. | - Country Progress Reports - Annual reports of IPARD Programme |  |
| Project purpose | Objectively verifiable indicators | Sources of Verification | Assumptions |
| 2. Institutional capacity building to implement preparatory actions for pilot agri-environmental measures under IPARD. | 2.1. Start for the implementation of IPARD agri-environment measure in 2011. | 1.1. Country Progress Reports 1.2. Annual reports of IPARD Programme 1.3. Conferral of Management decision of EC. | - Continued Government and EU commitment towards Turkey’s accession |
| Results | Objectively verifiable indicators | Sources of Verification | Assumptions |
| 3.1. The Managing Authority and the IPARD Agency institutional capacities are ready for the implementation of the IPARD agri-environmental measures. 3.2. Strengthened institutional capacity of Managing Authority and IPARD Agency for the implementation of agri-environmental measures under IPARD. 3.3. Raised awareness of related institutions and public on preparation and implementation of agri-environmental measures. | 3.1.1.The detailed measure fiche (finalised version) for inclusion in the IPARD Programme is ready by the second quarter of the project. 3.1.2. Determined needs (market analysis and feasibility study) for the improvement of IT system (and supporting elements) of the IPARD Agency by the third quarter of the project. 3.1.3. The measure accreditation packages of Managing Authority and IPARD Agency are ready by the end of the project. 3.2.1. Trained 30 staff of Managing Authority and IPARD Agency on the agri-environmental measures under IPARD for 21 working days by the third quarter of the project. 3.2.2 Self-assessment of IPARD Agency completed by the end of the project. 3.3.1. Five workshops organized for raising the knowledge and awareness about the mandatory standards of agri-environmental measures and implementation procedures of the agri-environmental measure for the central and local environmental public authorities, related NGOs and related stakeholders including farmers for 300 people in total by the fourth quarter of the project. 3.3.2. Ten meetings with central and local stakeholders, public authorities and NGOs on local areas organized in the fourth quarter of the project. | 3.1.1.Revised IPARD Programme 3.1.2. Market analysis and feasibility study report 3.1.3; Accreditation package 3.2.1 Participation list and certificates of trainers and training questioners. 3.2.2 Self assessment report 3.3.1&3.3.2. Workshops and meetings conclusion reports and participant lists. | - timely start for implementation (conferral of management decision) of other IPARD measures (the measures determined for the first phase 2007-2009 ) and already established capacity for IPARD. - Sufficient allocation of financial and human resources by the Turkish Government |
| Activities | Means | Costs | Assumptions |
| - 1. Assessment of the legal and institutional framework and the determination of the required legislation and institutional arrangements - 2. Detailed evaluation of the Turkish situation with regard to agri-environmental issues and assessment of strengths and weaknesses to review the strategy for the measure. - 3. Assessment of the current guide of good agricultural practices in parallel with the analysis of EU Member States experience and the determination of the changing needs of the legislation with minimum requirements. Revision of Turkish Regulation on Good Agricultural Practices in terms of its compatibility with EU baseline for agri-environmental payments. - 4. Preparation of the additionally required legislation on obligatory mandatory standards. 5. Establishment of contacts with the scientific institutes for the establishment of the amounts of payments for the selected actions. Establishment of the amounts of the payments. - 6. Determination of pilot zones/sites and the inclusion of the financial tables of the measure and sub-measures. - 7. Elaboration of the monitoring and evaluation indicators as well as baseline indicators (in line with Common Monitoring and Evaluation Framework). - 8. Preparation of the detailed measure fiche and sub-measure fiches for inclusion in the IPARD Programme. - 9. Preparation of the accreditation package (preparation of project application forms, guidelines and implementation manuals, operational manuals, sample grant contract, on the spot control principles etc…) for the implementation of the measure. - 10. Assessment of the training needs, preparation of training Plan for the necessary training needs in order to establish the capacity of Managing Authority and IPARD Agency staff as well as the related institutions (Ministry of Environment and Forestry) on the agri-environmental measures of the IPARD. - 11. Training of 30 staff of Managing Authority and IPARD Agency on the agri-environmental measures under IPARD (EU legislation, agri-environmental measures programming and technical-fiche design, establishment of monitoring and evaluation indicators, establishment of the amounts of payments, implementation procedures, monitoring and evaluation procedures as well as on the training needs identified in the training plan). - 12. The project training for 20 advisers on agri-environmental actions involved to help farmers to select suitable actions. 13. Preparation of Communication Strategy for the publicity of the measure. - 14. Raising awareness of the central and local public environmental authorities, related NGOs and related stakeholders including farmers on the mandatory standards and implementation procedures of the IPARD agri-environmental measure by workshops and meetings. - 15. Internship and study visits to EU Member States - 16. Preparation of The leaflets and manuals for the public awareness of the measure. 17. The analysis of the available IT system of the IPARD Agency and the identification of the needs to implement and monitor the agri-environmental measure. 18. A comprehensive needs analysis of the IPARD Agency will be performed. Carry out a feasibility study and market survey of the needs of the IT system of IPARD Agency for agri-environmental measures. 19. Technical specifications for the supply to improve the IT system of the Agency will be prepared. | Activities 1 - 16 through Twinning Activities 1-10 through Component 1 of Twinning Activities 11- 16 through Component 2 of Twinning Activities 17-19 thorough TA | Twinning: EUR 1.0 million. TA: EUR 0.14 million. | - the staff are released for and absorbed training - Close collaboration between Managing Authority and IPARD Agency - There is interest and willingness of relevant institutions and local authorities. |

Precondition:   The tender for this project can be launched on the condition that, by submitting a formal Declaration of Assurance, showing that the beneficiary has sufficient staff in a list  for technical implementation and monitoring of the contracts.

- ANNEX II:	amounts (in EUR) Contracted and disbursed by quarter for the project

- (IPA contribution only)

| Contracted | 2009 3rd | 2009 4th | 2010 1st | 2010 2nd | 2010 3rd | 2010 4th | 2011 1st | 2011 2nd | 2011 3rd | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Twining Contract |  | 950,000 |  |  |  |  |  |  |  | 950,000, |
| TA |  |  |  | 105,000 |  |  |  |  |  | 105,000 |
| Cumulated |  | 950.000 |  | 1,055,000 |  |  |  |  |  | 1,055,000 |
| Disbursed | 2009 3rd | 2009 4th | 2010 1st | 2010 2nd | 2010 3rd | 2010 4th | 2011 1st | 2011 2nd | 2011 3rd | Total |
| Twinning Contract |  | 427,500 |  |  |  | 522,500 |  |  |  | 950,000 |
| TA |  |  |  | 63,000 | 42,000 |  |  |  |  | 105,000 |
| Cumulated |  | 427,500 |  | 490,500 | 532,500 | 1,055,000 |  |  |  | 1,055,000 |

ANNEX III:  	Institutional Framework

Main beneficiary of this Project will be the Ministry of Agriculture and Rural Affairs. MARA will work in close cooperation with related public institutions and will provide the personnel necessary to administer and resolve issues concerning the management of the project including reporting, preparation of terms of reference, tendering, contracting, monitoring and evaluation activities.

The Central Finance and Contracts Unit (CFCU) will be Implementing Agency and will be responsible 
for all procedural aspects of the tendering process, contracting matters and financial management, including payment of project activities.

For monitoring of project management and activities on a monthly base, the beneficiary will organize DIS meetings and prepare the monitoring reports to be submitted to EUSG, ECD and National Aid Coordinator (NAC).

The Steering Committee:

- is the decision-making body for the Project. Composed with the participation of project leaders, representatives of EC Delegation, EUSG, CFCU, IPARD Agency and SPO. Representatives from other related institutions (Ministry of Environment and Forestry, Undersecretariat of  Treasury, Undersecratariat of State Planning Organisation,  General Directorate of State Hydraulic Works) will  join the PSC if needed. The PSC will supervise and co-ordinate the overall progress and implementation of the project components. The SPO  will chair the PSC meetings. The Project life cycle can be shown as below chart.

Ministry of Agriculture    and Rural Affairs

Main Beneficiary

CFCU

Tendering and Contracting

Internal Control Dept. of SDB (Managing Authority)

Project Beneficiary

Project Steering Committee

EUSG

Project Leader

EC Delegation

IPARD     Agency

Co- Beneficiary Institution

International and local short term experts pool

Core Teams  preparation  of documents and daily implementation of project activities

- The PSC;

- will review all the activities and analyses the achievement of project outputs and objectives. It discusses problems which arise during the implementation of the contract and makes recommendations.

- monitors the implementation of the project and, if needed, proposes adjustments to the time schedule of the next steps of the project.

- comments on the draft report, which is sent to PSC two weeks before each meeting. These comments are taken into account before the official submission of the reports to the EC Delegation.

ANNEX IV Reference to laws, regulations and strategic documents:

NATIONAL LEGISLATION

-  Law on Environment No 2872 (OJ 11/8/1983,   No 18132)

- Law on the Organisation and Duties of the Ministry of Environment and Forestry No 4856 (08/05/2003, No 25102)

- Law on National Parks No 2873 (OJ dated 09/08/1983, No 2873)

- Law on Forestry No 6831 (OJ dated 31/08/1956 No 6831)

- Law on geothermal resources and naturally mineralised water No 5686 (OJ dated 13/06/2007 No  26551)

- Law on Terrestrial Hunting No 4915 (OJ dated 11/07/2003, No 25165)

- Law on Agriculture No 5488 (OJ dated 25/04/2006, No 26149)

- Law on Soil Conservation and Land Utilization No   5403 (OJ dated 09/02/007, No  26429)

- Law on Pastures No 4342 (OJ dated 28/02/1998 No 23272)

- Law on Organic Agricultural Production   No 5262 (OJ   3/12/2004 No 25659)

Secondary legislations:

- Regulation on the implementation of the contract with regard to the trade of the wild animals and plant varieties   under the risk of extinction (OJ 27/12/2001, No 24623)

- Regulation on protection of waters against agriculture based nitrate pollution (OJ dated 18/02/2004, No 25377)

- Regulation on the control of water pollution (OJ dated 31/12/2004 No 25687)

- Regulation on the protection of wetlands (OJ dated 17/05/2005, No 25818)

- Regulation on the reduction of methyl bromide use in agriculture (OJ dated 23/06/2000, 24088)

- Regulation on the control of air pollution caused by the industrial facilities (OJ dated 22/07/2006, No 26236)

- Regulation on the support of the producers using agricultural techniques for the protection of the environment (OJ 15/11/2005 No 25994)

- Regulation on Good Agricultural Practices (OJ dated 08/09/2004, No  25577)

- Regulation on the protection of air quality (OJ 02/11/1986, No 19269)

- Regulation on forestation (OJ dated 09/10/2003, No  25254)

- Regulation on Environmental Impact Assessment (OJ dated 16/12/2003, No  25318)

EU LEGISLATION

- Council Regulation (EC) No 1698/2005 of 20 September 2005 on support for rural development by the European Agricultural Fund for Rural Development (EAFRD)

- Commission Regulation (EC) No 1974/2006 of 15 December 2006 laying down detailed rules for the application of Council Regulation (EC) No 1698/2005 on support for rural development by the European Agricultural Fund for Rural Development (EAFRD)

- Council Regulation (EC) No 1085/2006 of 17 July 2006 establishing an Instrument for Pre-Accession Assistance (IPA)

- Commission Regulation (EC) No 718/2007 of 12 June 2007 implementing Council Regulation (EC) No 1085/2006 establishing an instrument for pre-accession assistance (IPA)

- Council Directive 76/116/EEC of 18 December 1975 on the approximation of the laws of the Member States relating to fertilizers

- Directive 97/63/EC of The European Parliament and of The Council of 24 November 1997 amending Directives 76/116/EEC, 80/876/EEC, 89/284/EEC and 89/530/EEC on the approximation of the laws of the Member States relating to fertilizers

- Council Directive 91/676/EEC of 12 December 1991 concerning the protection of waters against pollution caused by nitrates from agricultural sources

- Council Directive 86/278/EEC of 12 June 1986 on the protection of the environment, and in particular of the soil, when sewage sludge is used in agriculture

- Council Directive 79/117/EEC of 21 December 1978 prohibiting the placing on the market and use of plant protection products containing certain active substances

- Council Directive 91/414/EEC of 15 July 1991 concerning the placing of plant protection products on the market

- Council Directive 80/778/EEC of 15 July 1980 relating to the quality of water intended for human consumption

- Council Directive 79/409/EEC of 2 April 1979 on the conservation of wild birds

- Council Directive 92/43/EEC of 21 May 1992 on the conservation of natural habitats and of wild fauna and flora

- Council Regulation (EEC) No 2078/92 of 30 June 1992 on agricultural production methods compatible with the requirements of the protection of the environment and the maintenance of the countryside

ANNEX 5 Details per EU funded contract

ANNEX 5.1. TWINNING CONTRACT

1. The objective

The objective is to establish and strengthen the institutional capacity of Managing Authority and IPARD Agency in the area of the implementation of the agri-environmental measures as well as the raising the public awareness for the agri-environmental measures in respect to IPA and  EU Rural  Development regulations.

The project has two components;

Component 1: Institutional capacity development

Component 2: Public awareness

The breakdown of costs of the Project is as follow:

Human Resources

1. Project Leader:

Project leader should have experience on  rural development and/or agri-environmental  activities projects. He/she should also have international experience. He/she will be responsible for overall implementation of the project. Furthermore, project leader will manage financial issues and coordination with RTA and also beneficiary project leader and SPO.

2. Resident Twinning Advisor (RTA):

Resident Twinning Advisor (RTA), who will be residing in Turkey for 12 months, will be responsible for overall management and coordination of project activities. He is expected to carry out the following tasks during his full-time working period:

- To assist the Turkish experts and short term experts in preparing detailed work programs, to co-ordinate and manage their inputs and outputs, according to the project objectives,

- To supervise the assessment of current EU and Turkish legislation,

- To assist the Internal Control Department  of Strategy Development Board and IPARD Agency on related activities of project,

- Organization of workshops,  seminars trainings,

- To prepare quarterly meetings and project meetings,

- To collect, review and comment reports of the short term experts and study visitors,

- To draft the quarterly project reports to be finalized by the project leaders,

- To organize training and study visit activities.

Qualifications of the RTA (Resident Twinning Advisor) (12 months)

- Relevant knowledge and experience in legislative harmonization on agri-environmental  issues,

- Strong communication facilities, ability to work in different environments with local experts,

- Good links and cooperation with EU professionals in Member States,

- Educational background in the environment related area.

- Professional experience at least 5 years on agri-environmental issues working in the Managing Authority or Paying /SAPARD Agency.

- Fluent English and good computer literacy required.

- Experience in at least one of the project on  capacity development for  EU agri-environmental  measures as RTA.

3. Short and Medium Term MS experts:

Short term expert visits will a part of Twinning Project. The short terms experts will be responsible for the execution of the following tasks:

- 1. Assessment of the legal and institutional framework and the determination of the required legislation and institutional arrangements

- 2. Detailed evaluation of the Turkish situation with regard to agri-environmental issues and assessment of strengths  and weaknesses to review the  strategy for the measure.

- 3. Assessment of the current guide of good agricultural practices in parallel with the analysis of EU Member States experience and the determination of the changing needs of  the  legislation with minimum requirements. Revision of Turkish Regulation on Good Agricultural Practices in terms of its compatibility with EU baseline for agri-environmental payments.

- 4. Preparation of the additionally required legislation on obligatory mandatory standards.

5. Establishment of contacts with the scientific institutes for the establishment of the amounts of payments for the selected actions. Establishment of the amounts of the payments.

- 6. Determination  of pilot zones/sites and  the inclusion of  the  financial tables of the measure and sub-measures

- 7. Elaboration of the monitoring and evaluation indicators as well as baseline indicators (in line with Common Monitoring and Evaluation Framework)

- 8. Preparation of the detailed measure fiche and sub-measure fiches for inclusion in the IPARD Programme

- 9. Preparation of the  accreditation package (preparation of project application forms,  guidelines and implementation manuals, operational manuals, sample grant contract, on the spot control principles etc…)  for the implementation of the   measure.

- 10. Assessment of the training needs , preparation of a training Plan for the necessary training needs in order to establish the capacity of Managing Authority and IPARD Agency  staff as well as the related institutions (Ministry of Environment and Forestry)  on the agri-environmental measures   measures of the IPARD.

- 11. Training of 30 staff of Managing Authority and IPARD Agency on the agri-environmental measures    under IPARD (EU legislation, agri-environmental measures programming and technical-fiche design, establishment of monitoring and evaluation indicators, establishment of the amounts of payments, implementation procedures, monitoring and evaluation procedures as well as on  the training needs  identified in the training plan).

- 12. The project training for 20 advisers on agri-environmental actions  involved to help farmers to select suitable actions

13. Preparation of Communication Strategy for the publicity of the measure.

- 14. Raising awareness of the central and local public environmental  authorities, related NGOs and related stakeholders including farmers  on the mandatory standards and  implementation procedures  of the IPARD agri-environmental measure   by workshops and meetings.

- 16. Preparation of The leaflets and manuals for the public awareness of the measure

The expert visits to carry out project activities will be organized by the RTA together with the project leader. The RTA will provide all relevant documentation and information on the situation in Turkey to the experts and their contribution will be expected. Each expert will write a ‘mission report’ upon completion of his/her visit to Turkey. This will give a brief appraisal of the situation upon arrival, the work done (developments achieved, meetings attended, people met) during the stay, recommendations for future action including specific tasks to be mandated to the Turkish specialists, and difficulties encountered during the visit.

Qualifications of Short Term and Medium term Experts:

Minimum of 5 years professional experience in the following subject/s:

  - Experience at least one project related to the implementation of agri-environmental measures under SAPARD or EU Rural Development Programmes.

  - Minimum 3 years experience in Managing Authority or  Paying Agency/SAPARD Agency.

Candidate for the Senior Programme Officer of the Project: Mr. Enver AKSOY

Head of Internal Control Department

Strategy Development Board (Managing Authority)

Eskişehir Yolu. 9.km Lodumlu/ANKARA

Tel: +90 312 286 58 76

Fax: +90 312 285 69 40

E-Posta: enver.aksoy@tarim.gov.tr

The Senior Programme Officer is responsible for the technical implementation of the project.

BC Project Leader for Twinning;

Mr. Enver AKSOY

Head of Internal Control Department

Strategy Development Board (Managing Authority)

Eskişehir Yolu. 9.km Lodumlu/ANKARA

Tel: +90 312 286 58 76

Fax: +90 312 285 69 40

E-Posta: enver.aksoy@tarim.gov.tr

RTA Counterpart;

Ilknur DEDE

Internal Control Department

Strategy Development Board (Managing Authority)

Ministry of Agriculture and Rural Affairs

Eskişehir Yolu. 9.km Lodumlu/ANKARA

Tel: +90 312 287 33 60 /2209

Fax: +90 312 285 69 40

E-Posta: ilknur.dede@tarim.gov.tr

Seher MUĞLA

Internal Control Department

Strategy Development Board (Managing Authority)

Ministry of Agriculture and Rural Affairs

Eskişehir Yolu. 9.km Lodumlu/ANKARA

Tel: +90 312 287 33 60 /2209

Fax: +90 312 285 69 40

E-Posta: seher.mugla@tarim.gov.tr

ANNEX 5.2. TECHNICAL ASSISTANCE

1. The objective;

The objective of the project is:

- To identify the needs of the IPARD Agency  to implement the agri-environmental measures and make the technical specifications for the IPARD Agency in order to improve  the IT system of the IPARD Agency  (software and supporting elements)  for  implementation of  the agri-environmental measures of IPARD programme.

2. Requested Services, including suggested methodology;

The services to be provided by the consultant under this contract includes:

a) Identification of the needs of the agency, feasibility study and market survey.

b) Preparation of the technical specifications for the IT System (software and supporting elements) of  the Agency to implement the measure.

4. EXPERTS PROFILE

4.1.1- Team Leader (Rural Development Specialist)

Job Description:

- He/she will be responsible for the overall co-ordination of the implementation of the project activities.

- He/she will be responsible for the management of the team short-term experts.

- He/she will be the primary contact for all the communications, elaboration and delivery of reports to the beneficiary, the CFCU and the EC Delegation.

- He/she will co-ordinate and supervise the organization and delivery of all necessary inputs for ensuring proper implementation of the activities in accordance with the EC rules.

- He/she will be responsible for the fulfilment and submission of the technical specifications

4.1.2- Software and Network Specialist

Job Description:

- He/she will be responsible for the identification of the needs and  preparation of the technical specifications of the Agency.

- He/she will be work in coordination with other experts involved in the preparation of the technical specifications and tender dossier for IT system of the Agency.

- He/she will be responsible for the other tasks that will be assigned by team leader.

4.1.3 – Hardware Specialist

Job Description:

- He/she will be responsible for the identification of the needs and the technical specifications for IT system of the Agency.

- He/she will be work in coordination with other experts involved in the project

- He/she will be responsible for the other tasks that will be assigned by team leader

- 5.  Number of requested experts per category and number of man-days per expert

The Consultant shall make a team of 3 experts available for the successful completion of the assignment and ensure that these experts work in cooperation with each other according to the following inputs:

| No of Experts | Short-Term Experts | Minimum Working Days | Category |
| --- | --- | --- | --- |
| 1 | Team Leader Rural Development Specialist | 55 | II |
| 2 | Software and Network Specialist | 55 | III |
| 3 | Hardware Specialist | 50 | III |
|  | TOTAL | 160 |  |

5. Foreseen finishing period or duration

- The TA will be completed in 3 months (88 calendar days).

ANNEX 6.

3.6.1. Environmentally Based Agricultural Land Protection Programme (ÇATAK)

The implementation started in pilot provinces Isparta, Kayseri, Kırşehir and Konya on 5,000 ha area. The payments to be effected are classified into three categories of environment related activities.If the producer prefers to practice two or more of the mentioned techniques in  each category or replacement of their current production practices,  they are awarded an annual payment per ha for a total of 3 years.

Category 1 includes;

Erosion combat (embankment, fencing for protection, application of ideal tillage techniques (contour tillage) and/or leaving the land uncultivated for protection reasons), Land improvement, Drainage and

Stone collection.

Category 2 includes;

Practicing suitable irrigation techniques, Controlled usage of pesticide, fertilizers and hormones, Usage of organic, green and barn fertilizers compost etc. Application of organic production and Good Agricultural Practices

Category 3 includes;

Establishing permanent plant coverage, Improvement of existing or formulation of new grass meadows-pastures, Prevention of excessive grazing, Production of fodder plants

3.6.2.Anatolia Watershed Rehabilitation Project

The objectives of the project are:

-  Improving the management of pastures, rehabilitation of pasture and forest areas,

- enhancing the vegetation of those areas,

-  increasing the production of fodder crops,

-  reducing fallowed lands

- adopting environment-friendly and

- reduction of the pollution caused by  agricultural techniques.

The project targets  totally 28 micro water- basins areas  of the rivers Yeşilırmak and Kızılırmak including the provinces Samsun, Amasya, Tokat, Çorum, Sivas and Kayseri.

Local people have been   assisted for some family income increasing activities including expanding the scope of small-scale irrigation, terracing dry lands, horticulture and apiculture and improving local husbandry.  Besides this, necessary measures will be taken to evaluate and prevent the water pollution in water flowing to the Black Sea.

The activities includes; fallow reduction, pasture rehabilitation, demonstration, production of fodder crops in irrigated land, beekeeping and orchards in dry area, correct use of marginal agricultural area, afforestation.

The project activities were started in 2005 in 5 micro water basins  and continued in the same area.