ANNEX C1

STANDARD TWINNING PROJECT FICHE

1.	Basic Information

1.1	Programme: IPA 2010

1.2	Twinning Number: SR 10 IB JH 01

1.3	Title: Establishment of Efficient System for Prevention and Suppression of Illegal Migrations on the Territory of the Republic of Serbia

1.4	Sector: Justice and Home Affairs - Ministry of Interior

1.5	Beneficiary country: Republic of Serbia

2.	Objectives

2.1	Overall Objective(s):

To contribute to the efficient prevention and fight against organized crime with the special attention on the suppression of illegal migrations and cyber crime in the Republic of Serbia.

2.2	Project purpose:

Capacity building of the Ministry of Interior of the Republic of Serbia with the aim to develop effective and operational administrative system for illegal migration issues trough accordance of legal, procedural and technological framework with EU standards in that field regarding special investigative techniques, connection between the high-tech criminal and illegal migrations, necessary skills in combating high-tech criminal and the application of international standards in the treatment of illegal migrants and high-tech crime.

2.3	Contribution to National Development Plan/Cooperation agreement/Association Agreement/Action Plan

European Partnership in the Chapter pertaining to justice and home affairs, building of mechanism for control and management in the field of visas, asylum and migrations is foreseen.

Stabilization and Association Agreement in the Article 6 stipulates as follows:

„Serbia commits itself to continue to foster cooperation and good neighbouring relations with the other countries of the region including an appropriate level of mutual concessions concerning the movement of persons, goods, capital and services as well as the development of projects of common interest, notably those related to border management and combating organised crime, corruption, money laundering, illegal migration and trafficking, particularly in human beings, small arms and light weapons, as well as illicit drugs.’’

National Program for EU Integration (NPI, 2008.) defines migrations management as a priority in the sector of justice and home affairs.

Multi-annual Indicative Plan Document (MIPD) identifies as one of the main priorities, in co-operation with Republic of Serbia, the following: „Support to further harmonization with EU standards in the area of visas, border, asylum and migrations management“.

Strategy for Fight against THB adopted in 2006, among other strategic goals, under point 7.1 underlines the need to improve capability of state officials to identify victims of different forms of THB (which is more complicated if in different stages of this criminal act, high-technology is being used), indicating necessity for strengthening capacities for investigations of high-tech crime. Building of these capacities would significantly contribute to increase in number of promptly identified victims. Also, within the Goal 8.2 it is foreseen to improve regulations for the purpose of more efficient victims’ protection and enablement of discovering, prosecution and sanctioning of THB criminal offenders. In order to raise efficiency, and especially in cases related to illegal migrations and high-tech crime (ex. when victims are foreign citizens illegally residing in our country, who were sexually exploited and recruited by advertisements posted via Internet, or by SMS, etc), it is necessary to strengthen joint capacities of both Border Police and Criminal Police Directorates.

Integrated Border Management Strategy adopted by the Government of the Republic of Serbia in 2006, clearly expresses determination of the state to improve capacities for securing and control of state border through development and upgrade of infrastructure to support the work of border police in order to provide openness of border for movement of people and goods and closeness for illegal activities and crime. The particular objective 6 of the IBM Strategy foresees optimal development of the information technology, as support to integrated border management, which means, inter alia, connecting of border services information systems.

In accordance to recommendations presented in the “Road Map towards liberalization of visa regime of the European Union towards the Republic of Serbia” submitted by European Commission to Republic of Serbia, Government of Republic of Serbia adopted Strategy for Illegal Migrations Suppression on 26th of March 2009. Strategy foresees general and specific goals which Republic of Serbia needs to achieve in order to efficiently manage migrations. Strategy for Illegal Migrations Suppression is based on the national programme for the EU integration, adopted IBM Strategy of the Republic of Serbia and current reform processes in the country. In the part 2.1.12, of the Strategy the use of modern technology, as proactive measure in suppressing illegal migrations has been recognized.

In that sense, as a special objective of the Strategy for Illegal Migrations Suppression, the item 3.12 foresees proactive measure of improvement of modern technology implementation in the illegal migration suppression.

National strategy for the fight against organized crime was published in Official Gazette of RS, no. 55/05, 71/05-correction, 101/07 and 65/08. Existing forms of organized crime present in the Republic of Serbia are: drug trafficking, extortion, kidnapping, extortion, human trafficking, smuggling, corruption, money laundering, abuse of office, forgery of money and other means of payment, prostitution, trafficking in arms and explosive materials, international smuggling of cars, the smuggling of excise goods and high-tech crime.

The current situation in the area of cyber crime suggests that the rate of increase of this type of crime and number of returns in the commission of these crimes is large, especially in the area of unauthorized access to a protected computer, computer network and electronic data processing, and infringement of intellectual property rights. In 2008 year has seen an enormous number of unauthorized access to protected computers and computer networks related to the website, as government institutions and the Internet presentation of legal and natural persons from the Republic of Serbia. Also, an organized criminal group for drug traffics, money counterfeiting, human trafficking, and money laundering increasingly use new technologies in communication, which is reflected in the implementation of VoIP technology, electronic mail, instant messenger (MSN, ICQ, etc.). It is anticipated that future period characterized by high-tech crime greater involvement of organized crime in the use of computers during the distribution of narcotics, child abuse, abuse of credit cards, then, prostitution, trafficking in human organs, electronic transfer of money to offer attractive opportunities for fast and reliable money laundering "greater involvement of juveniles in the commission of serious crimes, identity theft and misuse in electronic commerce.

It is anticipated that the further movement and the development of organized crime in Serbia, varying intensity, affect all the above factors and the economic crisis, the trend of increased drug use and psychoactive substances, investing money gained through criminal enterprise in the legal channels, the expansion of high-tech crime, environmental crime and others.

3.	Description

3.1	Background and justification:

Migrations are a global phenomenon of contemporary world including all aspects such as political, economic, social, security etc. Controlled migration flows can bring a series of positive effects for society (influx of labour power, development of economy, etc.). On the other side, uncontrolled and chaotic process of migrations carries risk of destabilization. Risk factors are most prominent in illegal migrations flows which are more and more controlled by organized crime: beside economic migrants more and more THB victims are transferred through illegal channels, while in some cases even a link between terrorist groups is proved – groups which are either financed from profit gained by organizing illegal migrations or using the same channels for their purposes.

Territory of the Republic of Serbia is a transit area on migrants’ ways from non-EU countries to EU countries; therefore, activities of state authorities in the field of migrations management can be considered as a part of overall efforts in fight against organized crime and terrorism.

All forms of organized crime, including illegal migrations and THB, more and more rely on high-tech crime. Therefore, efficient establishment of prevention system requires increase of investigative methods and capacities in the field of high-tech (cyber) crime.

Since IT development, and its usage, affects wide areas of society, the need for establishment of IT infrastructure on the highest level is obvious. In order to achieve higher level of protection and stability in work, IT infrastructure has to enable prevention and discovering of potential attacks and misuses.

Contemporary development in IT, as well as the development of global computer network, allows preconditions for committing criminal offences from the area of high-tech crime which were not possible before. Frequency of criminal offences in this field requires international co-ordination and co-operation in discovering, suppression and prosecution.

Republic of Serbia is more often becoming target of international high-tech crime, as a territory which is on the borders of EU Members States. During 2007, officers of Border Police Directorate discovered 639 forged payment cards in possession of 12 citizens of Bulgaria, controlling them on border crossings with Bulgaria, which would have been misused. During 2008 (till November 6th) on the border crossings with Bulgaria, Romania and Croatia, officers of Border Police Directorate discovered 197 forged payment cards in possession of 14 citizens of Bulgaria and Romania. Besides that, the following equipment for misuses of IT was discovered: 4 skimmers, equipment for keyboard and laptop with details of 21 bank accounts in United Kingdom, etc.

Illegal migrants use high-tech crime for provision of forged documents later used for travelling to EU countries. Criminal associations involved in THB and illegal migrations more and more rely their communication and communication with potential victims on IT misuse, by covering their identity, and by usage of services and technologies they obstruct efficient electronic surveillance of communication by competent authorities. Improvement of capacities in Criminal Police and Border Police Directorates in the field of high-tech crime could significantly contribute to efficient co-ordination and communication, as well as to discovering and prosecution of high-tech crime related offences. During 2007, officers of Border Police Directorate discovered 333 forged travel documents on border crossings, of which 60 were used by illegal migrants and forged using IT, because countries issuing travel documents use sophisticated protection elements (67 travel documents of Bulgaria, 21 of Slovenia and 2 of Slovak Republic), while in 2008 of 273 forged travel documents 49 were forged using sophisticated technologies (travel documents of Bulgaria – 28, Slovenia – 16 and Slovak Republic – 5).

In the region, there were cases of migrants smuggling where beside usual communication by mobile telephones that was intercepted by the order of court, criminals started to make “appointments” for conversations via Internet i.e. Skype, and from that moment all interception measures were useless.

Aware of the state of affairs and trends in this field, Republic of Serbia accessed and signed Council of Europe „Cyber Crime Convention“ in April 2005. On 18th March 2009 the National Parliament adopted the Law on ratification of the Convention on Cybercrime. One of obligations, stipulated I by the Convention, is to install so called “Network 24/7”. Network 24/7 will enable direct and constant contact of all states that ratified Convention, in order to exchange information and provide evidence necessary for criminal investigations. Establishment of Network 24/7 implies supply of equipment and training of state bodies engaged in the Network, which in most of EU member states, as well as other countries that have this service (USA, Japan) is the police.

The Parliament of the Republic of Serbia passed the “Law on Organization and Competencies of State Authorities in Fight against High-tech Crime” in July .2008. This Law defines organization and competencies of certain organizational units within state authorities responsible for discovering, criminal prosecution and court proceedings of high-tech criminal offences.

After the Law got into force, the following state authorities have been formed tasked with fight against high-tech crime:

- within the Prosecutor’s Office in Belgrade “Department for Fight Against High-tech Crime” was established;

- while within the Ministry competent for interior issues “Department for High-tech Crime Suppression” were formed.

According to the World Bank analyses, technology is spreading faster in developing countries than in wealthy countries, and having in mind that developing countries are also countries with high migrations rate it can be reasonably presumed that in the future illegal migrants from high-migration risk countries, due to better availability of modern technologies, will more use and misuse it for illegal migrations towards EU countries. Since officers of Border Police Directorate do not possess sufficient knowledge and skills in usage of modern technologies, nor capacities or techniques to monitor such phenomenon and activities on Internet related to illegal migrations, there is a need for coordinated work of specialized services involved in suppression of illegal migrations and suppression of high-tech crime.

Process of illegal migrants identity check in Serbia is not sufficiently efficient, because Alien Shelters do not have IT connection with Directorate HQ nor with Interpol bureau. Migrants’ identification process is conducted in following manner: forensic technicians take fingerprint data and take them for processing, that significantly slows down identification process – either identification of migrants or other persons involved in THB chain, terrorism and organized crime.

In the future information exchange with FRONTEX, transfer of knowledge regarding new technologies will be important in order to keep the pace of evolving smuggling of migrant’s techniques and THB. This would allow feed the Early warning system already presents in Serbia with international information as well.

Building capacities for establishment of electronic database with data on illegal migrants using biometric data (image, fingerprints), in accordance to Dublin Convention and EURODAC EU system, would create possibilities for more efficient establishment of illegal migrants’ identities, particularly those in Alien Shelter and would be valuable contribution for more efficient work and discovering of illegal migrants.

It is necessary to provide basis for harmonization with "EURODAC" system which includes central EU unit and fingerprint database, which is developed for support in functionality defined by Dublin Convention and by Directive for performing asylum related procedures (Convention determining the State responsible for examining applications for asylum lodged in one of the Member States of the European Communities - Dublin Convention, Official Journal C 254, 19/08/1997 p. 0001 – 0012)

This would require further improvement of the Integrated Information System of the Ministry of Interior (JIS). It is one of the larges and the most complex information systems in the Republic of Serbia, established with the aim to support all operational lines of the MoI. The functioning of the JIS of the entire Ministry is based on the Intranet network that covers police department on entire territory of the Republic of Serbia and is very complex and wide spread.

3.2	Linked activities (other international and national initiatives):

The CARDS Regional Project ''Establishing Compatible Legal, Regulatory & Institutional Frameworks in the Field of Visas, Migrations and Asylums'' was implemented in the period from 2004 to 2005. The Project was developed through three modules - asylum, visa and migrations, and one international organization (UNHCR, ICMPD and IOM) was responsible for each.  Each module was implemented through 6 to 8 seminars, and the results published as a ‘’Road Map’’.

Starting from year 2004 DCAF (Democratic Control for Arm Forces) has organized conferences on “Border Security”. Aims of the conferences were to enhance international co-operation in the SE Europe in the field of Border Control. Work is organized in several working groups, including a separate Committee for the IT with the primary goal to exchange information according to the current state of development of national border management systems, analyze possible technologies and ways of information exchange in order to support cross border cooperation and information exchange. The general basis for this work is the Vienna Convention which is accepted by the Republic of Serbia authorities.

The CARDS 2006 twinning project had the goal to analyse the current Human Resources Management system, including the legal framework, design a new Human Resources Management System, carry out training of the key personnel and develop the curricula for education and training of the staff involved in the IBM activities.

Finally under IPA 2007 planned actions of Assisting the Serbian Customs Administration to set up Community Transit corresponding administrative, legal and equipment structures and preparing for the implementation of an NCTS-compatible automated transit system is directly linked to the activities of this project.

IPA 2007 also provides €5.5 million for conducting organizational review, gap analysis of the needs and requirements for technical equipment including training at borders. Resources are also secured for the supply and installation of required telecommunication equipment, special vehicles and special equipment for the borders with Bosnia and Herzegovina and Croatia. IPA 2007 will assist the Serbian Police force in meeting EU standards of professionalism and conduct and create higher control standards at Serbian borders in line with the Integrated Border Management Strategy.

Prerequisite for establishment of more efficient system for exchange of data on illegal migrations will be fulfilled by providing basic communication IT infrastructure covered by project implemented by IPA funds for 2007 (contains the component of transmission pass) and for 2008 (contains the component of IT infrastructure). Scope of these projects is to provide adequate technical infrastructure for border crossing check, and there are requests for further capacity building in special areas like illegal migration prevention. This means to upgrade procedure of prevention of illegal migration using new technological solutions, and increase efficiency and reliability of the identification of illegal migrants

It is envisaged that IPA 2007 project will provide in depth gaps and needs analysis with respect to information exchange and technical preconditions for implementation of IBM Strategy, whereas IPA 2008 project, on the bases of conducted assessment and improved technical preconditions, should commence with creation of an integrated information system along with priorities of IBM Strategy.

Based on these strategic preconditions that would be implemented through previous two projects, this project will tackle more specific areas and develop more specialised segments of the integrated information system, such as illegal migrants database and provide for necessary capacities for data exchange with similar services in the region and in the EU (EURODAC).

3.3	Results:

- Result 1.

- Measures for tracking high-tech criminal have been assessed, improved and used in the process of overall illegal migrations prevention in responsible MoI Departments.

- Measurable indicators:

- Document of the assessment with the recommendations for further improvements has been made, adopted and applied in the process of the system enhancement.

- The border police and the criminal investigation police have the capacities for regular tracking of the activities on the Internet which are related to organization of illegal migrations

- Increased number of forged documents which have been discovered due to the usage of high technology  in combating organised crime, especially in combating THB in connection with the Early Warning System which distributes information via BCPs online

- Improved analyses of statistical data and risk assessment procedures

- Decreased number of visa applications on the basis of forged documents compared to the average number of visa applications over the past three years.

Result 2.

The employees in the Ministry of the Interior are using database for gathering, saving and verification of the data regarding illegal migrants and they are able to exchange data efficiently with similar services in the region and in EU.

Measurable indicators:

- Increased number of discovered criminal offence  connected with illegal migrations by abuses in the area of informational  technologies

- Financial savings accomplished a result of the shortened time which foreigners used to spend in the Foreigners shelter.

- Efficiency of return to their country of origin.

- Database of illegal migrants is applied in everyday work  of the Border Police Department  and it is fully integrated within IS of the Ministry of the Interior

Result 3.

Capacities and the procedures for permanent cooperation, exchange of information and experiences with specialized and similar services in the region and Europe regarding the EU standards have been provided.

Measurable indicators:

- Developed protocols for the exchange of information between the relevant institutions and applied with no major difficulties.

Result 4.

The employees in the Ministry of Interior poses adequate skills for applying  investigative techniques and the equipment necessary for combating high-tech crime  with the purpose of discovering, documenting and processing criminal offences connected with illegal migrations and providence of adequate treatment to the illegal migrants.

Measurable indicators:

- The employees apply in their everyday work the knowledge received during the training

- The reduction of financial losses that appear as a result of the credit card abuse, e-banking and e-trade transfer abuse committed by illegal migrants

- The improvement of government employees’ capacities to reveal and timely identify the victims of various types of human trafficking

3.4	Activities:

Activities related to result 1

1.1. Within the MoI, to prepare the assessment of the existing system for suppression illegal migrations and high technology crimes with identification of key gaps and provide recommendations for improvement.

1.2. To prepare a plan for the improvement of the illegal migration control system with regards to the use of new technologies and special investigation techniques.

1.3 Training for specialised technical equipment (software’s - commercial and for government purposes and for hardware) and necessary applications in order to use investigation techniques for discovering criminal offences within the domain of high technology crime, in accordance with the recommendations of the conducted assessment.

Activities related to result 2

2.1.  Provide support and advice in preparation of the illegal migration database in accordance with the EU standards and technical means at the BCPs for automatic detection of passengers.

2.2. Support design and establishment of an electronic database of illegal migrants in the Republic of Serbia with a necessary capacities for data exchange with similar services in the region and in the EU.

2.3. Support  process of integration of the illegal migrants database into a existing  information system of MoI in accordance with the Plan on improvement of illegal migration control and best practices in suppression of high-technology crime.

2.4. Provide assistance in preparation and dissemination of the protocols and the instructions for secured and safe use of new technical and technological solutions.

2.5. Prepare and deliver trainings for the MoI employees for usage of the electronic database of illegal migrants and technologies on which the migration control system is based.

Activities related to result 3

3.1. Organisation of national conference on abuse of high technologies in the area of illegal migrations where all the necessary steps for promotion of coordination and data exchange among countries would be defined.

3.2. Preparation of documents of protocols and agreements necessary for the information and data exchange with the interested partners in the region.

- 3.3. Organisation of study visits in one of the EU member states with proven results in combating illegal migrations by using high technologies.

3.4. Organisation of internship of liaison officers with one of the EU member states.

Activities related to result 4

4.1. Preparation of 4 modules of training for the employees in the Ministry of Interior regarding special investigative techniques, connection between the high-tech criminal and illegal migrations, necessary skills in combating high-tech criminal and the application of international standards in the treatment of illegal migrants.

4.2. Organisation and conducting of training of the employees.

4.3. Preparation and printing of booklets and manuals on the basis of the created training modules.

3.5	Means/ Input from the MS Partner Administration:

3.5.1	Profile and tasks of the Project Leader

The Project Leader will manage the project team and co-ordinate the implementation. He/she will also be responsible for ensuring that experts input and distribution of their working days will be used in the most efficient and effective way.

Minimum qualifications required:

- High ranked police officer in a filed of cyber crime

- Police experience in internal affairs (high tech crime department) minimum 10 years

- University degree (BSc.) is an advantage

- At least 5 years of experience in project management

- Familiar with twinning rules and procedures

- Familiar with the relevant EU legislation in the field of cyber crime and illegal migration issues

- Experience in programme management will be considered as an advantage

- Experiences in work in international and multicultural environment

- Excellent knowledge of English,

- Skills: good communication and coordination skills.

3.5.2 Profile and tasks of the RTA

The RTA will be in charged for project implementation team and co-ordinate the implementation. He/she will also be responsible for ensuring that experts input and distribution of their working days will be used in the most efficient and effective way and coordination with national contacts points for project.

Must be a person with good knowledge in area of cyber crime suppression and in the area of computer related crimes with at least 3 years of experience in this area. RTA must have an excellent knowledge of English language, written and oral.

Minimum qualifications required:

- High ranked police officer in a filed of cyber crime

- Police experience in internal affairs, high tech crime department minimum 5 years

- University degree (BSc.) is an advantage

- Familiar with twinning rules and procedures

- Familiar with the relevant EU legislation in the field of cyber crime and illegal migration issues

- Experience in programme management will be considered as an advantage

- Experiences in work in international and multicultural environment

- Excellent knowledge of English,

- Skills: good communication and coordination skills.

3.5.3 Profile and tasks of the short-term experts

- Experts with practical experience in High Tech crime suppression such as investigators, forensic experts etc.

- Experts with practical experience in illegal migration issues

- Organized crime experts

4. 	Institutional Framework

The Ministry of Interior is in charge of implementation and monitoring of this project.  Key beneficiaries would be the Border Police Directorate and the Department for High-tech Crime Suppression.

The work, mandate and competencies of the Ministry are regulated by the Law on Ministries and Law on the Police.

The Ministry of Interior consists of the following departments:

- Police Directorate (Border Police Department, IT Department, Criminal Police Department, Traffic Police Department, Gendarmerie, etc)

- Internal Control Department

- Finance and HR Department (Directorate for Police Education, Professional Development and Science)

- Protection and Rescue Sector

Border Police Department has been established as general and centralized service, hierarchically organized at central, regional and local level, and in charge of direct organisation and performance of activities related to control of crossing and securing the state border.

At central level, this authority exercises the above-mentioned function through Department for border, Departments for foreigners, Department for prevention of cross-border criminal and criminal intelligence affairs, then through Department for international cooperation and Duty Operation Centre. At regional level this function is exercised through Border Police Regional Centres established for every neighbouring country. At local level Border Police Authority exercises its function through Border Police stations for control of crossing the state border and its security; their work is coordinated under Regional Centres.

Department for High-tech Crime Suppression is an organisational unit within Criminal Police, established in 2008. According to new   Law on Organization and Competencies of State Authorities in Fight against High-tech Crime and is responsible for investigation of high-tech crime cases upon request of Special prosecutor for High-tech crime.

High Tech Crime Department is situated in Service for Combating Organized Crime and has two sectors: Cyber Crimes and Intellectual Property Crimes. It has a head of Department, Deputy of Head of the Department and two Chiefs of Sectors. Organizational chart is in the chart no.1. The Department has 11 employees, working in a field of electronic crimes, IP crimes, child pornography cases etc.

Chart No.1

Other relevant stakeholders are: Ministry of Foreign Affairs, Ministry of Finance (Customs Administration), Ministry of Justice, Prosecutor’s Office in Belgrade - Department for Fight Against High-tech Crime, Ministry for Human and Minority Rights, Ministry of Labour and Social Policy (Department for Gender Equality), Ministry of Health and Commissariat for Refugees.

5. 	Budget

Twinning budget for this project amounts € 1 million.

The Ministry of Interior will provide the twinning partner with adequate office space for RTA and experts and meeting rooms necessary for relevant everyday activities and training foreseen in twinning fiche.

6. 	Implementation Arrangements

6.1   Delegation of the European Union to the Republic of Serbia

Mr Gianluca Vannini

Programme Manager – Operations 1

Address: Vladimira Popovića 40, GTC Avenue block 19a

Tel: +381 11 3083 298

Fax: +381 11 3083 201

E-mail: gianluca.vannini@ec.europa.eu

6.2   Main counterpart in the BC

Project leader

Mr Lazar Janković

Deputy Head of Service for Combating Organized Crime

Address: Bulevar Mihajla Pupina No.2

Phone +381113148465

Fax: +381113148464

Cell Phone: +381648922309

E mail: lazar.jankovic@mup.gov.rs

RTA

Mr Vladimir Urošević

Chief of Cyber Crime Section

Address: Bulevar Mihajla Pupina No.2

Phone +381113121276

Fax: +381113148464

Cell Phone: +381648920201

E mail: vladimir.urosevic@mup.gov.rs

A Project Steering Committee (PSC) will be organized on a quarterly basis. Their role will be overall project coordination and supervision.

Members of PSC will be representatives of Ministry of Interior (Service for Combating Organized Crime, Cyber Crime Section, Border Police Department, Department for Combating Trans-border Crime and Criminal Intelligence, Directorate of Information Technology, Sector for finance, human resources and common affairs as well as representatives of the Delegation of the European Union and Serbian European Integration Office

6.3 	Contracts

This project will be implemented through one twinning contract.

7.	Implementation Schedule (indicative)

7.1	Launching of the call for proposals (Date) Q2 2011

7.2	Start of project activities (Date) Q4 2011

7.3	Project completion (Date) Q4 2013

7.4	Duration of the execution period (number of months)	24

8.	Sustainability

Migrations and cyber crimes represent global phenomenon whose impacts and consequences go beyond national borders and this project shall contribute to the reduction of illegal migrations and cyber crimes related to this topic, not only in the region, but in the EU as well.  The efficient control functions will also result with a reduction of illegal activities (smuggling of goods, humans, vehicles and travellers, corruption) and will facilitate trade in the region.

Coupled with the need to combat terrorism, border agencies need unprecedented levels of collaboration across agencies, among nations and with the private sector. Any type of technical modernisation requires coordination among many diverse functions and initiatives.

The equipment for efficient suppression of high tech crime will be maintained, managed and updated after project completion. The costs of this will be met by the Ministry of Interior and the provision of training to the maintenance and IT teams within the respective stakeholder organisations is a critical activity in terms of project sustainability. The project will also produce manuals to guide users on how to input and manage data. The project will build training capacity so that the MoI can carry out data management training in the future.

9.	Crosscutting issues

9.1 Equal Opportunity

The project will be implemented in a way which provides equal opportunity for men and women from within the Ministry of Interior and other stakeholders to participate in project activities. No discrimination will be made on the basis of gender and activities, training will be designed in such a way that they are equally accessible to men and women. The number of men and women participating in training events will be monitored during the project.

9.2 Environment

The project has no negative effect on the environment. The project introduced an electronic information system for the management of the border crossing points and this will directly reduce the amount of paper storage and reduce the environmental cost of transporting paper based reports and data transfer.

9.3 Minorities

The project will be implemented in a way which does not discriminate against any individual on the grounds of their ethnic origin, race or religion.

10.	Conditionality and sequencing

The government is committed to the control and efficiency of Serbia’s border in terms of reducing criminal activities. In order for this to be realised, the Ministry of Interior must work closely with other key line ministries such as the Ministries of Justice and Finance. The partnership structures required for this collaboration must be established during the project and the participating ministries must be committed to the achievement of project objectives.

The Ministry of Interior must continue its progress regarding the implementation of the IBM strategy. This project forms only a part of the necessary reforms necessary to achieve the IBM goals. The Ministry of Interior must also remain committed to finding new ways to integrate border police control with other institutions in Republic of Serbia responsible for migration issues such as Ministry for human and minority rights, Commissariat for refugee’s etc.

This project aims to upgrade system of illegal migrations management by establishment of the system that should guarantee on-line, real time cross-checks of data with the national and international databases. In this respect, it is important that the legislative bases for data exchange and information exchange with custom at the national level, neighbouring countries at international level and with Europol and Frontex and Interpol is in place.

ANNEXES TO PROJECT FICHE

1. 	Logical framework matrix in standard format

2. 	Reference list of relevant laws and regulations

- ANNEX I: Logical framework matrix in standard format

| Programme name and number: Establishment of Efficient System for Prevention and Suppression of illegal Migrations on the Territory of the Republic of Serbia |  |  |  |
| --- | --- | --- | --- |
|  |  | Contracting period expires: 2 years after the signature of the FA | Disbursement period expires: 5 years after the signature of the FA |
|  |  | Total budget : 1 million EUR | IPA budget: 1 million EUR |
| Overall objective | Measurable indicators | Sources of verification |  |
| To contribute to the efficient prevention and fight against organized crime with the special attention on the suppression of illegal migrations and cyber crime in the Republic of Serbia | Established system for prevention of illegal migrations is positively assessed by the European Commission | EC Progress Report for Serbia |  |

| Project purpose | Measurable indicators | Sources of verification | Assumptions |
| --- | --- | --- | --- |
| Capacity building of the Ministry of Interior of the Republic of Serbia with the aim to develop effective and operational administrative system for illegal migration issues trough accordance of legal, procedural and technological framework with EU standards in that field regarding special investigative techniques, connection between the high-tech criminal and illegal migrations, necessary skills in combating high-tech criminal and the application of international standards in the treatment of illegal migrants and high-tech crime. | Time necessary for the verification of biometrical data of illegal migrants and asylum seekers is reduced by the end of the project. Increased number of discovered criminal offence connected with illegal migrations by abuses in the area of informational technologies Enhanced efficiency in discovering and processing of criminal offences with the elements of high-tech criminal until the end of the project. | MoI statistical reports for the defined period. Regular reports about the work of the Border Police and the Criminal Investigation Police. | Willingness for cooperation of all relevant institutions. |

| Results | Measurable indicators | Sources of verification | Assumptions |
| --- | --- | --- | --- |
| 1. Measures for tracking high-tech criminal have been assessed, improved and used in the process of overall illegal migrations prevention in responsible MoI Departments. | Document of the assessment with the recommendations for further improvements has been made, adopted and applied in the process of the system enhancement. The border police and the criminal investigation police have the capacities for regular tracking of the activities on the Internet which are related to organization of illegal migrations Increased number of forged documents which have been discovered due to the usage of high technology in combating organised crime, especially in combating THB in connection with the Early Warning System which distributes information via BCPs online Improved analyses of statistical data and risk assessment procedures Decreased number of visa applications on the basis of forged documents compared to the average number of visa applications over the past three years. | Document of the analysis. Regular reports of Border Police Directorate and the Criminal Investigation Police. Reports of competent institutions on submitted visa applications in Serbia. | Existence of the necessary legal framework |
| 2. The employees in the Ministry of the Interior are using database for gathering, saving and verification of the data regarding illegal migrants and they are able to exchange data efficiently with similar services in the region and in EU. | Increased number of discovered criminal offence connected with illegal migrations by abuses in the area of informational technologies Financial savings accomplished a result of the shortened time which foreigners used to spend in the Foreigners shelter. Efficiency of return to their country of origin. Database of illegal migrants is applied in everyday work of the Border Police Department and it is fully integrated within IS of the Ministry of the Interior | Annual reports of the Ministry of Interior and the relevant international bodies. Regular project implementation reports. | Existence of infrastructural conditions for the installation of software and hardware solutions. |
| 3. Capacities and the procedures for permanent cooperation, exchange of information and experiences with specialized and similar services in the region and Europe regarding the EU standards have been provided. | Developed protocols for the exchange of information between the relevant institutions and applied with no major difficulties. | The text of the protocol Regular project implementation reports. |  |
| 4. The employees in the Ministry of Interior poses adequate skills for applying investigative techniques and the equipment necessary for combating high-tech crime with the purpose of discovering, documenting and processing criminal offences connected with illegal migrations and providence of adequate treatment to the illegal migrants. | The employees apply in their everyday work the knowledge received during the training The reduction of financial losses that appear as a result of the credit card abuse, e-banking and e-trade transfer abuse committed by illegal migrants The improvement of government employees capacities to reveal and timely identify the victims of various types of human trafficking | Evaluation of employees by the executives Regular project implementation reports. Reports on conducted training and the evaluation of the participants. |  |

| Activities | Means /Costs | Assumptions |
| --- | --- | --- |
| Result 1: 1.1. Within the MoI, to prepare the assessment of the existing system for suppression illegal migrations and high technology crimes with identification of key gaps and provide recommendations for improvement. 1.2. To prepare a plan for the improvement of the illegal migration control system with regards to the use of new technologies and special investigation techniques. 1.3. Training for specialised technical equipment (software’s - commercial and for government purposes and for hardware) and necessary applications in order to use investigation techniques for discovering criminal offences within the domain of high technology crime, in accordance with the recommendations of the conducted assessment. Result 2: 2.1. Provide support and advice in preparation of the illegal migration database in accordance with the EU standards and technical means at the BCPs for automatic detection of passengers. 2.2. Support design and establishment of an electronic database of illegal migrants in the Republic of Serbia with a necessary capacities for data exchange with similar services in the region and in the EU. 2.3. Support process of integration of the illegal migrants database into a existing information system of MoI in accordance with the Plan on improvement of illegal migration control and best practices in suppression of high-technology crime. 2.4. Provide assistance in preparation and dissemination of the protocols and the instructions for secured and safe use of new technical and technological solutions. 2.5. Prepare and deliver trainings for the MoI employees for usage of the electronic database of illegal migrants and technologies on which the migration control system is based. - Result 3: 3.1. Organisation of national conference on abuse of high technologies in the area of illegal migrations where all the necessary steps for promotion of coordination and data exchange among countries would be defined. 3.2. Preparation of documents of protocols and agreements necessary for the information and data exchange with the interested partners in the region - 3.3. Organisation of a study visits in one of the EU member states with proven results in combating illegal migrations by using high technologies 3.4. Organisation of intership of liaison officers with one of the EU member states - Result 4: - 4.1. Preparation of 4 modules of training for the employees in the Ministry of Interior regarding special investigative techniques, connection between the high-tech criminal and illegal migrations, necessary skills in combating high-tech criminal and the application of international standards in the treatment of illegal migrants 4.2. Organisation and conducting of the training of the employees on a regional level. 4.3. Preparation and printing of booklets and manuals on the basis of the created training modules. |  |  |
| PRECONDITIONS: Secured basic normative framework for conducting activities foreseen by the Strategy and its action plan. |  |  |

- ANNEX II: Reference list of relevant laws and regulations:

General:

- National programme for integration with the European Union (NPI)

- Action Plan for the Implementation of the European Partnership Priorities

- Stabilisation and Association Agreement

Sector Legislation

- Law on the Police (Official Gazette of Republic of Serbia 101/05)

- Law on Organization and Competencies of State Authorities in Fight against High-tech Crime (Official  Gazette of Republic of Serbia 61/05)

- Law on Ratification of Convention on Cybercrime (Official Gazette of Republic of Serbia 19/09)

- Law on Ratification of Additional Protocol to the Convention on cybercrime, concerning the criminalisation of acts of a racist and xenophobic nature committed through computer systems (Official Gazette of Republic of Serbia 19/09)

- Criminal Code (Official Gazette of Republic of Serbia 85/05)

- Criminal Procedure Code (Official Gazette of Republic of Serbia 85/05)

- Law setting the Organisation and Competences of Government Agencies in suppression of Organised Crime  (Official Gazette of Republic of Serbia 42/02, 27/03, 39/03, 67/03, 29/04, 45/05, 61/05)

- Law on Personal data Protection (Official Gazette of Republic of Serbia 97/08)

- Law on Public Prosecution (Official Gazette of Republic of Serbia 116/08)

- Law on Organisation of Courts (Official Gazette of Republic of Serbia 116/08)

- Law on the Ombudsman (Official Gazette of Republic of Serbia 79/05)

EU Regulation

COUNCIL REGULATION (EC) No 343/2003, of 18 February 2003, establishing the criteria and mechanisms for determining the Member State responsible for examining an asylum application lodged in one of the Member States by a third-country national

COUNCIL REGULATION (EC) No 2725/2000, of 11 December 2000, concerning the establishment of ‘Eurodac’ for the comparison of fingerprints for the effective application of the Dublin Convention

Convention determining the State responsible for examining applications for asylum lodged in one of the Member States of the European Communities - Dublin Convention, Official Journal C 254 , 19/08/1997 p. 0001 – 0012

For Twinning light the Project fiche should be detailed as it will form an annex to the Twinning light contract together with the selected Member State proposal.