Twinning Fiche TR 10 IB JH 05

Standard Summary Project Fiche – IPA decentralised National  programmes

(maximum 12/15 pages without the annexes)

1. Basic information

1.1   CRIS Number: TR2010/0136.13

1.2   Title: Improved Court Expert System

1.3   ELARG Statistical code: 36 Political Criteria

1.4   Location: Turkey

Implementing arrangements:

1.5   Implementing Agency:

Mr. Muhsin Altun

Central Finance and Contracts Unit

Tel: +90 312 295 49 00

Fax: +90 312 286 70 72

E-mail:muhsin.altun@cfcu.gov.tr

Address: Eskisehir Yolu 4.Km.2.Street Halkbankasi Kampusu No: 63 C-Blok 06580

Sogutozu/Ankara

1.6   Beneficiary (including details of SPO):

Main Beneficiary	: Ministry of Justice DG for Criminal Affairs

SPO			: Galip Tuncay TUTAR

Deputy Undersecretary of the Justice Ministry

Tel: +90 0 312 204 10 50

Fax: +90 0 312 425 34 55

E-mail: gttutar@adalet.gov.tr

Contact  Person	:  Ziya Bekir Buğuçam

Judge, DG for EU Affairs

Tel: +90 312 414 61 47

Fax: +90 312 419 11 63

E-mail: ziya.bekir.bugucam@adalet.gov.tr

Address: Adalet Bakanlığı, Ana Bina Vekaletler Cd. No: 6 Kızılay – Ankara / 	TURKEY

Co-Beneficiary: Justice Academy of Turkey

Postal Address: İncek Yolu, Ahlatlıbel Yerleşkesi, Çankaya 06059 Ankara - TURKEY

Contact Person: Abdullah Yıldırım

Position: Judge

Institution: Justice Academy of Turkey

Tel: +90 0312 489 81 80

Fax: +90 312 489 81 01

abdullahy@adalet.gov.tr

Financing:

1.7   Overall cost (VAT excluded): 1.500.000 Euro

1.8   EU contribution: 1.425.000 Euro

1.9   Final date for contracting: 2 years after signature of financing agreement

1.10 Final date for execution of contracts:  2 years after the last day of the contracting deadline.

1.11 Final date for disbursements: 1 year after the end date for the execution of contracts.

2.   Overall Objective and Project Purpose

2.1 Overall Objective:

Strengthening the impartiality, reliability and efficiency of the judiciary

2.2 Project purpose:

Complete reform and standardization of the court expert system so that their 	contribution maximizes the efficiency, effectiveness, impartiality of the 	judiciary.

2.3 Link with AP/NPAA / EP/ SAA

2008 AP Document provides;

-To strengthen the efficiency of the judiciary through, in particular, reinforcing its institutional capacity,

2008 NPAA

Functionality and Efficiency of the Judiciary;

- In order to increase the efficiency and functionality of the Judiciary, in-service training of judges, public prosecutors and auxiliary personnel by Turkish Justice Academy and by department of Training of Ministry of Justice will continue.

- Develop and strengthen all law enforcement institutions and align their status and    functioning with European standards, including through developing inter-agency cooperation and to develop the use of modern investigative techniques.

2.4 Link with MIPD

“ Addressing the Copenhagen political criteria by supporting those institutions

directly concerned by political reforms:

- Judiciary: Comprehensive training for the consistent interpretation of legal provisions related to human rights and fundamental freedoms; Strengthening the independence, impartiality and efficiency of the judiciary; Implementation of the Istanbul Protocol throughout the country; Training of judges in judicial cooperation on civil matters; Enhancement of opportunities for effective defence such as access to legal aid and qualified interpretation services; Strengthening of legal and judicial protection of religious freedoms; as well as of minorities and vulnerable groups, in view of addressing all types of discrimination;”

  - Link with National Development Plan (where applicable)

5 year National Development no: 9 part 5.6.5 paragraph 321 states as follows:

“Moreover, providing judicial services in efficient and qualitative way is prevented because of not materializing rule of law with its all institutions and conditions, not following new developments sufficiently in drafting legal rules, slowly functioning of judicial process, not overcoming the quantitative and qualitative problems of judiciary regarding human resources and not meeting physical and technical infrastructural needs adequately.”

  - Link with national/ sectoral investment plans(where applicable)

Progress report (2009)

The Progress report suggests that ‘The court experts system continues to function as a parallel judiciary system without improving overall quality’.

Fourth Advisory Report on Effectiveness of the Judicial System (2009)

The last Advisory Report indicates that ‘A specific problem in Turkey appears to be the use of court experts, court experts can of course be of great value in technical matters where about an ordinary judge will not have sufficient knowledge of his own. But in Turkey it seems not uncommon that a judge, just to feel secure and to minimize the chance of his decision being overturned in appeal, will seek for outside guidance even in cases where he himself should be expected to have the necessary expertise. It is clear that this is far from efficient: it causes, sometimes considerable, delays and it can turn out to be a costly affair.’

Fourth Advisory Report on Criminal Justice System

Fourth Advisory Report on Criminal Justice System highly recommends:

· That the process on transferring forensic examinations to state hospitals or health

centres in accordance be expedited.

· That in cases of alleged torture or mistreatment lawyers should always be allowed to

attend forensic examinations when the person to be examined so requests.

· That the Ministry of Justice and the Ministry of Interior take all necessary steps to

inform and train law enforcement officers and physicians carrying out forensic

examinations on the subject about the provisions contained in the by-law on Apprehension, Detention, and Statement Taking

Judicial Reform Strategy

Under the title of “Reviewing expert witness (court expert) system”, the relevant paragraph states as follows:

## Widespread complaints are raised in connection with problems arising from the institution of legal expertise and court experts. In particular, there is a complaint that court experts act as if they give final judgment rather than expressing their views on issues requiring special knowledge and expertise. In addition, judges resort to court experts’ views very often due to excessive workload.

Field study in civil, administrative and military judiciary in civil, criminal and administrative procedure separately, taking into account geographical regions, the number of files received, specialized court and subject-matters of disputes will be conducted. In light of the outcomes attained, revising of institution of legal expertise, application of scientific and objective criteria in determination of court experts only specialized in private and technical fields and selection and inspection of court experts.

In this scope, the goal is to set ethical principles, to prepare a legal guide for court experts and give it to TJA and to effectively draw up a list of court experts by judicial commissions.

3. Description of project

  - Background and justification:

Legal expertise system is regulated separately under the civil and criminal procedural laws of Turkey. All of the transactions ranging from the appointment of a court expert to rejection are being regulated in Criminal Procedure Code between the article 62 and 73. Court experts on civil matters are regulated under Article 275-286 of the Civil Procedure Code which are similar to the provisions of the Criminal Procedure Code.

The courts are allowed to use court experts in the issues where the solution depends on technical and special knowledge. It is not legally possible for the courts to use court experts on the issues which judges can solve with their general and legal knowledge. In this context, court experts are viewed as assistant of judges used in the issues that are needed to be solved within the framework of the procedural law. Within the Turkish legal system, a court expert should have the technological background, should have the capacity to judge the law, should be impartial and honest in addition to possessing the relevant expertise in his/her field court expert.

In practice, those who would like to be a court expert apply to court and request to be selected as a court expert. Taking into consideration these applications, the lists of court experts are established by the judicial commissions of the courts throughout Turkey each year. It is possible to select a court expert who is not in the list provided that a justification is given. The court experts recorded in the lists are required to take an oath and have no right to deny the task. A duration is given to the court expert to prepare his/her report. In case there is an unclear point in the report, the court experts might be asked to give an additional report by the request of the parties or upon the will of the judge. Likewise where the judge is not convinced from the report a different report can be asked from a different court expert. Additionally, if there is a discrepancy between the first and second report, a third one should be taken from another court expert. It should be noted that judges or prosecutors are not bound by the reports prepared by the court experts.

Currently, judicial authorities need opinions of the court experts on very different and unpredictable issues. There are 3033 registered court experts in different fields only for İstanbul (Sultanahmet) courthouse, which is one of the 25 courthouses in İstanbul. Issues on which a court expert report is sought are mentioned below to give an overall idea on extensiveness of the issue though this is not an exhaustive list:

- textile,

- infringement of trademarks,

- industrial products,

- paternity test,

- fire, explosion,

- genetic, hereditary diseases,

- environment, water pollution, waste water,

- banking sector, credits, financial matters, accounting, credit cards, internet banking,

- embezzlement, insurance,

- labour law and labour accidents,

- taxation, misuse of power,

- cyber crimes, cd, vcd, dvd, micro casette, child pornography, voice recording,

- mobile phones, prices of computers and electronic products,

- professional diseases,

- cultural heritage values,

- licence for building,

- traffic accidents,

- cadastre works, property rights.

The court expert system has been and still is one of the most controversial issues of the Turkish judiciary. It is highly believed that the system is malfunctioning for both civil, criminal and administrative judiciary in Turkey which causes serious problems like prolonging the court proceedings, affecting adversely the impartiality and confidence in the judiciary.

The court expert system suffers from problems stemming from both the quality and competence of court experts and appointment process of them. It will not be unfair to say that some of the court experts are lacking certified professional capacity. In terms of the quality and content of reports some of them are far from being satisfactory due to the reason that the court experts do not have enough special and technical knowledge and background because the lack of education in expertise issues. Since a court expert report has an effect on the outcome of the case, it should be prepared diligently without any deficiency. The principles of reasonable trial period and the right to a fair trial are emphasized under article 6 of ECHR. The malfunctioning of court expert system is a challenge for these rights affecting negatively the efficiency and effectiveness, of the judiciary. Since reports of court experts are not standardized, courts usually receive court expert reports of poor quality and therefore need complementary second sometimes even third report which is a time consuming and exhaustive process.

In terms of the problems arising from the process itself, there is no written rules on how the service to be rendered and what qualifications the court experts need to have and last but not least no code of ethics.

Due to lack of objective criteria in the process of selection, appointment and reporting of the court experts, it has also been observed that usually same court experts are appointed in all cases by courts. This practice also puts shadow on impartiality and reliability of the judiciary.

Another criticism raised is that the court experts act as if they give the final judgment rather than expressing their views on issues requiring special knowledge and specialization. Because of excessive workload, judges resort to the expertise process so often even when it comes to matters completely interpretation of law. Unfortunately these implementations are also urged by the practices of High Courts.

This project is designed to address all these problems. It will start with a comprehensive study on court expert system to assess the gaps and needs of the current system. The study will allow new solutions to be defined during this needs assessment phase. Judges, prosecutors, authorities of relevant department of the Ministry of Justice, universities, court experts working without being affiliated to an institution, hospitals, medical faculties etc. are all the stakeholders of this project. Ministry of Justice in cooperation with Justice Academy of Turkey is in a position to gather all these stakeholders and will take lead in launching an effective study to deal with the problems of the subject matter.

Following the comprehensive study, a new system will be introduced including the guidelines, standardised reports, code of ethics and secondary legislation. It will be tested through pilot implementations.

There is no provision in the existing legislation which limits or complicates the implementation of the proposed new system. Therefore the dissemination will be performed through this secondary legislation in addition to publications and trainings throughout Turkey In an effort to implement the new system to be established throughout the country, secondary legislation will be prepared and made public by the Ministry of Justice. It is expected that the project will contribute to the whole judicial system in Turkey.

3.2 Assessment of project impact, catalytic effect, sustainability and cross border impact (where applicable)

The project will contribute to the shortening of the duration and the costs of court proceedings as well as the quality of the justice. In this way, public confidence in judiciary will be enhanced.

Through pilot implementations the system shall have a chance to observe and report the positive and negative aspects of the implementations and will have chance to modify the implemented system in local areas before dissemination.

Sustainability regarding training activities will be ensured by training of trainers in the Academy within the framework of this project, so that trainers will continue to train other court experts after the completion of project. These activities will be carried out annually and regional seminars will also be held in certain periods after the completion of the project.

Necessary measures will be gradually taken to ensure that the trained court experts will be selected by the courts and prosecution offices. By this way the court experts will be encouraged to attend the trainings.

The Ministry of Justice commits itself for the adoption of the following:

- determination of qualifications of a court expert,

- setting up of objective criteria in the process of selection and appointment of court  experts,

- development of guidelines,

- development of quality measures,

- development of code of conduct,

- development of standardised reporting system.

To ensure the implementation of the new system throughout the country, secondary legislation will be prepared and made public.

3.3 Results and measurable indicators:

3.3.1- Overall quality of the expertise services raised and court expert system subjected to concrete standards and ethical rules.

- Objections against reports of court experts decreased by 10% by first quarter of 2014 in pilot provinces.

- Demands of additional court experts reports by courts, due to the lack of clarification decreased 10 % by the last quarter of 2013 in pilot provinces.

- Discrepancies between the expertise reports conducted on same issues under the same circumstances decreased 20 % by the end of the project in pilot provinces.

- Individual- based complaints lodged to the judicial authorities about the impartiality and objectivity of court expert reports and procedural objections have decreased by 20% by the end of the pilot implementations  in pilot provinces.

3.3.2- Awareness raised in high courts, first instance courts and related parties.

- Mistakes made in first instance courts in terms of selecting the competent court expert  is reduced by 20%  in 2 years time starting from the end of the project.

- Application of individual court experts to the Justice Academy increased by a hundred percent.

  - Activities

3.4.1 Comprehensive Study on the Court Expert System for Civil, Criminal and Administrative Judiciary

At least 3 working groups will be established to review the present system, identification of shortcomings and deficits in different jurisdictions (criminal, civil and administrative) in addition to elaboration of the existing legal structure. To this end, pilot courts will be selected among the ones where different expertise fields were being used with high rates. All expertise fields will be determined in different jurisdictions in order to design standardised reporting format for expertise areas. Expert fields will be grouped under main categories. Surveys will be conducted for the baseline data to check the indicators.

3.4.1.1 Working groups including sitting judges and prosecutors from pilot courthouses, court experts from various fields of expertise, representatives of Ministry of Justice, MS experts, court experts from the other stakeholders like universities, bar associations will be established to review the present system in order to identify problems in different jurisdictions (civil, criminal and administrative judiciary).

3.4.1.2 Study visits of 5 days (for each) will be organized for the working group participants (at least 30) to three EU member states in order to observe the best practices of court expert system.

3.4.1.3 Workshops will be organized in order to discuss, compare and share the results of analyses obtained from study visits and activities of working groups with the participation of relevant stakeholders. A comprehensive assessment will be prepared taking into consideration the thoughts of relevant stakeholders including universities.

3.4.2 Development of Quality Measures For Court Experts

Following the results of the assessment report prepared in the first phase, quality measures will be developed by the project.

3.4.2.1 Qualifications will be determined for court experts from various fields

3.4.2.2 Objective criteria will be set up for the selection and appointment process of court experts.

3.4.2.3 Guide(line)s  will be prepared for court experts in order to  ensure standardisation  and  harmonization of  the implementation.

3.4.2.4 Quality (standardisation) measures will be set for individual court experts and institutions

3.4.2.5 A code of conduct will be drafted for court experts

3.4.2.6 Standardized reporting format will be drafted for main categories of expertise which were determined after need analyses as mentioned under 3.4.1.

3.4.3 Pilot Implementation

3.4.3.1. Five seminars will be organised for the professional organisations providing court experts to the pilot provinces on the new system.

3.4.3.2 Five seminars will be organised for the judges and prosecutors of the pilot courthouses on the implementation of objective criteria for the selection and appointment process of court experts and standardization of court expert reports.

3.4.3.3 A curriculum on code of ethics, standardized reports, guidelines and basic legal knowledge for court experts will be drafted together with the MS experts.

3.4.3.4 100 trainers will be trained within the framework of curriculum designed under activity 3.4.3.3 in the academy

3.4.3.5 Since the total number of court experts listed under the pilot courthouses is unknown at this stage at least 300 court experts will be trained by trainers in line with curriculum.

3.4.3.6 Following the results of the pilot implementation, secondary legislation will be drafted for dissemination of the system to whole country.

3.4.4 Awareness raising activities / Dissemination of the results of the project and publication of the rules and standards

3.4.4.1 An international seminar will be held at the Justice Academy with the participation of the judges and prosecutors from high courts and first instance courts where pilot implementations were held, universities having forensic branches, court experts from professional chambers and relevant stakeholders.

3.4.4.2. The outcomes of the seminar will be published. The book will be distributed to all courthouses and relevant stakeholders and will be made accessible to all court experts through the website of Ministry of Justice.

3.4.4.3. The Code of conduct will be disseminated through publications, distributed to all professional chambers and relevant stakeholders and made available on-line on the websites of the courthouses throughout Turkey.

3.4.4.4 Reporting formats, guidelines and determined objective criteria for selection standards of court experts will also be publicized through publications, distributed to all professional chambers and relevant stakeholders and made available on-line on the websites of the courthouses throughout Turkey.

3.4.4.5 For the dissemination of the new system; in line with the curriculum designed, training activities will start for the rest of the court experts by the Justice Academy.

3.5 Conditionality and sequencing:

NA

3.6 Linked activities NA

3.7 Lessons learned

One of the lessons learned in this area is that projects addressing the political criteria should not be defined with overly ambitious objectives. Thus, this project has been designed so as to focus on standardization of court expert reports as well training of court experts in this area and ethical rules.

In addition, these training activities should be undertaken in a more professional and institutionalized manner in which the Academy should involve. For that purpose, the Academy should be able to deliver training for judges and prosecutors through well-structured trainers/experts pool. Thus it is of great importance to train trainer/experts on particular issues in order to enable the Academy to have the above mentioned training pool. Sustainability plans to be attained in this way.

Full contribution of beneficiary country personnel in the project must be provided, and the workshops and other activities must be held out of the facilities where they are in charge. This would prevent the lack of concentration stemming from the unexpected interruptions of their daily occupations.

Since the project will be run through a twinning covenant, the project team shall have a very good cooperative approach. Particularly, the resident twinning advisor and his counterpart should work in close collaboration and mutual understanding.

4. Indicative Budget (amounts in EUR)

|  |  |  |  |  | SOURCES OF FUNDING |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | TOTAL EXP.RE | TOTAL PUBLIC EXP.RE | IPA CONTRIBUTION |  | NATIONAL PUBLIC CONTRIBUTION |  |  |  |  | PRIVATE CONTRIBUTION (Council of Europe) 5% |  |
| ACTIVITIES | IB (1) | INV (1) | EUR (a)=(b)+(e) | EUR (b)=(c)+(d) | EUR (c) | % (2) | Total EUR (d)=(x)+(y)+(z) | % (2) | Central EUR (x) | Regional/Local EUR (y) | IFIs EUR (z) | EUR (e) | % (3) |
| Activity 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Twinning contract | X |  | 1500000 | 1500000 | 1425000 | 95 | 75000 | 5 | 75000 | 0 | 0 | 0 | 0 |
| TOTAL IB |  |  | 1500000 | 1500000 | 1425000 |  | 75000 |  | 75000 | 0 | 0 | 0 | 0 |
| TOTAL INV |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT |  |  | 1500000 | 1500000 | 1425000 |  | 75000 |  | 75000 |  |  |  |  |

NOTE: DO NOT MIX IB AND INV IN THE SAME ACTIVITY ROW. USE SEPARATE ROW

Amounts net of VAT

(1)	In the Activity row use "X" to identify whether IB or INV

(2)	Expressed in % of the Public Expenditure (column (b))

(3) 	Expressed in % of the Total Expenditure (column (a))

For Twinning contracts joint cofinancing will be provided to cover 5% of the costs of the Twinning contract. Additional parallel cofinancing will be provided in order to cover costs of activities not eligible for IPA support in line with the Twinning Manual.

5. Indicative Implementation Schedule (periods broken down per quarter)

| Contracts | Start of Tendering | Signature of contract | Project Completion |
| --- | --- | --- | --- |
| Twinning Contract (2 Year) | IQ 2011 | IVQ 2011 | IVQ 2013 |

All projects should in principle be ready for tendering in the 1ST Quarter following the signature of the FA

6. Cross cutting issues (where applicable)

6.1	Equal Opportunity

Participation in his project will be open to both males and females involved in the sector. Records of professionals’ participation in all project related activities will reflect this and will be kept with the project documentation. All the staff of the pilot execution offices will involve the activities of the project equally.

6.2	Environment

NA

6.3	Minorities and Vulnerable Groups

According to the Turkish Constitutional System, the word minority encompasses only group of persons defined and recognized as such on the basis of multilateral or bilateral instruments to which Turkey is a party. This project has no negative impact on minority and vulnerable groups.

6.4 	Civil Society

Turkey Bars Association has been informed about the preparation of the project. Although the project preparation team could not find the opportunity to work on the project fiche together with the representative of the Association, having received information about the content of the project, the representative gave a very positive reaction to the purpose and the activities. It is worth mentioning that the Association would very much like to contribute to the project especially in the implementation phase.

ANNEXES

1-	Log frame in Standard Format

2-	Amounts contracted and Disbursed per Quarter over the full duration of Programme

3-	Description of Institutional Framework

4 -	Reference to laws, regulations and strategic documents:

Reference list of relevant laws and regulations

Reference to AP /NPAA / EP / SAA

Reference to MIPD

Reference to National Development Plan

Reference to national / sector investment plans

5-	Details per EU funded contract (*) where applicable:

For TA contracts: account of tasks expected from the contractor

For twinning covenants:  account of tasks expected from the team leader, 	resident twinning advisor and short term experts

For grants schemes:  account of components of the schemes

For investment contracts: reference list of feasibility study as well as technical specifications and cost price schedule + section to be filled in on investment criteria (**)

For works contracts: reference list of feasibility study for the constructing works part of the contract as well as a section on investment criteria (**); account of services to be carried out for the service part of the contract

(*) non standard aspects (in case of derogation to PRAG) 	also to be specified

(**) section on investment criteria (applicable to all infrastructure contracts and constructing works):

- Rate of return

- Co financing

- compliance with state aids provisions

Ownership of assets (current and after project completion)

ANNEX 1: Logical framework matrix in standard format

| LOGFRAME PLANNING MATRIX FOR Project Fiche |  | Programme name and number PIS 45 |  |  |
| --- | --- | --- | --- | --- |
| Improving the Functioning of Court Expert System in Turkey |  | Contracting period expired 2 years after the signature of financing agreement | Disbursement period expires 1 year after the end date for the execution of the contracts |  |
|  |  | Total budget : 1.500.000 € | IPA budget: 1.425.000 € |  |
| Overall objective | Objectively verifiable indicators | Sources of Verification |  |  |
| Strengthening the impartiality, reliability and efficiency of the judiciary. | Positive assessment on the efficiency of the judiciary in the Regular Report issued in the last quarter of 2013. Substantial decrease in criticism in EU documents by 2014 | EU Regular Reports Relevant EU Documents |  |  |
| Project purpose | Objectively verifiable indicators | Sources of Verification |  | Assumptions |
| Completed reform and standardisation of the court expert system so that their contribution maximizes the efficiency, effectiveness, and impartiality of the judiciary. | Expertise services standardised and its credibility raised by 10 % by the end of the project. Decrease by %10 in average duration of trials in the pilot courthouses. At least 300 court experts trained by the end of project Seminars held to increase awareness | Evaluation and expert mission reports. Statistical data gathered by the Ministry of Justice. Project Reports |  |  |

| Results | Objectively verifiable indicators | Sources of Verification | Assumptions |
| --- | --- | --- | --- |
| 1-Overall quality of the expertise services raised and court expert system subjected to concrete standards and ethical rules. 2- Awareness raised in high courts, first instance courts and related parties | - Objections against reports of court experts decreased by 10% by first quarter of 2014 in pilot provinces. - Demands of additional court experts reports by courts, due to the lack of clarification decreased 10 % by the last quarter of 2013 in pilot provinces. - Discrepancies between the expertise reports conducted on same issues under the same circumstances decreased 20 % by the end of the project in pilot provinces. - Individual-based complaints lodged to the judicial authorities about the impartiality and objectivity of court expert reports and procedural objections have decreased by 20% by the end of the pilot implementations in pilot provinces. - Mistakes made in first instance courts in terms of selecting the competent court expert is reduced by 20% in 2 years time starting from the end of the project. - Application of individual court experts to the Justice Academy increased by a hundred percent. | -Project reports -Monitoring and Progress reports -Quarterly Reports to Steering Committee -Peer Based Mission Reports (Advisory Reports) -Surveys conducted among the relevant stakeholders and public. | -Full commitment of the involved authorities (Turkish Justice Academy) - |
| 2- Awareness raised in high courts, first instance courts and related parties. | - Quash rate of judgments which are given from the courts in the appeal process reduced on the grounds that the process was lacking appointment of a court expert despite it was required 5% within 3 years ( taking into account of the average duration of an ordinary appeal process) from end of the project activities. - Mistakes made in first instance courts in terms of selecting the competent person as expert witness is reduced by 20% in 2 years time starting from the end of the project. |  |  |

| Activities | Means | Costs | Assumptions |
| --- | --- | --- | --- |
| 3.4.1. Comprehensive Study on the Court Expert System For Civil, Criminal and Administrative Judiciary At least 3 working groups will be established to review the present system, identification of shortcomings and deficits in different jurisdictions (criminal, civil and administrative) in addition to elaboration of the existing legal structure. To this end, pilot courts will be selected among the ones where different expertise fields were being used with high rates. All expertise fields will be determined in different jurisdictions in order to design standardised reporting format for expertise areas. Expert fields will be grouped under main categories. Surveys will be conducted for the baseline data to check the indicators. 3.4.1.1. Working groups including sitting judges and prosecutors from pilot courthouses, court experts from various fields of expertise, representatives of Ministry of Justice, MS experts, court experts from the other stakeholders like universities, bar associations will be established to review the present system in order to identify problems in different jurisdictions (civil, criminal and administrative judiciary). 3.4.1.2. Study visits of 5 days (for each) will be organised for the working group participants (at least 30) to three EU member states in order to observe the best practices of court expert system. 3.4.1.3. Workshops will be organized in order to discuss, compare and share the results of analyses obtained from study visits and activities of working groups with the participation of relevant stakeholders. A comprehensive assessment will be prepared taking into consideration the thoughts of relevant stakeholders including universities. 3.4.2 Development of Quality Measures For Court Experts Following the results of the assessment report prepared in the first phase, quality measures will be developed by the project. 3.4.2.1 Qualifications will be determined for court experts from various fields 3.4.2.2 Objective criteria will be set up for the selection and appointment process of court experts. 3.4.2.3 Guide(line)s will be prepared for court experts in order to ensure standardisation and harmonization of the implementation. 3.4.2.4 Quality (standardisation) measures will be set for individual court experts and institutions 3.4.2.5 A code of conduct will be drafted for court experts 3.4.2.6 Standardized reporting format will be drafted for main categories of expertise which were determined after need analyses as mentioned under 3.4.1. 3.4.3 Pilot Implementation 3.4.3.1. Five seminars will be organised for the professional organisations providing court experts to the pilot provinces on the new system. 3.4.3.2. Five seminars will be organised for the judges and prosecutors of the pilot courthouses on the implementation of objective criteria for the selection and appointment process of court experts and standardisation of court expert reports. 3.4.3.3. A curriculum on code of ethics, standardized reports, guidelines and basic legal knowledge for court experts will be drafted together with the MS experts. 3.4.3.4 100 trainers will be trained within the framework of curriculum designed under activity 3.4.3.3 in the academy 3.4.3.5 Since the total number of court experts listed under the pilot courthouses is unknown at this stage at least 300 court experts will be trained by trainers in line with curriculum. 3.4.3.6 Following the results of the pilot implementation, secondary legislation will be drafted for dissemination of the system to whole country. 3.4.4 Awareness raising activities / Dissemination of the results of the project and publication of the rules and standards 3.4.4.1 An international seminar will be held at the Justice Academy with the participation of the judges and prosecutors from high courts and first instance courts where pilot implementations were held, universities having forensic branches, court experts from professional chambers and relevant stakeholders. 3.4.4.2. The outcomes of the seminar will be published. The book will be distributed to all courthouses and relevant stakeholders and will be made accessible to all court experts through the website of Ministry of Justice. 3.4.4.3. The Code of conduct will be disseminated through publications, distributed to all professional chambers and relevant stakeholders and made available on-line on the websites of the courthouses throughout Turkey. 3.4.4.4 Reporting formats, guidelines and determined objective criteria for selection standards of court experts will also be publicized through publications, distributed to all professional chambers and relevant stakeholders and made available on-line on the websites of the courthouses throughout Turkey. 3.4.4.5 For the dissemination of the new system; in line with the curriculum designed, training activities will start for the rest of the court experts by the Justice Academy. | Twinning | 1.500.000 € |  |

ANNEX II:	amounts (in €) Contracted and disbursed by quarter for the project (IPA contribution only)

| Contracted | 4Q/2011 | 1Q/2012 | 2Q/2012 | 3Q/2012 | 4Q/2012 | 1Q/2013 | 2Q/2013 | 3Q/2013 | 4Q/2013 | 1Q/2014 | 2Q/2014 | 3Q/2014 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Twinning Contract 1.1 | 142.500€ |  |  |  |  |  |  |  |  |  |  |  |
| Cumulated | 142.500€ |  |  |  |  |  |  |  |  |  |  |  |
| Disbursed |  | 570.000€ |  |  | 262500 |  |  | 225000 |  |  | 225000 | 142.500€ |
| Cumulated |  | 570.000€ |  |  | 832500 |  |  | 1057500 |  |  | 1282500 | 1.425.000€ |

**

ANNEX III Description of Institutional Framework

Ministry of Justice has established a permanent unit called “Project Coordination Board” (PCB) consisting of the Director Generals of seven Directorates of the Ministry. This Board is responsible not only for the EU funded projects but also all other projects including bilateral, multilateral ones etc. The DGs in the Ministry have to report all their activities regarding project works at the meetings of the PCB. Main function of the Board is to contribute towards restructuring Turkish Judiciary and enhancing its efficiency, by conducting coordination among relevant directorates of the Ministry in the Project activities with the EU, other countries and International Institutions. Head of the PCB is a deputy undersecretary who is the Senior Project Officer (SPO) of the Project at the same time. High level representation of the Directorates shows strong commitment of the relevant departments of the Ministry. In addition, within the DG for EU Affairs, there are five rapporteur judges whose responsibilities are to, among others, contribute to all project activities. In this way, they will be available for substituting each other in case of any absence.

For this project specifically, a Steering Committee (PSC) will be set up. At quarterly intervals, the Project Leaders, the RTA, the RTA Counterpart, senior representatives of the Ministry of Justice, representative of Turkish Bars Association, CFCU, the EUSG and the EU Delegation will meet to discuss the progress of the project, verify the achievement of the outputs and mandatory results and discuss actions to be undertaken in the following quarter. The Project Steering Committee will also discuss the draft of the quarterly report submitted to it beforehand, recommend correction. The responsibility for the organization of the Project Steering Committee meeting lies with both Project Leaders.

The co beneficiary Justice Academy of Turkey, with its new Administration consisting of open-minded superiors, provides strong support to the project. Furthermore, it has number of personnel most of whom are judges and prosecutors having good command on foreign language(s) and experiences on project implementation. In addition, legislation regarding the establishment of the Academy enables to recruit contracted personnel in case it is needed in the course of the project implementation phase. Moreover, the budget of the Academy is rather sufficient to undertake the project responsibilities. Therefore, there is no concrete obstacle to run the project.

The Academy is able to accommodate around 400 trainees in its facilities. 1200 trainees can be trained in the same period. It has around 300 trainers. A project department solely responsible for running projects exist in the academy

The above information points to the capability of the Academy to be involved as a co-beneficiary of the project.

### Steering Committee

It will be formed by the representatives from the Twinning Partner,

Justice Academy of Turkey,

The Ministry of Justice (Under secretariat, DG for Criminal Affairs, DG for EU Affairs, DG for Civil Law Affairs , DG for Legislation , IT Department, Strategic Development Department),

Turkish Bars Association,

EUSG,

EU Delegation to Turkey.

Representatives from the CFCU will participate in the Steering Committee meetings as observers.

The Steering Committee will elaborate the strategic options of the programme and address the major problems that the programme might face. The Steering Committee shall be called to meet at the beginning of the programme and every three months or when a serious problem arises.  The responsibilities of the Steering Committee are the following:

- To make an assessment of emerging needs for a sound project implementation.

- To adopt the overall work programme and the annual work plans

- Recommend strategies in the light of national sectoral priorities and Accession Partnership

- To conduct a final review of the implementation.

- To ensure that any measure is taken to ensure the widest possible dissemination of the project results (e.g. to organise additional training activities to be conducted by the trainers who benefited from the programme courses).

- To recommend strategies for future sustainability.

ANNEX IV Reference to Laws, Regulations and Strategic Documents

Reference list of relevant laws and regulations

1--Criminal Procedural Code

2- Turkish Penal Code

3- Turkish Civil Code

4- Civil Procedural Code

5- Administrative Procedural Code

6- Act on Establishment, Duties and Competences of First Instance Courts and Regional Courts of Appeal.

7- Advocateship law

8-Turkish Commerce Law

Reference to AP /NPAA / EP / SAA

1-AP 2008

2-NPAA 2008

Reference to MIPD

1-MIPD 2008 – 2010

Reference to National Development Plan

5 Year Development Plan no: 9

Reference to national / sector investment plans

N/A

ANNEX V Details per EU funded contract (*) where applicable

For twinning contracts:  account of tasks expected from project leader, resident twinning advisor and short term experts

The project will be implemented in the form of a Twinning contract between Turkey and a Member State/Member States. The overall duration of the project is envisaged to be 24 months with activities to take place during the 21 months.

The Twinning partner(s) will provide a Resident Twinning Advisor (RTA) and also secure a pool of short- term experts, who will be called upon whenever necessary to contribute to the achievement of the mandatory results and especially for the purpose of advisory services and training according to the work plan that will be prepared as part of the corresponding contract.

The EU Twinning partner will be a Member State institution directly involved in Court Expert System. Member States may also form a consortium which could result in a wide range of qualified senior experts gathered from public administrations or mandated bodies from up to two Member State, provided that national approaches can be harmonized within this consortium.

1. PL (Project Leader):

The PL should be a high ranking official with broad knowledge of all processes in the area of   Justice and Home Affairs that the project deals with, who will continue to work at his/her Member State (MS) administration but devote some of his/her time to conceive, supervise and co-ordinate the overall thrust of the Twinning project.

The PL will allocate a minimum of 3 days per month including one visit every 3 months (more for complex projects) to Turkey as long the project lasts.

a) Qualifications:

1 - Broad long-term knowledge of all processes in the area of acquis that the project is dealing with;

2 - High-ranking official, commensurate with an operational dialogue at vice-ministerial level;

3 - Overall appreciation of the problems and solutions in the sector;

4 - Capable of unblocking any problems at highest level;

5 - Good leadership skills.

6 - Good written and oral command of English

b) Tasks:

1 - Overall project co-ordination;

2 - Co-chairing, with the Turkish PL, the regular project implementation steering committee meetings;

3 - Mobilizing short term experts;

4 - Executing administrative issues (i.e. signing reports, administrative order etc.).

2. Resident Twinning Advisor (RTA):

a) RTA background

The RTA is expected to co-ordinate all training and awareness raising activities of the project. He will be located at the Ministry of Justice Ankara, General Directorate for Criminal Affairs. He/she has to be a person with significant experience as a manager and should have a capacity for initiating new projects. Experience of working outside of the home country administration would be an advantage. In addition to the short term experts, he/she will also occasionally work together with Ministry of Justice to provide inputs focused on:

-Advice to the Ministry of Justice in the design and establishment of a training system

-The co-ordination - together with Ministry of Justice   in Ankara - of the organization of training and lecturers

-facilitation of EU member states best practices and potential for their implementation in expertise fields in Turkey

The RTA must be highly qualified in public affairs and the field of court expert system  covered by the twinning contract, and must possess good management skills. Experience with the operation of pre-accession programmes would be a comparative advantage.

b) RTA qualifications

- Minimum of  5 years  experience in the field;

- Long term experience in the court expert system, the  problems they have faced, the relations between the relevant institutions including  courts, Ministry of Justice etc.

- Familiar with expertise issues in a European Union Member State with particular emphasis on institutional set-up and implementation;

- Preferably a comparative knowledge of other Member States systems;

- Experience in project management;

- Experience in the participation of a legislative process/law drafting;

- Broad international contacts/exposure will be an asset;

- Advanced university degree;

- Strong written, oral and inter-personal communication skills in English;

- Good communication skills and experience in developing, co-coordinating and conducting training programmes;

- Experience in managing a large team of experts;

- Experience in working in a different cultural environment an advantage.

c) RTA tasks

To design a work plan for the implementation of the programme and to assist the process of drawing up a contract;

Assist in the preparation of all strategic project documents [inception study, sector strategy/policy/plan, quarterly monitoring reports, final project report, training manuals etc.]

To ensure continuity of implementation through: the enforcement of the day to day management; working on a daily basis with the Ministry of Justice staff to implement the project;

To plan and coordinate outputs;

Together with the Project Leader: to nominate and mobilize the short term experts;

To supervise the short term experts

To coordinate and organize study visits, training activities, workshops and public awareness activities;

To ensure proper quality of outputs;

To provide detailed reports on the impact of the project.

3. Short-term experts

a) Experts’ qualifications

Minimum of 3 years professional experience in their respective field,

- Advanced university degree in a relevant subject;

- They should be professionally qualified and have the appropriate experience in the area and subjects that they are selected for.

- Previous experience of working in other cultures and countries will be an advantage.

Good written and oral command of English;

Proven contractual relation to public administration or mandated body;

Capacity to integrate into a large expert team;

Willingness to work in a different cultural environment.

b) Experts’ tasks

  - To contribute to the project with specialist knowledge in the area of  judiciary;

  - To provide specialist support services [e.g. providing Turkey with access to databases];

  - To prepare training course modules;

  - Delivery of selected training modules to the probation officers.

  - Advice and backstopping from a national EU Ministry of Justice.

Short Term Experts will work together with the staff of the beneficiary institution under the overall direction of the beneficiary institution and the Project Steering Committee. In addition to providing the twinning partner with adequate staff and other resources to operate effectively, the senior management of the beneficiary institution is expected to be involved in the development and implementation of policies and institutional change required to deliver the project results.

Estimated Costs For Each Item

MS - Project Leader

(Including costs of visits to Turkey)	50.000

RTA – Costs	 350.000

Linguistic Assistant	40.000

RTA Assistant                                                                                          40.000

Short–time experts (incl. seminars, working groups, training of

Trainers and etc.)                                                                                    500.000

Expenses for Holding an international seminar    	 70.000

Study visits to MS                                                                                           70.000

Documentation, publications, awareness raising activities	 220.000

Translation costs                                                                                             100.000

Contingency	60.000

TOTAL					              1.500.000

In the context of beneficiary staff participating in missions outside of Turkey paid for under a contract, the maximum amounts eligible for accommodation costs and daily allowances ("per diems") are the official rates provided for by Europe Aid for the destination country (see website for the latest rate). Provided the total cost of daily allowance and accommodation charged to the contract remains below these maximum rates, the applicable Turkish rules and regulations for per diems shall be applied when reimbursing these costs for public servants from the beneficiary institutions. Where a contract foresees the reimbursement of such expenses for Turkish public servants and other beneficiaries of IPA projects during missions inside of Turkey, the maximum costs reimbursed under the contract will be those provided for domestic missions under the applicable Turkish legislation provided that they are subject  to the same ceiling for maximum rates. This provision cannot be construed and applied in contradiction with the IPA Framework Agreement and in particular the IPA Implementing Regulation.

The total cost of the project should be net of VAT and/or other taxes. Should this not be the case, the amount of VAT and the reasons why it should be considered eligible should be clearly indicated (see Section 7.6)