2009 Project Fiche Kosovo – IPA centralised programmes

KS 09 IB JH 01

1. Basic information

1.1   CRIS Number:	2009/021-145

1.2   Title: 					Improved education in the Public Safety and Security

Sectors

1.3   ELARG Statistical code: 	01.24

1.4   Location: 				Kosovo (UNSCR 1244)

Implementing arrangements:

1.5   Contracting Authority: 	European Commission Liaison Office to Kosovo

1.6   Implementing Agency: 		N/A

1.7   Beneficiary (including details of project manager):

| Project activity | Beneficiary (institutions, target group etc) | Contact point responsible for project coordination |
| --- | --- | --- |
| 1. Improved education in the Public Safety and Security sectors | Ministry of Internal Affairs | Mr. Xhelal Shaqiri, IPA Coordinator, MIA |

1.8   Overall cost:  		EUR 1.5 million

1.9   EU contribution:  		EUR 1.5 million

1.10 Final date for contracting:

Three years after the signature of the financing agreement between the European Commission and the Kosovo Authorities.

1.11 Final date for execution of contracts:

30 months after the final date for contracting.

1.12 Final date for disbursements:

One year after the final date for the execution of contracts

2.   Overall Objective and Project Purpose

2.1 Overall Objective:

To strengthen the rule of law in Kosovo through further reform of the relevant institutions and alignment with and implementation of the acquis and European standards in the area of Justice, Freedom and Security.

2.2 Project purpose:

To improve education in the Public Safety and Security sectors

Training of police, penitentiary staff, customs officials and fire-fighters in Kosovo is currently done in a training centre set up by OSCE that has been transformed into an executive agency under the Ministry of Internal Affairs in March 2008. Basic training for police is below internationally acceptable standards (40 weeks in total), and more specialised training is done on an ad-hoc basis by international trainers. No systematic higher education or accredited training courses are currently available for middle and higher management. The development of curricula and accreditation procedures for both basic and advanced training, including the setting up of a Higher Education Institution in the field of public safety, in line with the requirements of the Bologna process, would help to strengthen management, in the medium and long-term to address capacity deficits in the police, customs, the penitentiary and the fire-fighting services, thus increasing the efficiency of the fight against (inter alia) organised crime, including trafficking in human beings and smuggling.

2.3 Link with: European Partnership; Stabilisation and Association process; Proposal for the Kosovo Status Settlement

The European Partnership calls for:

- Continuous strengthening of property rights, the legal framework and the accessibility of courts, with a view to promoting a business friendly environment.

- Ensuring effective, independent, accountable and impartial courts and prosecution offices, free from political influence.

- Strengthening of the prosecutor's office to ensure that it is able to comply with the principles of autonomy and impartiality. Continued strengthening of the Special Prosecutor's Office. Ensure the implementation of a n efficient witness protection scheme

- Implementation of an automated case management system fully in all courts and prosecution offices.

- Reduction in the backlog of cases and the enforcement of civil court decisions.

- Further development of legal education and training, particularly for judges, prosecutors and administrative personnel. Transformation of the Judicial Institute into a viable institution responsible for judicial training.

- Strengthening the administrative capacity, coordination and effectiveness of the judiciary and all law enforcement agencies. Ensuring the viability of a comprehensive legal aid system

- Improving the functioning of the judiciary, guarantee its independence, accountability, professionalism and efficiency and ensuring that the career development and recruitment of judges and prosecutors is based on technical and professional criteria and free from political influence. Ensuring proper functioning of the Constitutional Court.

- Improving the effectiveness of investigation of crime. Adopt and implement legislation to establish the KPS and strengthening its investigative and internal control capacities. Strengthening its leadership.

- Further strengthening local capacity in the organised crime directorate within the KPS.

- Implementing the law on the suppression of corruption and the anti corruption plan. Strengthen the anti corruption agency and take measures to fully ensure its independence and functioning.

2.4 	Link with the Multi-Annual Indicative Planning Document (2009-2011) for Kosovo (MIPD)

The project supports key objectives of the MIPD - for 2009 – 2011, the strategic choices are reflected in the following three Axes:

Axis 1: Political Criteria

- The authorities of Kosovo should be assisted by the international presence (International Civilian Representative, EU rule of law mission EULEX, International Military Presence) which has corrective, monitoring and mentoring functions. Donors will be called upon to help set up administrative structures and build local capacities. While UNMIK and Kosovo's PISG have made good progress in setting up an administrative system, starting almost from scratch in 1999, it is recognised that due to its specific history, Kosovo needs to further develop in order to establish a multi-ethnic, democratic society firmly anchored in the rule of law. EC assistance should focus on achieving this aim. As a result, the focus under this Axis should be on the fulfilment of the EU's political criteria and consolidation of Kosovo's institutional, administrative and judicial set-up, including the fight against corruption, the protection of the Serb and other minorities and the promotion of civil society activities.

- Consolidating the rule of law by strengthening the wider judicial system and supporting police reform and the fight against corruption, in close cooperation with the ESDP mission to ensure a coordinated and mutually reinforcing approach.

2.5 Link with National Development Plan

The project links to the following MTEF Sector Objectives in the field of Rule of Law:

Justice System Goals: I. Construction and renovations of facilities for Kosovo Judiciary (in particular courtrooms, prosecution offices and KJC premises), II. Reduction in backlog of court cases and III. Combat and prevent crime;

Law Enforcement Goal IV: Increased service quality for citizens – will be achieved through these objectives:

1. Supplying citizens with personal documents in line with EU standards:

a) Supplying citizens with personal documents.

b) Setting up a secure and functional civil registration system.

2. Necessary information – communication infrastructure, improvement of work space and conditions, and training facilities:

a) Upgrade of information technology;

b) Necessary work space, higher efficiency in provision of services to citizens;

c) Upgrade of work and safety conditions

  - Link with national/ sectorial investment plans

- No investment plan other than the MTEF is available

- Description of project

3.1. To improve education in the Public Safety and Security sectors

One of the key factors in the development of the rule of law sector in Kosovo is education, especially in the law enforcement related issues.

Training of police, penitentiary staff, customs officials and fire-fighters in Kosovo is currently done with guidance from the OSCE in the Kosovo Centre for Public Security, Education and Development, which was converted into an executive Agency under the Ministry of Internal Affairsin March 2008. A working group has been established by Minister of Internal Affairs to draft the Law establishing what will be "the Kosovo Centre for Public Safety".

Basic training courses are far below international acceptable standards, as an example police basic training lasts just 40 weeks, and currently not even all basic training courses are conducted anymore. Most of the training delivered is only on a basic level, with more specialised training done on an ad-hoc basis by international trainers. No systematic higher education or accredited training courses are available for middle or higher ranking law-enforcement officers. The development of curricula and accreditation procedures for both basic and advanced training, including the setting up of a Higher Education Institution in the field of public safety, in line with the requirements of the Bologna process, would help to address, in the medium and long-term management deficiencies in Police, Customs, the penitentiary and the fire-fighting services, thus increasing the efficiency of the fight against (inter alia) organised crime, including trafficking in human beings and smuggling. In the past, the KCPSED has received substantial (and continuing) assistance from other donors (OSCE, US); however, it is critical that this institution is set up in line with European best practices and with the requirements of the Bologna process.

3.2 	Assessment of project impact, catalytic effect, sustainability and cross border impact

To improve education in the Public Safety and Security sectors

Developing of training curricula, the accreditation of the KCPSED, the delivery of training for trainers, elaboration of training materials,  and the establishment and accreditation of a higher training institution will increase the level of professionalism of public safety workers (police, customs, penitentiary and fire-fighters), improve the fight against organised crime and smuggling (and thus the rule of law), increase public security and the acceptance of the public safety institutions by the broader public. Raising the professional competence of customs officials can drastically increase the collection of revenue for the Kosovo Consolidated Budget (KCB).

3.3 Results and measurable indicators

Component 1. To improve education in the Public Safety and Security sectors

- Expected Results:

- Higher professionalism, efficiency and public acceptance of Kosovo Police, Customs, Penitentiary Service and Fire-fighters

- Basic Training Courses for Police, Customs, Penitentiary Service, Fire-fighters improved and institutionalized and meeting international minimum standards

- Higher education institution for public safety and security set up and functional

- Training curricula accredited by Kosovo authorities and in line with Bologna requirements

- Mechanism  for using ECTS system in place

- Measurable indicators:

- EC reports, statistics, number of criminal cases forwarded successfully to prosecution, amount of revenue raised for KCB

- Training courses set up

- Higher education institution functional and accredited

- Curricula accredited

- ECTS system in place and accredited

3.4 Activities:

Component 1. To improve education in the Public Safety and Security sectors

This activity, implemented via a Twinning Contract, will consist in helping the Kosovo Center for Public Safety Education and Development to review its curricula and training activities for basic training of Police, Customs, Penitentiary staff as well as fire-fighters in line with European standards. The RTA will review the organisational structure of the KCPSED, including an analysis of workflow and control, and provide recommendations for improvement based on best practice examples. He/she will advise the KPCSED management on setting up a higher education institution for public safety and security studies and on the developing of curricula for higher education in line with the Bologna Process and the ECTS. He/she will set up training courses, in particular "train-the-trainer" activities, and work, together with the Ministry of Internal Affairs and the Ministry of Education, towards the accreditation of the Centre by both the relevant national and international bodies. This activity shall be implemented in close cooperation with EULEX and OSCE.

Contracting arrangements:

1. Improved education in the Public Safety and Security sectors

The instrument of twinning will be used to implement this activity. Standard twinning procedures are to be used. The Resident Twinning Advisor (RTA) is expected to be a senior civil servant from a similar institution of member states (i.e. Police Academy). The RTA will be assisted by EU MS short and medium-term experts.

RTA Profile:

- Experience in higher education institute closely related to policing;

- Experience in the development of the curricula and training activities for basic Police, Customs, Penitentiary and fire and rescue;

- Fluency in English;

- Degree in social sciences, law or other relevant area to the sector.

Project management and administration

The European Commission Liaison Office in Pristina will manage the procurement, implementation, quality control, reporting and coordination with EULEX and other donors.

A Project Steering Committee will be responsible for the overall direction of the project and comprise of representatives from the beneficiary institutions and the Commission Office.

Monitoring will be performed centrally by the Commission.  The project may be evaluated at the interim or ex-post stages under the supervision of Commission’s Evaluation Unit. The project may be audited by Court of Auditors - in line with the standard European Commission procedures.

3.5 Conditionality and sequencing:

The project includes the following conditionalities:

Component 1. Improved education in the Public Safety and Security sectors

- Retention mechanisms in place (obligation for graduates to work for a defined number of years in their field of specialisation in the Kosovo public sector)

- Kosovo accreditation agency functional

- Career plans for public safety workers available

In the event that conditionalities are not met, the European Commission Liaison Office to Kosovo reserves itself the right to suspend or cancel the Project.

3.6 Linked activities

Activities of other donor have an important role to play in Kosovo and the coordination of this help is an important and complex task. Key donors with significant on-going or planned activities in the Rule of Law sector include the US (USAID/NCSC and US Department of Justice), UNDP, Swiss Cooperation Office and SIDA. Close coordination with the Eulex Rule of Law mission have to be ensured.

One of the initial tasks of the OSCE Mission was to establish a police school that would train a multi-ethnic Kosovo police service. As the police school’s excellence and training capacity grew it also started providing training to other public safety institutions, such as customs, corrections and fire and rescue services. Even after the transfer into an executive agency under the Ministry of Internal Affairs, OSCE still provides support in developing joint training programmes for all the public safety institutions to improve their co-ordinated performance according to the international best practices. It also provides specialized training to police and customs officers on combating organized crimes such as money laundering, trafficking in human beings and smuggling of drugs, vehicles and other goods. Also, OSCE engages in raising public safety awareness through a number of outreach activities ranging from school lectures and police open days to public information campaigns promoting the work and role of the police and fire and rescue services. In 2010, OSCE has carried out a review of the organisational structure of the Kosovo Centre for Public Safety and Education and has been planning to support the KPSED in planning a development strategy.

United States Agency for International Development USAID support to the RoL sector is wide ranging. It has supported the court system of Kosovo by working with both the Kosovo Judicial Council and the Kosovo Judicial Institute. It provides support to the Ministry of Justice in the legal drafting procedures. USAID has also provided support to improving the access to justice of minority (non-Albanian) population. It has capacity building projects with the Chamber of Advocates and the University of Pristina. Its anti-trafficking programme focuses on supporting shelters, dealing with victims of domestic violence and trafficking, and on reintegration of victims by providing vocational training. USAID started a pilot project to improve the court-prosecution cooperation. This was tested in the Gjilan municipality and is a good opportunity to link up with efforts to improve the police prosecutor cooperation. It is also helping in the establishment of the Prosecutorial Council of Kosovo and supporting the prosecution services by upgrading their data management software.

International Criminal Investigative Training Assistance Program (ICITAP) under the US Department of Justice's plan for continuing support through 2008 and beyond includes providing a Law Enforcement Advisor to the MIA and three additional consultants to help the MIA restructure itself. This is an ambitious program dealing with administrative and strategic issues as well as looking into regional cooperation. Technical assistance will also be offered in Integrated Border Management, an Anti-trafficking in Human Beings Program, Financial Crime Investigations, advisors on Policing across Ethnic Lines and support to KCPSED. A major program aimed at providing an IT system across the rule of law sector is especially important for Kosovo, particularly as without such expensive and complex systems intelligence led-policing will be functionally impossible to implement. ICTIAP are also providing a small short program on Police and Prosecutor Training, properly tailored to Kosovo; however the program will only work with one prosecutor and ten police officers.

National Centre for State Courts (NCSC) contracted by USAID, is implementing a Justice Sector Support Program. The program involves six principal tasks supporting key functions and organizations necessary to ensure an independent functioning judiciary: a) improve the capacity of the KJC to operate effectively and efficiently, b) improve court administration, c) improve professionalism and ethics of judges and court staff, d) support the transformation of the court system to more effectively represent and serve non-Albanian populations, e) develop Ministry of Justice legal drafting and policy formulation/ guidance skills, f) establish and support the organization and critical tools necessary to build and effective public prosecutors service . In particular, NCSC have earmarked USD 5m for renovating of existing court premises

The American Bar Association Rule of Law Initiative (ABAROLI) in Kosovo currently focuses its work primarily in the following areas: Legal Education Reform, respectively in Curriculum Reform and Development; Legal methodology course, legal clinics for civil and criminal law at the Law Faculty of Pristina University.

United Nations Development Program UNDP is a major contributor in the rule of law sector in terms of engagement on an institutional level, but perhaps less so in terms of funding. UNDP’s involvement in the sector is presently focused primarily in four areas: Support to the Security Sector Development (3SD), Transitional Justice, Capacity Building projects throughout the sector and a Women’s Safety and Security Initiative (WSSI). UNDP’s involvement in the Ministry of Internal Affairs through the 3SD project is currently focusing on the municipal and local (village) level and is aimed at functionalizing the Public Safety Councils (Municipal and Public Safety Councils and Local Safety Councils). 3SD is engaged at the central level in the Ministry; however their engagement is most welcomed in the public safety councils. 3SD are also offering support outside the RoL sector to both NATO and the ICO on issues such as drafting internal regulations for the new Kosovo Security Force. The Transitional Justice project mainly focuses on awareness raising and University level teaching programmes in relationship to the law. Their capacity Building programme has several projects that involve the Chamber of Advocates and support to the Kosovo Judicial Institute for training and developing logistical capacities, supporting the Kosovo Judicial Council, and in the development of an Official Court Gazette to allow for court rulings to be shared with a view to promoting the development of jurisprudence. The WSSI project focuses on issues of Trafficking and Domestic Violence. UNDP conducted a comprehensive Access to Justice Survey in June 2008, pinpoints areas where rapid impact is possible. Following that a UNDP Justice and Security Sector Reform mission arrived to Kosovo from New York in July 2008.

The Swedish International Development Cooperation Agency (SIDA) support to RoL sector includes providing exchange visits for probation service staff. The Swedish National Police Board scoped and designed an extensive project for enhancing intelligence led-policing in Kosovo but a final decision on its implementation is still pending.

Swiss Cooperation Office SCO has been involved in the RoL sector in two main strands, by providing support to the judicial system and the correctional services. n order to deal with the large number of on contentious cases (certifications, authorizations) in the municipal courts, the Swiss have supported the development of the Law on Notary services and also support the establishment of the notary service. In the Kosovo Correctional Service (KCS) support has been provided to the organisational development of the prison system by creating a staff development programme with training being provided. Support to KCS has also included other components such as establishing vocational training, work schemes for inmates and refurbishment of prison infrastructure etc. Future plans to provide advisory services in support of KCS management at HQ and prison director’s level and this will be focused on thematic fields that include: Staff management, Prison rules; Laws, rules and regulations; Programmes and regimes; Project management; Agriculture / horticulture; and Prison inmate’s occupation. An ad-hoc fund for support to small-scale projects implemented by KCS staff at local level has been created.

This project builds-on previous EC assistance to the Rule of Law sector, particularly the following projects funded under the Instrument for Pre-Accession and CARDS instrument:

Eulex Rule of Law mission through its Strengthening Department has deployed at the end of 2010 an advisor to the Executive Chief of Kosovo Centre for Public Safety and Education. A second advisor is supposed to be deployed shortly pending recruitment.

| Name of project (Amount EUR million) | Start End | Activities/Results |
| --- | --- | --- |
| IPA 2007-2008 |  |  |
| Legal Education System Reform | 2009-2011 | A comprehensive project for reforming initial and continuous legal education, starting from University and covering the KJI/Magistrates School and the Chamber of Advocates. |
| Twinning with the Ministry of Justice. | 2009-2011 | This EUR 2.4 million Twinning project builds on the activities carried out under previous EAR projects. In addition to capacity building, this project also looks at developing mechanisms for arbitration, juvenile justice and the setting up of a bailiff system in order to reduce the backlog of cases in courts. |
| Asylum/Migration/Readmission. | 2009-2011 | This EUR 1 million Twinning aims at enhancing both the policy making skills in the MIA as well as the practical handling of readmission/asylum cases (link to the housing facility under IPA 2007). |
| Supply for the Border and Boundary Police: | 2009-2010 | EUR 3 million have been allocated for the setting up of an EU compliant computer system for the BBP in order to replace the current non-compliant system (PISCES). Purchase of equipment (passport readers, boats, cars, night-vision devices). |
| High security prison: | 2009-2011 | The objective of the project is the construction of high security prison. The EC Multi-Annual Indicative Planning Document (MIPD) for Kosovo (2009-2011) considered a key objective to ‘Consolidate the Rule of Law through reinforcing the wider judicial system, police reform, supporting the fight against corruption”. |
| Construction of the Palace of Justice Building | 2009-2012 | After the July 2008 Donor conference, another EUR 25 million have been allocated for the building of a palace of justice building in or near Pristina. This building will house the district and municipal courts and prosecutorial office, the Kosovo Judicial Institute, the Kosovo Special Prosecutors Office, the Legal Aid office and the Chamber of Advocates |
| Twinning for the Kosovo Border and Boundary Police: | 2008-2010 | The Twinning Partner is NICO UK (with the Polish Border Police as junior partner) has been awarded and now is in the process of preparing the Twinning Work plan. Activities shall start in the first quarter of 2009 depending on the finalising of the work plan. Overall budget is EUR 2.6 million |
| Support to the Anti-Corruption Agency | 2008-2009 | The activity will consist of the following indicative inter-linked components, in line with the Anti-Corruption Action Plan in Kosovo. The specific activities will be further defined during the inception phase of the project: Assessment of current situation and of the anti-corruption legislation framework. Development of policy and measures to systematically tackle corruption and increase public awareness Building the institutional and operational capacity of the Kosovo Anti-Corruption Agency (KAA); |

| CARDS |  |  |
| --- | --- | --- |
| Further Support to the Ministry of Internal Affairs | 2008-2009 | The “Further Support to the Ministry of Internal Affairs” project aims to support the functioning of the MIA. Furthermore, the project focuses on the development and strengthening of effective internal security and public order structures, which guarantee a space of freedom, security and justice for all habitual residents of Kosovo, in accordance with EU standards and best practices. At the present, the efficiency of MIA has still to be improved especially in the areas of legal drafting. The value of the project is EUR 1million, it lasts 15 months (May 08 – Aug 09) and it is implemented by the European Consultants Organisation (ECO). |
| Further support to Justice Institutions | 2008-2009 | The previous project has laid the foundation for the "further support to Justice Institutions" Project and is currently being implemented by the contractor Human Dynamics. This EUR 1.2 million project is expanding the assistance provided to Kosovo justice institutions to facilitate the transfer of competencies from the Justice Pillar of UNMIK to MoJ |
| Case Management Information System | 2005-2008 | A Case Management Information System (CMIS) is being rolled out to all minor offence, district and municipal courts, the Supreme Court and the Public Prosecutors Offices. Once in place and fully utilized he EUR 3 million system established by UNMIK will enable the courts to process cases in a much more efficient manner, therefore reducing the backlog cases. At the present, the CMIS is only partially functioning. |
| Juvenile Justice | 2007-2009 | The aim of this project is to establish a juvenile justice system based on children rights and evidence based research that will offer alternatives to detention and promote a juvenile crime prevention programme and social rehabilitation of juveniles in conflict with the law |

3.7. Lessons learned

Although the overall impact realised through previous assistance is satisfactory, a number of challenges remain: the important donor assistance delivered to some of the beneficiaries in the past could, due to insufficient absorption capacities, not always be used to the best potential extent. The simultaneous presence of several donors (in particular non-EU donors) with sometimes different agendas did not always lead to the necessary synergies. Also, the delivering of Technical Assistance through consultants, rather than civil servants, contributed to focussing on achieving short-term results rather than on sustainable capacity building.

4.  Indicative Budget (amounts in EUR million)

|  |  |  |  |  | SOURCES OF FUNDING |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | TOTAL EXP.RE |  | IPA EU CONTRIBUTION |  |  | BENEFICIARY CONTRIBUTION |  |  |  |  | PRIVATE CONTRIBUTION |  |
| ACTIVITIES | IB (1) | INV (1) | EUR (a)=(b)+(c)+(d) |  | EUR (b) |  | % (2) | Total EUR (c)=(x)+(y)+(z) | % (2) | Central EUR (x) | Regional/Local EUR (y) | IFIs EUR (z) | EUR (d) | % (2) |
| Activity 1 (KCPSED) |  |  | 1.5 |  | 1.5 |  | 100 | 0 | 0 |  |  |  |  |  |
| Contract Twinning | x |  | 1.5 |  | 1.5 |  | 100 | 0 | 0 |  |  |  |  |  |
| TOTAL IB |  |  | 1.5 | 1.5 |  | 100 |  | 0 | 0 |  |  |  |  |  |
| TOTAL INV |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TOTAL PROJECT |  |  | 1.5 | 1.5 |  | 100% |  | 0 | 0 |  |  |  |  |  |

Note: Amounts net of VAT

(1)	In the Activity row "X" is used to identify whether IB or INV

(2)	Expressed in % of the Total Expenditure (column (a))

5.  Indicative Implementation Schedule (periods broken down per quarter)

| Contracts | Start of Tendering | Signature of contract | Project Completion |
| --- | --- | --- | --- |
| Activity 1 (KCPSED) |  |  |  |
| Contract 1.1 Twinning | Q1 2011 | Q4 2011 | Q1 2014 |

All projects should in principle be ready for tendering in the 1ST quarter following the signature of the FA.

6. Cross cutting issues (where applicable)

Human rights and in particular minority rights and participation, as well as gender issues will be mainstreamed within all activities and project deliverables.  Planning and policy development in the Rule of Law sector planning must encompass the protection of human rights, the fight against corruption, trafficking in human beings, and discrimination.

6.1  Equal Opportunity (gender mainstreaming)

The project will ensure that men and women will have equal access to all project deliverables.

6.2  Minorities’ inclusion/participation

Failure to integrate Kosovo’s minorities can lead to further violations of human rights.  Therefore, this project will aim to contribute to the establishment of multi-ethnic representation in the institutions benefiting from the project, which will address the ethnic groups fairly and equitably under the law, as well as other marginalized groups such as people with disabilities.

6.3  Environment

The project is expected to have a neutral environmental impact.  The Project’s infrastructure component will be consistent with Environmental implications as set out in relevant Regulations consistent with the Law on Environmental Protection. This project intends to promote also environmental improvements through energy savings through implementing energy efficiency measures in building, including the use of alternative sources of energy.

- ANNEXES

1-	Log frame in Standard Format

2-	Amounts contracted and Disbursed per Quarter over the full duration of Programme

- 3-	Description of Institutional Framework

- 4 -	Reference to laws, regulations and strategic documents:

Reference list of relevant laws and regulations

Reference to AP /NPAA / EP / SAA

Reference to MIPD

Reference to National Development Plan

Reference to national / sectoral investment plans

Reference to audit and analytical review

5-	Details per EU funded contract (*) where applicable:

ANNEX 1:	Logical framework matrix in standard format:

| Project Title: Improved education in the Public Safety and Security sectors | Programme name and number: Strengthening the Rule of Law |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sector: Rule of Law | Contracting period expires three years after the date of conclusion of the Financing Agreement between the European Commission and the Kosovo Authorities |  |  |  | Disbursement period expires one year after the final date for the execution of contracts |  |
|  |  |  |  | Total budget : EUR 1.5 million | IPA budget: EUR 1.5 million |  |
| Overall objective | Objectively verifiable indicators |  |  | Sources of Verification |  |  |
| To strengthen the rule of law in Kosovo through further reform of the relevant institutions | Ability of the institutions to comply to the European Partnership and the EP Action Plan |  |  | EC Regular Reports |  |  |
| - Project purpose | - Objectively verifiable indicators |  |  | - Sources of Verification |  | - Assumptions |
| Improvement of Policing Services therefore public safety improved | - Increased number of cases handled by the Public Prosecution Service |  |  | - Europol/Interpol/KPS reports and statistics - KCRA-KJC statistics - EC and EULEX and other donor reports - Ballistic examination reports - Number of students registered - Accreditation/Certification documentation - MIA examinations reports - Databases and equipment - MoJ Annual Report - CMIS statistics - MoJ/Probation Service statistics |  | - Legislative and institutional framework approved/adopted - Competencies fully clarified; Extent of retention of trained/qualified personal Good cooperation among all relevant stakeholder KCB allocates the necessary resources for co-financing Sufficient resources of institutions involved into juvenile justice |
| - Results - Expected Results: - Higher professionalism, efficiency and public acceptance of Kosovo Police, Customs, Penitentiary Service and Fire-fighters - Basic Training Courses for Police, Customs, Penitentiary Service, Fire-fighters established and meeting international minimum standards - Higher education institution for public safety and security set up and functional - Training curricula accredited by Kosovo authorities and in line with Bologna requirements - Mechanism for using ECTS system in place | - Objectively verifiable indicators - Measurable indicators: - EC reports, statistics, number of criminal cases forwarded successfully to prosecution, amount of revenue raised for KCB. - Training courses set up - Higher education institution functional and accredited - New curricula established - ESCT system in place and accredited |  |  | - Sources of Verification Licensing documentation Educational offer of the Institution. Number of candidates applying. |  | Assumptions Political will and commitment Absorption capacity ensured Envisaged legislation enacted. Good cooperation among relevant stakeholders Extent of retention of trained/ qualified personnel |
| Activities |  | Means | Costs |  |  | Assumptions |
| 1. helping the KCPSED to review its curricula and training activities for basic training of Police, Customs, Penitentiary staff as well as fire-fighters in line with European standards 2. reviewing the organisational structure of the KCPSED, including an analysis of workflow and control, and providing for recommendations for improvement based on best practice examples 3. advising the KCPSED management on setting up a higher education institution for public safety and security studies and on developing curricula for higher education in line with the Bologna Process and the ESCT 4. setting up training courses, in particular "train-the-trainer" activities 5. working together with the Ministry of Internal Affairs and the Ministry of Education towards the accreditation of the Centre by both the relevant national and international bodies. . |  | Twinning | EUR 1.5 million |  |  | Beneficiaries allocate sufficient staff and office space to the project Key legislation in place Organisational structure of beneficiary has been decided upon Co-financing ensured Continued political support |

- ANNEX 2:    Amounts (in EUR million) Contracted and disbursed by quarter for the project

|  | 2011 |  |  |  | 2012 |  |  |  | 2013 |  |  |  | 2014 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contracted | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 |
| Contract 1.1 Twinning |  |  |  | 1.5 |  |  |  |  |  |  |  |  |  |
| Cumulated |  |  |  | 1.5 |  |  |  |  |  |  |  |  |  |
| Disbursed |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contract 1.1 Twinning |  |  |  | 0.6 |  |  | 0.3 |  |  | 0.3 |  |  | 0.3 |
| Cumulated |  |  |  | 0.6 | 0.6 | 0.6 | 0.9 | 0.9 | 0.9 | 1.2 | 1.2 | 1.2 | 1.5 |

Annex 3:	Description of the Institutional Framework

- Ministry of Justice

UNMIK Regulation 2005/53, amending Regulation 2001/19 on the Executive Branch of the Provisional Institutions of Self-Government in Kosovo, dated 20th December 2005, provided for the establishment of a Ministry of Internal Affairs (MOIA) and Ministry of Justice within Kosovo and Annex XV to the Regulation set out the initial competences of MOJ. The date of appointment of the Minister of Justice (10 March 2006), is referred to as the effective date of the establishment of MOJ.

In the first phase (Regulation 2005/53) MOJ responsibilities included developing and implementing policy and legislation within the scope of its responsibilities in the field of justice including prosecution, correctional services and probation, as well as for ensuring fair and effective access to justice, and managing the administrative, financial and budgetary affairs of the ministry (see Section III: “Functions”). Further competences have been legally transferred to MOJ, in a new Annex XV through Regulation 2006/26, promulgated by the SRSG on 27 April 2006 and announced in the media on 9 May.

In the second phase (Regulation 2006/26) the responsibilities of MOJ have been expanded to include further competences relating to the correctional services, probation services, missing persons and forensic medicine (these responsibilities are also explained in more detail in Section III: “Functions”). The full text of MOJ’s responsibilities (Annex XV, Regulation 2006/26) is available from the Official Gazette on www.unmikonline.org. In line with the constitutional provision for the separation of powers, especially between the executive and the judicial branch, MOJ does not have responsibility for the administration of the judiciary and courts.

UNMIK Regulation 2005/52, also dated 20 December 2005, established the Kosovo Judicial Council, which has full independence in the performance of its functions, and is under the authority of the SRSG. Regulation 2006/25, also dated 27 April 2006, is called a “Regulatory Framework for the Justice System in Kosovo” and mostly relates to the role of KJC. All staff working in courts will be part of the KJC. All administrative staff working in prosecutors’ offices will be attached to the MOJ, although policy and rules for the careers of prosecutors themselves remain with the KJC as a transitional measure, until the Kosovo Prosecutorial Council is created. At the time of developing this plan, much work has still to be done on clarifying our mandate, particularly through discussions with UNMIK and other PISG. Our mandate will be further shaped by Normative Acts (legal and sub-legal acts) which reflect the political processes and priorities. Of particular importance at this time are the Kosovo Standards (1-4) and European Partnership Action Plan, (as well as a number of draft laws, examples of which include the Draft Law on Organisation of the Courts, the Draft Law on Public Prosecution, the Draft Law on Notaries and the Draft Law on Judicial Tariffs.

The functions of the MOJ have been defined in this plan as those which are derived from the ministry's mandate as determined in law through Regulation 2005/53 and Regulation2006/263. Therefore, at the time of finalising this plan these may be summarised as follows:

Justice policy and legislative drafting

Develop governmental policies in the field of its responsibility

Draft relevant legislation pertaining to the scope of its responsibilities

Participate in the overall legislative drafting process at the governmental level

Develop policies and action plans for the implementation of legislation in the filed of its responsibilities.

Administrative Support

Manage, in cooperation with other PISG as appropriate, the administrative functions which support the entire Ministry’s work including:

- - Human Resources,

- - Finance

- - Procurement

- - IT

- - General Services.

- Prosecutorial policies and legislation

- Facilitate preparation and implementation of the legislation for the public prosecution

- Provide guidance for the development and implementation of the prosecutorial policy of the Office of the Public Prosecutor of Kosovo (OPPK)

- Cooperate with appropriate organisations in respect of independent monitoring of the prosecutorial system;

- Provide training for prosecutors in cooperation with the Kosovo Judicial Institute;

- Facilitate the organisation of examinations for the qualification of prosecutors, lawyers (including trial  attorneys) and other legal professionals through the Kosovo Judicial Institute and other independent professional bodies;

- Manage in cooperation with the Ministry of Finance and Economy the development of administrative, technical and financial rules and rules governing support personnel and material resources to ensure the effective functioning of the prosecutorial system; Provide information, statistics and professional analysis for the functioning of the prosecutorial service. Undertake necessary measures to ensure the protection of personal data relating to the prosecutorial services. In carrying out any of these functions in relation to the prosecutorial system, the Ministry of Justice must not in any way limit, hamper or interfere arbitrarily with the prosecutorial operations of any prosecutor or prosecutor’s office in Kosovo.

- Coordination and administration of the Kosovo Correctional Service

- Develop policies and initiate legislative drafting in the field of correctional services

- Exercise executive oversight over the correctional services and probation system (with the exception of the emergency situations in the Dubrava prison, as foreseen in Article VII of the UNMIK Regulation No.2006/26);

- Assist in recruitment, training and evaluation of the staff of correctional services;

- Provide analysis, statistics and information on the correctional services; Undertake necessary measures to ensure the protection of personal data relating to the correctional services;

- Cooperate with other organisations with respect to the independent monitoring of correctional services.

- Coordination and Administration of the Department for Execution of Alternative Sanctions (Probation Service of Kosovo)

- Develop policies and initiate legislation drafting in the field of probation services

- Exercise executive oversight over the probation system

- Assist in recruitment, training and evaluation of the staff of probation services;

- Provide analysis, statistics and information on the probation services

- Undertake necessary measures to ensure the protection of personal data relating to the probation services.

- Cooperate with other organisations with respect to the reintegration and reconciliation who are under probation

- Legal help and assistance to victims of crime

- Organise a system for providing assistance to the victims of crime in particular domestic violence, trafficking in human beings and sexual violence.

- Administer the Victims Protection and Assistance Division

- Cooperate with other organisations with regards to providing the assistance to the victims or crime, domestic violence and trafficking.

- Cooperate with the Ministry of Health in provision of assistance to victims of crime

- Missing persons

- Undertake measures aiming at seeking, obtaining, providing and verifying information about the location of missing persons;

- Provide assistance on legal matters related to the fate of missing persons;

- Assist, when necessary, in the process of returning the remnants of missing persons

- Cooperate and coordinate with the Office of Missing Persons and Forensics, and other entities (subject to UNMIK’s authority over all investigations of individual cases of disappearance);

- Forensic medicine

- Subject to the exemptions arising from the Article X of the Regulation No. 2006/26 which refer to responsibilities which remain reserved powers of UNMIK, MOJ shall:

- - exercise powers related to the forensic medicine;

- - administer the Medical Examiners Office 4

- International legal assistance and cooperation

- Provide expert support for the preparation by the Government of international agreements, which are in conformity with the Governments responsibility as foreseen in the Constitutional Framework and other relevant normative acts;

- Assist UNMIK, when appropriate, with regards to international legal cooperation, including cooperation with international courts.

- Litigation on behalf of Government

- Provide legal representation of the Government in disputes and procedures before courts and arbitration tribunals

- Other functions

- Conduct research activities and projects related to the field of its responsibility

- Exercise other specific functions, pursuant to its current or future legal mandate

- As mentioned above at the end of Section II, the mandate of the Ministry is dynamic, and will be affected by changes to Kosovo legislation arising from political processes, which may subsequently give rise to these functions also changing.

- Section 3 (I) describes how the plan can be updated, through a review process after two years or sooner if thought necessary. This is one of the reasons behind the structure and content we have chosen for this plan, which is based on a thematic approach (i.e. focusing on general strategic themes that are important to the Ministry as a whole) as opposed to a functional (i.e. developing objectives specifically relevant to each of the departments and the functions they carry out) approach. This thematic approach ensures that this plan will continue to be relevant no matter how the mandate changes. A more functional approach would most likely become out of date relatively quickly given the changing environment in which the Ministry must operate, and the further clarifications which are likely to be made to the legal mandate.

- The strategic objectives developed under this thematic approach will continue to be critical to ensuring that the Ministry as a whole and each of its parts carries out the above (or any future) functions to the required standard, no matter how the mandate changes. Implicit to this thematic approach is that each department has a role to play in achieving the strategic objectives under each strategic theme (such as management, performance, anti-discrimination and so on).The thematic approach which we have opted for in this document does not mean that we need not think strategically about our core functions, as assigned to us by applicable legislation. However, given the lack of clarity surrounding the MOJ’s mandate, and the operational nature of our core functions, plans at the level of departments are the more appropriate place to develop that kind of strategic thinking than the present document. We will set out our current understanding of each of the core functions assigned to us in law, along with operational objectives concerning their implementation (including any constraints we face) in the departmental plans.

- Ministry of Internal Affairs:

The legal framework for the establishment of the Government of Kosovo’s Ministry of Internal Affairs can be found in UNMIK Regulation No. 2005/53 of 20 December 2005 on the amendments of the UNMIK Regulation No. 2001/19 on Executive Branch of PISG in Kosovo (attachment XVI).

In the beginning, the framework of MIA authorisations in the area of security and internal affairs was defined based on the so called „early transfer of competencies“. As a result of the comprehensive work of MIA, and especially developmental policies of the Ministry for Internal Affairs, that were based on the principles and within predicted framework, a so called „later transfer of competencies“ has been effectuated by entry into force of the UNMIK Regulation No. 2006/26 of 27 April 2006, in attachment XVI (ii).

By this the transfer of competencies to KPS started: „Monitoring of Kosovo police service, as authorised by SRSG, acting through the police commissioner and without interventions in the actions of the Kosovo Police Service and in implementing criminal investigations“. In addition, in this attachment and by this Regulation, The Pillar I (Police & Justice) has, consequently, formally ceased to exist and remained only the Office of Policy and Rule of Law.

Legal Basis

In the process of establishment of Provisional Self-Governing Institution (PISG) in Kosovo, it is created the Ministry of Internal Affairs in accordance with UNMIK Regulation no. 2005/53, 2006/26.

The institutional structure of the MIA has undergone a functional review approved the by the Kosovo authorities. A lot of Departments and Units are in the process of being established. An administrative Instruction have been adopted reorganising the Minister of Internal Affairs (Administrative instruction No 16/2010-MIA on Internal Organisation and structure of MIA). The KPCSED remain one of the 5 agencies under the Minister of Internal Affairs.

- Kosovo Centre for Public Safety, Education & Development

The Kosovo Centre for Public Safety, Education and Development (KCPSED) is located in the Vushtrri/Vučitrn municipality. The Centre was originally founded in 1999 when the Department of Police Education and Development of the OSCE established the Kosovo Police Service School. The school reached its key benchmark when 7,500 police officers had graduated in 2005. Upon entry into force of UNMIK Administrative Directive No. 2008/3, the KCPSED operates as an executive agency of the Ministry of Internal Affairs. It provides technical, administrative and educational (basic and advanced training) support for all agencies of the public security sector. It is governed by UNMIK Regulation No 2008/17 amending UNMIK Regulation No. 2005/54 on the Framework and Guiding Principles of the Kosovo Police Service and UNMIK Regulation No. 2008/18 on the Establishment of the Kosovo Board on Public Safety Standards and Education. A working group has been established by Minister of Internal Affairs to draft the Law establishing what will be "the Kosovo Centre for Public Safety".The Centre is responsible for the training and education of members of the four different public safety and security agencies, namely the Kosovo Police, Kosovo Customs Service, Department of Emergency Management and Correctional Service of Kosovo. The first basic training commenced in September 1999. It started with a 6-week basic training course (followed by field trainings) as the aim was to get local police deployed as quickly as possible. By the end of 2002, 5213 Kosovo Police Service Officers had graduated. After this emergency phase the transition phase followed which was characterized by the capacity building of local staff. In 2005 the transformation into the current public training centre was proposed.

- The KCPSED has 28 classrooms and dormitory with a capacity for 711 students. The buildings host administrative support offices, a learning centre, two sports halls, a gym room, armory, and medical services.

- ANNEX 4:	Reference to laws, regulations and strategic documents:

The project links to the MTEF Sector Objectives in the field of Rule of Law that are:

Justice System Goals: I. Construction and renovations of facilities for Kosovo Judiciary (in particular courtrooms, prosecution offices and KJC premises), II. Reduce backlog of court cases and III. Combat and prevent crime;

Law Enforcement Goal IV: Increase service quality for citizens – will be achieved through these objectives:

1. Supplying citizens with personal documents in line with EU standards:

a) Supplying citizens with personal documents.

b) Setting up a secure and functional civil registration system.

2. Necessary information – communication infrastructure, improvement of work space and conditions, and training facilities:

a) Upgrade of information technology;

b) Necessary work space, higher efficiency in provision of services to citizens;

c) Upgrade of work conditions and safety

- Reference to audit and analytical review Fonctional review of the Kosovo Centre for Public Safety and Education by FRIDOM – Functional Review and Institutional Design of Ministries, a DFID-funded project, implemented by HELM Corporation, Consulting and Public Management Group, Governance institute Slovakia and Altair Asesores, April 2010.

- Self Report for Evaluation and Accreditation by AQAS e.V, Osce, May 2008.

- Report on the Evaluation and Certification of the Kosovo Centre for Public Safety, Education and Development, Site inspection at the KCPSED in Vushtrri on 30 and 31 July 2008 by AQAS e.V.

- ANNEX 5:	Details per EU funded contract (*) where applicable

1. Improved education in the Public Safety and Security sectors

The instrument of twinning will be used to implement this activity. Standard twinning procedures are to be used.  The Resident Twinning Advisor (RTA) is expected to be a senior civil servant from a similar institution of member states (i.e. Police Academy).  The RTA will be assisted by EU MS short and medium-term experts. The RTA's counterparts in the beneficiary institution (both Project Leader and day-to-day counterpart) will be senior staff from KCPSED.

RTA Profile:

- Experience in higher education institute closely related to policing

- Experience in the development of the curricula and training activities for Police, Customs, Penitentiary and fire fighters

- Fluency in English;

- Degree in social sciences, law or other relevant area to the sector