- Twinning Project Fiche

- 1. Basic Information

1.1. Programme: IPA 2009

1.2. Twinning number: AL 09 IB JH 01

- 1.3."Support to the Albanian Penitentiary Reform"

1.4. Sector: 01.24 Justice Reform/ Penitentiary Reform / Fundamental Rights

1.5 Beneficiary country: Albania, Ministry of Justice

2. Objectives

2.1 Overall Objective

- Guaranteeing basic and fundamental rights for all convicted persons, ensure the human treatment of detainees and the transformation of criminal punishment into a re-education/correctional opportunity.

2.2 Project Purpose

The project will support the development of the national probation service in Albania to improve the system of executing criminal-justice sanctions and improve the treatment of those entering the criminal justice system, through development of alternatives to imprisonment and diversion.

2.3 Contribution to AP/NPAA / EP/ SAA:

European Partnership priorities 2008

The issues that will be addressed by the actions included in the present Twinning fiche are along the lines of the priorities mentioned in the EP 2008 as quoted below.

Short-Term Priorities

Key priorities

Increase the independence, accountability and transparency of the justice system.

Medium-Term Priorities

Ensure continued and appropriate training of judges and prosecutors, including on human rights, ethics and commercial and corporate matters and SAA-related issues.

SAA

This project’s intervention field is in line with the objectives set out by the Stabilization and Association Agreement, in particular Article 78 – “Reinforcement of institutions and rule of law”: "In their cooperation on justice and home affairs the Parties shall attach particular importance to the consolidation of the rule of law, and the reinforcement of institutions at all levels in the areas of administration in general and law enforcement and the administration of justice in particular.

- According to the 2007-2012 National Plan for the Implementation of the SAA, one of the requirements to be met in reforming the justice system in Albania is to ensure the protection of victims and the social reintegration of convicted persons. Strengthening and improvement of the penitentiary system, in compliance with European standards, is also required. In the framework of guaranteeing basic and fundamental rights for all convicted persons, the National Plan provides for all law enforcement agencies to ensure the human treatment of detainees and the transformation of criminal punishment into a re-education/correctional opportunity.

2.4 Link with MIPD:

- The 2009-2011 MIPD states that "In the area of democracy and rule of law, the capacity of the Albanian institutions remains to a large extend limited, in particular as regards the judiciary, the implementation of the public administration reform and the fight against corruption and organised crime". The Multi-annual Indicative Planning Document underlines the need for improvements in the penitentiary system. This project’s goals comply with the priority set out by the MIPD: “Support to the Reform of the Judicial System” with the overall strategic objective of an independent, reliable and efficient functioning judiciary that guarantees the rule of law. Furthermore, the MIPD stipulates that some of the programmes which should be implemented ought to include: “Provision of the conditions for adequate staffing, infrastructure and equipment to the Judiciary. Support to the High Council of Justice will continue. Institution and capacity building for the Ministry of Justice, subordinated and other independent institutions.

2.5	Link with National Development Plan

- The National Strategy for Development and Integration stresses the necessity on the improvements of the penitentiary system, the prison facilities, and the pre-trial detention centres are all considered to be below European standards.

- With regard the Probation Services, the project is in line with the following priority in the draft National Strategy for Development and Integration 2007-2013 “Introduction of a structure for the application of alternative sentences”.

2.6 Link with Sectoral investment plans

NA

3. Description

- This project will contribute towards increased efficiency of the law enforcement system through improving the supervision and rehabilitation of conditionally released offenders and offenders sentenced with alternatives to imprisonment in Albania.

- This project will support the development of a national probation service in Albania to improve the treatment of those entering the criminal justice system, through development of alternatives to imprisonment and diversion. This will help offenders reintegrate into society and alleviate the social problems caused by inappropriate and excessive use of custody as a sanction.

- This project will support the establishment of a strong national probation service delivering constructive flexible community penalties eases financial and population pressure on the prison system. It allows prisons to concentrate on their core task of security and on rehabilitation which can be reinforced post-release.

The project will support the improvement the execution of alternatives to imprisonment, like semi-liberty, stay at home, performing labour in favour of public interest, probation and parole.

This project will support the development of the training system of prison officers, including the training of the uniformed staff in the prisons to rehabilitation activities.

3.1 Background and justification:

- The present project intends to support the progress of the judicial system in Albania in accordance with the priorities of the EU acquis in Judiciary and Fundamental Rights.

- Albania's progress on its European integration path is measured on the basis of criteria established by "Copenhagen” political criteria. The reform and development of the Albanian justice system is one of the key priorities in the SAA. The rule of law is a fundamental pre-condition for membership; setting the mechanisms that permit the rule of law to be implemented properly is a fundamental task for all political forces.

The Albanian criminal justice system is mainly prison based, with lengthy sentences and very few alternatives to imprisonment imposed by the courts. The Criminal Code of Albania provides for some provisions of the alternative sentences to imprisonment, but many judges lack confidence in the execution of community sentences and measures (for example article 59 (suspending the execution of a sentence) has been applied by the courts only for 796 persons in 2003, for 1300 persons in 2004, for 1102 persons in 2005, for 945 in 2006 and for 727 persons in 2007, 941persons in 2008.

Their implementation is not fully secured due to the fact that the probation service has just been established in Albania and it is not fully operational yet in all regions.

The prison population in Albania has risen constantly and has reached the highest level during recent years by now – almost 5000 persons are detained when the current capacity of the penitentiary system is 4340 persons (and with the opening the Kavaja institution another 40 places will be added and capacity will be 4380).

Additionally there are about the same number of prisoners with Albanian origin in other European countries. The prison system is encountering severe overcrowding, poor hygiene, and medicine and food shortages. This is alarming and very costly, because overcrowding can only damage instead of rehabilitate the persons detained in prisons.

The European Commission’s 2009 Progress Report highlights that The probation service is starting to operate but application of alternative sentencing by the judiciary ids progressing slowly. […] Overall, progress has been made in establishing a probation service and in improving the prison and pre-trial detention system, but overcrowding continues and detention standards in older prisons remain poor."

Amendments to the Criminal Code and the Law on the Execution of Criminal Decisions have been adopted and provide the statutory framework which will allow for the greater use of alternative measures for offenders in the criminal justice system. These reforms represent an important part of the reform of the Albanian criminal justice system.

However, for the alternative measures and sanctions to be effective in reducing the rate of re-offending they have to have the confidence of the judges and prosecutors. This can gradually be achieved if the measures are implemented by a statutory established probation service with the requisite legal powers to implement the supervision of sentenced offenders and with well trained, professional staff that is accountable under the law and to their professional ethics to carry out their duties.

The establishment of a Probation Service which can conduct pre-sentence reports and offer planned supervision of offenders in the community will encourage judges to impose more alternative sentences. The project will provide assistance at the national level to the staff in the Ministry of Justice to enable a national lead, strategic planning, co-ordination, management and training in probation area. Locally the project will support the development of probation teams in different areas of the country, as resources and local conditions permit; also, support will be provided in building the capacity of these teams to expand and consolidate practice across the breadth of probation activity. Very importantly, an integral part of this project is the development of a modern probation information system as well as a national system of probation education to provide a trained workforce.

3.2 Linked activities

The activities foreseen under this fiche will follow up on recommendations and assessment of previous assistance and complement efforts of the Albanian authorities which are also supported by the EU and other organisations. The main project directly relevant and close to the assistance proposed under this project fiche are the following:

EURALIUS II:

In 2010 will provide the General Directorate of Probation with further consultation and support regarding the training of probation officers and drafting the sub-legal acts and sample materials for the local probation offices, organise for the management team of the General Directorate of Probation a study-visit to an EU member state.

OSCE

The OSCE Presence in Albania plans to support in 2010 the Probation service with assistance in expanding the probation services at national level in order to improve the capacities of probation staff in order to ensure that alternative sentences are implemented and combine effective punishment with success in reducing the level of re-offending

Following the recruitment of probation officers in local offices and training organised by EURALIUS and the OSCE in June, and September 2009, the probation service has started to function in Albania. In September 2009, four local offices are supervising over 350 orders for alternative sentences that have been given by the courts since the probation service started functioning.

Although the total number of prisoners has slightly decreased during recent months (there were 4693 persons detained as of 31 July, compared with 4900 at the end of April and 5080 at the end of December 2008), the prisons are still overcrowded by 350 persons. The General Directorate of Prisons has identified around 800 prisoners whose sentence could be converted into some kind of alternative sentence and has established good working relations with the General Directorate of Probation.  This would result in a further decrease of the number of prisoners.

The following measures have been identified by previous assistance projects as priorities in the sector:

- Finalise the subordinate legal acts in the penitentiary field. Subordinate legal acts that have already been drafted need to be approved and implemented, such as: “Rules of procedure of the General Directorate of Prisons,” “Rules and procedures for work relations, training, career development and disciplinary measures of prison police,” “the Rules of the Prison Police”, internal rules of all penitentiary institutions.

- Develop a standardised risk assessment and individual sentence planning system for prisoners in all prisons (connected with the previous priority and targeted towards further reducing the number of prisoners).

- The training centre for prison staff should be further developed to guarantee the sustainability of the prison officers’ training.

3.3 Results:

- Results :

- Standards, procedures and criteria for qualification, selection and recruitment of probation officers developed

- Probation training strategy and curriculum prepared and training delivered

- Probation officers received appropriate level of training and education

- Trained team of trainers prepared.

- Study materials on social rehabilitation work with offenders developed and published

- Judges, prosecutors and other criminal law practitioners briefed on probation work

- Probation structures on central and local level built

- Increased use of alternatives to custodial sanctions and measures facilitated

- Active involvement of the community in the social reintegration of the offenders

- A probation case record and data collection system created

- Public tolerance regarding the probationeers increased.

- Improved execution of alternatives to imprisonment

- Overpopulation of prisons reduced

- Indicators:

- Probation structures functioning.

- Developed curricula for initial and in-service training for probation officers and related staff

- Number of Probation staff trained.

- Training of trainers conducted .

- Courts and prosecution offices using more alternatives to imprisonment.

- Criminal law prractitioners including judges, prosecutors and police briefed.

- Case management and data collection system in function.

- Approved standard formats for all reports produced by probation officers.

- A proactive public relations strategy in place .

- Public openness regarding the probation procedures.

- Inter-agency cooperation at national and local level .

- Training Centre for Prisons functioning

3.4. Activities

- Component 1 - Support to the Ministry of Justice for implementing the national probation standards and probation service methodologies

- Main Beneficiary: MoJ - General Directorate of Probations

- Secondary beneficiary: General Directorate of Prisons, Court, Prosecutor offices

- Through a process of advice and monitoring by the Resident Twinning Advisor to the Ministry of Justice assist in:

- Updating the probation development strategy and yearly action plans

- Providing Pre-trial information to prosecutors / bail information reports.

- Supervising pre-trial cases.

- Providing victim related services including support, victim-offender mediation and restorative justice practices.

- Preparation and writing pre-sentence reports for the courts.

- Sentence and supervision planning in case of offenders sentenced with alternatives to imprisonment (including obligations for unpaid work, prohibited activities, mental health treatment, group and individual programme to address behaviour such as violence, sex offending, drug/alcohol abuse, domestic violence etc.).

- Preparation and writing of pre- release reports.

- Supervision of conditionally released prisoners.

- Appropriate enforcement of community sentences, securing the offender’s cooperation and compliance with the order/obligations imposed by the courts.

- Work with other agencies, particularly the courts, police, prosecutors and prison service based on protocols at the local level.

- Monitoring the performance against the Standards and the outcomes of the probation work.

- Component 2 - Creating a probation information system which enables political and management decisions to be made on the basis of accurate information, informs developments and targeting and can demonstrate the efficiency and effectiveness of probation work

- Main Beneficiary: MoJ - General Directorate of Probations

- Secondary beneficiary: General Directorate of Prisons, Court, Prosecutor offices:

- Develop common case record and data collection system to be used by probation officers in their supervision of offenders which could be linked with the prison, prosecution and court info systems.

- Develop with the appropriate authorities of the requisite legal documentation that will be required for each of the new measures.

- Develop standard formats for reports to judges and prosecutors (bail information reports; pre-sentence reports; supervision plan/reports; pre-release reports, risk assessment reports).

- Train probation staff from local and central level as probation information managers in order to assist all probation teams to understand how to use information as a resource

Component 3 - Designing the training strategy, preparing the training curriculum and training the probation staff

Main Beneficiary: MoJ - General Directorate of Probations

Secondary beneficiary: Ministry of Education, General Directorate of Prisons, Court, Prosecutor offices:

- Update and implement the probation education and training policy.

- Update the training curriculum for the probation service agreed by the Ministry of Justice and institutions involved in delivery the training

- Update the standards, procedures and criteria for qualification, selection and recruitment of probation officers Conduct a systematic analysis of the education and training needs of the existing staff and agree a programme to meet the identifying needs

- Design a training of trainers programme Design a in-service training provision

- Manage the delivery of the training by Short Time Experts throughout the project

- Deliver by use of Short Time Experts a programme to train staff to become the future trainers of the Albanian Probation Service

- Deliver training to probation managers at central and local level, as well as training of probation inspectors

- Establish a Probation Fellowship Programme and a programme of exchange of staff to place Practice Facilitators from EU countries for up to two months in the Albanian probation teams

- Organize study visits designed for probation staff to EU Member States in order to get familiar with and see the probation services in action

Component 4 - Developing probation offices in different regions of Albania

Main Beneficiary: MoJ - General Directorate of Probations and Local Probations Services Offices:

- Support setting up new probation offices and assess the required probation staff for each region based on criminal justice statistics and criminological analysis of case data

- Set up and maintain an advisory group comprising heads of probation projects, information manager from headquarters, representatives of judiciary, prosecutors, international experts and other key persons

- Prepare a formal review process of the pilot projects and conduct a continual assessment of each area

- Review of the pilot probation projects.

- Component 5 - Developing and implementing a public relations strategy and briefing of judges, prosecutors, police, prison service, local authorities and NGOs about the probation system

- Main Beneficiary: MoJ - General Directorate of Probations

- Secondary beneficiary: General Directorate of Prisons, Court, Prosecutor offices:

- Identify and develop protocols with NGOs all over the country to work in partnership for ensuring that all the requirements of the probation legislation can be implemented throughout Albania.

- Develop protocols with police, judges, prosecutors, General Directorate for Prisons, local authorities and other Government departments, as well as with Mediation services in order to ensure maximum cooperation, best possible working environment and understanding.

- Conduct probation briefings and seminars for judges, prosecutors, police, prison staff, local authorities, mediation and social services, and NGOs.

- Prepare a public relations strategy and its action plan

Component 6: Further developing the permanent Training Centre for Prisons and a permanent staff training system.

- Main Beneficiary: MoJ - General Directorate of Prisons

- Secondary beneficiary: General Directorate of Probations

- Update and implement the prison education and training policy.

- Support the sustainability of the initial and continuous trainings of the Training Centre for Prisons.

3.5.1 Profile and tasks of the Project Leader

Profile:

- Long-term civil servant from an EU Member State Justice administration or relevant institution;

- Experienced in the field of management and organization;

- At least 5 years working experience in a leading management;

- Very good command of English (oral and written);

- Excellent computer skills (Word, Excel).

Tasks:

- Overall co-ordination of the project;

- Leading the project activities.

- Project financial management.

3.5.2 Profile and tasks of the RTA

One Resident Twinning Adviser (RTA) over a period of 24 months as well as medium/short term experts will implement the above-listed components. The RTA has the responsibility to guide the work of the team. The medium/short term experts will work in close cooperation with the RTA and the staff in order to meet the specific objectives as set out above.

The RTA is expected to fill the following profile:

- Minimum 10 years of experience in the justice/penitentiary administration field.

- Be an administrator from public administration of an EU member's state with expertise in alternative measures to detention and human rights.

- Sound comparative knowledge of relevant EU legislative and institutional requirements related to the various components of this project.

- Wide knowledge of related good practice/acquis communautaire.

- Solid knowledge of probation services, alternative measures to imprisonment, release measures, prisoners rights, etc..

- Have excellent management, leadership, communication and coordination skills.

- Proven abilities of manager in forming an appropriate team of short-term experts.

- Experience in developing similar projects implemented in other countries.

- Good training, public speaking and written communication skills.

- Excellent computer literacy (Word, Excel, Power Point).

- Excellent command of spoken and written English.

Additional assets are:

- Sound background in drafting and/or implementing strategies, policies or regulations

- Previous experience as project coordinator/project manager in similar projects;

- Some relevant working experience in the new Member States and the Western Balkans;

- Knowledge regarding the situation and the administrative structures of Albania would be a plus.

- Relevance of other language skills will be considered as well.

Tasks:

- Overall supervision of the project implementation and coordination of all activities, as well as management of the project administration;

- Advise on Justice and Fundamental Rights standards and practices in EU Member States;

- Advice on Probation and penitentiary reform matters;

- Coordination of the activities of the team members in line with the agreed work programmes to enable timely completion of project outputs;

- Preparation of project progress reports;

- Permanent contact with the beneficiary RTA counterpart;

- Liaison with EC Programme Manager;

- Liaison with other relevant projects.

The RTA is expected to ensure, together with the beneficiary administration, the achievement of the objectives listed in 2.1/ 2.2. In order to meet these purposes, and if fully justified, the RTA may propose alternative and/or complementary project activities and/or outputs to those identified in the section 3.4.

3.5.3 Profile and tasks of the medium/ short-term experts

Tasks of medium and short term expertise

Terms of Reference for mid/short-term adviser(s) will be elaborated by Project Leader/RTA at the work plan preparation stage.

Profile of short and medium-term expertise

There should be a pool of short/medium term experts. Their "mix" should be identified by the Project Leader/RTA in the course of designing the delivery of the project. The actual duration of the assignments of each of the short-term expert(s) (in principle from 2 to 8 months) will be defined during the drafting of the twinning agreement. The medium-term expert(s) will work in close co-operation with the Team-Leader/ RTA and the Beneficiary in order to meet the specific objectives as set out above.

The short and medium- term experts are expected to have:

- Degree in law or in criminology, social work, education or psychology.

- In depth knowledge of European legal framework and European Community law

- Minimum 8 years relevant experience in the field of judiciary, including 5 years experience dealing with the probation and penitentiary system

- Strong coordination and communication skills

- Experience with EU funded projects would be an asset

- Previous work experience in Transition Countries would be an asset

Additional assets are:

- Sound communication skills and previous experience of working in multi-disciplinary and multi-national team;

- Sound background in drafting and/or implementing strategies, policies or regulations;

- Some relevant working experience in the new Member States and the Balkans.

4. Institutional Framework

The General Directorate of Probation is a State body under the responsibility of the Ministry of Justice (Article 31/7, :aw 10024, dated 27.11.2008) which helps to supervise the enforcement of alternative sentences, submit information and reports to the prosecutor and the Court, helps the sentenced persons to socially reintegrate.

The activity of the probation service is regulated with the Law No.8331, dated 21.04.1998 “On the Execution of Criminal Decisions”, amended, and the Decision of the Council of Ministers, dated 25.03.2009 “On the organisation and functioning of the probation service and the standards and procedures of supervising the execution of alternative sentences.

As per the Article 6 of the Council of Minster Decision, dated 25.03.2009 the mission of the Probation Service in Albania is to protect public interests, prevent the commission of criminal offences, provide assistance for the convict to meet obligations stemming from alternative sentence; assist the convict to overcome difficulties related to his/her social reintegration.

The General Directorate of Probation at the Ministry f Justice represents the central level of the institution.

Local Offices at the district Courts represent the local level with a total of 4 local offices in Tirana, Shkodra, Durres and Fier. As the local probation offices should operate at the first level courts some more local offices will be established in other regions in the future.

The probation services staff consists of 50 persons, of whom 38 s the number of officers from 4 local offices.

The General Directorate at the central level is composed of: Finance/Budget, Inspection, Legal and Public relations, Human resources and Statistics

5. Detailed Budget in Euros

The beneficiary will provide in kind contribution in the form foreseen in the twinning manual.

Total budget of the action: € 1 million.

|  | Programme | Support |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Investment Support (I) | Institution Building (IB) | Total Programme(=I+IB) | National Co-financing | IFI | TOTAL |
| Twinning |  | 1,000,000 | 1,000,000 | 0,000 | 0 | 1,000,000 |
| Total |  | 1,0000,000 |  | 0,000 |  |  |

6. Implementation Arrangements

6.1. Implementing Agency

The European Commission Delegation in Tirana will be responsible for tendering, contracting, payments and financial reporting, and will work in close cooperation with the beneficiary. The Programme Manager at the EC Delegation, OPS I, will be Ms Lora Ujkaj, lora.ujkaj@ec.europa.eu

6.2 Main counterpart in the Beneficiary Country:

Arben Shefgjini, General Director of Probation, Ministry of Justice

6.3. Contracts:

The project will be implemented through one twinning agreement.

| Contract | Contract Value ( € ) |
| --- | --- |
|  | 2010 |
| Contract = Twinning with a Member State | €1.000.000 |
| Total € 1.000.000 |  |

7. Implementation schedule (indicative)

7.1. Launching of the call for proposals (date) February 2010

7.2 Start of the project activities (date) November 2010

7.3. Project completion (date) November 2012

7.4. Duration of the implementation period (number of months) 24 months

8. Sustainability:

- The sustainability of the project rests entirely upon the Government of Albania as a whole in the fostering of a professional, merit based public administration.

9. Cross cutting issues

9.1. Equal Opportunity

The principle of equal opportunity will be integrated into all stages of the project implementation, which it is also in conformity with the Albanian Constitution which provides for equal opportunity for men and women be treated equally despite of their race, nationality, gender, origin, religious and political beliefs.

9.2. Environment

NA

10. Conditionality and sequencing

The implementation of the project requires the full commitment and participation of the senior management of the General Probation Directorate.

The Beneficiary shall:

- Ensure that appropriate staff is made available to work with the EU twinning partner(s). Counterparts for each of the objectives will be appointed to facilitate the implementation of the respective activities of the twinning project;

- Be responsible for the selection of trainees - in consultation with the EU experts - as well as for providing the EU experts with legislation and any other documents necessary for the implementation of the project;

- Ensure that appropriate staff for training are made available, that trainees are released from their duties during their training and that once trained they are retained in post;

- Ensure that staff trained under this project are permitted to remain in post and not subject to arbitrary and frequent transfer into posts where their newly acquired skills are of no use or dismissed without due cause/process. To address this, a detailed database of what training was provided to which person should be maintained by the implementing partner(s) to allow for monitoring of the investment in future to ensure those trained have not been transferred;

- Shall provide all possible assistance to solve any unforeseen problem that the EU twinning partner(s) may face;

- Fully support the RTA with accommodation, trainings rooms and logistical assistance.

- Ensure that additional local offices will be established to guarantee adequate supervision over the implementation of alternatives to imprisonment in all regions of Albania

- Ensure that adequate installations and hardware will be provided for running the electronic probation information system.

Equally, the Twinning team, as led by the Twinning Resident Adviser must ensure full collaboration with the counterparts at the institution. Communications should be open and consistent. The Twinning team must carry out activities in the interest of the institution, and maintain its involvement at all stages of activities.

11. Investment criteria

- 10.1	Co-financing: Co-financing will come from the beneficiary in the form of provision of accommodation, training rooms, electricity and telephone, etc.

- 10.2	Additionality: IPA assistance under this project will not overlap with funds provided by the national budget or other bilateral support

Annexes to project Fiche

- Logical framework matrix in standard format

- Implementation Chart

- Contracting and Disbursement Schedule by Quarter

- List of relevant Laws and Regulations

- ANNEX 1: Logical framework

| - LOGFRAME |  | - IPA 2009 |  |  |
| --- | --- | --- | --- | --- |
| - Development of Probation Service and Alternative Measures to Detention in Albania |  | - Contracting period ) expires - 2 years following the conclusion of the Financial Agreement |  | - Disbursement period expires - 1 year following the end date of the execution of contracts |
|  |  | - IPA budget: - EUR 1 million |  | - Total budget : - EUR 1million |
| - Overall objective | - Objectively verifiable indicators | - Sources of Verification |  |  |
| - Support the development of Probation Service and Alternative Measures to Detention in Albania |  |  |  |  |
| - Project purpose - improve the supervision and rehabilitation of conditionally sentenced and released offenders in Albania. | - Objectively verifiable indicators | - Sources of Verification |  | - Assumptions |
|  |  | - -Albanian laws and regulations, EU directives, Ministry of Justice monthly, quarterly, semi-annual and annual reports. - -Ministry of Justice statistics - -EU Adviser Reports - -Regular report of the EU Commission, - -GoA reports |  | - GoA commitment That the Beneficiaries provide cooperation and availability. - That the GoA maintains it’s stated commitment to improve the quality of legislation and strengthen the judiciary independence and the create the conditions for the respect of convicted rights |
| - Results - Standards, procedures and criteria for qualification, selection and recruitment of probation officers developed - Probation training strategy and curriculum prepared and training delivered - Probation officers received appropriate level of training and education - Trained team of trainers prepared. - Study materials on social rehabilitation work with offenders developed and published - Judges, prosecutors and other criminal law practitioners briefed on probation work - Probation structures on central and local level built - Increased use of alternatives to custodial sanctions and measures facilitated - Active involvement of the community in the social reintegration of the offenders - A probation case record and data collection system created - Public tolerance regarding the probationeers increased. - Improved execution of alternatives to imprisonment - Overpopulation of prisons reduced | - Objectively verifiable indicators - Probation structures functioning. - Developed curricula for initial and in-service training for probation officers and related staff - Number of Probation staff trained. - Training of trainers conducted . - Courts and prosecution offices using more alternatives to imprisonment. - Criminal law practitioners including judges, prosecutors and police briefed. - Case management and data collection system in function. - Approved standard formats for all reports produced by probation officers. - A proactive public relations strategy in place . - Public openness regarding the probation procedures. - Inter-agency cooperation at national and local level . - Training Centre for Prisons functioning | - Sources of Verification - - Regular report of the EU Commission - - GoA reports - - EU Adviser Reports - - MoJ annual statistics - Statistics on executive decisions of judiciary - - Regular report of the EU Commission - - GoA reports - - EU Adviser Reports - - MoJ annual statistics - - Reports of national and international human rights organisations - - Opinion polls |  | - Assumptions - The beneficiary maintains its stated commitment to respect the rights of convicted persons establishing the rules of functioning of the probation service and creating the conditions for high quality activity of this structure. |
| - Activities | - Means | - Costs |  | - Assumptions |
| - Component 1 - Support to the Ministry of Justice for implementing the national probation standards and probation service methodologies - Main Beneficiary: MoJ - General Directorate of Probations - Secondary beneficiary: General Directorate of Prisons, Court, Prosecutor offices - Through a process of advice and monitoring by the Resident Twinning Advisor to the Ministry of Justice assist in: - Updating the probation development strategy and yearly action plans - Providing Pre-trial information to prosecutors / bail information reports. - Supervising pre-trial cases. - Providing victim related services including support, victim-offender mediation and restorative justice practices. - Preparation and writing pre-sentence reports for the courts. - Sentence and supervision planning in case of offenders sentenced with alternatives to imprisonment (including obligations for unpaid work, prohibited activities, mental health treatment, group and individual programme to address behaviour such as violence, sex offending, drug/alcohol abuse, domestic violence etc.). - Preparation and writing of pre- release reports. - Supervision of conditionally released prisoners. - Appropriate enforcement of community sentences, securing the offender’s cooperation and compliance with the order/obligations imposed by the courts. - Work with other agencies, particularly the courts, police, prosecutors and prison service based on protocols at the local level. - Monitoring the performance against the Standards and the outcomes of the probation work. - Component 2 - Creating a probation information system which enables political and management decisions to be made on the basis of accurate information, informs developments and targeting and can demonstrate the efficiency and effectiveness of probation work - Main Beneficiary: MoJ - General Directorate of Probations - Secondary beneficiary: General Directorate of Prisons, Court, Prosecutor offices: - Develop common case record and data collection system to be used by probation officers in their supervision of offenders which could be linked with the prison, prosecution and court info systems - Develop with the appropriate authorities of the requisite legal documentation that will be required for each of the new measures - Develop standard formats for reports to judges and prosecutors (bail information reports; pre-sentence reports; supervision plan/reports; pre-release reports, risk assessment reports) - Train probation staff from local and central level as probation information managers in order to assist all probation teams to understand how to use information as a resource Component 3 - Designing the training strategy, preparing the training curriculum and training the probation staff Main Beneficiary: MoJ - General Directorate of Probations Secondary beneficiary: Ministry of Education, General Directorate of Prisons, Court, Prosecutor offices: - Update and implement the probation education and training policy. - Update the training curriculum for the probation service agreed by the Ministry of Justice and institutions involved in delivery the training - Update the standards, procedures and criteria for qualification, selection and recruitment of probation officers Conduct a systematic analysis of the education and training needs of the existing staff and agree a programme to meet the identifying needs - Design a training of trainers programme Design a in-service training provision - Manage the delivery of the training by Short Time Experts throughout the project - Deliver by use of Short Time Experts a programme to train staff to become the future trainers of the Albanian Probation Service - Deliver training to probation managers at central and local level, as well as training of probation inspectors - Establish a Probation Fellowship Programme and a programme of exchange of staff to place Practice Facilitators from EU countries for up to two months in the Albanian probation teams - Organize study visits designed for probation staff to EU Member States in order to get familiar with and see the probation services in action Component 4 - Developing probation offices in different regions of Albania Main Beneficiary: MoJ - General Directorate of Probations and Local Probations Services Offices: - Support setting up new probation offices and assess the required probation staff for each region based on criminal justice statistics and criminological analysis of case data - Set up and maintain an advisory group comprising heads of probation projects, information manager from headquarters, representatives of judiciary, prosecutors, international experts and other key persons - Prepare a formal review process of the pilot projects and conduct a continual assessment of each area - Review of the pilot probation projects. - Component 5 - Developing and implementing a public relations strategy and briefing of judges, prosecutors, police, prison service, local authorities and NGOs about the probation system - Main Beneficiary: MoJ - General Directorate of Probations - Secondary beneficiary: General Directorate of Prisons, Court, Prosecutor offices: - Identify and develop protocols with NGOs all over the country to work in partnership for ensuring that all the requirements of the probation legislation can be implemented throughout Albania - Develop protocols with police, judges, prosecutors, General Directorate for Prisons, local authorities and other Government departments, mediation services in order to ensure maximum cooperation, best possible working environment and understanding. - Conduct probation briefings and seminars for judges, prosecutors, police, prison staff, local authorities, mediation and social services and NGOs. - Prepare a public relations strategy and its action plan Component 6: Further developing the permanent Training Centre for Prisons and a permanent staff training system. - Main Beneficiary: MoJ - General Directorate of Prisons - Secondary beneficiary: General Directorate of Probations - Update and implement the prison education and training policy. - Support the sustainability of the initial and continuous trainings of the Training Centre for Prisons. | - Implemented through a Twinning contract with a Member State. - 1 RTA , 1 TL and additional STEs Seminars Roundtables Study reports Monitoring reports - Trainings - Training materials Study visits | - EUR 1.0 million |  | - Assumptions Component 1: - The beneficiary maintains its stated commitment to create the condition for respecting the rights of the persons in pre-trial and to the convicted with one of the alternatives to imprisonment by establishing the rules of functioning of the probation service and creating the conditions for high quality activity of this structure. Full commitment of the Ministry of Justice and other involved authorities involved in development of probation services in Albania. - Assumptions Component 2: - The beneficiary maintains its stated commitment to offer support in creating a database system for probation cases and establishing standard rules and procedures for reporting. - Assumptions Component 3: The beneficiary maintains its stated commitment to establish cooperation memorandums with the Ministry of Education and other institutions involved for creating a training curricula and for defining the standards, procedures, criteria for recruitment of probation officers. The Ministry of Education and universities support and contribute to the development of probation curricula and to the training. - The beneficiary maintains its stated commitment to develop a training programme for trainers and probation inspectors and to establish a sustainable training system. - Assumptions Component 4: - The beneficiary maintains its stated commitment to support the establishment of the probation offices throughout the country providing for staff, accommodation and equipment for the probation service. Albanian authorities will identify and allocate office space for all local probation offices in regions. - Assumptions Component 5: - The beneficiary maintains its stated commitment to establish protocols of cooperation with NGO-s, The General Directorate of Prisons, Government Departments and local authorities to the better functioning of the probation service. - The beneficiary maintains its stated commitment to support the establishment of a strategy to address the public impact of the probation service. Judges, prosecutors and staff from the MoJ provide active support in implementing the alternatives to imprisonment. |

- ANNEX 2:	Implementation chart

Project:

2010

| January T | February T | March T | April T | May D | June D | July D | August D | September D | October D | November C | December I |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

2011

| January I | February I | March I | April I | May I | June I | July I | August I | September I | October I | November I | December I |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

2012

| January I | February I | March I | April I | May I | June I | July I | August I | September I | October I | November I | December X |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

2013

| January X | February X |
| --- | --- |

D = Design

T = Tendering

C = Contracting period

#### I = Implementation

X = Closure

ANNEX 3

Contracting and disbursement schedule by quarter

Contracting and Disbursement Schedule by Quarter

|  |  | 2009 1Q | 2009 2Q | 2009 3Q | 2009 4Q | 2010 1Q | 2010 2Q | 2010 3Q |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contract Twinning (Components 1, 2, 3,4, ) | Contracted € 1,000,000 |  |  |  |  |  |  |  |
|  | Contracted |  |  |  |  |  |  | X |

|  |  | 2010 4 Q | 2011 1Q | 2011 2Q | 2011 3Q | 2011 4Q |
| --- | --- | --- | --- | --- | --- | --- |
| Contract Twinning (Components 1, 2, 3, 4, ) | Contracted € 1,000,000 |  |  |  |  |  |
|  | Disbursed | x |  |  |  | x |

Annex 4

Reference to relevant reports/documents

Description of Institutional Framework

Ministry of Justice, in compliance with Constitution, law no. 8678, dated 14.05.2001 “On organization and functioning of Ministry of Justice” (amended) and the by-law acts issued in application of it as well as the Internal Regulation of Ministry of Justice has the duty and the responsibility for the conception and implementation of state general policies on justice system issues. In order to realize these legal and constitutional obligations, Ministry of Justice has the authority to compile and follow the policies, to prepare laws and by-law acts, to offer legal assistance through the opposition of legal initiatives carried by other institutions and participation in the working groups, which are created for this purpose. Ministry of Justice also exercises the necessary services related to the judicial system, to the system of executing the penal and civil decisions, to the system of free juridical - professional services, international cooperation in the penal and civil field, other judicial fields and its competence according to the law, and for the co-ordination, harmonization and reformation of the Albanian legislation as a whole.

In compliance with the legal framework which regulates the activity of Ministry of Justice and with the program of the Government, the Ministry of Justice is committed to fulfil all its functions with a clear vision and high rhythm, where the most important role is the Reform in Justice. The whole activity of the Ministry of Justice is described from the objective declared in the Program of the Government “on returning the power of the legal state, where laws are fully applied and equally for everyone, dismantling the systems of corruption”. The Reform in Justice is designed to take measures of a legal, institutional and administrative character, which aim to strengthen the legal state, to return citizens trust on justice, the combat without compromise against corruption and the transparency of the work of the judicial organs.

Beginning with the importance and the role of the Ministry of Justice in the judicial system, in the function of the Reform in Justice undertaken by the Albanian Government, this Ministry has broken this reform down into two levels:

- In the legislative level, paying special attention to the compilation and improvement of the legal framework in almost all the fields of the judicial system, realized by the General Directorate of Codification; and

- In the executive level of the legal framework through verification/control in practice of the legal framework, identification of needs for changing the existing legal framework and taking measures for a general prevention by the General Directorate of Judicial Issues

The realization of the Reform has always taken into consideration the objectives foreseen in the Partnership document, recommendations of CTF and National Plan for the Application of Stabilization Association Agreement, intensifying for this purpose the close cooperation with the international partners. As a result of this cooperation it has been achieved:

- improvement of the legal framework in the field of justice and the bringing it closer to the international standards;

- deepening the combat against the corruptive appearances in the judicial organs through the improvement of the status of the employers in these organs and the exercising of the disciplinary procedures through continuous inspections;

- transparency in the work of the judicial organs;

- intensification and the efficiency of the international judicial cooperation;

- improvement of the judicial power infrastructure;

- noticeable improvement of the living conditions and  the treatment of convicts;

- rapid execution of the judicial decisions.

The Reform in Justice in the legislative level is perceived by the Ministry of Justice as a process including justice delivery which starts with the submission of acts in trial up to the execution of judicial decisions. This process includes three components:

- Improvement of organization and  functioning of courts;

- Improvement of organization and functioning of the operators participating in trial; and

- Improvement of the procedures, as well as organization and functioning of the operators in the execution of the judicial decisions.

If we were to use as a measuring standard the positioning of the judicial system operators against the procedural moment of giving the judicial decision by the courts for disagreement as the object of adjudication, then the reforming point of view of the Ministry of Justice is from the operators in the center to the periphery. Thus, from the central procedural subject the court (the law for the organization of the judicial power, draft–law for the administrative courts, draft-law for the judicial administration), in a way to continue with the operators which are closer to it such as the parties in adjudication (prosecutor office, solicitors, state advocacy) and to conclude with the preliminary peripheral following operators against the judicial process (notary, mediators, judicial police, judicial bailiffs, probation). This point of view doesn’t imply the specific importance of each of these operators but neither denies the importance of each of them in the functioning of the judicial system.

ANNEX 4 -Reference to laws, regulations and strategic documents:

Reference list of relevant laws and regulations:

Law No. 8417, dated 21.10.1998 On approval of the Constitution of the Republic of Albania”

Law No. 7850, dated 29.7.1994 “Civil Code of the Republic of Albania”

Law No. 8116, dated 29/03/1996 “Code of Civil Procedure of the Republic of Albania”

Law No.7895 dated 27.01.1995 “Criminal Code of the Republic of Albania”, amended

Law No. 7905, dated 21.3.1995 “Code of Criminal Procedure of the Republic of Albania”, amended

Law No.8678, dated 14.05.2001 “On the Organisation and Functioning of the Ministry of Justice”;

- Law No.8136, dated 31.7.1996 “On School of Magistrates of the Republic of Albania”

Law No. 9877, dated 18.02.2008, “On organization and functioning of the judicial power in the Republic of Albania”

Law No. 8737, dated 12.02.2001 “On organisation and functioning of the Prosecutor’s Office in the Republic of Albania”,

Law No. 8677, dated 02.11.2000 “On organisation and functioning of the judicial police”,

- Order No. 3155, dated 28.04.2008 “On categorisation of institutions of execution of criminal judgments”, amended

Law No. 7905, dated 21.03.1995 “Criminal Procedure Code”;

Law No.8678, dated 14.05.2001 “On the Organisation and Functioning of the Ministry of Justice”;

Law No.8331, dated 21.04.1998 “On the Execution of Criminal Decisions”;

Law No.8328, dated 16.04.1998 “On the Rights and Treatment of Prisoners”;

Decision of the Council of Ministers, dated 25.03.2009 “On the organisation and functioning of the probation service and the standards and procedures of supervising the execution of alternative sentences” and relevant By-laws.

Reference to SAA (Stabilization and Association Agreement)

The Stabilisation and Association Agreement (SAA) between the Government of Albania and the European Community has been signed in July 2006. Article 78 “Reinforcement of institutions and rule of law” states that:

Article 78“Reinforcement of institutions and rule of law”. Parties cooperation on justice and home affairs shall attach particular importance to the consolidation of the rule of law, and the reinforcement of institutions at all levels in the areas of administration in general and law enforcement and the administration of justice in particular. Cooperation shall notably aim at strengthening the independence of the judiciary and improving its efficiency, improving the functioning of the police and other law enforcement bodies, providing adequate training and fighting corruption and organised crime.

Reference to European Partnership

The project will assist to achieve the priorities included in the proposal of the European Commission dated 06.11.2007 for a Council Decision on the principles, priorities and conditions contained in the European Partnership (EP) with Albania repealing Decision 2006/54/EC. The European Partnership outlines the following short and mid term priorities:

Short – term priorities:

- Ensure that all law enforcement bodies are aware of their human rights obligations and implement them rigorously in accordance with the code of ethics for the prisons system and with international conventions ratified by Albania, in particular the European Convention on Human Rights.

- Ensure that the relevant international conventions are observed in establishing and running new penitentiary facilities.

Medium – term priorities:

- Ensure that detainees and prisoners on remand are treated in accordance with international standards.

- Guarantee that human dignity and personal safety are respected in detention centres, prisons and mental institutions, in accordance with international conventions.

Reference to MIPD

The 2008-2010 MIPD states that "In the area of democracy and rule of law, the capacity of the Albanian institutions remains to a large extend limited, in particular as regards the judiciary, the implementation of the public administration reform and the fight against corruption and organised crime". The Multi-annual Indicative Planning Document underlines the need for improvements in the penitentiary system. This project’s goals comply with the priority set out by the MIPD: “Support to the Reform of the Judicial System” with the overall strategic objective of an independent, reliable and efficient functioning judiciary that guarantees the rule of law. Furthermore, the MIPD stipulates that some of the programmes which should be implemented ought to include: “Provision of the conditions for adequate staffing, infrastructure and equipment to the Judiciary. Support to the High Council of Justice will continue. Institution and capacity building for the Ministry of Justice, subordinated and other independent institutions.

Reference to National Development Plan

The National Strategy for Development and Integration stresses the necessity on the improvements in the justice system, in terms of strengthening the relationship with independent judicial institutions, including the clarification of the respective competences of the judicial inspectorates of the Ministry of Justice and the High Council of Justice.

The reorganisation of courts to improve the efficiency and transparency of decisions and the provision of adequate space, equipment and computer networks.

The strengthening of status, independence and constitutional protection of judges and prosecutors and progress in their training, recruitment, case assignment and evaluation.

The transparency of the civil and criminal justice processes through the publication of court decisions and the results of checks on violation of the procedural code.

The execution of court decisions, which remains low, particularly in cases where the state is obliged to compensate citizens.

The penitentiary system, the prison facilities, and the pre-trial detention centres are all considered to be below European standards.

With regard the Probation Services, the project is in line with the following priority in the draft National Strategy for Development and Integration 2007-2013 “Introduction of a structure for the application of alternative sentences”.

End of Twinning Fiche

_______________________________