IPA 2009 MONTENEGRO

STANDARD TWINNING PROJECT FICHE
Implementation of Personal Data Protection Strategy

- 1.	Basic Information

1.1	Programme:

IPA 2009 (Priority Axis 1 - Political Criteria)

1.2	Twinning Number: MN 09 IB JH 03

1.3	Title:

Implementation of Personal Data Protection Strategy

1.4	Sector:

ELARG Statistical code: 01.24

1.5	Beneficiary country:

MONTENEGRO

- 2.	Objectives

2.1	Overall Objective(s):

To ensure the realization of the fundamental right of protection of personal data, and strengthen cooperation with European Union in this respect

2.2	Project purpose:

The project aims at strengthening the capacity of Montenegro for protection of personal data and implementation of the data protection legislation.

2.3	Contribution to National Development Plan/Cooperation agreement/Association Agreement/Action Plan

European Partnership underlines as short term priorities the following:

- Adopt legislation on the protection of personal data and set up an independent Data Protection Supervisory Authority

- Take the necessary steps to prepare for the conclusion of a cooperation agreement with Europol.

And as mid term priorities the following:

- Ensure the smooth functioning of the Data Protection Supervisory Authority.

- Ensure the capacity of state authorities, in particular law enforcement bodies, to implement the legislation on protection of personal data.

Stabilization and Association Agreement between the European Communities and their Member States and the Republic of Montenegro, Article 81, provides that upon the entry in force of this Agreement, Montenegro shall harmonize its legislation in the field of personal data protection with the Community law and with other European and international privacy law, and Montenegro shall establish independent supervisory authority with financial and human resources sufficient to carry out efficient control and guarantee implementation of the law in the field of personal data protection.

- 3.	Description

- 3.1	Background and justification:

Personal data protection as fundamental human right is guaranteed by the Montenegrin Constitution (Article 43).

Montenegro adopted a new Law on Personal Data Protection in December 2008. Until the entry into force of the new law (June 2009) Montenegro continued to apply the Law on Personal Data Protection from ex-State Union Serbia and Montenegro. However, this law had substantial gaps and was not in line with EU legislation and international conventions. Under this previous Law Montenegro did not have an Independent Supervisory Authority to provide efficient control and guarantee the implementation of the Law on personal data protection. The Montenegrin officials have no previous experience of managing personal data protection issues, which were the responsibility of the Belgrade-based federal autorities up until independence in 2006.

The Government of Montenegro adopted the Personal Data Protections Strategy and the corresponding Action Plan. According to the Personal Data Protection Strategy after adoption of the Personal Data Protection Act, new secondary legislation related to the personal data protection is to be developed. The Personal Data Protection Strategy prescribes the establishment and building up the capacity of a special independent institution for personal data protection supervision and for development and implementation of the secondary legislation in the field of Personal Data Protection.

Furthermore by a Decree, the Government of Montenegro decided that the Ministry of Interior and Public Administration shall be responsible for the policy guidance in this area, for drafting laws and bylaws and the implementation of the Strategy and the Action Plan.

With the adoption of the new law on personal data protection, establishing institutional, human resource and all other required capacities for its implementation, Montenegro aims at regulating the protection and realization of this fundamental human right.

The most important reasons for adopting and implementing data protection legislation are as follows:

- to ensure the realization of the guaranteed right and freedom to personal data protection in accordance with Article 43 of the Constitution of Montenegro;

- the necessity  to adopt new legal framework for personal data protection and ensure the basis for information of exchange with EU Member States and EU institutions, including of sensitive data.

- the need to fulfil obligations resulting from the signed Stabilization and Association Agreement (Article 81);

- to harmonize domestic legislation with the EU law;

- to ensure conditions for realization of obligations resulting from the membership in the Council of Europe;

- to realize the objectives of the Administration Reform Strategy in Montenegro;

Personal data protection is an important part of a broader right to privacy, in theory known by the name ‘Information Privacy’. Personal data protection is one of the subcategories of the fundamental human right to privacy. This is a matter which is thoroughly and strictly regulated by several international legal instruments that will have to be implemented by Montenegro in its legal system in view of international integrations.

To ensure a more efficient and more effective personal data protection, it is necessary to regulate measures which are suitable to prevent the data from a private life of an individual to be published publicly or transmitted to other entities beyond the purposes laid down by the law.

The confidence of the citizens in the institutions of the public and private sectors is one of the main preconditions for efficient implementation of the new Law on Personal Data Protection. Ensuring the security of citizens through establishment of adequate personal data protection mechanisms and continuous informing of the citizens of their rights and obligations in this sphere, the Government of Montenegro will strengthen their confidence in the institutions of public and private sectors. It is necessary to raise the awareness that the keeping of filing systems will reduce the abuse and unlawful disclosure or use of the data.

The independent authority for personal data protection will be the basis for implementation of this law in practice. Full independence of this authority must be ensured, because it must have the power of supervision the respect for the data protection rules by the police, the judiciary, the administration of the ministries, the health care institutions, etc. The independent authority must also have the competence to implement such supervision.  It is envisaged that about 15 persons will be hired for the Independent Supervisory institution.

Directive 95/46/EC prescribes in Article 28 that each Member State shall provide that one or more public authorities are responsible for monitoring the application within its territory of the provisions adopted by the Member States pursuant to this Directive. These authorities must act with complete independence in exercising the functions entrusted to them. Each Member State shall provide that the competent authorities are consulted when drawing up administrative measures or regulations relating to the protection of individuals' rights and freedoms with regard to the processing of personal data.

Schengen Convention, in Article 114, requires independent supervision, by prescribing that each Contracting Party shall designate a supervisory authority responsible in accordance with national law for carrying out independent supervision of the data file of the national section of the Schengen Information System and for checking that the processing and use of data entered in the Schengen Information System does not violate the rights of the data subject. For this purpose, the supervisory authority shall have access to the data file of the national section of the Schengen Information System.

In accordance with the new Personal Data Protection Law and the prevailing practice in the EU Member States, the Independent Agency shall ensure:

- Review and supervision of the personal data filing systems;

- Guidelines regarding the manner of collection, storage, processing and publishing of personal data;

- Supervision over collection, storage, processing and publishing of personal data.

- 3.2	Linked activities (other international and national initiatives):

There has not been any previous programme financed by the EU or other donors in Montenegro in the  area of personal data protection.

- 3.3	Results:

- Result 1: Legislation harmonised with the EU acquis

Objectively Verifiable Indicator:

- At least 15 amended laws and at least 50 amended by-laws in accordance with Personal Data Protection Act.

- Clarified needs for amending the Personal Data Protection Act in accordance with new EU legislation from this field.

- Result 2: Improved capacity for managing personal data

Objectively Verifiable Indicator:

- At least 15 employees in Independent institution trained.

- At least 100 employees in state authorities and in local self-government trained;

- At least 30 employees in public institutions across different sectors of work trained;

- At least 20 representatives of private sector trained.

- 3.4	Activities:

- Activity 1: Harmonising the legislation

1.1. Preparation of catalogue of all regulations setting out the obligation to keep personal data filing systems and who is their controller;

1.2. Identifying regulations in the field of public administration that need to be brought in line with the systemic law, in particular:

- state authorities competent for large filing systems (Register of Electors, Register of Passports, Register of Identity Cards, Register of Weapon Owners, Register of Car Owners,  Register of Drivers' Licences, Registers of Births, Marriages and Deaths, registers of nationality, registers of residence,  Register of Taxpayers, Land Registry, Central Personnel Register...),

- state authority competent for penal records,

- state authority competent for records on misdemeanours,

- judiciary,

- prosecutors,

- other state authorities managing smaller registers,

- police,

-    services responsible for protection of national safety;

1.3 Preparation and adoption of the action plan and formation of working groups responsible for amendments and supplements to the regulations identified in the field of public administration;

1.4 Identifying regulations that need to be brought in line with the systemic law and formation of working groups responsible for amendments and supplements to the regulations identified in the following fields:

- health care sector,

- pension and disability insurance,

- labour,

- education system and electric power industry;

1.5 Preparation and adoption of the action plan and formation of working groups responsible for amendments and supplements to the regulations identified in the fields of health care, pension and disability insurance, labour, education system and electric power industry;

1.6 Identification and harmonization of internal documents, processes and procedures of other legal persons;

1.7. Preparation and issuing of the manual for the filing system controllers to inform them of their rights and obligations;

1.8. Preparation and issuing of the manual for the citizens to inform them of their rights and obligations;

1.9. Entering a selected number of records into the Register (pilot project), e.g..:

- Register of Identity Cards,

- state authority competent for penal records,

- prosecutors’ offices,

- Police…

1.10. Preparation of a complete List of all EU regulations in field of Personal data protection and analysis of the compliance of the Montenegro legislation in the field with the EU acquis.

1.11. Draft Recommendations for further harmonisation of the Personal Data Protection Act.

- Activity 2: Training on data protection

2.1. Revision of the Plan for professional training and development for those responsible for personal data protection;

2.3. Professional training and development of the persons employed in state authorities and in local self-government;

2.4. Professional training and development of the persons employed in public institutions across different sectors of work;

2.5. Professional training and development of the persons employed in the private sector.

- The planned twinning project activities are part of the wider intervention to be implemented through the following contracts: Contract 1: Supply, Contract 2: Service – to be funded by National contribution and Contract 3: Twinning– EU contribution.

- 3.5	Means/ Input from the MS Partner Administration:

- 3.5.1	Profile and tasks of the Project Leader

The PL must have at least ten years of relevant practical working experience as a high-ranking official from an authority in charge of the supervision of personal data protection in the EU with broad knowledge and practical experience, in a new EU Member State (MS) or an EU candidate country.

The PL will continue to work at his/her MS administration but devote some of his/her time to conceive, supervise and co-ordinate the overall thrust of the Twinning project and ensure the commitment of the MS Twinning Partner to the project.

The PL will allocate a minimum of 3 days per month including one visit every 3 months to Montenegro as long as the project lasts.

- 3.5.2 Profile and tasks of the RTA

A senior professional with at least 8 years of professional experience, including some experience in the key areas covered by this assignment: Personal Data Protection legislation and practise in EU and capacity building in this field.

- Experience and profound knowledge of EU standards related to the activities

- Strong written, oral and inter-personal communication skills

- Excellent oral and written English

- Experience in legal drafting

- Management skills

- Experience in similar technical and legal assistance assignments in third countries (especially new EU MS and Potential Candidate/Candidate Countries) will be considered an asset.

- Knowledge of  Montenegrin language (or other close languages spoken in the region) will be considered an asset

- The Project Assistant will assist the RTA in coordination and implementation of the activities and the exact profile will be decided at the level of the detailed work programme elaboration.

The duration of the RTA secondment will be minimum 15 months.

- 3.5.3 Profile and tasks of the short-term experts

- Short term experts (STEs) will cover the twinning project  activities. The STEs should have:

Relevant University degree

Minimum of 5 years professional experience in the respective field

Good written and oral command of English

Experience in training or legislation drafting.

- 4. 	Institutional Framework

The Independent Supervisory Authority as per the new Law on Personal Data Protection has not been established yet and the members of the Council of the Personal Data Protection Agency have not been selected by the Parliament.

The Ministry of Interior and Public Administration will be responsible for the implementation of this project as this Ministry  has been assigned with the task of defining the policy in the area of personal data protection, drafting legislation and monitoring the implementation of the Personal Data Protection Strategy and Action Plan. In order to deal with this matter a small Unit is in the process of being established at the Ministry.

Organisational scheme of the Ministry of Interior and Public Administration follows.

GENERAL SECRETARY

MINISTER

MINISTER’S OFFICE

DEPARTMENT FOR SECURITY, PROTECTION AND CONTROL

STRATEGIC, DEVELOPMENT, AND NORMATIVE AFFAIRS DIVISION

DEPARTMENT FOR INTERNAL ADMINISTRATIVE AFFAIRS

CITIZENSHIP

SECTION

MIGRATION, VISA AND READMISSION SECTION

ASYILUM OFFICE

RESIDENCE AND TRAVEL DOCUMENTS DIVISION

TRAFFIC AND WEAPONS DIVISION

DEPARTMENT FOR EMERGENCY SITUATION AND CIVIL SECURITY

STRATEGIC, DEVELOPMENT, AND NORMATIVE AFFAIRS DIVISION

OPERATIONAL TASKS DIVISION

CIVIL PROTECTION DIVISION

CRISIS MENAGEMENT DIVISION

EMERGENCY CALLING CENTER 112

INSPECTION AND PREVENTION DIVISION

CHELICOPTER UNIT

DEPARTMENT FOR PUBLIC ADMINISTRATION

STRATEGIC, DEVELOPMENT, AND NORMATIVE AFFAIRS DIVISION

SECTION FOR LEGAL EXPERTISE HELP IN REFORM PROCESS

INSPECTION CONTROL DIVISION

DEPARTMENT FOR LOCAL SELF-GOVERNMENT

SECRETARIAT

INFORMATION TECHNOLOGY PROJECTS OFFICE

IT

SECURITY AND PROTECTION

OFFICE

ADVISERS TO THE MINISTER

RESIDENCE AND CITIZENSHIP SECTION

DRIVING LICENCES SECTION

LOCAL UNIT IN  TUZI

TRAVEL DOCUMENTS AND WEAPONS SECTION

LOCAL UNIT IN  GOLUBOVCI

UNIT IN MUNICIPALITY CETINJE

SECTION FOR VEHICLE’S REGISTRATION

SUBORDINATE UNIT IN MUNICIPALITY BIJELO POLJE

RESIDENCE AND WEAPONS SECTION

UNIT IN MUNICIPALITY PLUZINE

UNIT IN MUNICIPALITY SAVNIK

UNIT IN MUNICIPALITY ULCINJ

LOCAL UNIT IN  VLADIMIR

UNIT IN MUNICIPALITY BUDVA

UNIT IN MUNICIPALITY KOTOR

UNIT IN MUNICIPALITY TIVAT

LOCAL UNIT IN PETNJICA

UNIT IN MINICIPALITY ROZAJE

UNIT IN MUNICIPALITY PLAV

UNIT IN MUNICIPALITY ANDRIJEVICA

UNIT IN MUNICIPALITY ZABLJAK

UNIT IN MUNICIPALITY MOJKOVAC

INTEGRATED BORDER MENAGEMENT

SERVICE

EUROPEAN AFFAIRS AND INTERNATIONAL COOPERATION DIVISION

INFORMATION TECHNOLOGY

SERVICE

STRATEGIC, DEVELOPMENT, AND NORMATIVE AFFAIRS  DIVISION

STRATEGY AND DEVELOPMENT OFFICE

INTEGRATED BORDER MENAGEMENT OFFICE

ACCOUNTING AND FINANCE

OFFICE

SUPERVISION ON LAW APLICATION

AND LAW ENFORCEMENT SECTION

BORDER CROSSING

MENAGEMENT

OFFICE

SUPERVISION OF POLICE, COMPLAINTS AND PETITIONS

DIVISION

SUPERVISION ON LAW APLICATION

AND LAW ENFORCEMENT DIVISION

PROCUREMENT AND INVESTMENS OFFICE

SECURITY AND PROTECTION DIVISION

CLASSIFIED INFORMATION DIVISION

UNIT IN MUNICIPALITY DANILOVGRAD

FILIJALA KOLAŠIN

IT ADMINISTRATION OFFICE

HUMAN RESOURCES MENAGEMENT OFFICE

IT

IMPLEMENTATION OFFICE

SUBORDINATE UNIT IN MUNICIPALITY HERCEG NOVI FOR MUNICIPALITIES HERCEG NOVI, KOTOR AND TIVAT

ADMINISTRATION OFFICE

SUBORDINATE UNIT IN MUNICIPALITY PLJEVLJA FOR MUNICIPALITIES PLJEVLJA AND ZABLJAK

SUBORDINATE UNIT IN MUNICIPALITY PODGORICA FOR MUNICIPALITIES PODGORICA, CETINJE, DANILOVGRAD AND KOLASIN

SUBORDINATE UNITS FOR EMERGENCY SITUATION AND CIVIL SECURITY

SUBORDINATE UNIT IN MUNICIPALITY BIJELO POLJE FOR MNUCIPALITIES BIJELO PLJE AND MOJKOVAC

SUBORDINATE UNIT IN MUNICIPALITY BERANE FOR MUNICIPALITIES BERANE, ROZAJE, ANDRIJEVICA AND PLAV

SUBORDINATE UNIT IN MUNICIPALITY BAR FOR MUNICIPALITIES BAR, ULCINJ AND BUDVA

SUBORDINATE UNIT IN MUNICIPALITY NIKSIC FOR MUNICIPALITIES NIKSIC, SAVNIK AND PLUZINE

SUBORDINATE UNITS

FOR INTERNAL ADMINISTRATIVE AFFAIRS

SUBORDINATE UNIT IN MUNICIPALITY PODGORICA

SUBORDINATE UNIT IN MUNICIPALITY NIKŠIĆ

SUBORDINATE  UNIT IN MUNICIPALITY BAR

SUBORDINATE UNIT IN MUNICIPALITY HERCEG NOVI

SUBORDUINATE UNIT IN MUNICIPALITY BERANE

SUBORDINATE UNIT IN MUNICIPALITY PLJEVLJA

CITIZENSHIP, TRAVEL DOCUMENTS AND WEHICLE’S REGISTRATION SECTION

- 5. 	Budget

The budget allocated for this twinning project is 700,000€.

- 6. 	Implementation Arrangements

- 6.1 	Implementing Agency responsible for tendering, contracting and accounting

Delegation of the European Commission to Montenegro

Mr Nicola Bertolini, Head of Operations

Vuka Karadžića 12, 81 000 Podgorica, Montenegro

Telephone: +382 20 444 600

Fax: +382 20 444 666

Email: Nicola.BERTOLINI@ec.europa.eu

- 6.2 	Main counterpart in the BC

Government of Montenegro

Ministry of Interior and Public Administration (MIPA)

Bulevar Svetog Petra Cetinjskog 22, 81000 Podgorica, Montenegro

ProjectLeader: Svetozar Djurovic, Secretary of the MIPA

Contact Person: Milorad Janjevic, Advisor in Department for European Affairs and International Cooperation  MIPA

Phone: 00 382 20 248 812

Mobile: 00 382 67 289 624

Fax: 00 382 20 225 384

E-mail: mupsekretar@cg.yu

- 6.3 	Contracts

One twinning contract

- 7.	Implementation Schedule (indicative)

- 7.1	Launching of the call for proposals

October 2009

- 7.2	Start of project activities

Second quarter of 2010

- 7.3	Project completion

Third quarter of 2011

- 7.4	Duration of the implementation period

15 months

- 8.	Sustainability

The project activities are in line with EU sector policy acquis and the strategic documents of Montenegro in this area. The Ministry of Interior and Public Administration is in a position to effectively sustain the project deliverables in the long run. All supported actions are sustainable in the long term beyond the date of accession and comply with EU norms and standards. The sustainability is guaranteed by the compliance with the acquis and compliance with the obligations of EU membership in area of data protection. The beneficiary foresees allocation of adequate staff and financial resources to ensure the administrative and operational functions of the integrated national regulatory and supervisory authority.

The project’s main impact will seek to strengthen the independence and efficiency of new Independent institution for Personal Data Protection as well as its capacity to operate according to EU standards. This will allow better secondary legislation and its implementation. Sustainability of the results of the project will be enhanced by securing Government commitments to provide the necessary financial and human resources to manage personal data protection. The project will provide training of professionals in Independent Institution as well as in other institutions.

- 9.	Crosscutting issues

9.1	Equal Opportunity

Equal opportunity for men and women will be secured trough appropriate information and publicity material, in the design of projects and access to the opportunities they offer and trough early monitoring of the composition of take up.

An appropriate gender balance will be sought on the managing bodies of the project.

During capacity building activities and trainings through the twinning programme specific attention will be given to equal treatment and opportunities for women.

9.2	Environment

The project is expected to have a neutral impact on the environment.

9.3       Minorities

The project will address minorities’ issues as an integral part of its overall objectives and project purpose. While implementing the project all minority related topics will be respected in raising awareness and trainings.

- 10.	Conditionality and sequencing

There are a number of preconditions necessary for implementation of this project:

- The first precondition for this project is adoption of the Personal Data Protection Act in

- After the adoption of the Personal Data Protection Act the next important step will be the establishment of the independent supervisory institution (Agency for Personal Data Protection) and the election by the Parliament of the members of its Council. Preparation and adoption of the Rulebook on Internal Organization and Systematization of work posts in this independent supervisory authority is also very important..

- Appointment of key personnel, allocation of working space and facilities for the Personal Data Protection Agency by the time of the start of this project.

- Next steps are employment of complete staff for the independent institution, providing equipment and capacity development activities at the supervisory authority and  at other institutions:  nomination of relevant staff by the beneficiary to participate in capacity building as well as in working groups, study visits, steering and coordination committees, as per the Work Plan of the Twinning Contract. This would be particularly important for those assigned to deal with the harmonization of the entire legislation that prescribes maintaining of a registry with personal data.

In the event that these conditions are not met, suspension or cancellation of the project will be considered.

- ANNEXES

1. 	Logical framework matrix in standard format

2. 	Detailed implementation chart - Not included

3. 	Contracting and disbursement schedule by quarter for full duration of programme (including disbursement period)

4. 	Reference to feasibility /pre-feasibility studies. For all investment projects, the executive summary of the economic and financial appraisals, and the environmental impact assessment should be attached - Not included

5. 	List of relevant Laws and Regulations

6. 	Reference to relevant Government Strategic plans and studies (may include Institution Development Plan, Business plans, Sector studies etc) - Not included

Annex 1-	Log frame in Standard Format

| LOGFRAME PLANNING MATRIX |  | Programme title and number: Implementation of Personal Data Protection Strategy |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Contracting period expires two years from the date of the conclusion of the Financing Agreement |  | Disbursement period expires one year from the final date for execution of contracts |  |
|  |  | Total budget: 700 000,00 € |  | IPA 2009: 700 000,00 € |  |
| Overall objective | Objectively Verifiable Indicators |  | Sources of Verification |  |  |
| To ensure the realization of the fundamental right of protection of personal data, and strengthen cooperation with European Union in this respect | - Positive conclusions of the EU Commission, European Parliament, and Council of Europe in period 2008-2010; - Provisions of Personal Data Protection Act completely harmonised with the Acquis. |  | EU Progress reports 2009 and 2010, European Parliament and Council of Europe Reports; |  |  |
| Project Purpose | Objectively Verifiable Indicators |  | Sources of Verification |  | Assumptions |
| To strengthen the capacity of Montenegro for protection of personal data and implementation of the data protection legislation. | - Independent Institution established; - Personal Data Protection Action Plans adopted by all relevant institutions; - Primary and secondary legislation in other fields harmonized with the systemic Personal Data Protection Act; - Information exchange with EU Member States and other countries; - Automatically connected personal data filing systems; - Standardised electronic access to the personal data filing system by means of IT ; - Case Law; |  | - Reports of the Ministry competent for public administration affairs relating to the personal data protection; - Independent Institution Annual Report; - Statistics excerpt on information exchange between Montenegro and EU Member States, and other countries; - Project Report; |  |  |

| Results | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| --- | --- | --- | --- |
| - Result 1: Legislation harmonised with the EU acquis - Result 2: Improved capacity for managing personal data | - At least 15 amended laws and at least 50 amended by-laws in accordance with Personal Data Protection Act. - Clarified needs for amending the Personal Data Protection Act in accordance with new EU legislation from this field. - At least 15 employees in Independent institution trained. - At least 100 employees in state authorities and in local self-government trained; - At least 30 employees in public institutions across different sectors of work trained; - At least 20 representatives of private sector trained. | - Reports of the Ministry competent for public administration affairs relating to the personal data protection, - Independent Institution Annual Report incl. Institution Report on Inspection; - Official Gazette of Montenegro - Recommendations on legal harmonisation in the data protection field - Reports of the Independent institution, incl. Report on realization of the Plan for Further professional training and development of the staff of the Independent institution, and other organisations; | Government committed to maintain and strengthen capacities for data protection Community involvement and support from all entities included in this project Strategy for personal data protection and Action plan being implemented |
| Activities | Resources/ means | Budget | Assumptions |
| - Activity 1: Harmonising the legislation 1.1. Preparation of catalogue of all regulations setting out the obligation to keep personal data filing systems and who is their controller; 1.2. Identifying regulations in the field of public administration that need to be brought in line with the systemic law, 1.3. Preparation and adoption of the action plan and formation of working groups responsible for amendments and supplements to the regulations identified in the field of public administration; 1.4. Identifying regulations that need to be brought in line with the systemic law and formation of working groups responsible for amendments and supplements to the regulations identified in the fields of health care, pension and disability insurance, labour and education system and electric power industry. 1.5. Preparation and adoption of the action plan and formation of working groups responsible for amendments and supplements to the regulations identified in the fields of health care, pension and disability insurance, labour, education system and electric power industry; 1.6. Identification and harmonization of internal documents, processes and procedures of other legal persons; 1.7. Manual for the filing system controllers to inform them of their rights and obligations; 1.8. Manual for the citizens to inform them of their rights and obligations; 1.9. Entering a selected number of records into the Register (pilot project), 1.10. Preparation of a complete List of all EU regulations in field of Personal data protection and analysis of the compliance of the Montenegro legislation in the field with the EU acquis. 1.11. Draft Recommendations for further harmonisation of the Personal Data Protection Act. - Activity 2: Training on data protection 2.1. Revision of the Plan for professional training and development for those responsible for personal data protection; 2.3. Training of the persons employed in state and local authorities 2.4. Training of persons employed in public institutions 2.5. Training of persons employed in the private sector. | Contract 3: Twinning– EU contribution | IPA – Twinning – 700.000 EUR | Ministry and public institutions fully committed to implementation of this project Expert and technical available during the initial stage of establishing the Independent Institution and strengthening its Human Resources capacities (2009). Good cooperation among all beneficiaries involved Motivation and willingness of the staff of the Independent Institution and other relevant actors dealing with personal data to participate in the programs of the professional development and trainings Obtaining the list of the legal and natural persons, other than controllers to whom personal data were disclosed for their use Pre-conditions - Adoption of the Personal Data Protection Act in 2009 - Appointment of key personnel in Independent Agency for Personal Data Protection - Premises for new Independent institution provided - Plan for Further Professional Training and Qualification. |

- ANNEX 3:	indicative amounts (in €) Contracted and disbursed by quarter for the project

|  | 2010 | 2010 | 2010 | 2010 | 2011 | 2011 | 2011 | 2011 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Q 1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |
| Contracted |  |  |  |  |  |  |  |  |
| EC support | 700.000 |  |  |  |  |  |  |  |
| Total | 700.000 |  |  |  |  |  |  |  |
| Cumulated | 700.000 |  |  |  |  |  |  |  |
| Disbursed |  |  |  |  |  |  |  |  |
| EC support |  | 700.000 |  |  |  |  |  | 700.000 |
| Total |  | 700.000 |  |  |  |  |  | 700.000 |
| Cumulated | 0 | 700.000 |  |  |  |  |  | 700.000 |

- ANNEX 5:	Reference list of relevant laws and regulations, and strategic documents

Strategy for Personal Data Protection has been adopted in June 2008. The main objectives of this Strategy are:

- To ensure the publicity of work and supervision over the activities of public and private sectors;

- To protect the right to privacy and other human rights and fundamental freedoms with respect to the processing of personal data;

- To strengthen the confidence of citizens in the institutions of the public and privates sectors which dispose of their personal data;

- To raise the level of quality of the personal data protection standardization and to harmonize legislation regulating other fields with the systemic law;

- To establish responsibilities and to introduce certain control mechanisms in all spheres of public and private sectors with the aim to reduce the disclosure of personal information to the minimum extent in terms of content required by an open and democratic society;

- To develop institution which will be responsible for monitoring and control of the use of databases containing data on individuals;

- To introduce modern information technology – control mechanisms for the lawful processing of personal data with particular focus on prevention of violation of the right guaranteed by the Constitution;

Specific objectives of the Strategy are as follows:

- To adopt the systemic Personal Data Protection Act harmonized with the EU law;

- To identify the ministry to be competent for public administration affairs relating to the personal data protection;

- To harmonize primary and secondary legislation in other fields with the Personal Data Protection Act;

- To establish independent institution the activities of which will be aimed at appropriate implementation of the Personal Data Protection Act;

- To make the public aware of the personal data protection system;

- Further professional training of the persons responsible for the personal data protection.

The List of relevant EU legislation:

Directive 95/46/EC of the European Parliament and of the Council of 24 October 1995 on the protection of individuals with regard to the processing of personal data and on the free movement of such data.

Directive 2002/58/EC of the European Parliament and of the Council of 12 July 2002 concerning the processing of personal data and the protection of privacy in the electronic communications sector (Directive on privacy and electronic communications).

Directive 2006/24/EC of the European Parliament and of the Council of 15 March 2006 on the retention of data generated or processed in connection with the provision of publicly available electronic communications services or of public communications networks and amending Directive 2002/58/EC

Convention of the Council of Europe for the protection of individuals with regard to automatic processing of personal data (ETS 108), adopted on 28 January 1981 in Strasbourg.

Convention implementing the Schengen Agreement of 14 June 1985 between the Governments of the States of the Benelux Economic Union, the Federal Republic of Germany and the French Republic on the gradual abolition of checks at their common borders ((which must be complied with by all member states of the Schengen border regime)

Convention on the Use of Information Technology for Customs Purposes Convention Based on Article K.3 of the Treaty on European Union, on the Establishment of a European Police Office (Europol Convention)

Act No 1/99 of the Joint Supervisory Body of Europol of 22 April 1999 laying down its rules of procedure Council Decision of 17 October 2000 establishing a secretariat for the joint supervisory data-protection bodies set up by the Convention on the Establishment of a European Police Office (Europol Convention), the Convention on the Use of Information Technology for Customs Purposes and the Convention implementing the Schengen Agreement on the gradual abolition of checks at the common borders (Schengen Convention).

European Convention on Protection of Human Rights and Freedoms.