- Twinning Number: TR 08 IB JH 04

- Action Plan on Integrated Border Management-Phase 2

- Note for the information of future Twinning partners:

- Please note that this fiche concerns 3 different contracts, of which one takes the form of a Twinning (Result 1, see paragraph 3.4)

- The indicative budget for the Twinning component of activity 1 is € 1.4 million (see paragraph 4)

- The indicative duration of the Twinning project is 18 months (see paragraph 5)

- Please see Annex V on page 34 for further details on the Twinning component

- Standard Project Fiche

- Basic Information

  - CRIS Number: TR080210

  - Title: Action Plan on Integrated Border Management-Phase 2.

  - Sector: 24-Justice, freedom and security

  - Location: Turkey

Implementing arrangements:

  - Implementing Agency:

The Central Finance and Contracting Unit (CFCU) will be Implementing Agency and will be responsible for overall coordination and monitoring of project implementation, all procedural aspects of the tendering process, contracting matters and financial management, including payment of project activities.

The Director of the CFCU will act as Programme Authorizing Officer of the project.

Mr. Muhsin ALTUN (PAO-CFCU Director)

Central Finance and Contracting Unit

Phone: +90 -312- 295 49 00

Fax: +90 -312- 286 70 72

E-mail: muhsin.altun@cfcu.gov.tr

Address: Eskişehir Yolu 4.Km. 2.Cad. (Halkbank Kampüsü) No:63 C-Blok

06580 Söğütözü/Ankara Türkiye

  - Main Beneficiary:

Ministry of Interior (Project Implementation Directorate on Integrated Border Management)

SPO:  The Director of the PIDIBM will act as SPO of the project.

Mr. Şenol Arslan (SPO)

Project Implementation Directorate on Integrated Border Management

Phone: +90 -312- 412 49 70

Fax: +90 -312- 231 16 87

E-mail: senars@egm.gov.tr

Address: AB Projeleri İzleme ve Koordinasyon Merkezi Yücetepe mahallesi Necatibey caddesi No: 108 06580 Ankara/Turkey

Co-Beneficiaries:

1) General Staff (Land Forces)

2) Turkish National Police

3) Gendarmerie General Command

4) Coast Guard Command

5) Ministry of Health (represented by the Directorate General of Health for Border and Coastal Areas)

  - Overall cost: € 28,800,000

  - EU contribution: € 21,880,000

1.9   Final date for contracting: 2 years after the signature of the Financing Agreement

1.10 Final date for execution of contracts: 2 years following the end date for contracting

1.11 Final date for disbursements: 3 years following the end date for contracting.

2.       Overall Objective and Project Purpose

2.1 Overall Objective(s):

To achieve the EU overall strategic goal of open and secure borders by developing and strengthening Turkey’s legal, institutional and technical capacity for alignment with EU integrated border management (IBM) policy.

2.2 Project purpose:

To support the Turkish Government in transforming the current border management to an integrated border management and enlarging the prototype green and blue border surveillance and check points and ensure further development and implementation of high level border management architecture and standards in line with EU’s IBM policies and strategies.

2.3 Link with Accession Partnership (AP)/ NPAA / EP /SAA

2008 Accession Partnership

Short-term priorities:

- Continue efforts to implement the National Action Plan on Integrated Border Management including through the definition of a precise road map. Steps should be taken to establish the new border law enforcement authority,

- Continue efforts to implement the National Action Plan on Asylum and Migration (including through the adoption of a roadmap), increase capacity to combat illegal migration in line with international standards,

- Implement the national strategy on organized crime. Strengthen the fight against organized crime, drugs, trafficking in persons, fraud, corruption and money-laundering.

Medium-term priorities:

- Accelerate efforts to set up an integrated border management system in line with the acquis, based on close interagency coordination and professionalism of staff, covering inter alia, a pre-screening mechanism to identify persons in need of international protection at borders.

According to the NPAA (National Programme for the Adoption of the Acquis) for Turkey, there are four main objectives to be completed to fit the requirements in this field:

- Cooperation and coordination between the competent Ministries and other public institutions will be strengthened.

- Border management will be reinforced and preparations will be made to fully implement the Schengen Convention.

- Work will be undertaken for the alignment of Turkish visa legislation and practices with the EU.

- Measures already underway will be enhanced to further decrease the number of people attempting to reach Western European countries illegally, and additional initiatives will be taken to strengthen these measures.

Regular report priority

Chapter 24 of “Turkey 2007 Progress Report” prepared by European Commission suggests that:

- The National Action Plan needs to be equipped with a more precise roadmap containing concrete actions, targets, realistic deadlines, responsible authorities and an estimated budget for each of the actions requiring important investment. Further attention needs to be paid as regards training and professionalism of border staff, risk analysis capacity and modernization of checking equipment,

- Turkey should continue its efforts in its regional law enforcement cooperation,

- The national strategy against organized crime should be complemented by a concrete action plan and implemented accordingly. To fight crime more effectively, infrastructure and equipment for forensic analysis need to be improved. Inter-agency cooperation, data protection and forensic capacity in investigations remain issues to be improved,

- Considerable and sustained efforts are required in areas such as police cooperation and external borders,

- Efforts should be made to establish a risk analysis unit within the police administration.

2.4 Link with MIPD

The Multi-annual Indicative Financial Framework for the period 2007 - 2009 foresees a financial envelope for EU assistance to Turkey of 1.6 billion euros in which the assistance for the Component I is 736 million euros. As a candidate country, Turkey is eligible for all five IPA components: I) Institution Building, II) Cross-border Cooperation, III) Regional Development, IV) Human Resource Development and V) Rural Development.

MIPD identifies the relevant priorities and actions required to address the three objectives of the pre-accession strategy.

The Institution Building component, representing the largest budgetary allocation, will address all three objectives.

As concerns the adoption and implementation of the acquis communautaire, the priority areas for support  reflecting the volume of legislation to be transposed and implemented as well as the investments required, will be: agriculture; environment; justice, liberty and security (particularly border management; migration and visa policy); and obligations stemming from the Customs Union agreement.

According to the first component of the MIPD (Multi-annual Indicative Planning Document for Turkey), I- Institution building; for 2007-2009, the eligible areas of intervention for the Institution Building components are defined by the Accession Partnership.

The priorities for assistance under the Institution Building component will be transposition and implementation of the Acquis for the Migration and asylum policy, Border management; Visa policy and practice, Fight against organized crime, drugs, protection of personal data under the chapter of Justice, Liberty and Security.

Under the title of Forms of assistance to be provided, “Institution Building support will continue to be provided principally through technical assistance and twinning, supplemented by supplies of equipment where appropriate. Training actions will focus as far as possible on training institutions to promote sustainability”.

2.5 Link with National Development Plan (Contribution to National Development Plan (and/or Structural Funds Development Plan/SDP)

According to point 726 of the 9th National Development Plan, in accordance with the National Action Plan towards the implementation of Turkey’s IBM Strategy; the legal and institutional framework action will continue towards establishing a professional border enforcement unit.

2.6 Link with national/sectoral investment plans

Turkey must provide the borders with technological equipment and implement certain projects with the EU funds to establish surveillance and controls meeting the EU standards in line with the institutional and legislative efforts for integrated border management.

A financing source from the EU funds and from the Turkish government should be created for the investments. The “Financing Plan” annexed to the national action plan should be taken into consideration in implementing the investments.

The investments included in the financing plan are distributed over the years, according to their priority. As these efforts are within the scope of a long term program, the future financing facilities should also be utilized for this purpose.

3.       Description of project

3.1 Background and justification

## a) Relevant country background

The conclusions of the Helsinki European Council in December 1999 recognized Turkey as a candidate for membership to the European Union. In December 2004, the European Council concluded that Turkey sufficiently fulfils the Copenhagen political criteria to open accession negotiations. Accordingly the accession negotiations started on 3 October 2005. The Turkish Government in the course of progress towards accession to the European Union and in response to the obligations of the EU and its Member States is actively following a National Programme for the Adoption of the Acquis. However the objective of the process of law approximation is to not only implement the relevant amendments to existing legislation but as importantly, to strengthen those institutions responsible for the enforcement or implementation of the new procedures. This process of ‘Institution building and Reform’ in order to enhance administrative capacity, is seen as crucial in ensuring that Turkey is successful in the transition to the standards, norms, expectations and obligations of similar EU Member State administrations.

## Current state of affairs in the relevant sector

Justice, freedom and security is one of the main and accurate subjects of the enlargement process and member countries major on the matters such as border controls. Matters such as border controls constitute the main subjects of which the member countries major on.

After the membership to the EU, as Turkey’s eastern borders will be the external eastern borders of the Union, management of a comprehensive border security and its implementation constitutes an important subject.

During recent years, with the increase of major acts of international terrorism and with the increase of cross-border flows of illegal goods, people and substances, the border management has taken a higher priority. The task is enormous and requires a coordinated and integrated approach.

Turkey has difficulties in providing border security as she is a country which has long mountainously steep land borders on the east and south west. She has also long costs which constitutes sea borders on her South, North and West. She poses a crossroads among Middle East, Asia and Europe. Due to this geographical location a strong border controlling and safeguarding organization is needed. Turkey has total 2.949 km. of land borders and a rugged land configuration. 65% of her land borders are on mountainous region. Borders in east and southeast lie on mountains. Besides, on some border regions, the climatic conditions are very harsh, where winter may last up to six months.

In the recent years, illegal border crossings, mostly in the form of multinational organized crime (smuggling, trafficking and terrorism etc.) nature have created serious ramifications not only for Turkey but also for European border management system. Illegal immigrants are smuggled into Turkey and also Europe either across unregulated land, sea or air borders or through regulated security check points using counterfeit/stolen passports or concealed in cargoes. Turkey is influenced by these illegal activities due to the fact that it sets a bridge between east and the west, holds the straits which are the only exits of the Black Sea to the open seas and has natural and cultural charms as well as democratic and universal principles of law embedded in the social structure. Within the framework of the fight against the criminal organizations of human trafficking, having an organized structure and establishing networks of communication both in source and destination countries; it should be kept in mind that a professional approach is an important factor positively affecting the success. Novel, reliable and scaleable solutions should be required if illegal immigrants are to be filtered out efficiently while not unduly impeding the flow of the vast majority of legitimate travelers and vehicles. Such solutions should naturally have to respect privacy and human rights.

The numbers of illegal migrants apprehended in Turkey between 2004 and 2007 are as following; in 2004 61.228, in 2005 57.428, in 2006 51.983 and in 2007 64.290. The numbers of trafficking in human beings victims identified in Turkey between 2004 and 2007 are as following; in 2004 239, in 2005 256, in 2006 246 and in 2007 148. The numbers of trafficking in human beings organizers apprehended in Turkey between 2004 and 2007 are as following; in 2004 227, in 2005 379, in 2006 422 and in 2007 308. Specifically for blue borders, 1665 illegal immigrants and 45 organizers have been captured in 163 events in 2006 and in 2007, 4832 illegal immigrants have been captured. The 93% (4512) of these captures happen in the Aegean Sea; in Kuşadası 1056, Ayvalık 944, Çeşme 478, Behramkale 431, Didim 437 and Ayvacık 258. Total amount of captures in 2007 is higher than the total amount of captures of the last three years (4012).

The Directorate General of Health for Border and Coastal Areas (HBCA) is the affiliated body of the Ministry of Health (MoH). It has been institutionalized before the MoH in 19th century. It is authorized according to international conventions, treaties and agreements. The HBCA of MoH is mainly responsible for protecting the country from communicable diseases and preventing trans-border spread of them. As being the responsible body for health care at borders (maritime and aviation), the HBCA of MoH has peripheral nation-wide units at coasts and international airports.

Peripheral organization:

Coastal Health Inspection Centers: 45

Airport Health Inspection Centers: 17

Human Resources:

There are 465 workers already employed.

Hence, the brief list of existing problems is identified as follows:

- The legal and institutional structures have to be developed and strengthened pertaining to the EU requirements and best practices,

- The Action Plan has to be detailed based on a common architecture,

- The technical capacity at the gates and border areas has to be strengthened through modern procedures and use of equipments.

## Related programs and other donor activities:

- TR 02 JH 02 Support for the Development of an Action Plan to implement Turkey’s Integrated Border Management Strategy

Output: An action plan to determine the legal and institutional reforms, training activities, and infrastructure and equipment investments expected to be realized for an integrated border management system in alignment with the EU requirements.

- TR 04 JH 04 Development of a Training System for Border Police

Output: A training strategy, programme and curriculum in EU standards for the new border police to be established and a practical “Common Manual of Checks at the External Borders” developed for personnel currently working at borders

- TR 03 JH 05 Visa Policy and Practice

Output: Legislative framework on visa issues as well as visa practices in accordance with EU acquis and implementation of document security

- TR 02 JH 03 Support for the Development of an Action Plan to Implement Turkey’s Asylum-Migration Strategy

Output: An action plan on asylum and migration strategy in line with EU legislation. It also improved the operational and administrative (coordination, human resources, equipment) capacity of the agencies responsible for management and implementation of Turkish asylum and migration policy.

- TR 03 JH 03 Strengthening Institutions in the Fight against Trafficking in Human Beings

Output: An Action Plan towards Strengthening Institutions in the Fight against Trafficking in Human Beings is prepared and waiting for the approval of Prime Minister.

- TR 06 01 07 Support to the set up of Asylum and Country of Origin Information (COI) Systems

- TR 07 IB JH 04 Action Plan on Integrated Border Management-Phase 1.

- Purpose: To support the Turkish Government in transforming the current border management to an integrated one by detailing the Action Plan in the form of a Roadmap defined in the Action Plan and ensure further development of high level border management and border surveillance architecture and standards in line with EU’s IBM policies and strategies.

Training and Cooperation Activities

“Specialized Training Program on Fight against Human Smuggling” was organized at TADOC jointly by the Department of Anti-Smuggling and Organized Crime and Germany Federal Police in 2 terms, first on May 29-June 01, 2007 and second on June 04-07, 2007. The mentioned training program was supported in particular by the experts from the German Federal Police and a public prosecutor from the Supreme Court of Appeals and experts from the Department of Combating Financial Crimes, who participated as trainers. Moreover, representatives from the Coast Guard Command, General Command of Gendarmerie and Undersecretariat for Customs, supporting the fight against this crime in the country, participated in the trainings as trainees.

“Meetings of National Institutions and Liaison Officers Fighting Against Human Smuggling and Trafficking in Human Beings” initiated by participation of foreign liaison officers assigned in Turkey and the representatives of the fighting agencies in October 2006 under coordination of the Department of Anti-Smuggling and Organized Crime with the purpose of increasing the effectiveness of the fight against human smuggling offence, continued in the year 2007 as well.

In these meetings, our policy in the fight against crime and model projects as well as the national and international cooperation activities in the field of both human smuggling and trafficking in human beings is shared.

Furthermore, active participation to the meetings on human smuggling and trafficking in human beings offence at the national and international level organized for training, operational cooperation and assessment purposes has been ensured. On the other hand, referral was made to the activities undertaken by our country in the fight against human smuggling and concrete progress enabled by the legal reforms within the scope of the activities for harmonization with the European Union acquis were emphasized in the “Regular Report on Turkey” published on November 6, 2007 by the European Commission.

- b) Current level of Progress

Within the scope of the studies to determine a comprehensive harmonization strategy on the protection of the external borders as a part of the efforts of alignment with the EU legislation and practice, Turkey set up a Task Force, bringing together different agencies responsible for border management, asylum and migration namely General Staff, Ministry of the Interior (General Directorate for Public Security, Gendarmerie General Command and the Coast Guard Command), Ministry of Foreign Affairs, the Under-secretariat of Customs to develop an overall strategy in these areas in 2002, under the coordination of the Ministry of Interior and three separate working groups connected to this task force were established in the fields of “asylum”, “migration” and “external borders.”

As a result of the studies which continued for one year, “the Strategy Paper for the Protection of External Borders” was issued in April 14, 2003, with the contributions of the representatives from institutions and agencies such as the General Staff, Ministry of Foreign Affairs, Ministry of the Interior (General Command of Gendarmerie, General Directorate for Security and the European Union Coordination Department).

Based on the aforementioned strategy paper, “National Action Plan towards to Implementation of Turkey’s Integrated Border Management Strategy” was drawn up as a result of the twinning project carried out in cooperation with France and UK Consortium and was approved by Prime Minister of Turkey on 27 March 2006.

The working group in the field of “external borders” continues to regular monthly meetings in which to convey information about the latest progress and deficiency about the projects that take place in the section of the infrastructural needs towards the border surveillance and control and to give information about the necessary requirements and the Roadmap to pursue.

A training strategy, programme and curriculum in EU standards for the new border police to be established and a practical “Common Manual of Checks at the External Borders” was developed for personnel currently working at borders as a result of the twinning project “Development of a Training System for Border Police” carried out in cooperation with Spain and Hungary Consortium in the end of 2007.

Within the context of TAIEX, a study visit for analyzing the technical infrastructure used for the border security was accepted as a result of the 2007-1. group applications, a study visit for analyzing the development of research relevant for the control and surveillance of external borders was accepted as a result of the 2007-3. group applications and a study visit to a member state for obtaining first hand info about developing a risk analysis model at strategic, operational and technical level in line with best practices, standards and procedures for border police units was accepted as a result of the 2008-1. group applications to a member state of EU in which the beneficiary is Ministry of Interior Directorate of Integrated Border Management.

Within the context of MATRA, a project proposal for training of law enforcement units in order to prevent use of forged travel documents by people was accepted as a result of 2008 programme applications.

Turkey has also adopted “Implementing Regulation on the Principles of Surveillance and Control of Communicable Diseases Whose Notification are Compulsory” published by the last quarter of 2005, in Turkish Official Journal. Revised Communicable Diseases Surveillance Guidelines are published by the last quarter of 2005. A regular bulletin (printed document/ web site) is in place by the end of 2006.

As the transition to integrated border management is to be started at the border gates and as the completion of the legislative, administrative and infrastructural efforts to strengthen the existing capacity in accordance with the EU acquis and standards will take a long time, it is decided to be done step by step. As a conclusion the project “Action Plan on Integrated Border Management- Phase I” was developed, accepted in the context of the first component of IPA in 2007 and will be started at the last quarter of 2008.

Human Smuggling

Within the framework of activities related to crime of human smuggling accelerated particularly in the recent years, planned operations and projects aimed at disclosing criminal organizations active both at national and international level were focused. Moreover, coordinated cooperation with national and international agencies, institutions and nongovernmental organizations has contributed to these operational activities.

As a result of our planned activities and projects targeting the criminal organizations of human smuggling detected to be active in our country, coordinated by the Department of Anti-Smuggling and Organized Crime and carried out by all the provincial units, 21 criminal organizations of human smuggling were disclosed.

Trafficking in Human Beings

Within the framework of the positive developments enabled by the activities undertaken in our country in the field of trafficking in human beings, planned activities and projects for disclosing criminal organizations of trafficking in human beings were intensified and the dignity of Turkey in her fight against this crime was strengthened by benefiting from the national and international chances and opportunities.

As a result of our planned activities and projects targeting the criminal organizations of trafficking in human beings detected to be active in our country coordinated by the Department of Anti-Smuggling and Organized Crime and undertaken by all the provincial units, 12 criminal organizations of trafficking in human beings were dismantled

- c) Implementing institutions

Ministry of Interior Project Implementation Directorate on Integrated Border Management through cooperation with the General Staff, Turkish National Police, Gendarmerie General Command, Coast Guard Command and the Ministry of Health.

- d) Final objective

The purpose of this project fiche is aimed at further improving the necessary structures, the integration of different systems, and enhancing the technical capacity in the enlarged selected prototyping areas for the interoperability of the standards and equipment used in order to optimize efficiency and effectiveness of the resources to combat illegal border crossing, smuggling, trafficking and terrorism that create serious issues not only for Turkey but also for the wider EU to provide the implementation of a high level integrated border management system in Turkey.

This project will tackle the problems identified above via;

- Continuation of the implementation process of EU best practices within Turkey as they apply to the field of Border Management;

- Basing on the technical needs assessment and related reports, procurement of necessary equipment and definition of future investment requirements in enlarged prototyping or pilot areas to ensure harmonization with the EU  requirements as it relates to Border Management;

- Implementation of high level Border Management system architecture in enlarged prototype or pilot locations;

- Spreading the access to the latest technologies in border control and surveillance in selected pilot locations for those involved in border duties.

- e) The corresponding Turkish legislation

Law No: 3497 on Protection and Security of Green Borders

Law No: 2692 Turkish Coast Guard Command

According to the aforementioned laws;

- Land Forces Command is tasked to protect and secure the green borders and this task shall be fulfilled by border units

- The responsibility of protecting and securing all coasts, territorial waters and internal waters is assigned to the Coast Guard Command under the Ministry of Interior

Passport Law No: 5682 The General Directorate of Security is in charge of the controls and checks at passenger entry and exit gates at the borders pursuant to the provision “Entry or exit gates procedures must be fulfilled by the police before customs and other procedures”.

General Directorate of Customs Protection performs the duties assigned by the following laws:

    - The Law on the Staff and Organization of Customs Protection,

    - The Law on Combating Smuggling,

    - The Statutory Decree on the Organization and Duties of the Undersecretariat of Customs,

    - The Law dated 12/6/1933 and no.2313 on the Control of Narcotic Substances,

    - The Law dated 19/4/1926 and no.815 on the Performance of Business and Commerce Activities in Turkish Coasts, Ports and in Turkish Territorial Waters,

    - The Law dated 22/3/1971 and no.1380 on Water Products,

    - The Law dated 8/6/1936 and no 3005 on the Trial Procedure for Flagrento Delicto,

    - The Law dated 10/7/1953 and no.6136 on Firearms, Knives and Other Tools,

    - The Law dated 13/11/1996 and no.4208 on the Prevention of Money Laundering,

    - The Law dated 21/7/1983 and no.2863 on the Protection of Cultural and Natural Entities.

The Land Forces Command is the authorized body for the security of the land borders of Turkey under the provisions of Act No. 3497 on the Protection and Security of Land Borders. However, pending the transfer of responsibility for border control to the Land Forces Command, 390 km. of the Turkish-Iranian border, the border between Turkey and Iraq (387 km.), and 83 km. of the Turkish- Syrian border, a total of 851 km. altogether, are currently under the control of the Gendarmerie General Command. The efforts for the transfer of the duties related to the borders in the mentioned regions to the Land Forces General Command in parallel with the harmonization studies to EU were stopped in 2004. As mentioned in the National Action Plan Towards the Implementation of Turkey’s Integrated Border Management Strategy; until the completion of the transfer of the duties the Land Forces General Command and the Gendarmerie General Command will continue to perform their duties under the Law no.3497 with the current deployment.

The Coast Guard Command is the authorized body for the security of the maritime borders. At land borders, seaports and airports, checks on the entry and exit of persons are carried out by the Directorate General for Public Security (The Turkish National Police-Ministry of the Interior); the Under-Secretariat of Customs carries out checks on the entry and exit of vehicles, passenger goods and commercial goods.

- Act No. 1593 on Public Health

- The International Health Regulation adopted in accordance with Act No. 6368, published in the Official Gazette No. 14517, dated 25 April 1973

- Regulation on the Health Safety of Passengers on Board Ships, published in the Official Gazette No. 5316, dated 28 January 1943

- Directive No. 12586 of 29 April 1967 on the Health Board and Temporary Lodgings for Seamen

f) Current institutional changes

In compliance with the provisions of Act No. 3497 on the Protection and Security of Land Borders, work is underway to transfer border controls currently under the responsibility of the Gendarmerie General Command to the Land Forces Command.

- As foreseen in the Action Plan, the new border management detachment will be a well trained, professional, centrally organized, civilian unit under the Ministry of Interior.

3.2. Assessment of project impact, catalytic effect, sustainability and cross border impact

Good functioning border management has two significant functions: one is smooth and efficient flow of goods and passengers and second is maintaining border security. Therefore, the project has significant impact and implications for a variety of sectors varying from commerce to public order and to national security.

National border management system needs to be reconsidered and redeveloped in line with the needs of the national context and taking into account best comparative models. The challenge is obviously to combine varying cross-sector needs and conflicting priorities, which should be addressed to by not ignoring one function for the other but by maximizing both functions of the border management system.

3.3. Results and measurable indicators:

Results expected from this project are the following:

R.1 Strengthened risk management capacity of the border agencies to achieve an integrated border management system in compliance with EU best practices. (Twinning)

Measurable indicators of R.1;

- A risk management model developed for the Turkish National Police (TNP) by project end

- A risk management model developed for the Ministry of Health (MoH ) by project end

- Recommendations for a tailor-made risk management model for Turkey’s integrated border management (IBM) delivered by project end

- At least 150 staff of the TNP -including the ones working at border crossing points, as well as personnel at headquarters- received trainings by project end

- At least 84 staff of the Border Agencies (BA) of MoH -including the ones working at border crossing points, as well as personnel at headquarters- and at least 20 staff of other border agencies (such as TNP, Undersecretariat of Customs, General Directorate of State Airport Authority, Port Authority) received trainings by project end

- Improved collaboration among border institutions by the project end

- Model training programs for TNP and MoH (for borders) on risk management developed by project end

- Revised National and Local Contingency Action Plans for borders published by project end

- Protocols on how to manage samples with accredited diagnostic laboratories of Refik Saydam National Hygiene Centre (RSNHC) developed by project end

R.2 Strengthened technical and institutional capacity of the pilot or prototype locations for border check practices in compliance with EU best practices

Measurable indicators of R.2;

- Increased level of technical capacity in prototype or pilot locations in compliance with the Schengen standards and best practices by the project end

- Increased capacity in controlling the flow of travelers in prototype and pilot locations by project end.

R.3 Strengthened technical and institutional capacity of the pilot or prototype locations for blue and green border surveillance and control in compliance with EU best practices.

Measurable indicators of R.3;

- Increased level of technical capacity in prototype or pilot locations in compliance with the Schengen standards and best practices by project end

- The illegal crossings decreased by at least 10% in the prototype and pilot border regions by project end

  - Activities (including inputs = precise list of contracts)

The contracts will be 1 x Twinning Contract for Result 1, 1 x Supply Contract for Result 2 and 1 x Supply Contract for Result 3. The national public contribution will be shared among Turkish National Police and all the other relevant institutions.

The activities planned here initially aims to strengthen the capacity of border security units and of pilot or prototype locations for border checks and surveillance. Twinning and supply components are planned in order to achieve the results mentioned above.

The general framework for these activities had been drawn up in National Action Plan and by building up on that framework and by taking into account the requirements of the institutions as of today, the listed activities are developed. In Phase I of this IBM project, a Roadmap is expected to come into being as defined in Action Plan and that Roadmap will draw up the whole picture of the high level Border Management system in Turkey and these activities will constitute some parts of that whole picture but would not solely depend on the results of Phase I and Roadmap because of the similar nature of the works that will be carried out to shape that Roadmap and the works carried out while developing these activities. The Roadmap drawn up would not be different in terms of the necessary requirements of training, technical equipment and systems presented in this project but would be complementary to this project in order to strengthen the capacity and contribute to the implementation of high level Border Management System in Turkey and would identify the further requirements in the coming projects.

According to the National Action Plan the activities related to the border management between the proposed years of 2007-2014 are as following:

The security systems and the infrastructure components deemed to be necessary for an efficient border management and control should be provided with the financial support of the EU, the necessary organization should be designed and the personnel should be hired and trained.

Necessary measures should be taken to create a common decision-making mechanism and to conduct operations. A common database involving everyone should be created with an integrated approach and a risk analysis should be conducted.

R.1- Strengthened institutional capacity of the border agencies to achieve an integrated border management system in compliance with EU best practices. (Twinning-15 months)

Component 1: Enhanced risk management capacity of the border agencies in compliance with the EU best practices

Sub-component 1: Enhancing the Risk Management Capacity of the TNP in terms of Integrated Border Management

The first component is designed to enhance the institutional capacity of TNP in order to provide a more efficient risk management related to border management in compliance with EU best practices.

1.1. Evaluation of the current situation by conducting a gap analysis to identify the needs

1.2. Defining the tools and techniques of a risk management model in compliance with the EU best practices

1.3. Delivery of know-how on risk management at strategic, operational and tactical level via seminars, conferences, workshops, study visits. These will comprise also training(s) for at least 150 TNP staff -including the ones working at border crossing points, as well as personnel at headquarters.

1.4. Drafting of a risk management model for the TNP’s border related tasks which would comprise the below topics indicatively:

- general strategy

- administrative and operational tasks

- basic and common risk analysis

- profiling and selectivity principles

- identifying key duties and responsibilities of TNP personnel involved

- contingency plans

This policy will take full account of EU and international best practice and will incorporate their key elements. It will also consider existing TNP strategic plans, mission and vision. Where there is any conflict, recommendations will be made to remove any discrepancies.

1.6. A model training program for TNP developed including but not limited to:

- training skills for training of trainers

- intelligence

- risk analysis

- profiling

- selectivity

- analytical methods/computerized data analysis

Sub-Component 2: Enhancing the Risk Management Capacity of the Ministry of Health (MoH) in terms of Integrated Border Management

This component aims to strengthen the capacity within the MoH to prevent infectious diseases and policies related to early warning and response at border crossing points (BCPs).

1.1. Needs assessment studies of the existing capacity within the MoH in terms of surveillance and response system at borders.

1.2. Recommendations on the legislative harmonisation for bringing in a public health risk management approach to the national legislation related to borders in compliance with the EU best practices and international requirements (International Health Regulations-IHRs2005)

1.3. Defining the tools and techniques of a risk management model for the MoH in compliance with the EU best practices. This model will take full account of EU and international best practice and will incorporate their key elements. It will also consider existing MoH strategic plans, mission and vision. Where there is any conflict, recommendations will be made to remove any discrepancies.

1.4. Revising the National and Local Contingency Action Plans on Communicable Diseases for borders integrated and coordinated with BCPs.

1.5. Delivery of know-how on risk management via seminars, conferences, workshops, study visits. These will comprise also training(s) for at least 73 staff of the Directorate General for Health for Border and Coastal Areas of MoH (HBCA of MoH) -including the ones working at border crossing points, as well as personnel at headquarters- and at least 11 staff of the Directorate General of Primary Health Care of MoH working for Provincial Health Directorates located in the provinces where land BCPs exist and at least 20 staff of other border agencies (such as TNP, Undersecretariat of Customs, General Directorate of State Airport Authority, Port Authority)

1.6. A model training program for the core activities (such as case detection, management of suspicious cases) and support functions (such as individual security and hygiene, epidemiology training, communication training on W5H) of the MoH developed including also training skills for training of trainers.

1.7. Awareness raising seminars for border staff on rapid response

Sub-Component 3: Recommendations for a tailor-made risk management model for Turkey’s integrated border management (IBM)

Risk management is a cornerstone for effective border management and represents an important part of the work of the related institutions. Taking into account the challenge to achieve this, cooperation and coordination should not only be limited to the units within border agency but should also occur both between all actors involved in border management within the country as well at international level.

3.1. Assessment and analysis of the risk management policies of all relevant border agencies and comparison with EU standards and procedures

3.2. Analysis of pros and cons of all proposed models via trainings, workshops, study visits for key staff and decision makers from the relevant border agencies.

3.3. Gathering, analysing and disseminating on current major risks and threats concerning  illegal immigration, and border security to relevant units at strategic, operational and tactical level

3.4. Drafting of recommendations for a tailor-made risk mangement model for IBM.

R.2- Strengthened technical and institutional capacity of the pilot or prototype locations for border check practices in compliance with EU best practices

Component 2:  Establishment of Systems and Modernization of border-crossing points in pilot or prototype locations (Supply)

This component aims to strengthen the technical capacity of the pilot or prototype locations for border check practices in compliance with EU best practices as it relates with Result 2. Strengthening the capacity for border check practices naturally requires the establishment of systems and the supply of equipment in pilot or prototype locations. Studies have already been made regarding the necessary technical infrastructure for border checks and surveillance during the formation of National Action Plan towards the Implementation of Turkey’s Integrated Border Management Strategy. According to that plan, the establishment of systems and supply of equipment for border checks and surveillance have been foreseen in different projects. The systems and related equipment required for the modernization of border checks and surveillance in this project has already been included in that National Action Plan and they are combined together in this project.

“Procurement of necessary equipment for the modernization of pilot or prototype border-crossing points”

The use of modern technologies at border-crossing points is an essential element in providing an efficient border management system. The increase in international terrorism, organized crime, drug trafficking and illegal migration is leading to new threats. In order to tackle with these new threats and to provide a secure flow of travellers as well, the technical capacity of selected border crossing points should be enhanced in compliance with EU standards and procedures.

For the selection of the border crossing points, the required needs analysis have already been carried out by the relevant institutions and some of the border crossing points had also been mentioned in National Action Plan.  If necessary some little changes in the selected border crossing points can be made according to the results of Phase I.

Detailed information about the necessary equipment is presented in Annex 5.

R.3- Strengthened technical and institutional capacity of the pilot or prototype locations for blue and green border surveillance and control in compliance with EU best practices.

The purchase and installation of equipment to strengthen the Turkish border management system and to harmonize it with EU best practices including controlling, screening and infrastructure equipment and technical devices.

The equipment to be procured as part of this component would assist in securing prototype or pilot locations and transit routes at predetermined checkpoints, yet at the same time provide a comprehensive feedback for the development of the overall architecture.

Component 3: Modernization of Border Surveillance and Control Systems in pilot or prototype locations (Supply)

The Integrated Border Management System should include CHECKS at the ports and gates and SURVEILLANCE between the gates. As it cannot be protected only with the physical barrier system because of the natural structure, the eastern borders of Turkey must be supported with technological systems. The need to start the assessment, surveillance, target acquisition, identification activities from long distance and if needed transfer them to the computer makes the physical barriers system has to be supported with surveillance and control systems in this region.

In the light of this information, it has been assessed that the precautions of surveillance and control systems concerning the security of borders in the said region between the determined border gates especially in Iraq and Iran would lessen the illegal crossings and related smugglings of immigrants, drugs and equipment and by this way it would be in conformity with EU acquis and foreseen technical of FRONTEX in the protection of borders.

The aim of this component is to enhance the border security measures via the utilization of additional technology and to prevent illegal border crossings. By the utilization of additional technology, the project will provide a more tight monitoring capability over illegal border crossing areas which could not be controlled by currently available technologies.

The main subject in this modernization work is to re-equip the border units who are responsible for blue and green border control and surveillance and also for certain crime detection and investigation tasks as part of the fight against organized crime. For their tasks operational mobility and state-of-the-art detection methods are of particular importance.

More details are presented in Annex 5.

3.5 Conditionality and sequencing

Prior to launching the supply tenders, the Senior Programme Officer (SPO) will provide further information on the destination and quantities of the equipment on the indicative list, as well as possible positive and negative variations to these, based on the operational situation at that time. To this effect, the SPO will submit with the tender documents information concerning the specific situation in the concerned areas and clarification on the end users for each type of equipment including locations.

In terms of basic sequencing, the activities shall proceed in the below order while the study visits and training seminars will be implemented in parallel:

- Assessment of current institutional capacity

- Needs assessment in terms of manpower and equipment for implementation

- Development of a structured implementation methodology and plan, based on common architecture and standards

- Organizational plan where relevant.

- Future institutions/structures

- Identification of detailed institutional and investment requirements

- Prototyping at selected border gates and blue and green border areas.

3.6 Linked activities

Twinning Project: “Development of a Training System for Border Police” which is carried out by the consortium of Spain-Hungary started in September 2006 and finished at the end of 2007. A training strategy, programme and curriculum in EU standards for the new border police to be established and a practical “Common Manual of Checks at the External Borders” was developed for personnel currently working at borders as a result of this project.

“Action Plan on Integrated Border Management-Phase 1” is newly accepted project at the last quarter of 2007. The purpose of this project is to support the Turkish Government in transforming the current border management to an integrated one by detailing the Action Plan in the form of a Roadmap defined in the Action Plan and ensure further development of high level border management and border surveillance architecture and standards in line with EU’s IBM policies and strategies.

3.7 Lessons learned

Unified and harmonized approach based on best practices should address the entire trafficking chain, comprising countries of origin, transit and destination alike, targeting recruiters, people who transport the victims, exploiters, other intermediaries, clients and beneficiaries. Also the development of a broader policy on border and migration management can offer a substantial contribution in reducing and preventing trafficking in human beings. It is important that this project is coordinated well with any EU assistance related to border management and migration that will result in overall architecture to further enable cross-agency cooperation.

As the Action Plan is setting out priorities for the most immediate investments required, determination of these priorities for the most immediate investments in pilot border, surveillance and control areas should be carried out in parallel with technical assistance in this project.

According to the EU standards expressed in the Schengen Catalogue, and given the nature of this area as a future external border, the border police must have a sufficient real time awareness of situation, and it must possess a sufficient reaction capacity.

It has been understood from the twinning projects carried out so far that the experts coming from a single member state would not be sufficient in reflecting the overall approach of the border management strategy implemented in EU Member States. Hence, the RTAs should be supported by medium term experts from different member states enabling transfer of know-how on different implementation schemes in line with EU.

In context of the results from the previous projects, training and professionalism of border staff, risk analysis capacity and modernization of equipment are important issues that have high priority for the future border management system.

In order to disseminate the information of the importance of the high level border management system more stakeholders and staff should take part in workshops, study visits, seminars, etc.

4. Indicative Budget

Current institutional framework is described briefly in Annex III. Below table is only for the institutional framework within this project.

Approximately estimated budget:

Unused funds are subject to transfer among different components.

|  |  |  |  |  | SOURCES OF FUNDING |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | TOTAL EXP.RE | TOTAL PUBLIC EXP.RE | IPA COMMUNITY CONTRIBUTION |  | NATIONAL PUBLIC CONTRIBUTION |  |  |  |  | PRIVATE CONTRIBUTION |  |
| ACTIVITIES | IB (1) | INV (1) | EUR (a)=(b)+(e) | EUR (b)=(c)+(d) | EUR (c) | % (2) | Total EUR (d)=(x)+(y)+(z) | % (2) | Central EUR (x) | Regional/ Local EUR(y) | IFIs EUR (z) | EUR (e) | % (3) |
| Component1 (Twinning) | x | _ | 1,400,000 | 1,400,000 | 1,330,000 | 95 | 70,000 | 5 | 70,000 |  |  |  |  |
| contract 1.1 (Twinning contract) |  |  | 1,400,000 | 1,400,000 | 1,330,000 | 95 | 70,000 | 5 | 70,000 |  |  |  | – |
| Component2 (Supply) | _ | x | 5,500,000 | 5,500,000 | 4,125,000 | 75 | 1,375,000 | 25 | 1,375,000 |  |  |  |  |
| contract 2.1 (Supply contract) |  |  | 5,500,000 | 5,500,000 | 4,125,000 | 75 | 1,375,000 | 25 | 1,375,000 |  |  |  | – |
| Component3 (Supply) | – | x | 21,900,000 | 21,900,000 | 16,425,000 | 75 | 5,475,000 | 25 | 5,475,000 |  |  |  |  |
| contract 3.1 (Supply contract) |  |  | 21,900,000 | 21,900,000 | 16,425,000 | 75 | 5,475,000 | 25 | 5,475,000 |  |  |  |  |
| TOTAL IB |  |  | 1,400,000 | 1,400,000 | 1,330,000 | 95 | 70,000 | 5 | 70,000 |  |  |  |  |
| TOTAL INV |  |  | 27,400,000 | 27,400,000 | 20,550,000 | 75 | 6,850,000 | 25 | 6,850,000 |  |  |  |  |
| TOTAL PROJECT |  |  | 28,800,000 | 28,800,000 | 21,880,000 | 75 | 6,920,000 | 25 | 6,920,000 |  |  |  |  |

- Indicative Implementation Schedule (periods broken down per quarter)

Duration of the contracts

| Component 1: Enhanced risk management capacity of the border agencies in compliance with the EU best practices (Twinning) | 15 months |
| --- | --- |
| Component 2: Establishment of Systems and Modernization of border-crossing points in pilot or prototype locations / (Supply 1) | 9 months |
| Component 3: Modernization of Border Surveillance and Control Systems in pilot or prototype locations (Supply 2) | 6 months |

| Component | Start of Tendering | Signature of Contract | Contract Completion |
| --- | --- | --- | --- |
| Component 1: Enhanced risk management capacity of the border agencies in compliance with the EU best practices (Twinning) | 1Q/09 | 3Q/09 | 4Q/10 |
| Component 2: Establishment of Systems and Modernization of border-crossing points in pilot or prototype locations / (Supply 1) | 2Q/09 | 4Q/09 | 3Q/10 |
| Component 3: Modernization of Border Surveillance and Control Systems in pilot or prototype locations (Supply 2) | 3Q/09 | 1Q/10 | 3Q/10 |

Duration of the project: 15 months

"All projects should in principle be ready for tendering in the first quarter following the signature of FA."

6.      Cross cutting issues

6.1 Equal Opportunity

PIDIBM is an equal opportunity employer. Selection of staff and other personnel to work on the projects will be based on objective assessments of qualification and experience, without regard to gender.

6.2 Environment

The equipment will not have any negative influence on the environment.

6.3 Minority and vulnerable groups

According to the Turkish Constitutional System, the word minority encompasses only groups of persons defined and recognized as such on the basis of multilateral or bilateral instruments to which Turkey is a party. This project has no negative impact on minority and vulnerable groups.

- ANNEXES TO PROJECT FICHE

- Logical framework matrix in standard format

- Contracting and disbursement schedule by quarter for full duration of program

- Institutional Framework

- Reference to laws, regulations and strategic documents

- Indicative breakdown of the budget for Technical Assistance contracts envisaged under the Project, Expert Qualifications and tasks

- Feasibility Study and Needs Analysis

- Market Research Table

| # ANNEX 1 – LOGICAL FRAMEWORK |  |  |  |
| --- | --- | --- | --- |
| LOGFRAME PLANNING MATRIX FOR Action Plan on Integrated Border Management-Phase 2 |  | Programme name and number |  |
|  |  | Contracting period expires 2 years after the FA | Disbursement period expires 3 years after the end date of contracting |
|  |  | Total budget : € 28,800,000 | IPA budget : € 21,880,000 |
| Overall objective | Objectively verifiable indicators | Sources of Verification |  |
| Developing and strengthening Turkey’s institutional and technical capacity for alignment with EU’s integrated border management (IBM) policy | - Turkish institutions can carry out IBM policy consistent with EU practices and procedures by the time of accession | - Monitoring by Delegation - Progress Reports in 2010 and onwards - Reports on expenditures of the Government |  |

| - Project purpose | - Objectively verifiable indicators | - Sources of Verification | - Assumptions |
| --- | --- | --- | --- |
| To support the Turkish Government in transforming the current border management to an integrated one by taking into consideration the Roadmap drawn up during the first phase of this project and supporting the institutional capacity by technical infrastructure and ensure further development of high level border management and border surveillance architecture and standards in line with EU’s IBM policies and strategies. | - Established border management systems in prototype border surveillance and control points and strengthened institutional capacity similar to EU Member States by project end - Prototype border, surveillance and control points modernized with latest equipment to the highest standards by 2010 | - New Border Security Detachment management and support structures - Monitoring by Delegation - Progress Reports in 2010 and onwards - Annual reports of PIDIBM - Reports on expenditures of the Government - Evaluation against the Roadmap and EU requirements - Project implementation reports - Prototype gates and areas with supplied equipment - Press coverage | - EU agrees to provide financial assistance towards the implementation of IBM - Prototyping projects for strengthening the border gates and surveillance areas implemented and necessary documentation produced for extension services - Government agrees on implementation of some support measures in line with EU practices through IBM. |

| - Results | - Objectively verifiable indicators | - Sources of Verification | Assumptions |
| --- | --- | --- | --- |
| Strengthened risk management capacity of the border agencies to achieve an integrated border management system in compliance with EU best practices. | - A risk management model developed for the TNP by project end - A risk management model developed for the MoH - Recommendations for a tailor-made risk management model for Turkey’s IBM delivered by project end - At least 150 staff of the TNP-including the ones working at BCPs, as well as personnel at headquarters-received trainings by project end - At least 84 staff of MoH-including the ones working at BCPs, as well as personnel at headquarters-received trainings by project end - Improved collaboration among border institutions by the project end - Model training programs for TNP and MoH on risk management developed by project end - Revised National and Local Contingency Action Plans for borders published by project end - Protocols on how to manage samples with accredited diagnostic laboratories of Refik Saydam National Hygiene Centre (RSNHC) developed by project end | - Assessment and analysis report on EU acquis and standards on risk analysis related issues - Comparative analysis report of the best practices of the EU Member State risk analysis models - Proposed institutional and organizational models - Cost benefit analysis of all proposed models - Training materials on risk analysis - Dissemination activities - Study visits, conferences & seminars, and participation of stakeholders - Training, conference and seminar participation records | - Continued Government and EU commitment towards Turkey’s accession - EU agrees to provide financial assistance - Project fiches submitted for EC funding on establishment and/or strengthening of institutional capacity implemented - Government agrees on implementation of some support measures in line with EU practices - Availability of experienced advisors and consultants |

| - Results | - Objectively verifiable indicators | - Sources of verification |  |  | - Assumptions |
| --- | --- | --- | --- | --- | --- |
| Strengthened technical and institutional capacity of the pilot or prototype locations for border check practices in compliance with EU best practices. | - Increased level of technical capacity in prototype or pilot locations by project end - Increased level of compliance with the Schengen standards and best practices by project end - Illegal crossings to EU countries decreased 10% in prototype and pilot border regions. - Increased capacity in controlling the flow of travelers in prototype and pilot border crossing points by project end. | - Proposed institutional and organizational models - Cost benefit analysis of all proposed models - Training materials on legislation, procedures, implementations, standards for staff and management - Training, conference and seminar participation records - Detailed Roadmap Document - IBM Procedures and Guidelines - Border gate operating, management and control standards - Internal web sites of agencies - Dissemination reports - High Level Risk Analysis Report - Project implementation reports - Technical Gap analysis and needs assessment reports - IBM Technical Framework Document |  |  | - Continued Government and EU commitment towards Turkey’s accession - EU agrees to provide financial assistance - Project fiches submitted for EC funding on establishment and/or strengthening of institutional capacity implemented - Government agrees on implementation of some support measures in line with EU practices - Availability of experienced advisors and consultants - Decision of GoT final decision on the IBM implementation roadmap - Decisions on the further PIDIBM responsibilities, staff numbers, agency cooperation roadmap - Agreement between all institutions involved |
| - Results | Objectively verifiable indicators | Sources of verification |  |  | Assumptions |
| Strengthened technical and institutional capacity of the pilot or prototype locations for blue and green border surveillance and control in compliance with EU best practices. |  | - Proposed institutional and organizational models - Cost benefit analysis of all proposed models - Surveillance and control equipment delivered and in regular use at prototype locations |  |  | Availability of experienced advisors and consultants |
| Activities | Means |  | Costs | Assumptions |  |
| Component 1: Enhanced risk management capacity of the border agencies in compliance with the EU best practices Sub-component 1: Enhancing the Risk Management Capacity of the TNP in terms of Integrated Border Management 1. Evaluation of the current situation by conducting a gap analysis to identify the needs 2.Defining the tools and techniques of a risk management model in compliance with the EU best practices 3.Delivery of know-how on risk management at strategic, operational and tactical level via seminars, conferences, workshops, study visits. These will comprise also training(s) for at least 150 TNP staff-including the ones working at BCPs, as well as personnel at headquarters. 4.Drafting of a risk management model for the TNP’s border related tasks which would comprise the below topics indicatively: general strategy, administrative and operational tasks, basic and common risk analysis, profiling and selectivity principles, identifying key duties an responsibilities of TNP personnel involved, contingency plans 5.A model training program for TNP developed including but not limited to: training skills for training of trainers, intelligence, risk analysis, profiling, selectivity, analytical methods/computerized data analysis | 1xTwinning Contract - RTA - STEs - Short term training - Study visits - Internship arrangements - Conferences & seminars - Workshops |  | 1,400,000 Euro | -Availability of suitable, appropriately qualified RTA and STEs -Know how on existing Turkish environment and legislation and organizational arrangements -Development of suitable workshops and seminars -Co-operation of all government agencies involved in border, surveillance and control activity |  |
| Activities | Means |  | Costs | Assumptions |  |
| Sub-component 2: Enhancing the risk Management Capacity of the MoH in terms of IBM 1.Needs assessment studies of the existing capacity within MoH - Recommendations on the legislative harmonisation for the establishment of the public health risk management at borders in compliance with the EU best practices - Defining the tools and techniques of a risk management model for the MoH in compliance with the EU best practices. - Developing a National Contingency Action Plan for borders integrated and coordinated with BCPs. - Delivery of know-how on risk management via seminars, conferences, workshops, study visits. These will comprise also training(s) for at least 50 staff of the DGH of MoH-including the ones working at BCPs, as well as personnel at headquarters - A model training program for the core activities (such as case detection) and support functions (such as epidemiology training) of the DGH of MoH developed including also training skills for training of trainers. 7.Awareness raising seminars for the staff on rapid response |  |  |  |  |  |
| Activities | Means |  | Costs | Assumptions |  |
| Sub-Component 3: Recommendations for a tailor-made risk management model for Turkey’s IBM - Assessment and analysis of the risk management policies of all relevant border agencies and comparison with EU standards and procedures - Analysis of pros and cons of all proposed models via trainings, workshops, study visits for key staff and decision makers from the relevant border agencies 3. Gathering, analyzing and disseminating on current major risks and threats concerning illegal immigration and border security to relevant units at strategic, operational and tactical level. 4. Drafting of recommendations for a tailor-made risk management model for IBM |  |  |  |  |  |
| Component 2: Establishment of Systems and Modernization of border-crossing points in pilot or prototype locations. Procurement of necessary equipment for the modernization of pilot or prototype border-crossing points | 1x Supply Contract |  | 5,500,000 | Budgetary adjustments of the institutions involved |  |
| Component 3: Modernization of Border Surveillance and Control Systems in pilot or prototype locations - Purchase and installation of equipments and the systems | 1x Supply Contract |  | 21,900,000 | Budgetary adjustments of the institutions involved |  |

ANNEX 2

DETAILED PROJECT IMPLEMENTATION CHART

| Component | 2009 |  |  |  |  |  |  |  |  |  |  |  | 2010 |  |  |  |  |  |  |  |  |  |  |  | 2011 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | O | N | D | J | F | M | A | M | J | J | A |  |
| C1- Twinning 1 | P | P | P | T | T | T | T | T | C | I | I | I | I | I | I | I | I | I | I | I | I | I | I | I |  |  |  |  |  |  |  |  |  |  |  |  |
| C2- Supply 1 | P | P | P | P | T | T | T | T | T | T | T | C | I | I | I | I | I | I | I | I | I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| C3 – Supply 2 | P | P | P | P | P | P | T | T | T | T | T | T | T | C | I | I | I | I | I | I |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| P | Preparation |
| --- | --- |
| T | Tendering |
| C | Contracting |
| I | Implementation and Payments |

CONTRACTING AND DISBURSEMENT SCHEDULE (Quarterly-Euro)

| Contracted | II/2009 | III/2009 | IV/2009 | I/2010 | II/2010 | III/2010 | IV/2010 | I/2011 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| C1:Twinning |  | 1,400,000 |  |  |  |  |  |  |
| C2. Supply1 |  |  | 5,500,000 |  |  |  |  |  |
| C3. Supply2 |  |  |  | 21,900,000 |  |  |  |  |
| Cumulated |  | 1,400,000 | 5,500,000 | 21,900,000 |  |  |  |  |
| Disbursed |  |  |  |  |  |  |  |  |
| C1. Twinning |  | 630,000 |  |  | 630,000 |  | 140,000 |  |
| C2. Supply1 |  |  | 3,300,000 |  |  | 2,200,000 |  |  |
| C3: Supply2 |  |  |  | 13,140,000 |  |  | 8,760,000 |  |
| Cumulated |  | 630,000 | 3,300,000 | 13,140,000 | 630,000 | 2,200,000 | 8,900,000 |  |

ANNEX 3

INSTITUTIONAL FRAMEWORK

Beneficiary

The main beneficiary and implementing institution PIDIBM set up within the Ministry of the Interior which is provided by the TNP in budgetary, personnel and venues issues is organized for the execution of the projects within the scope of Integrated Border Management. If there is more than one institution involved, the project is to be coordinated by the “Project Implementation Directorate for Integrated Border Management”. In this project, the Co-Beneficiaries are the Gendarmerie General Command / Land Forces, Coast Guard Command and the Ministry of Health. General Staff will be acting as the coordinating body for Land Forces as well as Gendarmerie General Command and the Coast Guard Command.

PIDIBM is organizing the Task Force meetings in the field and also trying to coordinate the efforts in establishing an integrated border management structure as defined in the Action Plan.

MoI-Project Implementation Directorate on Integrated Border Management (PIDIBM) is committed and for the time being resourced for the contracting and implementation of this project.

The Director of the PIDIBM (Şenol Arslan) will act as SPO of the project. The SPO and the Project Leader of the Twinning Partner will manage the project. The RTA and the RTA counterpart will be responsible for implementing the decisions of the Managers with the assistance of the PMU. Implementation includes but not limited to drawing up working plans, practical arrangements for seminars, workshops and study visits, coordinating co-beneficiary and stakeholders.

The Sub-component 2 of the Twinning project will be carried out by the Directorate General for Health for Border and Coastal Areas and Directorate General of Primary Health Care of MoH. This sub-component will be complementary to the third phase of the project “Surveillance and Control of Communicable Diseases” which is submitted by the Ministry of Health and accepted by the European Commission.

Project Steering Committee

A Project Steering Committee will be set up during the project’s inception period to ensure coordination between the different stakeholders. Membership of the Committee will consist of one representative from all the beneficiaries, from the Contracting Authority, European Commission Delegation and the General Secretariat for EU Affairs.

The Project Steering Committee will meet every three months and other occasions if necessary. If and where necessary, participants from other agencies involved in border management shall be invited to the Steering Committee meetings.

In particular, the Project Steering Committee will be responsible for the following activities:

◦ Monitoring project implementation

◦ Providing guidance on project management

For monitoring of project management and activities, the Beneficiary will prepare the monitoring reports to be submitted to National Aid Coordinator (NAC). Besides an Independent Interim Evaluation Team contracted by EC will also prepare Interim Evaluation Report for the evaluation of the project management and implementation.

PMU

PMU will be responsible for:

- Project management (coordination of the activities such as inviting beneficiary institutions, determining the personnel that will be participate in the activities both in MS study visits and in Turkey),

- Technical management (providing the teaching materials in Turkey including seminar places and accommodates, office for RTA and STEs),

- Financial management,

- Monitoring,

- Secretariat.

Contracting Authority

The Central Financing Contracting Unit (CFCU) will be the Implementing Agency and will be responsible for all procedural aspects of the contracting matters and financial management (including payments) of the project activities, in accordance with the Decentralized Implementation System (DIS) Manual. CFCU will involve in the Steering Committee meeting as an observer.

European Commission

The European Commission Delegation in Turkey and the funding agency will be involved in the monitoring of the project. ECD will be observer in Steering Committee.

The Commission is the politically independent institution that represents and upholds the interests of the EU as a whole. It is the driving force within the EU’s institutional system: It proposes legislation, policies and programmes of action, and it is responsible for implementing the decisions of the Parliament and the Council. Like the Parliament and the Council, the European Commission was set up in the 1950s under the EU’s founding treaties.

Overall organigram for project implementation responsibility can be depicted as below:

Minister of Interior

Turkish

National Police

Gendarmerie

Coast Guard

Integrated Border

Management

Project

Implementation

Directorate (SPO)

Project Leader

Deputy Undersecretary

(Political

Responsible)

CFCU

Undersecretary

Minister of Interior

Turkish

National Police

Gendarmerie

Coast Guard

Integrated Border

Management

Project

Implementation

Directorate (SPO)

Project Leader

Deputy Undersecretary

(Political

Responsible)

CFCU

Undersecretary

Ministry of Health

- ANNEX 4

- REFERENCE TO LAWS AND REGULATIONS AND STRATEGIC DOCUMENTS

- Act No. 3497 on the Protection and Security of Land Borders

- Act No. 4749 of 5 June 1945, (The 1944 Convention on International Civil Aviation and its Annexes)

- Act No. 5683 on the Residence and Travel of Foreigners in Turkey

- Act No. 4360 Amending the Act No. 5683 on the Residence and Travel of Foreigners in Turkey

- Act No. 5682 on Passports

- Act No. 1593 on Public Health

- The International Health Regulation adopted in accordance with Act No. 6368, published in the Official Gazette No. 14517, dated 25 April 1973

- Regulation on the Health Safety of Passengers on Board Ships, published in the Official Gazette No. 5316, dated 28 January 1943

- Directive No. 12586 of 29 April 1967 on the Health Board and Temporary Lodgings for Seamen

- Act No. 5683 on the Residence and Travel of Foreigners in Turkey

- Act No. 5682 on Passports

- Act No. 3497 on the Protection and Security of Land Borders

- The  Act on Military Zones and respective regulations

- Act No. 4749 on the 1944 Convention on International Civil Aviation and its Annexes

- National Action Plan towards the Implementation of Turkey’s Integrated Border  Management Strategy

- TAMPERE European Council Decisions (October 15/16, 1999), articles 3,25

- LAEKEN European Council Decisions (December 14/15, 2001), article 42

- SEVILLE European Council Decisions (June 21/22, 2002), articles 31,32,33

- Schengen Catalogue (February 8, 2002), Section B1

ANNEX 5

- DETAILS PER EU FUNDED CONTRACT

- COMPONENT I. ENHANCED RISK MANAGEMENT CAPACITY OF THE BORDER AGENCIES IN COMPLIANCE WITH THE EU BEST PRACTICES (TWINNING)

- Sub-Component 1.1. Enhancing the Risk Management Capacity of the TNP in terms of Integrated Border Management

Risk analysis is an essential part of border management. Identification of the threat at borders, its dimension, size and ramifications (nationally and internationally) and legal implications is paramount to tackling criminality coming through our borders. Current threats to internal security and border security need to be continuously assessed and identified in a professional manner. The same applies also to obvious trends in cross-border crime.

In order to establish a risk assessment competence that can provide adequate information to take appropriate measures to tackle identified threats and  risks with a view to improving the integrated management of external borders,  common methods of obtaining information, inter-operable data and software, and information sharing is considered to be pre-requisite.

As part of its ongoing work within Border Management integration and institutional development, Turkey is looking to strengthen the capacity of the Border Security Units capable of carrying out risk analysis at a strategic, operational and tactical level.  Turkey would like to benefit from the experiences and the know how of Member State Countries in this area.  In particular in identifying and assessing major risks and threats concerning border activity, and in creating a tailor made risk analysis solution.

Specifically twinning assistance is sought in order that a tailor made risk analysis solution can be developed, and in developing such a solution carrying out analysis at strategic, operational  and tactical level in line with the Acquis, best practices, standards and procedures of the EU.

- Sub-Component 1.2. Enhancing the Risk Management Capacity of the MoH in terms of Integrated Border Management

An integrated approach to communicable disease surveillance envisages all surveillance activities in a country as a common public service which carries out many functions using similar structures, processes and personnel. The surveillance activities that are well developed in one area may act as driving forces for strengthening other surveillance activities, offering possible synergies and common resources.

It thus should be possible to envisage a holistic approach which takes into consideration all core activities and support functions, in order to strengthen the national surveillance system through coordination, prioritization and streamlining of all surveillance activities.

Personnel that contribute to the national surveillance and response system are the most valuable part of the system itself. In this perspective, it is essential that appropriate training, support, feedback and motivation be guaranteed within the design of the surveillance system and through its supervision and overall support mechanisms.

Participants in the surveillance system should be properly trained for their surveillance tasks, through both initial and ongoing in-service training. In an integrated multidisease approach, field or intervention epidemiology training will provide general surveillance and response skills which can be applied almost anywhere in the system and for any disease surveillance and response needs. General surveillance and response skills are crucial in the event of the emergence of diseases not anticipated by the surveillance system.

The strategic goals at the national level in relation to the management of borders have classically been to prevent cross-border criminal activities and unlawful entry or exit into the state but also to protect the border against threats to national security, the national economy and public health. Border services, including border guards as well as customs and inspection services all play an important role to play in this regard.

The main objective for the inspection services will lie in the prevention of the introduction of diseases and harmful organisms which pose a threat to the national economy and the health of people and animals.

On the one hand, the border services are tasked to ensure the security and health of people, animals, plants and cultural heritage. As the potential threats are numerous, a control system is required which is expeditious and effective at the same time.

On the other hand, increased international trade and tourism, as well as the increase in cultural and educational exchanges make the facilitation of licit movement of persons and goods also an important strategic goal of most countries. Border services are therefore forced to strike a delicate balance between strict controls and fully open borders.

In order to balance these twin goals of modern border management – that is border security and trade facilitation – in an efficient and effective manner, appropriate equipment and well-trained and motivated staff are as important as a strong legal basis, a clear division of tasks and responsibilities, streamlined processes and an efficient exchange of information. Taking into account the complexity of the task, this cooperation and coordination should not only be limited to the units within one ministry or agency but should also occur both between all actors involved in border management within the country and at an international level. Most importantly, the services need to realise that they have common objectives and tasks, and their individual objectives can only be reached by working together.

Sub-Component 3: Recommendations for a tailor-made risk management model for Turkey’s integrated border management (IBM)

Risk management is a cornerstone for effective border management and represents an important part of the work of the related institutions. Taking into account the challenge to achieve this, cooperation and coordination should not only be limited to the units within border agency but should also occur both between all actors involved in border management within the country as well at international level.

It is expected that the duration of this component will be 15 months.

| EXPERT | Quantity | Unit € | Unit/Explanation | Cost € |
| --- | --- | --- | --- | --- |
| Resident Twinning Adviser (RTA) Remuneration | 15 | 9000 | Per month / Gross salary, social costs, 6 % *(salary + social costs) | 135.000 |
| RTA Allowances | 15 | 5.700 | Per month / daily allowance, insurance, accommodation, rent, real estate agency fees, etc. | 85.500 |
| Project preparation | 3 | 11.595 | For RTA (working days-fees, flat rate compensation, per diem, return tickets) | 34.785 |
| Project Co-ordination Costs | 1 | 92.000 | Audit, visibility costs, purchase of small office equipment, working days-fees, flat rate compensation, per diem, return tickets, etc. | 92.000 |
| Assistants | 15 | 4.000 | Per month / 2 assistants | 60.000 |
| Domestic activities (STE) | 30 | 18.000 | Per activity / working days, project management cost, per diem, return plane ticket, etc. | 540.000 |
| Study visits (10 staff for each visit) | 10 | 32.000 | Per activity / per diems, airfare for assistant, internal travel, incidental costs, etc. | 320.000 |
| Training material | 32 | 1000 | For domestic activities | 32.000 |
| Interpretation | 150 | 450 | Per day | 67.500 |
|  |  |  |  | 1.366.785 |
| Contingency |  |  |  | 35.000 |
|  |  |  | Total | 1.401.785 |

PL (Project Leader):

The PL is supposed to coordinate the activities, disseminate project information among stakeholders, take part in discussions with the high level officials, present and defends project input and expected outputs, manage the project team, prepare project management reports, help overcome project related problems, and assist the SPO for continuous development of project initiatives.

- The Project Leader must have at least 2 years of specific experience in project management, preferably in EU funded projects.

- Have demonstrated skills in problem solving.

- Relevant experience in decision making process in his/her own country in border security matters

- Overall appreciation of the problems and solutions in the sector,

- Capable of unblocking any problems at highest level,

- Good leadership skills

MS PL (Member State Project Leader):

The PL should be a high ranking official with broad knowledge of all processes in the area of development and implementation of risk analysis, institutional and operational aspects that the project component is dealing with; who will continue to work at his/her Member State (MS) administration but devote, some of his/her time to conceive, supervise and co-ordinate the overall thrust of the Twinning project.

The PL will allocate a minimum of 3 days per month including one visit every 3 months to Turkey as long the project lasts.

a) Qualifications:

- Broad long-term knowledge of all processes in the area of acquis that the project is dealing with;

- High-ranking official, commensurate with an operational dialogue at vice-ministerial level;

- Overall appreciation of the problems and solutions in the sector;

- Capable of unblocking any problems at highest level;

- Good leadership skills.

- To have sufficient language skills and to spare the necessary time to the project

b) Tasks:

- Overall project co-ordination;

- Co-chairing, with the Turkish PL, the regular project implementation steering committee meetings;

- Mobilizing short- and medium term experts;

- Executing administrative issues (i.e. signing reports, administrative order etc.)

- Budget management.

c) Profile:

- Long-term civil servant from an EU Member State administration;

- Educated and experienced in the field of management and organization

- At least 3 years working experience in a leading management

- Very good command of English (oral and written)

- Excellent computer skills (Word, Excel)

- RTA:

- Qualifications:

- Broad long-term knowledge of all processes in the area of development and implementation of risk analysis institutional and operational aspects that the project component  is dealing with,

- Wide experience of working in a consultative capacity,

- Previous experience in implementing similar missions,

- Minimum 5 years of hands-on experience in border security,

- Fluency in oral and written English,

- Ability to call on short term experts in support of the efficient implementation of the project and the full support at senior levels within Turkey,

- EU Project expertise,

- Multi-agency donor expertise,

- Good leadership skills.

- Tasks:

The RTA will be in charge of the Project activities conducted by the Member State and in particular:

- Play a key role in the management of the twinning project.

- Monitor the project implementation.

- Support and consultancy on training programmes, technical infrastructure and current trends.

- To plan and coordinate outputs.

- To nominate and mobilize the short term experts.

- To supervise the short term experts.

- To coordinate and organize study visits, training activities, workshops and public awareness activities in MS.

- To ensure proper quality of outputs.

- To provide detailed reports on the impact of the project.

- Assist in the preparation of all strategic project documents [inception study, sector strategy/policy/plan, quarterly monitoring reports, final project report, training manuals etc.]

- Contacts with the Member State administration representatives, respective participating organizations

- Coordinating the work of the Member State experts involved in the Project.

- To join the activities in the different places of Turkey accompanying the STE’s where necessary.

- RTA will carry out his responsibility according to the Twinning Manual.

- Budget Management

- Management of the Project Assistant and Language Assistant(s)

- Risk analysis expert

Qualifications and skills

- University graduate

- Have good commend of written and spoken English.

- Have full computer literacy,

- Turkish knowledge will be an asset,

- Broad long-term knowledge in developing risk management plans, covering identification, prioritization, impact analysis, and mitigation.

- Tasks:

- Development of a Risk Analysis model for TNP;

- Development of a Risk Management Plan covering identification, prioritization, impact analysis and mitigation.

- Coordination of development of a computerized risk management system;

- Coordinating risk related activities of other experts.

Public Health Expert

- Qualifications:

- University graduate

- Have good commend of written and spoken English.

- Have full computer literacy,

- Turkish knowledge will be an asset,

- Minimum 5 years of experience in public health

- Broad long-term knowledge in health control at borders

- Broad long term knowledge in IHRs

Tasks:

- Development of a Risk Analysis model for MoH;

- Development of a Risk Management Plan for MoH ;

- Coordination of development of a computerized risk management system;

STE:

STE will be employed as required for each function of risk analyzing model. These experts will provide the necessary field and operational expertise.

a) Experts’ qualifications

- Minimum of 3 years professional experience in their respective field

- Advanced university degree in a relevant subject;

- They should be professionally qualified and have the appropriate experience in the area and subjects that they are selected for.

- Previous experience of working in other cultures and countries will be an advantage.

- Good written and oral command of English (or other community language);

- Proven contractual relation to public administration or mandated body;

- Capacity to integrate into a large expert team;

- Willingness to work in a different cultural environment.

b)    Experts’ tasks

  - To contribute to the project with specialist knowledge in the area of  law enforcement systems and the risk analysis;

  - To provide specialist support services [e.g. providing Turkey with access to databases];

  - To prepare training course modules;

  - Delivery of selected training modules to the officers.

  - Advice and backstopping from a national EU Ministry of Interior.

- To provide necessary documents translated into Turkish about specific issues within the concept of Acquis EU

COMPONENT 2: ESTABLISHMENT OF SYSTEMS AND MODERNISATION OF BORDER-CROSSING POINTS (SUPPLY)

“Procurement of necessary equipment for the modernization of pilot/prototype BCPs”

Modern analysis software is not available for the Passport Police in Turkish BCPs. However, modern analysis software would be necessary for analytic police work. The TNP / Passport Police are not able to perform analytic police work properly. Since it can store millions of records it can easily compare the relation between those records and shows it as a graphic. 20 pieces of analysis software is essential for such an analytic police work.

“Modernization of Border Gateways’ IT Systems”

The General Directorate for Security has also an intranet system called as POLNET, and the central and field units of the border gates are connected to that network. With this system, it is aimed to modernize the IT infrastructure especially in border gateways which will be directly effect the establishment of other systems and for this reason it constitutes a very important part of this project. Reference is also made for POLNET in National Action Plan. According to Action Plan, the system should be improved and expanded according to the requirements of the whole system.

The cost for the operation of the systems will be borne by the Turkish National Police.

This indicative list will be revised and/or updated in line with operational situation at the time of tender dossier submission and based on information provided by the SPO on statistics and specific needs of each location and beneficiary. This applies for both the checking and surveillance equipment.

| Description of the equipment | Quantity | Unit Price € | Total Price € | Beneficiary |
| --- | --- | --- | --- | --- |
| Modernization of Border Crossing Points’ IT Systems | 1 | 5,000,000 | 5,000,000 | TNP |
| Computers for Border Crossing Points | 250 | 1,000 | 250,000 | TNP |
| Analysis software | 50 | 5,000 | 250,000 | TNP |
| Total Cost |  |  | 5,500,000 |  |

COMPONENT 3: Modernisation of Border Surveillance and Control Systems in pilot OR PROTOTYPE locations (SUPPLY)

As foreseen in Chapter 24 of Progress Report 2005, it has been stipulated that ‘member countries must have the operational capabilities to implement common EU measures concerning border security’. With the procurement of highly developed technological systems, all EU member countries have acquired full operational capability for border security. Having received the perspective for EU membership, Turkey prudently desires-rightfully deserves-to reach the technological border security level of other EU countries in order to successfully maintain the border security mission of EU external bounders in the area.

Due to its geographical location, Turkey has constituted a transit route for illegal border crossings from Asia-Africa to Europe. In recent years, rising number of illegal border crossings has not only created serious ramifications for Turkey’s national security but also constituted a negative pressure for the European border management system. The number of people captured for illegal crossing across the land borders surrounding Turkey was 10 270 in 2006 and has risen to 19 724 in 2007. More than half of that illegal crossing occurred at the east and southeast (Iran, Iraq and Syria) borders of Turkey. Annual average number of illegal crossings on the Turkish-Iranian border is around 5 000. Almost half of those crossings occur in Van-Ağrı. In plain terms, around 10 percent of annual illegal border crossings have taken place in Van-Ağrı region. Thus, both Turkey and the EU should give high priority to advance technological measures on the Iranian border. In order to fight against illegal migration and organized crime (smuggling, trafficking, terrorism etc.) more efficiently, enhancement of border security measures via the utilization of additional technological systems in Van-Ağrı are given high priority.

From all of the eight countries who have borders with Turkey there happens to be illegal crossings in different amounts. At the borders of Greece, Iran and Iraq high amounts of crossing is determined than the other countries. Illegal entrance events happen mostly in Van, Ağrı, Edirne and Şırnak, and illegal exits happen mostly in Edirne, İzmir, Muğla and Çanakkale.

Despite being put through intensive measures of border security at the Iraq and Iran border of Turkey, smuggling and the illegal border crossing cannot be fully prevented because of three shortcomings in terms of infrastructure, border security systems and equipment. Hence, Turkey’s border security is not sufficient to stop illegal immigrants and the people involved in different types of smuggling activities. For this reason Turkey is given preference to be a convenient way of transition or final point of destination of EU’s external borders. Therefore, priority should be given to improving the existing system to ensure complete security of the borders which will be the outer borders of the EU.

As Turkey has long and indented coasts it is hard to control the movements on sea and requires a strong coast guard organization. The blue borders of Turkey need to be controlled more effectively in order to prevent illegal migration, human and drug trafficking via determining, identifying and investigating the suspicious ships and other sea transportation vehicles. Hence, to improve the possibility of intervening in the border incidents, to shorten the intervention time and to identify/detect the vessels around, control boats and thermal cameras to be mounted on coast guard boats are required. In 2006, 1665 illegal migrants and 45 organizers were captured by Coast Guard Command units in 163 illegal migration cases and in 2007, 4832 illegal migrants were captured. The 93% of these captures (4512 illegal migrants) occurred in Aegean Sea and the most intensive regions that these captures happen in the Aegean Sea are Kuşadası 1056, Ayvalık 944, Çeşme 478, Behramkale 431, Didim 437 and Ayvacık 258. Total amount of captures in 2007 is higher than the total amount of captures of last 3 years (4 012)

The capacity of the detection and identification of large and small fast boats for blue borders and ports, the detection and identification of personnel and vehicle movements at unregulated borders are supposed to be enhanced and also goods and container intrusion control capabilities should be developed to avoid biological/chemical attacks and to detect illicit trafficking of drugs or explosives via this component.

Determination and identification capability of Turkish Coast Guard boats, under any kind of weather and sea condition, will be improved by providing and mounting thermal camera systems for coast guard boats located in Aegean Sea operation area, so our seas will be taken under control more effectively specifically in the prevention of illegal migration. The purpose would be to provide more effective observation and determination/identification by constituting electronic remote detection systems which can be integrated with the present systems for the prevention of illegal migration, trafficking in persons, smuggling and illegal trafficking of drugs.

The equipment to be procured as part of this component would assist in securing prototype or pilot locations and transit routes at predetermined checkpoints, yet at the same time provide a comprehensive feedback for the development of the overall architecture.

As mentioned in the National Action Plan the equipment such as thermal camera, land surveillance radar, binoculars and systems such as thermal camera systems to be installed in Coast Guard Boats should be purchased in terms of infrastructural needs for Border surveillance.

| Description of the equipment | Quantity | Unit Price € | Total Price € | Beneficiary |
| --- | --- | --- | --- | --- |
| Long distance Binoculars | 26 | 1.400 | 36.400 | Gendarmerie |
| New Generation Permanent Thermal Cameras | 60 | 105.000 | 6.300.000 | Gendarmerie |
| New Generation Mobile Thermal Cameras | 24 | 58.000 | 1.392.000 | Gendarmerie |
| 3rd Generation Thermal Camera System | 90 | 110.000 | 9.900.000 | Land Forces |
| Night Vision Binocular | 40 | 10.000 | 400.000 | Land Forces |
| Multi zoom Binoculars | 20 | 5.000 | 100.000 | Land Forces |
| Thermal Cameras to be mounted on Coast Guard Boats | 10 | 170.000 | 1.700.000 | Coast Guard |
| Control Boats | 10 | 200.000 | 2.000.000 | Coast Guard |
| TOTAL |  |  | 21,828,400 |  |

ANNEX 6

FEASIBILITY STUDY AND NEEDS ANALYSIS

COMPONENT 2: ESTABLISHMENT OF SYSTEMS AND MODERNISATION OF BORDER-CROSSING POINTS (SUPPLY)

SYSTEM REQUIREMENTS ANALYSIS

FOR

MODERNISATION OF BORDER CROSSING POINTS’ IT SYSTEMS

PolNet (Police Network) was setup by IT Department and is the short name of the computer network of the police. PolNet is a good example for the efforts of reorganizing our institutions and using technology. By the side of technical aspects PolNet is a fast, reliable, secure and nation-wide corporate network (intranet) for the requirements of Turkish National Police Force. PolNet includes a network infrastructure over fast LAN and WAN technologies. Beside infrastructure all the services like database queries, web services, e-mail needs, archiving and documentation, telephony (VoiceOverIP), video communications are also provided along the country.

Figure 1. PolNet Topology

About 30.000 users at 81 provinces, 749 counties, 93 border crossing points, over 1100 police offices and about 200 mobile users are connected each other by communication links. ATM, TDM, Frame Relay, IP and IP/MPLS VPN Technologies are provided by Telecom operators and Department of IT. 51 of police province offices have back up links over VSAT services provided by IT department. A Disaster Recovery Center is also built for continuity of service. Links speed varies between 64 Kbit/s to 155 Mbit/s on the network.

Since year 2000 PolNet is a growing project, aims to help police forces to accomplish the national security objective as in the fastest, the most secure and most efficient way as well as being in contact with other domestic and foreign organizations and helping the police to reach the information nationwide. Development of PolNet has provided real operational benefits to police forces and IT Department has become a prime factor in helping to improve the efficiency of the police duties. Many sub-projects and applications are supported and carried by PolNet such as  AFIS (Automatic Fingerprint Identification System), digital archive and document management systems, city command and control systems, GIS (geographical information systems), refugee and passport systems, traffic information systems. Over 40 other projects are also supplied and work on the system. PolNet is open to technological advances in future; the design philosophy brings all the integration needs between other public, national and international networks. Future projects like Installation of Police Digital Radio Communication System (planning by Department of Communication) and surveillance systems like Automatic Plate Recognition System (planning by Department of Anti-Smuggling and Organized Crime) will also use PolNet infrastructure and sub-systems. Using central database and applications police forces are able to gather what they need as information.

PolNet also serves as an e-government infrastructure. Government to Citizen and Government to Government services are given over PolNet. Citizens may obtain information over internet and make online processes like vehicle registration, driver registration and passport application supplied by PolNet projects.  Other government agencies can obtain information from police network trough their needs and share their data with Police Forces.

Serving at national border crossing points, Police Forces needs PolNet covering passport projects, personal identification database, refugees and aliens database for the requirements of secure borders. The passport application allows the borders to do the processes safely and rapidly.

As figured out in Table-1 there are 93 official border crossing points over the country, which are organized as air border gateways, sea border gateways, land border gateways and railway border gateways.

| Type | Distribution |
| --- | --- |
| Air | 24 |
| Sea | 48 |
| Land | 17 |
| Railway | 4 |
| Total: | 93 |

Table 1. Distribution of Border Crossing Points

As pointed at the start of this document, border gateways are also a member of PolNet network. Some large scale border gateways such as Istanbul Ataturk, Antalya, Izmir Adnan Menderes, Muğla Dalaman, Ankara Esenboga, Edirne Kapıkule, Habur have been directly connected to HQ of police network. Others are connected to province central offices.

| No. Of Units | Link Speed (Kbit/s) |
| --- | --- |
| 8 | 64 |
| 57 | 128 |
| 10 | 256 |
| 10 | 512 |
| 6 | 1024 |
| 2 | 2048 |

Table 2. Distribution of Link Speeds for Border Crossing Points

As figured out in Table-2, the connection speed to the PolNet of border crossing points varies between 64 Kbit/s and 2048 Kbit/s. TDM and Frame Relay Technologies are used in data transmission. Since top speed is limited to 2048 Kbit/s, the cost of ownership is expensive and the technology itself becoming outdated, growth in transferred data and data requirements make this technology not feasible.

Due to slower link speeds, end to end security is another trouble.

The growing need for bandwidth makes some projects such as AFIS, archive and documentation systems, image processing, video surveillance and voice based projects are unusable.

By the side of reliability, there is no VSAT back-up has been maintained at border gateways.

Another important subject is network users. Numbers of passport controlling points have increased number of users in the network. The capacity of network infrastructure is not enough to improve the system.

According to problems pointed out above, at first sight, the solution can be seen by upgrading the network infrastructure and the way of border gateways are connected into PolNet.  Offered Project includes;

- Increasing number of users by structural cabling (data and ups),

- Upgrading TDM technology to advanced S.HDSL and Metro Ethernet Technologies,

- Upgrading network topology referring Figure 2,

- Upgrading network devices such as switches, routers,

- Maintaining VSAT backup system,

- Installing cryptographic features to the links.

These improvements will allow;

- More users on the network for fastest service at border crossing points,

- More bandwidth for projects like AFIS (allows to do the fingerprint verification processes), the digital archive and document management applications (used in virtual media through the network), face recognition systems and other biometric identification systems, video surveillance, IP telephony etc.

- Connecting border crossing points directly to the HQ, it will also improve service continuity and quality,

- Changing the old 10 Mbit/s Ethernet hubs and switch devices and replacing with them faster Technologies, adding advanced multicast features etc.,

- More reliability by utilizing VSAT back-up system. VSAT system will include a HUB system maintained in disaster recovery center, so that border gateways can have a direct access to the disaster recovery center via satellites technology when the links of HQ are interrupted by a natural disaster. It will also prevent Single Point of Failure.

- More secure data transfer and enhanced network security.

Figure 2. Planning Network Topology

Since upgrading network communication systems and infrastructure by implementing this Project, it will be formed along the Figure 2, as seen on topology referred; any service failure will not end the communication, which will not cause problems on the applications like passenger passport verification, tracing the criminals, completion of the other processes. It will accelerate bureaucratic processes in fast and secure manner, bringing more control and service quality at border gateways by the side of police forces, homeland security and citizens.

The computers with high technological features that are compatible with the new upgraded system at the below listed border crossing points are of crucial importance for the efficient functioning of the system.

| INDICATIVE LIST OF BORDER CROSSING POINTS for the delivery of the computers |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| NO | CİTY | LOCATION | Computer | Unit Price Euro | Total Cost Euro |  |
| 1 | ADANA | İNCİRLİK Airport | --- | --- | --- |  |
| 2 | ADANA | ŞAKİRPAŞA Airport | 2 | 1000 | 2000 |  |
| 3 | ADANA | BOTAŞ Sea Border Gateway | 3 | 1000 | 3000 |  |
| 4 | AĞRI | GÜRBULAK Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 5 | ANKARA | ESENBOĞA Airport | --- | --- | --- |  |
| 6 | ANKARA | ETİMESGUT Askeri Airport | 3 | 1000 | 3000 |  |
| 7 | ANTALYA | ANTALYA Airport | --- | --- | --- |  |
| 8 | ANTALYA | ALANYA Sea Border Gateway | 3 | 1000 | 3000 |  |
| 9 | ANTALYA | BÜYÜK Yat Limanı | 3 | 1000 | 3000 |  |
| 10 | ANTALYA | KAŞ Sea Border Gateway | 3 | 1000 | 3000 |  |
| 11 | ANTALYA | KEMER Sea Border Gateway | 3 | 1000 | 3000 |  |
| 12 | ANTALYA | KALEİÇİ Yat Limanı | 3 | 1000 | 3000 |  |
| 13 | ANTALYA | FİNİKE Sea Border Gateway | 3 | 1000 | 3000 |  |
| 14 | ARDAHAN | POSOF-TÜRKGÖZÜ Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 15 | ARTVİN | HOPA Sea Border Gateway | 3 | 1000 | 3000 |  |
| 16 | ARTVİN | SARP Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 17 | AYDIN | KUŞADASI Sea Border Gateway | 3 | 1000 | 3000 |  |
| 18 | BALIKESİR | EDREMİT (Körfez) Airport | 2 | 1000 | 2000 |  |
| 19 | BALIKESİR | AYVALIK Sea Border Gateway | 3 | 1000 | 3000 |  |
| 20 | BALIKESİR | BANDIRMA Sea Border Gateway | 3 | 1000 | 3000 |  |
| 21 | BALIKESİR | AKÇAY Sea Border Gateway | 3 | 1000 | 3000 |  |
| 22 | BARTIN | BARTIN Sea Border Gateway | 3 | 1000 | 3000 |  |
| 23 | BURSA | MUDANYA Sea Border Gateway | 3 | 1000 | 3000 |  |
| 24 | BURSA | GEMLİK Sea Border Gateway | 3 | 1000 | 3000 |  |
| 25 | BURSA | YENİŞEHİR Airport | 2 | 1000 | 2000 |  |
| 26 | ÇANAKKALE | KEPEZ Sea Border Gateway | 3 | 1000 | 3000 |  |
| 27 | DENİZLİ | ÇARDAK Airport | 3 | 1000 | 3000 |  |
| 28 | DİYARBAKIR | DİYARBAKIR Airport | 2 | 1000 | 2000 |  |
| 29 | EDİRNE | KAPIKULE Terrestial Border Gateway | 5 | 1000 | 5000 |  |
| 30 | EDİRNE | KAPIKULE Rail Border Gateway | 5 | 1000 | 5000 |  |
| 31 | EDİRNE | HAMZABEYLİ Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 32 | EDİRNE | PAZARKULE Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 33 | EDİRNE | İPSALA Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 34 | EDİRNE | UZUNKÖPRÜ Rail Border Gateway | 3 | 1000 | 3000 |  |
| 35 | ERZURUM | Erzurum Airport | 2 | 1000 | 2000 |  |
| 36 | GAZİANTEP | GAZİANTEP Airport | 2 | 1000 | 2000 |  |
| 37 | GAZİANTEP | KARKAMIŞ Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 38 | GAZİANTEP | ISLAHİYE Rail Border Gateway | 3 | 1000 | 3000 |  |
| 39 | GİRESUN | GİRESUN Sea Border Gateway | 3 | 1000 | 3000 |  |
| 40 | HAKKARİ | ESENDERE Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 41 | HATAY | CİLVEGÖZÜ Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 42 | HATAY | YAYLADAĞI Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 43 | HATAY | İSKENDERUN Sea Border Gateway | 3 | 1000 | 3000 |  |
| 44 | IĞDIR | DİLUCU Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 45 | ISPARTA | S.DEMİREL Airport | 3 | 1000 | 3000 |  |
| 46 | İSTANBUL | Pendik Sea Border Gateway | 3 | 1000 | 3000 |  |
| 47 | İSTANBUL | Sabiha Gökçen Airport. KURTKÖY | --- | --- | --- |  |
| 48 | İSTANBUL | Atatürk Airport. Dışhatlar. BAKIRKÖY | --- | --- | --- |  |
| 49 | İSTANBUL | Deniz Limanı Şube Müdürlüğü. KARAKÖY | 3 | 1000 | 3000 |  |
| 50 | İSTANBUL | Zeytinburnu Sea Border Gateway | 3 | 1000 | 3000 |  |
| 51 | İSTANBUL | Ambarlı Sea Border Gateway | 3 | 1000 | 3000 |  |
| 52 | İSTANBUL | Haydarpaşa Sea Border Gateway | 3 | 1000 | 3000 |  |
| 53 | İZMİR | A.MENDERES Airport | --- | --- | --- |  |
| 54 | İZMİR | BÜYÜK ÇEŞME Sea Border Gateway | 3 | 1000 | 3000 |  |
| 55 | İZMİR | DİKİLİ Sea Border Gateway | 3 | 1000 | 3000 |  |
| 56 | İZMİR | İZMİR Sea Border Gateway (Alsancak) | 3 | 1000 | 3000 |  |
| 57 | İZMİR | Aliağa Sea Border Gateway | 3 | 1000 | 3000 |  |
| 58 | KARS | KARS Airport | 2 | 1000 | 2000 |  |
| 59 | KASTAMONU | İNEBOLU Sea Border Gateway | 3 | 1000 | 3000 |  |
| 60 | KAYSERİ | ERKİLET Airport | 2 | 1000 | 2000 |  |
| 61 | KIRKLARELİ | DEREKÖY Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 62 | KİLİS | ÖNCÜPINAR Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 63 | KOCAELİ | DERİNCE Sea Border Gateway | 3 | 1000 | 3000 |  |
| 64 | KONYA | KONYA Airport | 2 | 1000 | 2000 |  |
| 65 | MARDİN | NUSAYBİN Terrestial Border Gateway | 3 | 1000 | 3000 |  |
| 66 | MERSİN | ANAMUR Sea Border Gateway | 3 | 1000 | 3000 |  |
| 67 | MERSİN | TAŞUCU Sea Border Gateway | 3 | 1000 | 3000 |  |
| 68 | MERSİN | MERSİN Sea Border Gateway | 3 | 1000 | 3000 |  |
| 69 | MERSİN | TAŞUCU-SEKA Sea Border Gateway | 3 | 1000 | 3000 |  |
| 70 | MUĞLA | DALAMAN Airport | 2 | 1000 | 2000 |  |
| 71 | MUĞLA | DATÇA Sea Border Gateway | 3 | 1000 | 3000 |  |
| 72 | MUĞLA | FETHİYE Sea Border Gateway | 3 | 1000 | 3000 |  |
| 73 | MUĞLA | BODRUM MİLAS Airport | --- | --- | --- |  |
| 74 | MUĞLA | BODRUM Sea Border Gateway | 3 | 1000 | 3000 |  |
| 75 | MUĞLA | MARMARİS Sea Border Gateway | 3 | 1000 | 3000 |  |
| 76 | MUĞLA | GÜLLÜK Sea Border Gateway | 3 | 1000 | 3000 |  |
| 77 | MUĞLA | TURGUT REİS Sea Border Gateway | 3 | 1000 | 3000 |  |
| 78 | MUĞLA | BODRUM YALIKAVAK Sea Border Gateway | 3 | 1000 | 3000 |  |
| 79 | NEVŞEHİR | TUZKÖY Airport | 2 | 1000 | 2000 |  |
| 80 | ORDU | ORDU Sea Border Gateway | 3 | 1000 | 3000 |  |
| 81 | RİZE | RİZE Sea Border Gateway | 3 | 1000 | 3000 |  |
| 82 | SAMSUN | ÇARŞAMBA Airport | 2 | 1000 | 2000 |  |
| 83 | SAMSUN | SAMSUN Sea Border Gateway | 3 | 1000 | 3000 |  |
| 84 | SİNOP | SİNOP Sea Border Gateway | 3 | 1000 | 3000 |  |
| 85 | ŞANLIURFA | AKÇAKALE Terrestial Border Gateway | 4 | 1000 | 4000 |  |
| 86 | ŞIRNAK | HABUR Terrestial Border Gateway | 5 | 1000 | 5000 |  |
| 87 | TEKİRDAĞ | TEKİRDAĞ Sea Border Gateway | 3 | 1000 | 3000 |  |
| 88 | TEKİRDAĞ | ÇORLU Airport | 2 | 1000 | 2000 |  |
| 89 | TRABZON | TRABZON Airport | 2 | 1000 | 2000 |  |
| 90 | TRABZON | TRABZON Sea Border Gateway | 3 | 1000 | 3000 |  |
| 91 | VAN | KAPIKÖY Rail Border Gateway | 3 | 1000 | 3000 |  |
| 92 | ZONGULDAK | ZONGULDAK Sea Border Gateway | 3 | 1000 | 3000 |  |
| 93 | ZONGULDAK | KDZ. EREĞLİ Sea Border Gateway | 2 | 1,000 | 2000 |  |
|  |  | TOTAL | 250 |  | 250,000 |  |

# FEASIBILITY STUDY AND DETAILED JUSTIFICATION OF COMPONENT 3

COMPONENT 3: Modernisation of Border Surveillance and Control Systems in pilot OR PROTOTYPE locations (SUPPLY)

According to the National Action Plan “A single architecture and related common standards need to be developed for overall integration”

In Chapter 24 of Progress Report 2005, it has been stipulated that “member countries must have the operational capabilities to implement common EU measures concerning border security”. Having received the perspective for EU membership, Turkey desires to reach the technological level of EU countries in the area of border security. If and when Turkey gains accession to full membership status, its borders will constitute “EU’s external borders”. Hence, it is almost self-evident that the EU will induce much gain by enhancing Turkey’s technological capability in the area of border security.

The Integrated Border Management system consists of the systems to ensure physical surveillance and control of the national borders, fixed and mobile surveillance and control arrangements, secure integrated communication systems and operations and the government officials ensuring the security of the land, sea and air borders.

Surveillance is a major component of integrated border management. Checking at the border gates and ports is not sufficient for Border Management. The land border and sea border surveillance systems and infrastructure are much greater and more complex issues than only the equipments. They should be handled separately from mere equipment acquisition. However, it should be noted that the structure of the technical system on land is different from the system at sea. Different borders and threats require different type of sensors such as early warning, identification and tracking sensors.

According to the National Action Plan, a certain number of supply projects were decided to be developed for the purchase of the surveillance equipments for sea and land borders and within the project context land surveillance radars, binoculars, fixed and mobile sensors, night/daytime cameras, thermal cameras, covered SAGET boats or control boats were decided to be purchased. As it will take a long time for all those foreseen supply projects to be finished, it was assessed to be more useful gathering them under two consequent projects named as Action Plan on Integrated Border Management-Phase I and Phase II.

The risk analysis increases proportionally to the increase of people and goods traffic. The key factors of the risk are the level of threat, expected damages and impacts and recovery time. There is a security gap between the existing risk and acceptable risk. To reduce this gap, investments should be done phase by phase.

Some key capabilities must be provided by the Border Management System such as surveillance, detection, identification and authentication of people, goods and platforms, interoperability, training and reaction to fight against illegal immigration and illicit trafficking. With the help of thermal cameras (both permanent and thermal) and multi-zoom binoculars detection, identification and authentication capabilities will be enhanced and the reaction time will be shortened. The efficiency will be improved via reducing waiting times, increasing of traffic flow, search and rescue coordination, dangerous cargo control etc.

Thermal Cameras to be mounted at Coast Guard Boats

- Political instabilities, economical problems, ethnic conflicts in some Asian, Middle East and African countries as well as the policies encouraging migration are among the primary causes of illegal migration.

- Being a crossroad among the European countries of high prosperity level and underdeveloped ones in Asia, Middle East and Africa and proximity of its western coast to Greek Islands situates Turkey as a transit country in terms of illegal migration. Besides illegal migration by land and air; seaway is used for illegal transits towards EU countries. Furthermore increasing welfare has made Turkey a target country. Apparently, this strategic geographic location requires a strong border surveillance, control and safeguarding.

- Immigrant interdiction operations conducted by Turkish Coast Guard Command (TCGC) also have a humanitarian nature, in addition to being a law enforcement mission, as some of the immigrant interdiction cases handled by the Turkish Coast Guard Command actually begin as a Search and Rescue mission

- As one of the law enforcement units responsible for the fight against illegal migration, Turkish Coast Guard Command, in recent years, has;

  - Determined the sensitive areas for illegal migration by making risk assessments,

  - Increased the number units and presence of Coast Guard Boats in these areas,

  - Deployed mobile radars in these sensitive points,

  - Equipped TCGC boats with new night vision capabilities,

  - Increased the cooperation between Gendarmerie and National Police,

  - Enhanced the cooperation between TCGC and Hellenic Coast Guard and the foreign liaison officers assigned in Turkey,

  - Given utmost weight for the joint operations by helicopters and boats.

- In 2007, 4832 illegal migrants were seized in the Aegean Sea by Turkish Coast Guard Command. This number constitutes 93 % of the total seizures conducted in the whole jurisdiction area of Turkish Republic at sea. Areas where the number of illegal immigrants seized higher are Kusadasi (1056), Ayvalik (944), Çesme (478), Behramkale (431), Didim (437), Ayvacik (258), Fethiye (214), Marmaris (147), Dikili (146). Also Tasucu Region in Mediterranean Sea (with 214 seizures) is another area with a high incidence rate of illegal migration. The number of illegal immigrant seizures in 2007 is higher than total amount of seizures in the last 3 years.

- As a conclusion of the evaluation of the illegal migration events identified within last 5 years, there seems a certain increase in the usage of the smaller boats, especially the inflatable rafts, for illegal migration attempts, in order to decrease detection probability. However it was reported that the inflatable rafts which cannot be detected by radars on the Turkish Coast Guard Boats can be detected effectively by thermal cameras that are not currently equipped on these boats.

- In this context, in the scope of the project “Action Plan on Integrated Border Management Phase-2”; Turkish Coast Guard Command has expressed its demand for the procurement of 10 thermal cameras to be deployed on TCGC boats located in Çesme, Kucukkuyu, Didim, Fethiye, Marmaris, Dikili and Tasucu Region where illegal migration events occur densely.

Expected outcome:

Introduction of these cameras to the inventory of TCGC will make significant contribution to the technical capacity of TCGC in conducting its abovementioned duties via increasing the efficiency of Coast Guard Boats for detecting inflatable rafts used for illegal migration attempts. In addition, it will increase the overall performance of the implementation of Integrated Border Management Project.

Control Boats

Due to the geographic structure of the coastline along the Greek Islands and the proximity of the Turkish coasts to the Greek Islands, majority of the unregistered migrant cases occur in the Aegean Sea. Some migrants attempt to migrate using small fast boats. In order to prevent and combat such migration cases, TCGC needs several fast intervention boats deployed at various coastal points where migration cases occur more frequently. It is a proven fact that both maneuvering and immediate intervention capabilities of these kinds of boats are superior to those of the larger ones. And also, since the draughts of these boats are very low, they may easily be used in patrolling missions in shallow coast line where larger boats can not be used efficiently.

The reason of the difference between the Control Boat and the SAGET Boat types is the construction material used. While GRP (Glass Reinforced Plastics) boats can be tasked more in low seas missions, Aluminum boats can be tasked in high seas.

In this context, in the scope of the project “Action Plan on Integrated Border Management Phase-2”; Turkish Coast Guard Command has expressed its demand for the procurement of 10 Control Boats which is different from SAGET Boats that were demanded in the scope of the project “Action Plan on Integrated Border Management Phase-1” as it is mentioned above.

10 control boats are planned to be used in the region between Enez and Güllük where illegal migration events occur densely. The control boats are planned to be deployed to the ports in the mentioned region according to the requirements of the date that they will enter to the inventory. The regions where the illegal migration events occur densely may change due to the precautions taken. This situation requires the change of the ports where the purchased control boats will be deployed.

Expected outcome:

Introduction of these control boats to the inventory of TCGC will specifically make significant contribution to the technical capacity of TCGC in conducting its abovementioned duties via improving the combat against illegal migration attempts. It will also increase the overall performance of the implementation of Integrated Border Management Project.

THERMAL CAMERAS (MOBILE AND PERMANENT) AND MULTI-ZOOM BINOCULARS

The principal units in ensuring border security are the border stations. The border stations are located adjacent to the border, at approximately 5 to 10 km distances from each other depending on the topographic structure, climatic conditions and risk analysis. There are total 390 border stations deployed along 2.949 km. of land borders.

Turkey started the efforts to set up a physical security system at the borders in 1950s by enacting and issuing laws and regulations. The physical security system consists of two different categories, namely the “physical barriers system” and “border control and protection system”. The physical barriers system consists of barbed wires, ploughed stripes, fences and trace fields; and the border control and protection system consists of active and passive systems such as enlightening, vehicles, instruments, various air vehicles, steel watch towers, communication, alert and warning systems, night vision equipment, electronic night vision systems or thermal watch systems and contact routes/contact dikes. The physical system has not been set up on the whole of 2.949 km of borders, and the physical barriers system and the border control and protection systems have different characteristics in different zones.

At the borders of Iraq-Iran, despite of having taken intense border security precautions, the trafficking and illegal border crossings cannot be fully prevented. The physical barriers system is not sufficient because of the land structure and the negative weather conditions. From the borders not only the illegal immigrants but smugglers and fugitives are also passing and they may be too far from the border units to be seen. This leads the border units to observe the border zones day and night. Therefore, the identification of the person and the reaction that will be given to that person are vital.

Within Turkey, in 2003 56.219, in 2004 61.228, in 2005 57.428, in 2006 51.983 and in 2007 64.290 illegal immigrants have been captured.

For the purposes mentioned above the necessary equipments required for the East and Southeast border regions have been determined by the officers in charge according to the difficulties of the land structure, the amount of the equipment in the inventory and etc.

According to the National Action Plan investments in technology should be given priority to ensure that surveillance and checks at the borders are performed in accordance with the EU standards and for these purposes the investment projects included in the “Financing Plan” shall be carried on.

A supply plan was drawn up to provide needs for 7 border gates initially in “Action Plan on Integrated Border Management-Phase I” and in this supply plan some necessary equipments were demanded such as mobile and permanent thermal cameras and multi-zoom binoculars. As the financial assistance for the supply was limited, not all the required equipments were accepted within the context of Phase-I. Therefore, as the requirement for the mentioned equipments still exists the same equipments are demanded within the context of Phase-II. That’s the reason of the existence of the same equipments in both projects.

THERMAL CAMERA SYSTEM, NIGHT VISION AND MULTI-ZOOM BINOCULARS

Green Border surveillance prevents and discourages unauthorized border crossings, counters cross-border criminality and takes measures against persons who have crossed the border illegally. Surveillance may also be carried out by technical means, including electronic means (radars, sensors and infrared vision at night).

A great majority of the attempts at illegal entry into Turkey are made at the border zones other than the border gates. The most important reason is that Turkey has not fully satisfied the infrastructural needs for the security of the land borders because of the hard land and climate conditions and high costs.

The border control system must provide early detection of every attempt to cross Turkish borders, localization, classification and tracking of abnormal events at the borders, real time transfer of information to the command and control centers. Target detection will be made via magnetic sensors detecting intrusions and triggering other sensors in the network. Target identification will be made via thermal imaging and colour cameras allowing the operator to view the intruder and making an informed decision as to the appropriate response.

Electronic surveillance with automatic detection and tracking systems distribute the work load of operative resources in such a way that time saved in human and technical resources can be allocated to other tasks. The required equipments assist to control the entry of multiple intruders in different environments with early detection, identification and tracking, interception and capture within different types of borders against different types of intruders.

Due to its geographical location, Turkey has constituted a transit route for illegal border crossing from Asia-Africa to Europe. In recent years, rising number of illegal border crossings has not only created serious ramifications for Turkey’s national security but also it constituted a challenging pressure for the European border management system. The number of people detained for illegal crossing across the land borders surrounding Turkey has risen from 10.270 in 2006 to 19.724 in 2007. More than half of that illegal activity occurred over the eastern and southern (Iran, Iraq and Syria) borders of Turkey. Annual average number of illegal crossings on the Turkish-Iranian border is around 5.000. Almost half of those incidents happened within the city boundaries of Van and Ağrı. To put more clearly, around 10% of annual illegal border crossings has taken place in Van-Ağrı region. Thus, both Turkey and the EU should give high priority to advance technological measures to be taken on the Iranian border. In order to fight against illegal migration and transnational organized crime (smuggling, trafficking, terrorism, etc.) more effective border security measures should be taken. In the context of enhancing technological measures taken to prevent illegal migration and human trafficking, procurement of additional technology and pilot implementation in Van-Ağrı region is assessed to be in line with EU Integrated Border Management System.

As known, thermal cameras are devices which are sensitive to thermal differences. They provide vision of the target even through the smoke, fog and under the low light conditions. These devices do not shine in the intensive light like night vision devices. They are very useful especially in the areas where the border units cannot go closer and allow the units to observe the targets remotely. The disadvantage of these devices is the polarity of the device which means the records or the snapshots are either black, white or colored but do not enable the users recognize the targets in terms of gathering evidence. Night vision devices are more effective for evidence goals and the recognition of the targets. These devices are being used in many countries and are proved to be satisfactory.

As a conclusion of the statistical analysis of the annual illegal immigration events, the identified requirements according to the Van-Ağrı region reflects an objective assessment.

In 2007, approximately 20,000 people were captured throughout Turkey while crossing the border illegally. 20% of these events (4,000 people) occurred in Van-Ağrı region.

| Lot / Item No. | Description | Original Quantity | Brand names with Models | Estimated Unit Price (€) | Estimated Cost (€) | Country(ies) of Origin |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Land Border Surveillance Equipments |  |  |  |  |  |  |  |
| 1.1 | New generation permanent thermal camera | 60 | Aselsan-ASIR, Carl Zeiss Attica K | 105.000,00 | 6.300.000,00 | Turkey | Germany |  |
| 1.2 | New generation mobile thermal camera | 24 | CORAL, Carl Zeiss opusm/d, EMX 300 DX-3MWIR | 58.000,00 | 1.392.000,00 | Israel | Germany | USA |
| 1.3 | Long distance binoculars | 26 | STEINER-20X80, Transvaro-DG20x80 | 1.400,00 | 36.400,00 | Germany | Turkey |  |
| 1.4 | 3rd generation Thermal Camera System (thermal camera and target positioning system) | 90 | ASELSAN-ASIR | 110.000,00 | 9.900.000,00 | Turkey |  |  |
| 1.5 | Night vision binoculars | 40 | TV/UGG -2(NOD) | 10.000,00 | 4000.000,00 | Turkey |  |  |
| 1.6 | Multi-zoom binoculars | 20 | 20x120 Nikon | 5.000,00 | 100.000,00 | Germany |  |  |
| 2 | Sea Border Surveillance Equipments |  |  |  |  |  |  |  |
| 2.1 | Thermal Camera Systems | 10 | Aselsan-Şahingözü, EMX-Midwatch XR, Controp-SPIDER | 170.000,00 | 1.700.000,00 | Turkey | USA | USA-Israel |
| 2.2 | Control boats | 10 | Nothstar Boats Guardian 950, Asil Marine T-62/60, Madera RIBS H1T99 | 200.000,00 | 2.000.000,00 | Turkey | Turkey | Netherlands |
| 3 | Systems |  |  |  |  |  |  |  |
| 3.1 | Modernization of Border gateways IT systems | 1 |  | 5.000.000,00 | 5.000.000,00 |  |  |  |
| 3.1.1 | VSAT System(Backup of VSAT HUB Station) | 1 | Newtech, STMI, Viasat | 1,000,000,00 | 1,000,000,00 |  |  |  |
| 3.1.2 | VSAT Terminal and Peripheral Units | 93 | Newtech, STMI, Viasat | 20,000,00 | 1,860,000,00 |  |  |  |
| 3.1.3 | Crypto Device | 101 | IdQuantigue-AEE-ETH-1G, Compumatica-CGVPN-4850, Rohde-Schwarz/Ethernet Encryptor | 10,000,00 | 1,010,000,00 |  |  |  |
| 3.1.4 | Backbone Switch | 93 | Alcatel Omniswitch 6400, HP procurve 2900 24 G/48 G, Cisco catalyst 3750 24 TS/3750 48 TS | 2,500,00 | 232,500,00 |  |  |  |
| 3.1.5 | Router | 93 | Alcatel, HP, Cisco catalyst 3750 24 TS/ 3750 48 TS | 2,500,00 | 232,500,00 |  |  |  |

ANNEX 7

MARKET RESEARCH TABLE

| 3.1.6 | Modem | 93 |  | 750,00 | 69,750,00 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1.7 | Server | 77 | HP proliant DI 380/385 rack-tower bl 370, fujitsu-siemens rx 200 rack/tx 150 tower, dell power edge 2950 rack/pe 2900 tower | 8,000,00 | 616,000,00 |  |  |  |
| 3.1.8 | Structured cabling(quantity of 2500) | 1 |  | 250,000,00 | 250,000,00 |  |  |  |
| 3.1.9 | 5KVA UPS | 93 | Socomec, Masterguard, Eka | 1,000,00 | 93,000,00 |  |  |  |
| 3.1.10 | Central Metro Ethernet Backbone Device | 1 | Alcatel Omniswitch 9700, Procurve 9300, Cisco Catalyst 4500 | 200,000,00 | 200,000,00 |  |  |  |
| 3.1.11 | Spectrun Analyzer | 1 |  | 15.000,00 | 15.000,00 |  |  |  |
| 4 | Analysis and Inspection Devices |  |  |  |  |  |  |  |
| 4.1 | Analysis software | 50 | I2 Analyst Notebook, BTT-Visual analysis | 5.000,00 | 250.000,00 | UK | Turkey |  |
| 4.2 | Computers | 250 |  | 1.000,00 | 250.000,00 |  |  |  |
| TOTAL |  |  |  |  | 27.400.000,00 |  |  |  |