- Twinning Project Fiche

- AL 08 IB EC 01

- 1. Basic Information

1.1. Programme: IPA 2008

1.2. Twinning number:

1.3. Title:  Support for the strengthening of the Albanian Public Procurement, Concessions and Public Auctions systems.

1.4. Sector: 01.05

1.5 Beneficiary country: Albania-Public Procurement Agency, Contracting Authorities, Ministry of Economy, Trade and Energy.

2. Objectives

2.1 Overall Objective

To assist the Government of Albania to achieve EU standards as required under the SAA in the areas of Public Procurement, Concessions and Public Auctions.

2.2 Project Purpose

To contribute to improvements in the effectiveness, efficiency and transparency of the Public Procurement, Concessions and Public Auctions systems in Albania.

2.3 Contribution to AP/NPAA / EP/ SAA:

The project will help achieve the priorities included in the European Partnership (EP) for Albania, on public procurement, and those included in the Stabilisation and Association Agreement.

Key priorities of the EP:

- Enforce public procurement legislation and take steps to bring it fully up to EU

standards, especially as regards utilities sector and remedies;

- Further strengthen the administrative capacity of the Public Procurement Agency, public  procurement entities in line Ministries and local government and courts dealing with public procurement;

- Ensure investigation and criminal prosecution of procurement-related offences.

Likewise, in the framework of Article 70 and 74 of the SAA, Albania shall: adopt the necessary legislation to grant European companies access to contract award procedures.

The assessment of Albania's progress in the implementation of the Stabilisation and

Association process has led to a number of priorities, which are outlined in a National Plan for the implementation of Stabilisation and Association Agreement (NPISAA).

Short-term priorities of the NPISAA (2007-2008)

- The opening of public contracts on the basis of non-discrimination, in the framework of WTO, (priority already realised);

- Guarantee and observance of law and sub-law acts;

- Strengtheing of the current legislation on public procurement and measures taken to bring it in line with European Standards – (the is parially realised);

- Equality of Right of participation of european community companies registered in Albania re procurement procedures (already in force).

- Strengthening of Public Procurement Agency and procurement entities in Line Ministries;

- Elimination of avoidance from the open procedures of procurements, -  priority already realised after the open procedure is determined a basis and a more prefered one in the public procurement legislation;

- Transarency and rigororous enforcement of the procurement procedures, - (Priority already realised)

- Investigation and penal prosecution on infringements with respect to procurement.

Medium-term priorities of the NPISAA (2009-2010)

- To be provided the full harmonisation of the albanian legal frame with acquis communautaire;

- To become fully functional the public procurement structures, through the rigorous enforcement of public procurement procedures, in compliance with law and SAA requirements;

- Access of Albanian companies in procurement procedures in Community, according to this latter law.

- Companies of Community, which are not located in Albania, should have access  in procurement procedures according to the Albanian legislation, not latter than 4 (four) years after the SAA entered in force.

2.4 Link with MIPD:

The project aims to achieve as well, the priorities defined on the 2.2.3.3 section of the Multi-annual Indicative Planning Document (MIPD) 2007-2009 for Albania, and in concrete:

Capacity building for the Public Procurement Agency in order to develop and implement Acquis compatible legislation.

2.5	Link with National Development Plan

The National plan for Development and Integration foresees further approximation to EU standards in this area.

2.6 Link with Sectoral investment plans

NA

3. Description

3.1 Background and justification:

On November 20th 2006, the Parliament of the Republic of Albania adopted the new law no. 9643 "On Public Procurement", which entered into force on 1st January 2007. The law abrogates law no. 7971, dated 26.07.1995 "On Public Procurement", as amended and any other provisions that it is in contradiction with it. The law was drafted in light of European Union Directives in this area, specifically regarding Directives 2004/18/EC and 2004/17/EC. It is partially approximated. In addition, on 10.09.2007 the Parliament of the Republic of Albania adopted the law No. 9800, approved  some amendments and additions to the law no. 9643.

With the objective to improve and further align the institutional framework of the complaints review mechanism, the  Public Procurement Agency assisted by SIGMA, has drafted some amendments to the current law on public procurement concerning the establishment of a new review body,. With the proposed amendments the objective is to continue the process of approximation with the EC Directives in the field of public procurement and remedies also in keeping with the  recommendations of the  Progress Reports 2008 for Albania of the European Commission. These amendments regulate the establishment of a collegial review body, the Public Procurement Commission, which will be independent form the Prime Minister’s Office, and will have as competence the review of public procurement complaints. The decisions of this body will be administratively final, and it will be possible to appeal to the First Instance Court of Tirana. The proposed amendments, togethet with proposal for amendments regarding the utilities sectors (water, energy, transport and postal services), have been sent to the Council of Ministers for approval.

Pending the approval of the mentioned amendments at present the Public Procurement Advocate, and Public Procurement Agency, as foreseen in law 9643/2006, remain the two institutions dealing with complains against contracting authorities regarding public procurement procedures (PPA as decision makers and PPAv as advisor.

On 18.12.2006 the Law No. 9663 “On Concessions” was approved by Parliament. It is partially approximated to EU standards. In this light, it is foreseen that amendments will indeed be required. In addition, at the time of drafting this fiche no formal training courses have been provided in the area of concessions.

On February 2008, the Parliament adopted the law no.9874, dated 14.02.2008 “On Public Auctions”, a first law of its kind in Albania. For this reason, training courses will be required due to the lack of previous experience in the field.

In order to acquaint the public procurement officers with the new law No. 9643, dated 20.11.2006 “On Public Procurement”, 20 one-day seminars were provided for contracting authority employees throughout Albania. The total number of trainees was 550. However, due to the importance and complexity of the area of public procurement, much work remains to be done in order to achieve full approximation to EU requirements as well as to strengthen capacities of the contracting authorities.

In terms of the legal role of the Public Procurement Agency, it was established as Central Organ by the Council of Ministers Decision No. 496, dated 18.09.1995 “On the functioning of Public Procurement Agency”. From 2007 onwards its legal basis was found in law No. 9643, dated 20.11.2006 “On Public Procurement”, amended.

With the gradual increase of staff, since June 2007 PPA has had 36 employees (6 of whom are support staff). In accordance with the new law and the tasks and responsibilities therein of the PPA regarding both procurement and concessions, a new structure was created. According to the structure, the Legal and procurement Sector was reorganised to the Complaints and Legal Assistance on procurements Directory (7 persons); was created the Complaints and Legal Assistance on Concessions Directory, comprises 3 (three) persons; the Trainings, Finance, Integration & Management of the Human Resources Sector was increased and in total comprises 4 persons; the Inspection Sector was increased and in total comprises 6 persons, and also the Statistics and Bulletin Sector was increased and in total comprises 6 persons. An Information Technology Sector has been established and comprises 3 (three) staff. One of its principal functions is to maintain the PPA website, assuring the electronic publication of the information and documents of procurement procedures launched in Albania. All such directorates and sectors are under the management of the General Director.

According to the Law No. 9643, dated 20.11.2006 “On Public Procurement”, the main role of PPA is as follows:

- To submit proposals for procurement regulations to the Council of Ministers;

- To promote and organise training of central and local government officials engaged in public procurement activities;

- To compile and issue the Public Procurement Bulletin,

- To prepare standard tender documents to be used in awarding procedures, in accordance with the public procurement rules;

- In accordance with the requests, gives advice and provides technical assistance to contracting authorities conducting awarding procedures;

- To plan and coordinate foreign technical assistance to Albania in the field of public procurement;

- To encourage and support the use of international technical standards for the preparation of technical specifications, as well as maintains an ongoing relationship with the National Directorate of Standardisations;

- To verify the application of public procurement procedures in compliance with the requirements established by the law, requiring the contracting authorities to submit all the relevant information;

- In case of misconduct, penalizes with fines or proposes to the head of contracting authorities or higher bodies disciplinary measures against the individual in the contracting authorities who committed the infringement;

- To carry out the administrative review of complaints, as provided in Chapter VII of the PPL;

On the basis of Law No. 9663, dated 18.12.2006, Article 6, “On concessions”, the role of PPA in the concessions field is focused mainly in these directions:

- it verifies the application of concessionary procedures, in compliance with this law and other acts stemming from its implementation, while requesting from the concession authorities all the necessary information;

- it proposes disciplinary measures and imposes penalties to the extent defined in the procurement legislation, in the instances when it observes violation of the procedures of this law.

- it conducts the administrative review of complaints from bidders regarding concession procedures.

- it decides and announces the debarment from concession procedures  of bidders who have, during a concessionary procedure, deposited forged documents or declared false information;

- it provides to Council of Ministers its opinion regarding the procedure followed for concessions.

The role of the Concessionary Treatment Agency and Contracting Authorities on concessions.

In addition to the PPA on the concessions there are other interested parties, The Concessionary Treatment Agency (CTA) and the Contracting Authorities which lies under the Ministry of Economy, Trade and Energy. According to the law on Concessions, the role of the CTA is to promote and assist the contracting authority in evaluation and negotiation of concessions. It also collaborates with competent contracting authorities to identify the potential concessions.

The contracting authority can be a ministry or the local government unit, which in compliance with the legislation in force is responsible for the economic activity for which the concession

is granted. The contracting authority for local concessions is the responsible authority of the local government units. The Contracting Authority is identified case by case from Council of Ministers. Competent ministries or the Local Government units, in cooperation with the Concession Treatment Unit, shall carry out a viability and bank ability analysis to decide whether a potential concession should be implemented. This analysis shall be based upon the principles of value for money, alignment of potential Concessions with the national strategic objectives, as well as with sector strategic objectives, the technical and commercial feasibility of the potential Concession and its ability to attract potential Concessionaires and private and financing.

Therefore, the aim of this support is to address some of the areas of the European Commission’s  2008  Progress Report for Albania, specifically the one concerning Public Procurement which at paragraph 4.1.6 states:

"…

The role of the PPA as the central coordinating and advisory authority for legal and procedural reforms needs further strengthening to ensure consistent development in all areas of public procurement. Legislative activities in certain areas of public procurement are still split between various stakeholders.

The Public Procurement Advocate was established as an independent institution reporting to parliament. However, it has no particular executive powers and its functions duplicate the monitoring tasks of the PPA. The institutional framework for remedies is not in line with the acquis. Decisions on appeals are taken by the same unit of the PPA that is responsible for interpreting the law and giving advice to contracting authorities. Current procedures for handling complaints still do not meet recognised international standards.

Overall, preparations in the area of public procurement are advancing. However, there is no coherent, comprehensive strategy for further development of the procurement system in either the medium or long term..."

Lastly, and as well importantly,  the Government of Albania's Anti Corruption Strategy and Action Plan adopted by Council of Minister's decision in October 2008 makes explicit  reference to reforming the Public Services sector and notably the Public Procurement system by, inter alia, developing public procurement sub legal framework and standard documentation, establishing and consolidating the Public Procurement Ombudsperson, developing institutional mechanisms to prevent, identify and punish corruptive practices, and the implementation of data exchange systems with other sectors.

3.2 Linked activities

During the period September 2004-November 2006, the Public Procurement Agency was assisted by the CARDS 2002 Annual Programme with a project named “Support to the Public Procurement System in Albania”, funded by EU, which has been successfully implemented. A number of very positive activities, directly linked to the project objectives, were implemented  during this project implementation period. Some of the most important achievements of the project are as follows: New draft public procurement law developed; Secondary legislation developed; PPA Training Unit established; Train the Trainer programme completed; National Training Plan developed, Training Programme implemented to Public Procurement Officers Nationwide with corresponding training materials; PPA Web Site developed and launched

Major IT equipment installed within PPA, etc.

From October 1, 2006 to October 1, 2008 Public Procurement Agency has been assisted by the component “Reform in Public Procurement”, of the Millennium Challenge Threshold Agreement Program for Albania, managed by USAID. The assistance of this projects during the year of 2007 has consisted on three main directions:

-  Asisstance on the secondary legislation drafting in the field of Public Procurement;

- Assistance on administrative capacities building in the field of Public Procurement, and also     on monitor capacities of the Public Procurement Agency through the implementation of an integrated IT system;

- Public and business awareness raising about the public procurement system;

The assistance of this project during the year 2008 was focused mainly on e-procurement platform, assisting the Contacting Authorities and economic operators on implementing e-procurement system.

At the time, Albanian Government is formally submitting the Threshold Country Plan at the Millennium Challenge Corporation (MCC) and there are possibilities that this project will last for two other years 2009-2010. Also the assistance of this project will consist on implementation and trainings on e-procurement system.

From the year 2007, Public Procurement Agency is assisted by SIGMA, for drafting of the legislation in the utilities sectors. On this purpose, by the PPA was set up a working group, which, with the assistance of the experts of SIGMA, worked for drafting of this legislation, according to the Directive 2004/17/EC.

3.3 Results:

Component 1:	Legal and institutional reform:

Results:

- Fully  approximated legislation in the area of public procurement to EU directives.

- Competent public procurement actors and efficient institutional structures and processes.

- A complaints review mechanism in line with EU standards defined, approved and incorporated into the relevant legislation.

- Codes of Conduct prepared, approved and incorporated into respective operating procedures of the beneficiary institutions

- Periodical Internal Control Standards Reports prepared, reviewed and submitted

Component 2: Capacity building for the PPA, Review body, contracting authorities at both central and local government levels dealing with public procurement and public auctions.

Results

- Long term National Training Plan (at minimum a 3 years plan) drafted and approved

- 12 small regional units (most likely to be located within the 12 prefectures) established

- Specific training modules and manuals for use during trainings on procurement, public auctions and concession legislations prepared and approved.

- 10 training modules on procurement, public auctions and concessions delivered.

- Approximately 15 Trainers trained both from public and private sector, selected through a competitive procedure (training of trainers)

- 6 persons per Regional Training Unit trained.

- 1000 Contracting Authorities officers trained on principles, and procedures of public procurement, public auctions and concessions.

- Methodology for the evaluation of Training Units prepared and approved.

- Incorporation of anti-corruption tools (awareness, prevention, reporting, processing) within the main training curriculum of the beneficiary institutions, in compliance with the Anti-Corruption strategy;

- Evaluation report on the work of the Training Units.

Component 3: Communication regarding public procurement, concession and public auctions

Results:

- Wider awareness and knowledge among Contracting Authorities, suppliers/economic operators and the wider public.

- Communications Strategy on Public Procurement, concessions and public auctions  drafted, approved and implemented.

- More effective and clearer communication of PPA vis-a'-vis the mass media and the public.

- Improved web site  of PPA

3.4. Activities

Component 1: Legal and Institutional Reform

Activities:

- Assessment  of the current legal and institutional framework concerning public procurement and concessions;

- Preparation of an action plan for the implementation of the procurement system reform;

- The examination of the best practices and models of procurement in some of the Member States and their comparison to the Albanian public procurement and concessions legislation;

- Elaboration and Implementation of a periodical Internal Control Standards Review Mechanism

- Preparation of draft-law amending primary legislation in public procurements and concessions, according to the respective EU Directives.

- Consultations of the draft-law with representatives of the Line Ministries, Central Contracting Authorities and  the economic operators.

- Drafting of the secondary legislation on public procurement and concessions in line with the respective EU legislation.

Component 2:  Capacity building for the PPA and  contracting authorities at both central and local government levels,  dealing with public procurement and public auctions.

Activities

- Supporting PPA on preparation of a long term National Training Plan (at minimum a 3 years plan), including training on Anti Corruption.

- Assisting PPA on establishing 12 small regional units (most likely to be located within the 12 prefectures).

- Selection, appointment and training of Anti-Corruption Contact Points within each regional unit and at central level.

- Supporting the consolidation and strengthening of the review mechanism, through the development of capacity building activities.

- Delivery of Training of Trainers to approximately 15 trainees. (as above please specify in what institutions)

- Support to the PPA on organising and delivering trainings through the Training Units, on public procurement, public auctions and concessions, respectively for procurement, auctions and concession officers and representatives from private sector.

- Support the PPA monitoring the work of the Training Units and their  ability in  organizing and delivering trainings.

- Conducting 1 study visit, aiming the acquaintance with the functioning of the public procurement and concessions systems in the Twinning Member State.

- Preparation of 10 specific training modules and manuals for use during trainings on procurement, public auctions and concession legislations.

- Support the PPA in the preparation of the evaluating report on the work of the Training Units.

Component 3: Communication regarding public procurement, concession and public auctions

Activities

- Setting up a working group composed by PPA staff and other relevant stakeholders to draft a Communications Strategy on Public Procurement.

- Support the PPA in the  implementation of the approved Communications strategy to the PPA staff and the wider public, in coordination with other public information campaign implemented by the Government

- Preparation of  information material  such as leaflets, manuals, and other publications

- Supporting the PPA in keeping a regular dialogue with journalists and mass media in general.

- Supporting the PPA in improving its web site

- Publicity spots in TV and advertisement or articles in the national and local press. Conducting a public opinion survey on standards, quality, transparency, and value for money of public contracts (primarily focused on economic operators and citizens) at beginning and at the end of the project. .

3.5 Means/Input from the MS Partner Administration

3.5.1 Profile and tasks of the Project Leader

Profile:

- Minimum 10 years of experience in the public procurement field.

- Be an administrator from public administration of an EU member's state with expertise in public procurement issues. He/she should have the status of civil/public servant.

- Sound comparative knowledge of relevant EU legislative and institutional requirements related to the various components of this project.

- Wide knowledge of related good practice/Acquis communautaire.

- Have excellent management, leadership, communication and coordination skills.

- Proven abilities of manager in forming an appropriate team of short-term experts.

- Experience in developing similar projects implemented in other countries.

- Good training, public speaking and written communication skills.

- Excellent computer literacy (Word, Excel, Power Point).

- Excellent command of spoken and written English.

Tasks:

- To lead and direct the overall project implementation.

- The coordination of all activities.

- The management of the project administration.

- Permanent contact with the Twinning M.S counterpart.

- Overall supervision of the project implementation and coordination of all activities, as well as management of the project administration;

- Coordination of the activities of the team members in line with the agreed work programmes to enable timely completion of project outputs;

- Coordination of work with other relevant institutions in Albania for the implementation of the project.

3.5.2 Profile and tasks of the RTA

One Resident Twinning Adviser (RTA) over a period of 12 months as well as medium/short term experts will implement the above-listed components. The RTA has the responsibility to guide the work of the team. The medium/short term experts will work in close cooperation with the RTA and the staff in order to meet the specific objectives as set out above.

The RTA is expected to fill the following profile:

- Minimum 10 years of experience in the public procurement field.

- Be an administrator from public administration of an EU member's state with expertise in public procurement issues.  He/she should have the status of civil/public servant.

- Possess sound knowledge on internal control standards for Public Administration, including anti-corruption and integrity tools

- Sound comparative knowledge of relevant EU legislative and institutional requirements related to the various components of this project.

- Wide knowledge of related good practice/acquis communautaire.

- Solid knowledge of procurement legislation, work methods and procedures .

- Have excellent management, leadership, communication and coordination skills.

- Proven abilities of manager in forming an appropriate team of short-term experts.

- Experience in developing similar projects implemented in other countries.

- Good training, public speaking and written communication skills.

- Excellent computer literacy (Word, Excel, Power Point).

- Excellent command of spoken and written English.

Additional assets are:

- Sound background in drafting and/or implementing strategies, policies or regulations

- Previous experience as project coordinator/project manager in similar projects;

- Some relevant working experience in the new Member States and the Western Balkans;

- Knowledge regarding the situation and the administrative structures from

Albania would be a plus.

- Relevance of other language skills will be considered as well.

Tasks:

- Overall supervision of the project implementation and coordination of all activities, as well as management of the project administration;

- Advise on procurement standards and practices in EU Member States;

- Coordination of the activities of the team members in line with the agreed work programmes to enable timely completion of project outputs;

- Preparation of project progress reports;

- Permanent contact with the beneficiary RTA counterpart;

- Liaison with EC Task Manager;

- Liaison with other relevant projects.

The RTA is expected to ensure, together with the beneficiary administration, the achievement of the objectives listed in 2.1/ 2.2. In order to meet these purposes, and if fully justified, the RTA may propose alternative and/or complementary project activities and/or outputs to those identified in the section 3.4.

3.5.3 Profile and tasks of the medium/ short-term experts

Tasks of medium and short term expertise

Terms of Reference for short-term adviser(s) will be elaborated by Project Leader/RTA at the work plan preparation stage.

Profile of short and medium-term expertise

There should be a pool of short/medium term experts. Their "mix" should be identified by the Project Leader/RTA in the course of designing the delivery of the project. The actual duration of the assignments of each of the short-term expert(s) (in principle from 2 to 8 months) will be defined during the drafting of the twinning agreement. The medium-term expert(s) will work in close co-operation with the RTA and the Beneficiary in order to meet the specific objectives as set out above.

The short and medium- term experts are expected to have:

- Professional background in public procurement issues

- At least 5-10 years of experience in a specialised national administration of an EU Member State;

- Solid training skills and experience in organizing training courses

- Sound knowledge of relevant EU legislative and institutional requirements related to the various components of this project;

- Very good command of English (oral and written);

- Excellent computer skills (Word, Excel);

- University degree.

Additional assets are:

- Sound communication skills and previous experience of working in multi-disciplinary and multi-national team;

- Sound background in drafting and/or implementing strategies, policies or regulations;

- Some relevant working experience in the new Member States and the Balkans.

4. Institutional Framework

This project will be implemented by the Public Procurement Agency and Respective Concessions Authority.

The project is as well addressed to the following institutions: Contracting Authorities through Public Procurement Agency, Ministry of Economy, Trade and Energetic, and Public Procurement Agency.

5. Detailed Budget in Euros

The beneficiary will provide in kind contribution in the form foreseen in the twinning manual.

Total budget of the action: € 1 million.

|  | Programme | Support |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Investment Support (I) | Institution Building (IB) | Total Programme (=I+IB) | National Co-financing | IFI | TOTAL |
| Twinning | *500 000 | 1,000,000 | 1,500,000 |  | 0 |  |
| Total |  | 1,000,000 |  | **20,000 |  | 1,020,000 |

* The investment support will be provided through a separate contract. ECD will be responsible for tendering and contracting

** National Co- financing is in kind (support the RTA with accommodation, trainings rooms, and logistical assistance).

6. Implementation Arrangements

6.1. Implementing Agency

The European Commission Delegation in Tirana will be responsible for tendering, contracting, payments and financial reporting, and will work in close cooperation with the beneficiary. The Programme Manager at the EC Delegation, OPS I, will be Francesca Aquaro,  ABA Business Centre, 17th floor, Rr. Papa Gjon Pali II,   Tirana, Albania.  Tel: + 355 42 228 320 Fax: +355 42 270 678,  e-mail: Francesca.Aquaro@ec.europa.eu

- 6.2 Main counterpart in the Beneficiary Country:

- Project leader: Ms Reida Shahollari, Head of Training, Finance, Integration & Management of Human Resources Sector, Public Procurement Agency

- Bulevardi 'Deshmoret e Kombit' Keshilli I Ministrave, Tirana, Albania

- E-mail: rshahollari@app.gov.al  Tel: +355 42 277 516, Fax: +355 42 256 631

6.3. Contracts:

The project will be implemented through one twinning agreement.

| Contract | Contract Value ( € ) |
| --- | --- |
|  | 2009 |
| Project: Support for Albanian Public Procurement, Concessions and Public Auctions systems |  |
| Contract = Twinning Component 1: Legal and Institutional Reform Component 2: Capacity building for the PPA, contracting authorities at both central and local government levels and Courts dealing with public procurement and public auctions Component 3: Communication regarding public procurement, concession and public auctions | €1.000.000 |
| Total € 1.000.000 |  |

7. Implementation schedule (indicative)

7.1. Launching of the call for proposals (date) June 2009

7.2 Start of the project activities (date) May  2010

7.3. Project completion (date) May  2011

7.4. Duration of the implementation period (number of months) 12 months

8. Sustainability:

- The sustainability of the project rests entirely upon the Government of Albania as a whole in the fostering of a professional, merit based public administration.

9. Cross cutting issues

9.1. Equal Opportunity

The principle of equal opportunity will be integrated into all stages of the project implementation, which it is also in conformity with the Albanian Constitution which provides for equal opportunity for men and women be treated equally despite of their race, nationality, gender, origin, religious and political beliefs.

9.2. Environment

NA

10. Conditionality and sequencing

The implementation of the project requires the full commitment and participation of the senior management of the Albanian Public Procurement Agency

The Beneficiary shall:

- Ensure that appropriate staff is made available to work with the EU twinning partner(s). Counterparts for each of the objectives will be appointed to facilitate the implementation of the respective activities of the twinning project;

- Be responsible for the selection of trainees - in consultation with the EU experts - as well as for providing the EU experts with legislation and any other documents necessary for the implementation of the project;

- Ensure that appropriate staff for training are made available, that trainees are released from their duties during their training and that once trained they are retained in post;

- Ensure that staff trained under this project are permitted to remain in post and not subject to arbitrary and frequent transfer into posts where their newly acquired skills are of no use or dismissed without due cause/process. To address this, a detailed database of what training was provided to which person should be maintained by the implementing partner(s) to allow for monitoring of the investment in future to ensure those trained have not been transferred;

- Shall provide all possible assistance to solve any unforeseen problem that the EU twinning partner(s) may face;

- Fully support the RTA with accommodation, trainings rooms and logistical assistance.

Equally, the Twinning team, as led by the Twinning Resident Adviser must ensure full collaboration with the counterparts at the institution. Communications should be open and consistent. The Twinning team must carry out activities in the interest of the institution, and maintain its involvement at all stages of activities.

11. Investment criteria

- 10.1	Co-financing: Co-financing will come from the beneficiary in the form of provision of accommodation, training rooms, electricity and telephone, staff salaries, etc.

- 10.2	Additionality: IPA assistance under this project will not overlap with funds provided by the national budget or other bilateral support

Annexes to project Fiche

- Logical framework matrix in standard format

- Implementation Chart

- Contracting and Disbursement Schedule by Quarter

- Reference to feasibility /pre-feasibility studies

- List of relevant Laws and Regulations

- Reference to relevant Government Strategic plans and studies (may include Institution Development Plan, Business plans, Sector studies etc)

| ANNEX I - LOGFRAME PLANNING MATRIX FOR twinning fiche |  | Programme name and number : Support for the Albanian Public Procurement Agency |  |
| --- | --- | --- | --- |
|  |  | Contracting period expires: 3 years following the date of conclusion of the Financing Agreement | Disbursement period expires : One year after the end date for the execution of contracts |
|  |  | Total budget: €1,000,000 | IPA budget: €1,000,000 |
| Overall objective | Objectively verifiable indicators | Sources of Verification | Assumptions |
| To assist the Government of Albania in strengthening the public procurement system in line with EU standards. | - Public Procurement and concessions laws and regulations in compliance with the EU legislation. | European Commission’s Reports and Opinions through Progress Reports, and the Working Party on Internal Market. WB reports |  |
| - Project purpose | - Objectively verifiable indicators | - Sources of Verification | - Assumptions |
| Improved legislative and administrative framework for the PPA through more efficient legal and institutional set-up and processes and better trained public procurement officers. | - Improved transparency in all 3 systems - Greater number of national and international bids - Increased number of standard documents - Fewer complaints | - European Commission Progress Reports of Albania in the field of public procurement and Report of Public Procurement Agency. - WB public procurement reviews Public Procurement Statistics | - Commitment, availability, dedication and substantial involvement of the Public Procurement Agency and its staff, as well as other Contracting Authorities officers in the implementation of the project. - Good co-operation with Contracting Authorities and the Ministry of Economy, Trade and Energy. |
| - Results | - Objectively verifiable indicators | - Sources of Verification | Assumptions |
| Contract 1: Support to the Public Procurement Agency, Contracting Authorities and the Respective Concessions Authority. Component 1: Legal and institutional reform: Results: - Further approximated legislation in the area of public procurement to EU directives. - More informed and competent public procurement actors and more efficient institutional structures and processes. | - Approximated primary and secondary legislation to EU Directives. - Higher standards of service and quality of tenders prepared by contracting authorities - Greater number of applications for public concessions - Greater number of successful public tenders - Higher standards of quality of bidders | - Statistics of the PPA - Public Opinion - Number of Complaints made by economic operators to PPA | Will to change |

| LOGFRAME PLANNING MATRIX FOR Project Fiche – continued |  |  |  |
| --- | --- | --- | --- |
| - Results | - Objectively verifiable indicators | - Sources of Verification | Assumptions |

| Component 2: Capacity building for the PPA, contracting authorities at both central and local government levels and Courts dealing with public procurement and public auctions. Results - Long term National Training Plan (at minimum a 3 years plan) drafted and approved - 12 small regional units (most likely to be located within the 12 prefectures) established - Specific training modules and manuals for use during trainings on procurement, public auctions and concession legislations prepared. - 10 training modules drafted and executed. - Approximately 15 Trainers trained ( training of trainers) - 6 persons per Regional Training Unit trained. - 2000 Contracting Authorities officers trained on principles, and procedures of public procurement, public auctions and concessions. - Monitored training Units evaluating on ability to organise and deliver trainings. - Methodology for evaluation of Training Units prepared. Component 3: Communications regarding public procurement, concession and public auctions Results: - Wider awareness and knowledge among Contracting Authorities, suppliers/economic operators and the wide public. - Prepared, budgeted, and initiated Communications strategy on public procurement, concessions and public auctions, as Contracting Authorities, the economic operators and every Albanian taxpayer, interested on the processes. This communication strategy will improve the Public Relation of PPA with the other parties. Better informed contracting authorities. | - Higher standards of service and quality of tenders prepared by contracting authorities - Quantifiably and qualifiably increased capacity of contracting authorities to deal with the entire tendering process - Less complaints from economic operators - Quantifiably greater satisfaction of economic operators of the transparency, clarify, efficiency of the tendering and contracting process for public contracts, concession and public auctions. - Increased confidence of the Albanian taxpayer that public funds are being well spent. - Better quality bids from economic operators - Quantifiably improved image of public procurement as a corruption-free area. | - European Commission Progress Reports of Albania in the field of public procurement and Report of Public Procurement Agency. |  |
| --- | --- | --- | --- |

| Activities/Components or input | Means | Sources of verification | Assumptions |
| --- | --- | --- | --- |
| Component 1: Legal and Institutional Reform - The evaluation of the current legal and institutional framework in the area of public procurement and concessions. - Proposals for better alignment with EU legislation; - The examination of the best practices and models of procurement in some of the Member States and their comparison to the Albanian public procurement and concessions legislation; - Preparation of draft-law with amendments of primary legislation in public procurements and concessions, according to the respective EU Directives. - Consultations of the draft-law with representatives of the Line Ministries, Central Contracting Authorities and of the economic operators. These consultations will be organised in round tables with the participation of 10 representatives of the three groups of stakeholders (Line Ministries, Central Contracting Authorities and economic operators), aiming their introduction with the draft-law and consultation about their problematic encountered in practice. - Discussions and proposals for amendments to the secondary legislation. - Drafting of the secondary legislation on public procurement and concessions in line with the respective EU legislation. | Twi Long and short term experts from the TA project. Working group composed by PPA staff and EU experts 3 (three) round tables with the participation of representatives of the three groups of stakeholders (Line Ministries, Central Contracting Authorities and economic operators The established working group | - European Commission Progress Reports of Albania in the field of public procurement and Report of Public Procurement Agency. - The Project Progress Report | Capacity and interest of all beneficiaries Availability of staff Assurance that state budget will provide budget for sustainable training on all areas. Cooperation between stakeholders Quality of experts |
| Component 2: Capacity building for the PPA, contracting authorities at both central and local government levels and Courts dealing with public procurement and public auctions. Activities - Supporting PPA on preparation of a long term National Training Plan (at minimum a 3 years plan) - Assisting PPA on establishing 12 small regional units (most likely to be located within the 12 prefectures), - Delivery of Training of Trainers to approximately 15 trainees. - Organisation of seminars for this target group. - Support to the PPA on organising and delivering trainings through the Training Units, on public procurement, public auctions and concessions, respectively for procurement, auctions and concession officers and representatives from private sector. - Monitoring the work of the Training Units evaluating their ability on organizing and delivering trainings. - Conducting 2 study visits, aiming the acquaintance with the functioning of the public procurement and concessions systems in the Member States. The study visits could possibly take place in Slovenia and Austria. - Preparation of specific training modules and manuals for use during trainings on procurement, public auctions and concession legislations. - 10 modules are going to be prepared. - 12 Regions’ Training Units/6 persons per Unit, established and trained. - Preparation of a evaluating report on the work of the Training Units. - Conducting 80 trainings on public procurement, public auctions and concession, comprised of 25 persons in each training, for 2000 Contracting Authorities officers: | Long and short term experts from the TA project. Procurement and concessions officers in each study visit 10 modules are going to be prepared, and 3 manuals respectively in procurement, public auctions and concessions |  |  |
| Component 3 Communications Activities - Setting up a working group composed by PPA staff and other relevant stakeholders to draft a Communications Strategy on Public Procurement. - Promoting the approved Communications strategy to the PPA staff and the wider public - Preparation of informative information such as leaflets, manuals, and other publications - Regular dialogue with journalists. Representatives of PPA and Ministry of Economic, Trade and Energetic will conduct three meetings with journalists of Mass-Media, aiming the public awareness. - Advice on the user ability of the PPA website - Publicity spots in TV and advertisement or articles in the national and local press. - Impact assessment of public opinion on standards, quality, transparency, and value for money of public contracts (primarily focused on economic operators and citizens) at beginning and end of assistance. | Long and short term experts from the TA project. Use of all forms of media Public Survey |  |  |
| Contract 2 – IT Supplies to the PPA and the regional training units Equipping the new PPA staff and the Training Units in the Regions with necessary supplies, needed in every day work. | Supplies tender (It is foreseen that the technical specification and tender dossier for the supplies contract will be prepared by a short term expert recruited under the TA contract). |  |  |

- ANNEX II:	Implementation chart

Project: Support for the Albanian Public Procurement Agency

2009

| July T | August T | September T | October D | November D | December D |
| --- | --- | --- | --- | --- | --- |

2010

| January D | February D | March D | April C | May C | June I | July I | August I | September I | October I | November I | December I |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

2011

| January I | February I | March I | April I | May I | June I | July X | August X | September I |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

D = Design

T = Tendering

C = Contracting period

#### I = Implementation

X = Closure

ANNEX III

Contracting and disbursement schedule by quarter

Contracting and Disbursement Schedule by Quarter

|  |  | 2009 1Q | 2009 2Q | 2009 3Q | 2009 4Q | 2010 1Q | 2010 2Q | 2010 3Q | 2010 4 Q |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Contract Twinning (Components 1, 2, etc ) | Contracted € 1,000,000 |  |  |  |  |  | 1.000.000 |  |  |
|  | Disbursed |  |  |  |  |  |  |  |  |

|  |  | 2011 1Q | 2011 2Q | 2011 3Q | 2011 4Q | 2012 1Q | 2012 2Q |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Contract Twinning (Components 1, 2, etc, ) | Contracted € 1,000,000 |  |  |  |  |  |  |
|  | Disbursed |  |  |  |  |  |  |

Annex IV

Reference to relevant reports/documents

Annex V

List of relevant laws and Regulations

Laws:

- Law No.9643, dated 20.11.2006 “On public procurement”, amended;

- Decision of CM no.1, dated 1.01.2007 ‘Regulation on public procurement”, amended;

- Law no.9663, dated 18.12.2006 “On concessions”;

- Decision of CM no.27, dated 19.01.2007 ‘Regulation on concessions”;

- Law no.9874, dated 14.02.2008 ‘On Public Auction”

Reference to National Action Plan for the implementation of the SAA

More specifically, the legislative initiatives to be taken, in the medium term have been listed by the Albanian authorities as:

Reference to MIPD

The project aims to achieve as well, the priorities defined on the 2.2.3.3 section of the Multi-annual Indicative Planning Document (MIPD) 2007-2009 for Albania, and in concrete:

Capacity building for the Public Procurement Agency in order to develop and implement acquis compatible legislation.

Reference to National Development Plan

The National plan for Development and Integration foresees further approximation to EU standards in this area.

Reference to national / sectoral investment plans

NA

End of Twinning Fiche

____________________________________________________