Annex 1:

Logical Framework Matrix for the Twinning Project - Institutional Strengthening of Environment Health System in Georgia

| Institutional Strengthening of Environment Health System in Georgia |  | Programme name and number | ENI 2015 |
| --- | --- | --- | --- |
| National Center for Disease Control and Public Health of Georgia |  | Contracting period expires: | Disbursement period expires: |
|  |  | Total budget: EUR 1 300 000 |  |
| Overall objective | Objectively Verifiable Indicators | Sources of Verification |  |
| Promoting effective environmental health system and improving health-related conditions for the benefit of the population of Georgia. | - Decrease of Communicable Diseases cases in population - Improved environmental conditions in the Country | - GEOSTAT reports - MoENRP Annual Reports - MoLHSA Annual Reports - Independent publications and assessments |  |
| Project purpose | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| To strengthen the legal framework on environmental health in Georgia through harmonization with European requirements, improving environmental and health management, ensuring long-lasting environmental policy development and strengthening intersectoral collaboration. | - Institutional capacities and administrative provisions within NCDC&PH enhanced - Functional roadmap for all stakeholders elaborated - Legal regulatory framework amended and agreed with all stakeholders - Environmental health human resources well trained - Education Concept and Training programme for environmental health human resources developed - NEHAP implementation supported and Cost reflective Annual Action Plan developed | - EC Regular Reports on progress by Georgia in implementation of the AA - MoLHSA, MoENRP and NCDC&PH Annual Reports - Third party reports WHO, USAID and etc. | - Government continued commitment on legal harmonisation with EU - MoLHSA /NCDN&PH continues to develop and implement environmental health policy - Availability of local staff among all stakeholders - Adequate budgetary allocation to the NCDC&PH to undertake steps for development of Environmental Health System - Sufficient capacity within the NCDC&PH to absorb activities within Twinning project |

| 3.3. Results | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| --- | --- | --- | --- |
| Result 1: Georgian legal and regulatory framework in environmental health field revised in-line with the provisions of the relevant Annexes of the Association Agreement related to the environmental health, as well as taking into account Georgia’s commitments towards Multilateral Environmental Agreements and other relevant international pledges (e.g. Parma Declaration, UNECE Conventions); | - An intersectoral environmental health working group established - Assessment of environmental health legal framework carried out - Report and recommendations on existing environmental health legal acts provided - Priorities identified - New legal acts to be developed and necessary amendments to the existing “old” ones identified and agreed - Legal framework for the establishment of the environmental health system amended | - Minutes of the Working Group meetings - Project Reports - Experts’ mission reports - NCDC&PH official reports - Monitoring reports | - MoLHSA/NCDC&PH continues to develop environmental health policy - Adequate legal and regulatory drafting capacity within the MoLHSA/NCDC&PH and other stakeholders - Availability of sufficient staff along project lifetime - MoLHSA/NCDC&PH remains committed to carry out legal harmonisation process with EU - Availability of sufficient budgetary resources to extend the scope and range of tasks for the improvement of environmental health system - Cooperation and involvement of all stakeholder institutions in the development of regulations, procedures, strategies, programmes and etc. |
| Result 2: Institutional capacity of the Environment and Health Unit under the NCDC&PH strengthened; | - Report on structural status of the Environmental Health Division delivered - Recommendations for institutional and operational changes provided - Institutional Reform Plan drafted - Gap assessment of the environmental health system carried out and recommendations for improvement provided - Functional roadmap of all stakeholders elaborated - Procedures for regular information exchange on environmental health matters at horizontal level elaborated in line and building on SEIS regional project - Communication strategy and awareness raising action plan elaborated - communication materials developed - Study Visit performed | - Working group minutes - Experts mission reports - MoLHSA /NCDC&PH Annual Reports - NCDC&PH internal reports - Project Reports - Monitoring reports - Study visit report - Workshop agenda - Workshop report - Stakeholder reports |  |
| Result 3: Implementation of the National Environmental Health Action Plan (NEHAP) supported in line and building on Roadmaps for EU approximation in the environmental and climate action fields; | - ToR on the needs assessment of NEHAP implementation available - Report on needs assessment delivered to all stakeholders - Training on tools and methodologies on elaboration of cost reflective action plan conducted - Manual for the elaboration of the Costed Action Plan drafted - Cost reflective Annual Action Plan developed - Workshops for stakeholders organised - NEHAP revised - Changes to the NEHAP presented through workshops to all stakeholders | - Working group minutes - Experts mission reports - MoLHSA /NCDC&PH Annual Reports - NCDC&PH internal reports - WHO reports on NEHAP implementation - Project Reports - Monitoring reports - Workshop agenda - Workshop report - Training materials - Training reports - Assessment/feedback on Trainings |  |
| Result 4: Capacities of Existing Environmental Health Human Resources, Including Management and Decision Makers Strengthened Along with Operationalization of Effective Environmental Health Management System in Compliance with EU Best Practices; | - Assessment of the existing capacities of human resources engaged in environmental health field carried out - Education concept for environmental health professionals developed - Professional Development scheme for environmental health human resource developed - Training programme, materials and manual for environmental heath human resources professional development elaborated - Trainings and workshops for NCDC&PH central and regional office staff and other stakeholder institutions’ representatives delivered - Training of trainers conducted - Internship programme for NCDC&PH staff developed and internship organized - Study Visit performed | - Working group minutes - Experts mission reports - MoLHSA /NCDC&PH manual Reports - NCDC&PH internal reports - Project Reports - Monitoring reports - Workshop/Training agenda - Workshop/Training reports - Training materials - Assessment/feedback on Trainings - Internship programme - Internship report - Study visit report |  |

| 3.4. Activities | Means (Resources) | Assumptions |
| --- | --- | --- |
| General: | EUR 1.200.000 |  |
| Organise Kick-off Conference and Steering Committee | RTA + PL Interpretation + Translation + Conference Equipment + Refreshments | Good cooperation between project partners Interest on the part of other Government bodies, Higher Education Institutions , Civil Society Organisations and the mass media |
| Organise final “Closing conference” | RTA, PL, STEs Interpretation + Conference Equipment + Refreshments |  |
| Component 1: Georgian legal and regulatory framework in environmental health field revised in-line with the provisions of the relevant Annexes of the Association Agreement related to the environmental health, as well as taking into account Georgia’s commitments towards Multilateral Environmental Agreements and other relevant international pledges (e.g. Parma Declaration, UNECE Conventions); |  |  |
| 3.4.1.1 Assessment of legislative framework of Georgia in relation to environmental health field according to EU Directives and regulations | RTA, STEs 75 working days (wd) + Translation | - The NCDC&PH and all other relevant stakeholders assign appropriate staff/representatives to work within Working Group - The NCDC &PH nominates responsible staff at all levels to act as counterparts to the RTA and project’s experts - The NCDC&PH ensures access to all relevant legislation, regulations and any supporting documents relevant to the project scope - The NCDC&PH facilitates coordination among all partner administrations acting in the environmental health field |
| 3.4.1.2 Develop proposal including recommendations for harmonisation of the Georgian legislation related to environmental health in compliance with EU requirements and other Environmental Agreements Directives taking into account Georgian commitments related to Multilateral Environmental Agreements and other relevant international documents (e.g. Parma Declaration, UNECE Conventions) | RTA, STEs 70 wd + Translation |  |
| 3.4.1.3 Develop a legal framework for the establishment of environmental health system as a part of the health system of Georgia | RTA, STEs 80 wd + Interpretation + Translation |  |

| Component 2: Institutional capacity of the Environment and Health Unit under the NCDC&PH strengthened; |  |  |
| --- | --- | --- |
| 3.4.2.1 Review of the structure and functions of the Environmental Health Division under the National Centre for Disease Control and Public Health , including its relations with relevant counterparts (MoENRP, MoAG, other relevant line ministries) | RTA, STEs 30 wd + Interpretation + Translation | - Working Group remains active through component implementation - The NCDC&PH facilitates coordination among all partner administrations acting in the environmental health field - The NCDC&PH ensures access to all relevant regulations, orders and any supporting documents relevant to the component - The NCDC&PH and other stakeholders ensure availability of their staff to participate in project activities (e.g. reviews, workshops, study tours, communications activities) - The NCDC&PH ensures that the outcomes of the project are integrated in their regular working agenda |
| 3.4.2.2 Drafting an Institutional Reform Plan for the Environmental Health Division under the National Centre for Disease Control and Public Health | RTA, STEs 25 wd + Interpretation + Translation |  |
| 3.4.2.3 Gap Assessment of the Existing Environmental Health System | RTA, STE 30 wd + Translation |  |
| 3.4 2.4 Mapping of functions of all stakeholders | RTA, STE 25 wd + Interpretation + Translation |  |
| 3.4.2.5 Elaboration of the procedures for the regular information exchange among responsible bodies | RTA, STE 25 wd + Translation |  |
| 3.4.2.6 Development of a communication strategy and awareness raising action plan | RTA, STE 30 wd + Translation + printing |  |
| 3.4.2.7 Study Visit to MS to be acquainted with the European Models of Environmental Health Systems in Practice | Study visit costs (10 flights, 50 per diems) |  |
| Component 3: Implementation of the National Environmental Health Action Plan (NEHAP) in line with the roadmap for EU approximation in the environmental and climate action fields supported; |  |  |
| 3.4.3.1 Conduct Needs Assessment for implementation of NEHAP | RTA, STE 20 wd + Interpretation + Translation +Venue | - The NCDC&PH ensures availability of relevant staff to be engaged in the component activities - The NCDC&PH ensures that the outcomes of the project are integrated their regular working agenda |
| 3.4.3.2 Training on tools and methodologies of costing | RTA, STE 10 wd + Interpretation + Translation |  |
| 3.4.3.3 Development of the Annual Action Plan (AAP) and its costing | RTA, STE 30 wd + Interpretation + Translation |  |
| 3.4.3.4 Revision of NEHAP | RTA, STE 20 wd + Interpretation + Translation |  |
| Component 4: Capacities of Existing Environmental Health Human Resources, Including Management and Decision Makers Strengthened Along with Operationalization of Effective Environmental Health Management System in Compliance with EU Best Practices; |  |  |
| 3.4.4.1 Assessment of the existing capacities of human resources in environmental health with all stakeholders | RTA, STE 25 wd + Interpretation + Translation | - Working Group remains active through project component implementation - The NCDC&PH facilitates coordination among all partner administrations acting in the field - The NCDC&PH ensures access to all documentation relevant to the component - The NCDC&PH and other stakeholders ensure availability of their staff to participate in component activities (e.g. assessments, workshops, trainings, study tour, internship) - The NCDC&PH facilitates access of project partners to regional offices of the NCDC&PH |
| 3.4.4.2 Develop scheme for Professional Development | RTA, STE 20 wd + Interpretation + Translation |  |
| 3.4.4.3 Development of training programme and manual for environmental health human resources | RTA, STE 30 wd + Translation |  |
| 3.4.4.4 Human Resources Training of the Environmental Health Division of NCDC&PH, regional centres and stakeholder institutions | RTA, STE 50 wd +Interpretation + Translation + transportation to regions |  |
| 3.4.4.5 Conduct train-the-trainers course | RTA, STE 15 wd + Interpretation + Translation |  |
| 3.4.4.6 Internship for NCDC&PH Staff | Internship costs (2 flights, 60 per diem) |  |
| 3.4.4.5 Study Visit to MS to get familiar with training systems | Study visit costs (5 flights, 25 per diems) |  |