| No | ACTIVITIES | STE days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | RTA Installation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | 0.1: Kick-off Conference | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | 0.2: Closing conference | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Project Reporting and Steering Committee Meetings | 21 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Activities for Result 1.Georgian legal and regulatory framework in environmental health field revised in-line with the provisions of the relevant Annexes of the Association Agreement related to the environmental health, as well as taking into account Georgia’s commitments towards Multilateral Environmental Agreements and other relevant international pledges (e.g. Parma Declaration); |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.1.1 Assessment of legislative framework of Georgia in relation to environmental health field according to EU Directives and regulations | 50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.1.2Develop proposal including recommendations for harmonisation of the Georgian legislation related to environmental health in compliance with EU requirements and other Environmental Agreements Directives | 50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.1.3 Develop legal framework for establishment of environmental health system as a part of health system of Georgia | 70 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Activities for Result 2. Institutional capacity of the Environment and Health Unit under the NCDC&PH strengthened |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.2.1 Review of the structure and functions of the Environmental Health Division under the National Centre for Disease Control and Public Health | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.2.2 Drafting an Institutional Reform Plan for the Environmental Health Division under the National Centre for Disease Control and Public Health | 25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.2.3 Gap Assessment of the Existing Environmental Health System | 25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.2.4 Mapping of functions of all stakeholders | 25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.2.5 Elaboration of the procedures for the regular information exchange among responsible bodies | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.2.6 Development of a communication strategy and awareness raising action plan | 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.2.7 Study Visit to MS to be acquainted with the European Models of Environmental Systems in Practice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Activities for Result 3. Implementation of the National Environmental Health Action Plan (NEHAP) supported; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.3.1 Conduct Needs Assessment for implementation of NEHAP | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.3.2 Training on tools and methodologies of costing | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.3.3 Development of the Annual Action Plan (AAP) and its costing | 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.3.4 Revision of NEHAP | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Activities for Result 4. Capacities of Existing Environmental Health Human Resources, Including Management and Decision Makers Strengthened Along with Operationalization of Effective Environmental Health Management System in Compliance with EU Best Practices; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.4.1 Assessment of the existing capacities of human resources in environmental health with all stakeholders | 25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.4.2 Develop scheme for Professional Development | 20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.4.3 Development of training programme and manual for environmental health human resources | 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.4.4 Human Resources Training of the Environmental Health Division of NCDC&PH, regional centres and stakeholder institutions | 50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.4.5 Conduct train-the-trainers course | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.4.6 Internship for NCDC&PH Staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3.4.4.7 Study Visit to MS to get familiar with training systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Total | 563 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |