ANNEX C1

TWINNING LIGHT PROJECT FICHE

1. Basic Information

1.1 Programme: RRAA-A 2014 (UNIBE)

1.2 Twinning Number: TR 14 IPA JH 05 16 TWL

1.3 Title: Enhancement of IT Capabilities of Risk Analysis System in Ministry of Customs and Trade (MoCT)

1.4 Sector: Democracy and Governance-Regulatory Reform and Acquis Alignment Mechanism

1.5 Beneficiary country: TURKEY

2. Objectives

2.1 Overall Objective(s):

The overall objective of the project is to strengthen the evaluation, information and risk assessment abilities of MoCT so as to support efforts to facilitate legitimate trade and non-fiscal roles of the MoCT.

2.2 Project purpose:

Main purpose of the Project is to formulate the basis for a new Risk Analysis System that corresponds to simplified customs procedures and utilizes advanced risk analysis techniques ranging from risk scoring systems and automated feedback mechanisms to data mining methods.

2.3 Contribution to National Development Plan/Cooperation agreement/Association Agreement/Action Plan

Referring to 2015 Progress Report, it is clear that one of the major considerations of the Commission related to the Chapter on Customs Union is the need for Turkey to make additional efforts for improving risk-based controls and simplified procedures and facilitating legitimate trade.

On the 10th National Development Plan Component-3 it is suggested to improve physical and human resource capacity of customs and to extend information technology usage in customs so as to ensure effectiveness in operations. Another statement is related to physical infrastructure of customs that needs to be improved in accordance with the developments in information technologies for the expedition of procedures.

Above all, UCC Article 3 states that maintaining a proper balance between customs controls and facilitation of legitimate trade is of great importance. A well-functioning Risk Management System which is in line with modern needs is one of the major promoters of this objective.

3. Description

3.1 Background and justification:

Risk Management System in Turkish Customs has demonstrated a considerable development since the beginning of its implementation. However, concerning certain deficiencies related to the functioning of the system, further modernization of it is required.

Current Risk Analysis Program was formed in 2003 and has gone through no major changes in its functioning since then. It is clear that the program is unable to correspond to the developments in risk analysis (data mining, scoring system etc.) because of its lack of flexibility for adjustment. As another concern, the program does not have a feedback mechanism for measuring the effectiveness and efficiency of risk profiles. This leads our personnel to measure the effects of their work manually and results in loss of time. Besides, the process in which we extract data from our institutional data banks, decide which information would be beneficial and incorporate them to risk analysis is largely non-practical and requires long times of work.

With the project in question, it is intended to observe the processes of data analysis, scoring methods and feedback systems applied in member countries. By doing so, new approaches to risk analysis in customs will be analyzed and transferred to our system.

3.2 Linked activities (other international and national initiatives):

# An early Twinning Project that was titled “Strengthening the administrative, organizational and operational capacity of Risk management and Risk Analysis” was realized with the partnership of Germany and United Kingdom in 2012-2013. Our major aim was enhancement of risk assessment capacity of Turkish Customs Administration. Business Strategy and National Action Plan with reference to needs analysis report and Risk Analysis Working Directive that comprises of the principles of central and local risk analysis were prepared as main outputs of the project.

In Business Strategy and National Action Plan under the title of ‘General Issues 1.4 Equipment Business Strategy’, it was suggested that “Current risk analysis capacity will be increased continuously in line with trading demands and technological developments.” and “MoCT will continue to at least annually monitor its IT infrastructure’s strength to ensure that it continues to meet changing business requirements.” In addition to this, under the section named “Risk Management and Risk analysis in Customs clearance Issues 2.2 Feedback” it is declared that “Because the feedback mechanism is a significant tool for risk analysis MoCT will continue to evaluate and receive all the feedback data electronically and by the meetings held on the local level to ensure consistency.  MoCT will endeavor to get feedback under codes (For instance 0=Risk Not Proved, 1= Risk Partly Proved, 2= Risk Proved) by 2017.”

With the implementation of planned project, it is intended to discover the certain unrealized parts of above-mentioned objectives of the earlier project and to promote the sustainability of them in addition to our major purpose of modernizing current risk system.

3.3 Results:

In Relation to Activity I

I.I Needs Analysis Report on Risk Management System of MoCT has been generated.

I.II Action Plan has been produced based on Needs Analysis for both the project duration and for 5 years after the project completion.

I.III New risk targeting and feedback system has been planned-designed.

In Relation to Activity II

II.I. At least 11 personnel of MoCT Risk Management Unit has been effectively trained on data analysis.

II.II. At least 100 staff at 19 Regional Directorate Operation staff trained on the feedback system on risk analysis system implemented by the partnering country.

II.III A guideline prepared by the MoCT personnel and partnering country’ experts which clearly defines data mining methods, targeting techniques via scoring and feedback mechanism for risk analysis that are implemented by the partnering country. The guideline will be the base for a prospective risk analysis system.

Indicators;

- The number of trained staff on data mining and targeting will increase during the project.  At least 11 personnel from the Central Risk Management Unit and 100 customs inspectors/officers from the regional customs offices will attend study visits, internships and inbound training courses and will be certified by the end of the project.

- Physical checks will be better and more effectively targeted. At least %10 increase at the rate of redress on detailed declaration for both import and export. (Verification sources for data on rate of redress on detailed declaration and risk profile numbers are explained on the Logframe.)

- At least 10 risk profiles will be created by using scoring techniques. (Verification sources for data on rate of redress on detailed declaration and risk profile numbers are explained on the Logframe.)

3.4 Activities:

Activity 1- Evaluation

- The current situation of the Risk Management System will be evaluated. Especially the data banks that are currently in use and the methods in which we utilize them (collecting and processing data) will be assessed in terms of coherence with risk analysis logic. (Interpretation is required.)

- A questionnaire aimed at the customs inspectors/officers  will be conducted to examine their assessments and considerations regarding the efficiency of current risk analysis system. (Translation is required.)

- Gap and Needs analysis of the Risk Management System of MoCT on data analysis, targeting, profiling will be prepared. (Translation is required.)

Activity 2 – Training

- 1 study visit and 3 internships will be arranged to see how an EU member state’s practices on data mining and targeting via scoring are carried out. Study visit will be arranged to see the practices of an EU member country whose risk analysis system and related feedback mechanism are considerably developed. The duration of program will be 5 working days. 1 study visit including 5 participants for 5 days and 3 internships including 2 participants in each for 10 days will be organized. The fact that the Project is highly grounded on the need to acquire knowledge of and practices implemented by the participant country renders internships more significant for the Project in question since internships are more effective than study visits in enabling the beneficiary country to make more intensive and deep observations. That is why the project is designed to have a high number of internship activity. (Interpretation is required.)

- Selected staff of MoCT Risk Management Unit will be trained on data mining and targeting via scoring. (Interpretation is required.)

- 4 training workshops on the links between targeting results and feedback mechanism will be arranged with the inclusion of customs inspectors/officers in the prominent cities such as; Ankara, İstanbul, İzmir and Mersin.

3.5 Means/ Input from the MS Partner Administration:

3.5.1 Profile and tasks of the Project Leader

Project Leader should have experience on customs legislation and risk management, implementation of international projects and present and defend project input and expected outputs, manage the project team, prepare project management reports, help overcome project related problems. He/she should also have international experience. He/she will be responsible for overall implementation of the project. Furthermore, project leader will manage financial issues and coordination.

    - Profile and tasks of the risk management experts

- Extensive knowledge and expertise in customs and/or customs enforcement activities,

- Minimum 5 years of professional experience in risk management and customs inspection area with minimum 2 year of practical experience at the local level,

- Sound knowledge of legislation and policies of the European Union, in relation to the risk management in the Community

- Sound knowledge of English, appropriate knowledge in writing strategic documents and carrying out training on methodology of strategy development and good computer skills.

    - Profile and tasks of the training experts

- Having at least 5 years of professional experience in the field of risk management

- Having at least 1 year of experience as a trainer in the field of risk analysis

- Having demonstrated knowledge on data mining, targeting, and profiling.

* 5 years of experience in the field of risk management is crucial for the selection of both risk management and training experts for the project because it requires them to be fully equipped on customs processes and inspection procedures of their own country so that they can reflect those to the Turkish system. It is preferable to have an expert pool which is limited in number but consists more qualified candidates rather than having a large one.

4.  Institutional Framework

The beneficiary of this project is the Ministry of Customs and Trade, General Directorate of Risk Management and Control. Some of the main responsibilities of the Directorate are to analyze data on customs procedures through risk analysis methods, to evaluate the outcomes, and to transmit the results to the relevant departments, to determine risk measures, to sustain coordination regarding the risk management, to provide the required data exchange and cooperation among national and international institutions/organizations, to collect data about post-clearance audit operations by implementing the data on risk analysis, to evaluate and to archive the collected data, to transmit them to the relevant departments and to coordinate those departments.

5.  Budget

| Enhancement of IT Capabilities of Risk Analysis System in MoCT | IPA Community Contribution | National Co-financing | TOTAL |
| --- | --- | --- | --- |
| Twinning Light Contract | 95% 237.500,00 EUR | 5% 12.500,00 EUR | 250.00,00 EUR |

6.  Implementation Arrangements

6.1 Implementing Agency responsible for tendering, contracting and accounting

(AO/CFCU/PAO/ Commission), including contact person and full contact details.

Mrs. Emine Döğer

Acting PAO-CFCU Director

Central Finance and Contracts Unit

6.2 Main counterpart in the BC, including contact person and contact details. Also include RTA counterpart and the BC Project leader

SPO Delegate:

Hacı Hasan Murat ÖZSOY

General Director

Ministry of Customs and Trade Directorate General for Risk Management and Control

PL Counterparts:

Mrs. Ayşe Tuğba YEŞİL

Head of Risk Analysis Department

Ministry of Customs and Trade Directorate General for Risk Management and Control

7. Implementation Schedule (Indicative)

7.1 Launching of the call for proposals (Date) 2016 4th quarter

7.2 Start of project activities (Date):  2017 2nd quarter

7.3 Project completion (Date): 2017 4th quarter

7.4 Project duration (number of months): 9 months in total (6 months for implementation, totally 9 months for legal duration)

8. Sustainability

At the end of the project, MoCT will start to use new risk analysis techniques to ensure enforcement, security and trade facilitation at the same time. By using these techniques and getting fast and correct feedback from targeted cargo, conveyances and carriers, rate of redress on detailed declaration will increase. Moreover, improvement of risk analysis system by performing new techniques guarantees the sustainability of the earlier project.

Manual processes will decrease while time and labor efficiency will be sustained by applying new techniques into the system. By doing so, the staff responsible for data analysis will be able to make time for focusing on other processes of risk management, which will lead to a positive effect on the overall effectiveness of risk analysis.

In case of realizing that the present risk analysis program is not suitable for prospective updates at the end of the project, it is probable to sustain project outcomes by proceeding with a procurement project for a new program.

9. Crosscutting issues (equal opportunity, environment, etc…)

9.1    Equal Opportunity

Equal opportunity principles and practices in ensuring equitable gender participation in the project will be guaranteed. Male and female participation in the project will be based on EU standards and assured by official announcements published to recruit the necessary staff for the project. The main criteria for recruitment will be qualifications and experience in similar projects, not sex or age. Both men and women will have equal opportunities and salaries.

9.2     Environment

Not relevant to this project.

  - Minority and vulnerable groups

Not relevant to this project.

9.4	Civil Society

Not relevant to this project.

10. Conditionality and sequencing

Not Applicable

ANNEXES TO PROJECT FICHE

1.  Logical framework matrix

# ANNEX I: Logical framework matrix in standard format

| LOGFRAME PLANNING MATRIX FOR TWL Project Fiche |  | Enhancement of IT Capabilities of Risk Analysis System in MoCT |  |  |
| --- | --- | --- | --- | --- |
|  |  | Contracting period expires 3 years after the signature of the Financial Agreement |  | Execution period expires 3 years following the end date for contracting |
|  |  | Total budget | € 250.000 |  |
|  |  | IPA budget: | € 237.500 |  |
| Overall objective | Objectively verifiable indicators (OVI) | Sources of Verification |  |  |
| The overall objective of the project is to strengthen the evaluation, information and risk assessment abilities of MoCT so as to support efforts to facilitate legitimate trade and non-fiscal roles of the MoCT. | Level of concordance between Turkey and the EU practices and efforts to facilitate legitimate trade. | • EU Regular Progress Report on Turkey • Annual Activity Report of MoCT |  |  |
| Specific objective | Objectively verifiable indicators (OVI) | Sources of Verification |  | Assumptions |
| To formulate the basis for a more effective Risk Analysis System that corresponds to simplified customs procedures and utilizes advanced risk analysis techniques ranging from risk scoring systems and automated feedback mechanisms to data mining methods. | Rate of redress on detailed declaration for both import and export (at least 10% increase) | • Annual Activity Report of MoCT • MoCT website • Official statistics of MoCT • GÜVAS (MoCT data repository that will enable us to check any data including rate of redress on detailed declaration before and after the project) • MoCT Risk Analysis System (that keeps the data on risk profiles) |  | • Adequate financial resources will be timely available. • Risk Management Systems of partnering countries will be compatible with the existing Turkish Risk Management System in order to ensure a beneficial collaboration. • Project Management Group has adequate expert staff. • Senior management of the MoCT will give appropriate priority to the establishment of operational systems. • Senior management of the MoCT remains committed to the project. |
| Results | Objectively verifiable indicators (OVI) | Sources of Verification |  | Assumptions |
| In Relation to Activity I I.I Needs Analysis Report on Risk Management System of MoCT has been generated. I.II Action Plan has been produced based on Needs Analysis both for the project lifetime and for post 5 years. I.III New risk targeting and feedback system has been planned-designed. In Relation to Activity II II.I. At least 11 personnel of MoCT Risk Management Unit has been effectively trained on data analysis. (1 study visit including 5 participants in for 5 days and 3 internships including 2 participants in each for 10 days.) II.II. At least 100 staff at 19 Regional Directorate Operation staff trained on the feedback system implemented by the partnering country. II.III A guideline prepared by the MoCT personnel which clearly defines data mining methods, targeting techniques via scoring and feedback mechanism for risk analysis that are implemented by the partnering country in order for the guideline to be the base for a prospective risk analysis system. | • Rate of redress on detailed declaration for both import and export (at least 10% increase) • Number of risk profiles created by using scoring techniques (min. 10) • Number of risk profiles created with relation to simplified customs procedures (min. 5) • Number of MoCT personnel participated in study visits and internships (min. 11) • Number of trained staff on data mining and targeting (min. 100) | • Reports of study visits. • Reports of internships. • MoCT website • Official statistics of MoCT • GÜVAS (MoCT data repository) • MoCT Risk Analysis System (that keeps the data on risk profiles) |  | Relevant trainees will fully participate. |
| Activities to achieve results | Means / contracts | Costs |  | Assumptions |
| Activity 1- Evaluation - The current situation of the Risk Management System will be evaluated. Especially the data banks that are currently in use and the methods in which we utilize them (collecting and processing data) will be assessed in terms of coherence with risk analysis logic. - A questionnaire aimed at the clearance officers will be conducted to examine their assessments and considerations regarding the efficiency of current risk analysis system. - Gap and Needs analysis of the Risk Management System of MoCT on data analysis, targeting, profiling will be prepared. Activity 2 – Training - 1 study visit and 3 internships will be arranged to see how an EU member state’s practices on data mining and targeting via scoring are carried out. - Selected staff of MoCT Risk Management Unit will be trained on data mining and targeting via scoring. - 4 training workshops on the links between targeting results and feedback mechanism will be arranged with the inclusion of clearance officers and operational staff in the prominent cities such as; Ankara, İstanbul, İzmir and Mersin. | Twinning Light Contract |  |  |  |