Annex 1.	Logical Framework Matrix for “Enhancing the capacities for disaster risks reduction and for national crises management including the coordination of international response in Jordan” Project

| Overall objective | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| --- | --- | --- | --- |
| To support the effective and efficient management of large-scale disasters and national crises, by integrating and coordinating all the national efforts made to maintain a secure and stable environment toward a resilient society | Availability of a national platform concerned in disaster and crises management. | EC Regular Report on progress by Jordan in implementation of the ENP Action Plan priorities (and National Indicative Programmes beyond 2016). |  |
| Project purpose | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| To strengthen the national capabilities in assessing, planning and coordinating through training and qualifying all emergency responders' staffs of the respective institutions involved in dealing with crises and disasters, in order to achieve their missions in a coordinated and integrated manner | Availability of trained and qualified officers in the national institutions. Implementation of sustained capacity building programs in disaster risks reduction and management by the members of High Council of Civil Defence. | EC Regular Report on progress by Jordan in implementation of the Action Plan priorities (and National Indicative Programmes beyond 2016). Twinning project review mission report. | Availability of realistic plans for managing crises and disasters in Jordan and being enforced by concerned national institutions. |
| Results | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| Result 1: Strengthening the emergency management and governance in the country, on the basis of legal and strategic provisions in force and past capacity building programmes - Improved consistency of the legal and strategic framework as is. - The core characteristics of emergency management are assessed and are systematised vis-à-vis the findings and recommendations of past, on-going and future capacity building programmes | - Definition of the legal scope of emergency management under the umbrella of the JCD taking into account the mandate and competencies of the organisations in Jordan - Definition of the phases of emergency management - Definition of the levels of emergencies and assessing the principle and degree of subsidiarity - Definition of the individuals and organisations mandated to liaise with international partners in the area of civilian disaster response and in particular with the European Union - Inventory of past, on-going and planned capacity building initiatives since 2010 produced. - Inventory of main findings and recommendations of past/ongoing capacity building programmes produced including follow-up given or planned. - Monitoring system of ongoing national and international capacity building programs established. - Demonstrated coherence between the National Comprehensive Plan, the Strategic plan of the JCD and the operational and tactical agenda of the Disaster Department within the JCD including on-going and planned capacity building programs. - Baseline on the preparedness, continuity, sustainability of the individuals and organisations having a responsibility in the emergency management prepared. | - Interim Progress Reports. - Experts’ Mission Reports. - JCD internal reports - Training evaluation reports. - Seminars evaluation reports. | - Effective communication and active participation of all stakeholders throughout the duration of the project. |
| Result 2: Enhancing Disaster Risk Reduction (DRR) and Disaster Risk Management (DRM) in the risks of earthquakes, floods, drought, hazards material (NBC) and landslides - The capacity of concerned national institutions is strengthened through Train the Trainers and a first nationwide top exercise - The national efforts for handling disaster and emergency cases are formalized - public awareness toward disaster and emergency response is increased | - Training needs assessment - Design and develop trainings, also in a e-learning format - Definition of the minimal criteria for certification of the trained persons - Development of a database of ToT participants - Development of a database of certified personnel - Implementation of The National Comprehensive Plan for Countering Emergencies & Disasters assessed, definition of its weaknesses and formulation of proposals for corrective actions. - Updating the national plan as well as revising the JCD Strategic Plan - Drafting of the missing Standard Operating Procedures (SOPs) and Service Level Agreements in the appropriate executive or legal format based on the duties, and responsibilities of each of the concerned sectors and stakeholders at all levels to ensure disaster risk reduction and management in the concerned areas - Establishment of the overall purpose, objectives and outcomes of the campaigns. - Collecting relevant information needed to understand how to reach the purpose, objectives and outcomes of the campaigns - Definition of the Audiences, key messages and communication tools - Implementation of a nationwide campaign, its evaluation and lessons learned |  |  |
| Result 3: Strengthened coordination of the reception of international relief assistance during disaster and emergency cases . - a clear operational plan to receive and to coordinate the international relief assistance is drafted and ready for approval . - Elaborating lessons learned from the analysis of operational mechanism in European countries in the field of international relief assistance when a disaster occurs . | - Assessing the awareness of the existence of international coordination mechanism (UN; AIAE; etc) and the knowledge of the codes of conducts for International Disaster Relief operations - Identify the domain in which international relief and assistance are a priority - Define, and prepare for adoption national procedure, SOP's and SLA's for the acceptance and entry of international relief assistance in the sovereign Hashemite Kingdom of Jordan. - Draft model Joint National Memorandum of Understanding aiming at facilitating entry, distribution and dispatching of international relief assistance. - Establishment of a network for exchange of expertise in the region ( South-South cooperation) - Building an analytical and operational relation with the EU Emergency Response Coordination Centre through the Common Emergency Communication and Information System (CECIS) - Memorandum of Understanding between Jordan and the European Civil Protection mechanism ready for approval. |  |  |
| Activities |  |  |  |
| MS to develop activities which are needed in order to achieve the results |  |  |  |