Annex 1.	Logical Framework Matrix for Strengthening Central Bank of Jordan capacity for maintaining financial stability

| Overall objective | Objectively Verifiable Indicators | Sources of Verification |
| --- | --- | --- |
| To support Jordan in enhancing its standards for maintaining financial stability, by strengthening the capacities of Central Bank of Jordan through Financial Stability Department. | Positive EC opinion on the progress made in the financial stability area. | EC Regular Report on progress by Jordan in implementation of the macro-prudential policy. |
| Project purpose | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| To develop a comprehensive macro-prudential framework covering all aspects of financial stability in accordance with the European Union standards and best practices. | A macro-prudential framework in place. | - CBJ internal reports. - Project Progress Reports - Twinning project review mission report. | - Government of Jordan continues to support reforms in the financial system and economic system as a whole. - Sufficient Human Resources Provided. |
| Mandatory Results (Components) | Objectively Verifiable Indicators | Sources of Verification | Assumptions |
| Result 1: Development and implementation of a Macro-prudential framework. - Adopting and implementing a macro-prudential policy. - Identifying and assessing systemic risks at the macro level: excessive credit growth, financial sector exposure to bubbles asset, high exposure of over indebted household sector, high exposure to government debt, reliance on non-stable funding sources. In addition to developing macro-prudential tools to mitigate them. - Identifying a mechanism to activate macro prudential policy instruments and define the right tools and the right time to activate them to dampen the systemic risks. - Reviewing and developing the existing D-SIBs methodology and analyzing the contagion risks in the financial system. - Reviewing and Developing the existing Financial Stability Report Methodology. - Reviewing and developing the existing Early Warning System - Specialized training for FSD staff in the area of the financial stability and macro-prudential field is ensured in accordance with the European Union standards. - Training of Trainers in financial stability and macro-prudential field. - Assessing the sufficiency of the existing database. - Proposing any amendments to the existing databases. Result 2: Development and improvement of the existing Stress Testing methodologies. - Reviewing and developing the existing methodologies for the Solvency Stress Testing. - Reviewing and developing the existing methodologies for the Liquidity Stress Testing. - Developing methodologies of Reverse Stress Testing for Domestic Systemically Important Banks (D-SIBs). Result 3: Crisis Management Manual. - Reviewing and developing the existing crisis management manual. | - Ratios, indicators and tools for macro-prudential policy are identified. - Macro-prudential policy in place. - Training programme including curricula, methodology and training materials on crisis management manual developed. - Methodology of early warning system and stress testing are developed and enhanced. | - CBJ internal reports. - Projects Quarterly Reports. - Annual Reports Relevant International organizations Assessment Reports (i.e.IMF.) | Effective communication and active participation of all stakeholders throughout the duration of the project. |
| Activities MS to develop activities which are needed in order to achieve the results |  |  |  |