## Slide 1: Twinning Reform 2017 - New vs Old
Twinning Team
20 September, 2017

## Slide 2: Synoptical New Manual vs old Manual

## Slide 3: Synoptical new Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Needs analysis | Beneficiary, EUD, PAO (i.e IPA unit in Line ministries) | Programming phase (PP) | Beneficiary, EUD, PAO (i.e IPA unit in Line ministries) | Programming phase (PP)
Drafting of the « Twinning fiche » | Beneficiary, EUD, PAO, private experts | PP - Depends on nature and complexity | Beneficiary, EUD, PAO, private experts | PP - Depends on nature and complexity
Final fiche sent to HQs (Brussels) for Assessment | From EUD to DG NEAR Unit C3, Line DGs, CoTE | Only when sufficient quality | From EUD to DG NEAR Unit C3, Line DGs, CoTE for ENI | After ex-ante approval by CFCD/ EUD
Opinion on the fiche | DG NEAR Unit C3 to EUD | 2 weeks | n/a for IPA, DG NEAR Unit C3 to EUD for ENI | n/a for IPA, 2 weeks for ENI
Publication of the fiche | EUD - EuropeAid website | Asap after possible revisions | Standard TW -DG NEAR Unit C3 for IPA TWL published by EUD for IPA EUD for ENI | Asap after possible revisions following comments by DG NEAR

## Slide 4: Synoptical new Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Circulation of the "Twinning fiche" | Contracting Authority to MS NCPs | Same day after Publication | Standard TW -DG NEAR Unit C3, TWL circulated by EUD for IPA Contracting Authority to MS NCPs for ENI | 
Proposals | Member States | TW 8 weeks TWL 6 weeks | Member States | TW 8 weeks TWL 6 weeks
Evaluation of written proposals All participants shall sign Declaration of impartiality (template available annex C18) | BC by consensus of EUD | 2 weeks | BC representatives (3-4 persons, members of the selection panel); EUD/ CFCD observers Declaration signed (PRAG template used) | before the selection meeting

## Slide 5: Synoptical New Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Selection meeting 45 min for presentation of MS proposal; 30 min for Q&A | Organised at CA | 2 weeks | Organised at EUD, Chaired by HoC; 30 min for presentation of MS proposal; 30 min for Q&A | 2 weeks after the deadline for submission of proposals
Selection report | BC by consensus | Immediately after the selection meeting | BC representatives (3-4 persons, members of the selection panel); EUD/ CFCD observers; | Decision taken Immediately after the selection meeting; Selection report submitted to EUD in 2 weeks
Notification of result | Contracting Authority | 2 weeks | Contracting Authority | 3 weeks after the selection meeting
Preparation of the contract file, filling the templates listed in 3.1.1. No preparatory period= no preparatory costs before the signature of the contract | Contracting Authority | In max 12 weeks | BC Partners (commented by CFCD, EUD) | In max 4 months after the notification of the results the final draft should be sent to STC, otherwise the preparatory costs are not eligible

## Slide 6: Synoptical New Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Secondment of the RTA – Starting the implementation of the project | CA and MS | Max 12 weeks – after the notification of result | MS | Max 1 month after the notification letter for the signature of the contract
Drafting of initial work plan | RTA/MS PLs/CLs/staff | 4/6 weeks |  | 
First steering Committee | RTA/MSPLs | 2 weeks |  | 4 months after the notification of the Contract signature
Start of activities | RTA | 4 weeks | RTA | Coincides with the arrival of the RTA

## Slide 7: Synoptical New Manual vs old Manual
New Twinning Manual, 1st July 2017 |  |  | Twinning Manual 2012, revision 2013-14 | 
Activity | Actors | Timeline | Actors | Timeline
Secondment of the RTA – Starting the implementation of the project | CA and MS | Max 12 weeks – after the notification of result | MS, CA | Max 1 month after the notification letter for the signature of the contract
Drafting of initial work plan | RTA/MS PLs/CLs/staff | 4/6 weeks |  | RTA and MS PL negotiation of the contract : 4 months IPA and 5 months ENI.
First steering Committee | RTA/MS PLs | 2 weeks |  | 4 months after the notification of the Contract signature
Start of activities | RTA | 4 weeks | RTA | Coincides with the arrival of the RTA

## Slide 8: Synoptical New Manual vs old Manual
New Twinning Manual, 1st July 2017 | Twinning Manual 2012, revision 2013-14
FINANCIALS | FINANCIALS
One flat daily allowance set at 350€ for all expert categories Recently retired experts (less than three years) before the call for proposal could be engaged in line with the specific requirements | Different experts fees 250/350/450 €for the STEs from MB; Civil servants receive max 250€ Recently retired experts (less than two years) before the call for proposal could be engaged n line with specific requirements Art.5.4.5
Twinning Project Support Costs and setting the flat rate at 136% | Twinning Management costs 150%
Daily subsistence allowance for RTA = 75% of the per-diem for the BC | Daily subsistence allowance for RTA = 50% of the per-diem for the BC
Communication costs 3 % of the Twinning Budget | Max 5000 €for project to 1.000.000€ Max 10000 EUR for project above 1.000.000 €
Three Budget Headings 1. RTA and RTA related costs 2. Horisontal Cost items 3. Mandatory results | Not precise instructions exist
Two budget-lines Budget line Indirect costs fixed at 6% of Σ headings 1-3 (DC) Budget line Reserves (sustainability) fixed at 2,5% of Σ headings 1-3 (DC) | n/a Contingency 2.5 %
Training RTA counterpart and BC PL: Can participate in HQ training. Potential un-clarity under | BC Pl OR RTA counterpart could attend RTA training in Brussels, together with the RTA

## Slide 9: Synoptical New Manual vs old Manual
New Twinning Manual, 1st July 2017 | Twinning Manual 2012, revision 2013-14
FINANCIALS | FINANCIALS
- Number of RTA assignments (from months to maximum duration of projects etc) (4.1.6.7) max two consecutive assignments | Max four assignments art. 2.2.2(at least 12 months, max 36 months in one BC)
- Replacement of RTA assistants (from redo to use ranking) (4.1.6.10) | 
- EU MS component leaders designation (from "if relevant" to "obliged") | Not obligatory under the old Twinning manual; EUD always advises the Ms Partner to identify MS./BC Component Leaders in the drafting stage of the Contract
- Curricula to be inserted in the proposal: PL, RTA and CL (2.2) not any more STEs CVs) | PL, RTA, STEs, CL
BA staff available to support the RTA until the RTA assistant can be selected | Similar approach, but not obligatory in line with the TM
Initial work plan (6 months rolling plan for activities): prepared in 4-6 weeks following signature of the contract and arrival of the RTA including Communication and Visibility plan. Work plan to define how much time will be devoted to each activity of the project including STE CVs updates prepared by RTA and RTA counterpart, agreed and signed by two PLs discussed by SCs accepted by all contracting parties (max 14 days after SC) to accelerate the preparation EU MS PL's and/or Component Leaders and/or one support staff | For IPA: OSL 1 prepared together with the Draft Twinning contract, but not subject of approval by the STC; OSL 1 signed together with the twinning contract by the two PLs. Subsequent OSL prepared every three months, approved by the STC ( covering each time period of 6 months ( OSL1 (1-6m; OSL2 4-9 m;OSL3 14m) For ENI:: full contract and workplan prepared before the signature of the contract.

## Slide 10: Synoptical New Manual vs old Manual
New Twinning Manual, 1st July 2017 | Twinning Manual 2012, revision 2013-14
FINANCIALS | FINANCIALS
Reports – from detailed report every 3 months to possibility to only submit the extensive narrative report part every 6 months* and report to possibly include elements of wider reform context. (5.5.2.2) * In such case the rolling work plan update will still be discussed and so will the financial report and budget update every 3 months. | IQR submitted every three months/approved and discussed at the STC meetings
Bi-annual narrative report (extensive narrative report) | n/a
Costs for the private sector input, max 5000 €per component | 10000€per activity
Supply of equipment (exceptionally and dully justified) max 5000 € per project | 5000 €per project
Changes to the Twinning Contract: Addendum for significant changes and reallocation beyond 25% of the budget headings; Rolling work plan SL | Changes to the Twinning Contract: Addendum for significant changes and reallocations beyond 25% of the ttl budget; OSL SL