Annex 1.  Logical framework matrix in standard form

| Further enhancing the functioning of Montenegrin AFCOS system with the aim of efficient protection of EU financial interests Main Beneficiary: The Ministry of Finance of Montenegro, Independent Service for Combating Irregularities and Fraud (AFCOS office) |  | Total budget : 200,000 EUR | IPA financing: 100% National co-financing: 0% |
| --- | --- | --- | --- |
| OVERALL OBJECTIVE | OBJECTIVELY VERIFIABLE INDICATORS | SOURCES OF VERIFICATION |  |
| To improve the capacities of the Montenegrin administration to protect EU financial interests. | AFCOS system enhanced and fully adjusted for efficient protection of the EU financial interests with regard the widening of competences and roles of the AFCOS system bodies. | EU Monitoring report for Chapter 32 -Financial control OLAF's reports and assessments of functioning of AFCOS in Montenegro. Report on implementation of objectives and measures within National Anti-fraud Strategy for the Protection of EU Financial Interests and Action Plan following the Strategy Final Twinning light Report |  |
| SPECIFIC OBJECTIVE | OBJECTIVELY VERIFIABLE INDICATORS | SOURCES OF VERIFICATION | ASSUMPTIONS |
| To strengthen the role and capacities of the Montenegrin Anti-Fraud Coordination Service (AFCOS) to efficient coordinate the legislative, administrative and operational activities of its members network. | Legislative and operational framework ensures the efficient functioning of AFCOS system bodies regarding their wider competences and roles - All necessary mechanisms and tools for efficient cooperation and coordination in the field of protection of EU financial interests, between the competent bodies developed Capacities of employees within the Montenegrin AFCOS system strengthened | Report on implementation of objectives and measures within National Anti Fraud Strategy for the Protection of EU Financial Interests and Action Plan following the Strategy Final Twinning light Report Documentation produced under the project | Adopted legislation and procedures in the field of protection of EU’s financial interests are being followed Full commitment of the parties involved Good communication among bodies in AFCOS system |
| RESULTS | OBJECTIVELY VERIFIABLE INDICATORS | SOURCES OF VERIFICATION | ASSUMPTIONS |
| Component 1 1.1. Institutional set up and legal framework of the AFCOS system analyzed and recommendations for improvement prepared. 1.2. Decision on establishing the AFCOS Network amended and operational/co-operation protocols drafted; 1.3. New National Anti-fraud Strategy in the field of protection of EU financial interests and its Action Plan drafted for period 2018-2020; 1.4. Guidelines for managing irregularities and fraud developed; 1.5. Risk Assessment Methodology regarding irregularities and fraud developed; 1.6. Handbook about functioning of AFCOS in Montenegro developed. Component 2: 2.1. Representatives of the bodies in IPA structure, representatives of the bodies responsible for suppression of fraud, corruption and any other type of irregularity within the system and employees of the AFCOS office trained on new National Anti-fraud Strategy, on Law and procedures to manage irregularities and frauds; 2.2. Information materials for raising public awareness on anti-fraud issues prepared in electronic form; 2.3. Seminar for raising public awareness implemented | Analysis of the institutional set up and legal framework conducted and corresponding report with recommendations The amended Decision on Establishing the AFCOS Network The operational/co-operation protocol New National Anti-fraud Strategy and Action Plan Guidelines for managing irregularities and fraud Risk Assessment Methodology regarding irregularities and fraud Handbook about functioning AFCOS in Montenegro Training needs analysis (TNA) of employees and TNA report Training materials Seminar prepared and conducted Study visit to EU Member State conducted and organized Information materials for raising public awareness on anti-fraud in electronic form Seminar for raising public awareness | Documentation produced under the project Twinning Light report Documentation produced under the project Twinning Light report Number of participants in trainings Training assessment | Adopted legislation and procedures in the field of protection of EU’s financial interests are being followed Full commitment of the parties involved Good communication among bodies in AFCOS system Good communication and cooperation between Project Leader and STE Staff of the project beneficiary is fully available for project implementation |
| ACTIVITIES | MEANS | OVERALL COST | ASSUMPTIONS |
| Component 1 1.1. Support in the analysis of the institutional set up and legal framework in Montenegro (laws, regulations, strategic documents, methodology, decisions, procedures, etc.) in the context of functioning of the AFCOS system, in order to identify shortcomings and deficiencies, and prepare a report with recommendations for improvements; 1.2. Support in drafting Amendments to the decision on the establishment of the AFCOS Network and operational/co-operation protocols between competent institutions (e.g. State Attorney, European Anti-Fraud Office) and the Ministry of Finance 1.3. Support in drafting the new National Anti-fraud Strategy in the field of protection of EU financial interests for the period 2018–2020, including a detailed Action Plan. The results from the implementation of the CIF strategy 2015-2017 should be taken into consideration. 1.4. Support in drafting guidelines for managing irregularities and fraud that will be used by the AFCOS system bodies. 1.5. Support in developing a Risk Assessment Methodology regarding irregularities and fraud 1.6 Support in drafting a Handbook about functioning of AFCOS in Montenegro Component 2 2.1. Conducting training needs analysis (TNA) of employees of AFCOS system bodies related to the protection of EU financial interests regarding managing irregularities and fraud and preparing TNA report. 2.2. Preparing training materials (PowerPoint presentations, exercises, case studies, workshop scenarios, etc.) for seminars organized for AFCOS system bodies on the following topics: (i) New National Anti-fraud Strategy in the field of protection of EU financial interests; (ii) Procedures for managing irregularities and fraud. 2.3. Preparing and conducting seminars based on the outputs of the Activity 2.1.1 and 2.1.2. The seminars will be implemented through several modules. The target groups for will be representatives of the bodies in IPA structure, representatives of the bodies responsible for suppression of fraud, corruption and any other type of irregularity within the system and employees of the AFCOS office (AFCOS network). 2.4. Organizing and conducting one study visit to an EU Member State in duration of 3 days for 8 AFCOS network representatives (2 representatives of AFCOS office, 3 representatives of IPA structure and 3 representatives of AFCOS Network) and preparation of a report on the findings of the study visit. 2.5. Preparing information materials (leaflets and brochures) in electronic form2 for raising public awareness on anti-fraud. 2.6. Preparing and implementing at least 1 seminar for general public and media presenting the new National Anti-fraud Strategy and the amended Decision on establishing the AFCOS Network. | Twinning Contract | 200,000 EUR | Adopted legislation and procedures in the field of protection of EU’s financial interests are being followed Full commitment of the parties involved Good communication among bodies in AFCOS system Good communication and cooperation between Project Leader and Short term experts Staff of the project beneficiary is fully available for project implementation |

Annex 2. List of relevant Laws and Regulations (optional)

- Criminal Code, first adopted on 17 December 2003 and last amended on 30 July 2013 (Official Gazette of the Republic of Montenegro, No 70/2003, 13/2004, 47/2006 and Official Gazette of Montenegro, No 40/2008, 25/2010, 32/2011 and 40/2013);

- Criminal Procedure Code, first adopted on 27 July 2009 and last amended on 27 July 2010 (Official Gazette of Montenegro, No 57/2009 and 49/2010);

- Law on Liability of Legal Entities for Criminal Offences, first adopted on 27 December 2007 and last amended on 29 May 2012 (Official Gazette of the Republic of Montenegro, No 2/2007, 13/2007 and 30/2012),

- Law on International Legal Assistance in Criminal Matters, first adopted on 26 December 2007 and last amended on 9 July 2013 (Official Gazette of Montenegro, No 4/2008 and 36/2013).

- The Law on the Central Bank of Montenegro (Official Gazette of Montenegro, No 40/10; 46/10; 6/13), adopted by the Parliament of Montenegro on 16 July 2010

- Law on the State Audit Institution (Official Gazette of Montenegro 28/04, 27/06, 78/06, 17/07, 73/10, 40/11)

- Law on the Public Internal Financial Control System (Official Gazette of Montenegro 73/08, 20/11 and 30/12).

- Decision on Establishing Coordination Body for Monitoring and Managing Policy for Prevention and Suppression of Irregularities for Protection of the European Union Financial Interests (AFCOS network) (Official gazette of MN, No 60/2013), based on the Decree of the Government of Montenegro (Official gazette of MN, No 80/08).

- Framework Agreement between the European Commission and the Government of Montenegro signed on 15 November 2007 (Official Gazette of Montenegro, No 01/08)

- Framework Agreement between the European Commission and the Government of Montenegro signed on 26 February 2015 (Official Gazette of Montenegro, No 05/15)

- Decree on  organization of the indirect management of the implementation of EU financial assistance under the Instrument for Pre-Accession Assistance (IPA II), (Official Gazette of Montenegro 50/15)

- Decree on  organization of the indirect management of the implementation of EU financial assistance under the Instrument for Pre-Accession Assistance (IPA I), (Official Gazette of Montenegro 33/11;5/14)

Annex 3. Reference to relevant Government Strategic plans and studies (optional)

- Reference to Negotiation Chapter 32 – Financial Control

- Montenegro Program of Accession to the EU 2017-2018

- Indicative Strategy Paper for Montenegro 2014-2020

- Montenegro Public administration Reform Strategy 2016-2020

- Public finance Management Reform 2016-2020

- Strategy  for combating irregularities and fraud for the period 2015-2017 and the accompanying Action Plan

- Strategy for further development of public internal financial control system in Montenegro for the period 2013 - 2017