## Twinning Light Fiche Project title: Capacities development for the Anti-Fraud Coordination Service (AFCOS) Beneficiary administration: AFCOS and AFCOS Network Twinning Reference: MN 15 IPA OT 03 18 TWL Publication notice reference: EUROPEAID/159480/DD/ACT/ME

EU funded project TWINNING INSTRUMENT

1.	Basic Information

1.1 	Programme:  		Annual Action Programme for Montenegro for the year 2015

(Direct Management)

For British applicants: Please be aware that eligibility criteria must be complied with for the entire duration of the grant. If the United Kingdom withdraws from the EU during the grant period without concluding an agreement with the EU ensuring in particular that British applicants continue to be eligible, you will cease to receive EU funding (while continuing, where possible, to participate) or be required to leave the project on the basis of Article 12.2 of the General Conditions to the grant agreement.

1.2      Twinning Sector: 	Democracy and Governance

1.3      EU funded budget: 	EUR 200,000

2.	Objectives

2.1      Overall Objective:

To improve the capacities of the Montenegrin administration to protect EU financial interests.

2.2      Specific objective:

To strengthen the role and capacities of the Montenegrin Anti-Fraud Coordination Service (AFCOS) to efficient coordinate the legislative, administrative and operational activities of its network members.

2.3. The elements targeted in strategic documents National Development Plan/Cooperation agreement/Association Agreement/Sector reform strategy and related Action Plans:

This Twinning project will contribute to the implementation of the activities envisaged by the Montenegrin Programme for Accession 2017-2018 and, in particular, by Chapter 32 (Financial Control). The main objectives of the latter are: financial stability of the Member States, prevention of misuse of financial means, contribution to a more efficient, successful, and accountable spending, which offers an important mechanism for fighting corruption.

Also, Article 28 of the Framework Agreement between the European Commission and the Government of Montenegro signed on 15 November 2007 as well as Article 50 and 51 Framework Agreement between the European Commission and the Government of Montenegro signed on 26 February 2015, outline the tasks of AFCOS underline the need for establishing control and reporting mechanisms regarding irregularities in IPA beneficiary countries.

The Indicative Strategy Paper for Montenegro (2014-2020) outlines the importance of improving the quality of financial management and control and prevention of fraud and irregularities. This is part of a much wider public administration reform (PAR Strategy 2016-2018), which represents one of the cornerstones of Montenegro’s EU integration process.

Within this framework, the activities and the results of this Twinning Light Project will be complementary to the ones included in the PAR Action Plan 2018-2020.

3.	Description

3.1      Background and justification:

Protection of the EU financial interests implies the ability of a candidate country to apply the relevant acquis communautaire before its EU accession. With regard to that, a candidate country is expected to set up an operationally independent service for co-ordination with the European Anti-Fraud Office (OLAF) and to ensure the development of administrative capacities necessary for the application of the acquis communautaire, including the capacity of  legislative and judicial bodies to respond to cases where the EU financial interests are jeopardized.

In that regard, the Government of Montenegro adopted the Decision on Establishing a Coordinating Body for Monitoring and Managing Policy for Prevention and Suppression of Irregularities for protection of the European Union Financial Interests (AFCOS network). The service responsible for coordination of legislative, administrative and operational activities of the members of the AFCOS network is the Department for Combating Irregularities and Fraud (AFCOS office). It has been established within the Ministry of Finance and it is operationally independent from all other bodies of the AFCOS network.

In 2015, the Government of Montenegro adopted a Strategy for Combating Irregularities and Fraud for the period 2015-2017 (hereinafter referred to as the CIF Strategy), together with   the Action Plan. Most of the measures have been already implemented and the relevant bodies are regularly reporting to AFCOS office on the implementation of the remaining measures. A new CIF Strategy and a new Action Plan for the period 2018-2020 for the further improvement of the management of irregularities and frauds (prevention, detection, treatment, reporting and follow up of irregularities and fraud) still need to be drafted.

The AFCOS office, as the coordinating body of irregularities and frauds activities in Montenegro, will be the main beneficiary of this Twinning Light project. The project aims, inter alia, to strengthen the coordination role of the AFCOS office and to further enhance the cooperation between all bodies of the AFCOS network. This will also result in improved operational capacities within all structures of the AFCOS network in Montenegro. Furthermore, this will lead to the effective and efficient functioning of the AFCOS system and efficient protection of EU financial interests in Montenegro.

Other beneficiaries of the project are the members of the AFCOS network:

- IPA structures – authorities and institutions that manage and use the EU pre-accession assistance funds. Operating structures for each of the five components of IPA programme have been established and are responsible for programming, implementing and monitoring of use of the EU funds.

- Bodies responsible for suppression of fraud, corruption and any other type of irregularity within the system.

This Twinning project will have to take into consideration the existing domestic legal framework as outlined by the following laws:

- Decision on Establishing Coordination Body for Monitoring and Managing Policy for Prevention and Suppression of Irregularities for Protection of the European Union Financial Interests (AFCOS network), Official Gazette of Montenegro, 60/2013

- Decree of the Government of Montenegro, Official Gazette of Montenegro, 80/08

3.2       Ongoing reforms:

There are no ongoing specific reforms in the area of the protection of the EU financial interests.

This project is part of the public administration reform (PAR) Strategy 2016-2020. The objective of the reform is to contribute to an efficient and service-oriented public administration. Public Financial Management is part of the PAR reform and has an ad hoc PFM Strategy 2016-2020 which targets, among others, improvements in the internal audit and financial control system.

3.3       Linked activities:

SIGMA has supported the Department for Combating Irregularities and Fraud to draft the first Anti-Fraud Strategy and Action plan for the period 2015-2017.

In cooperation with the OLAF and with the support of TAIEX instrument, the Department for Combating Irregularities and Fraud organized the following activities:

- Study visit to Malta, ("Adoption of strategic document - mechanism for protection of EU financial interests", from 24-28 November 2014), Croatia ("Methodology preparations for Risk Assessment", from 5-9 December 2016), France ("Study Visit on Anti-Fraud Policy for EU Funds", from 19-21 December 2016), Belgium (“Study visit of Montenegrin authorities on the field of using the Irregularity Management System”, from 19-20 January 2017).

- Training on the Irregularity management system in the former Yugoslav Republic of Macedonia ("Country Workshop on Irregularity Management System", from 27-28 October  2016) and Croatian expert mission to Montenegro ("Enhancing protection of financial interests", from 3-7 July 2017).

Regional AFCOS seminar on "How to detect and report fraud" was held in Budva, Montenegro from 7-9 June 2017.

In cooperation with the Human Resources Management Authority several trainings were organized on Protection of financial interests of EU / Combating irregularities and fraud.

3.4 List of applicable Union acquis/standards:

1.	Council Regulation (EC) No 1085/2006 of 17 July 2006 establishing an Instrument for Pre-Accession Assistance (IPA);

2.	Regulation (EC) No 540/2010 of the European Parliament and of the Council of 16 June 2010  amending Council Regulation (EC) No 1085/2006 establishing an Instrument for Pre-Accession Assistance (IPA);

3.	Council Regulation (EC) No 718/2007 of 12 June 2007 implementing Council Regulation (EC) No 1085/2006 establishing an instrument for pre-accession assistance (IPA);

4.	Commission Regulation (EU) No 80/2010 of 28 January 2010 amending Regulation (EC) No 718/2007 implementing Council Regulation (EC) No 1085/2006 establishing an instrument for pre-accession assistance (IPA);

5.	Commission Implementing Regulation (EU) No 1292/2011 of 9 December 2011 amending Regulation (EC) No 718/2007 implementing Council Regulation (EC) No 1085/2006 establishing an instrument for pre–accession assistance (IPA);

6.	Council Regulation (EC, EURATOM) No 2988/95 of 18 December 1995 on the protection of the European Communities financial interests;

7.	Regulation (EU, Euratom) No 883/2013 of the European Parliament and of the Council of 11 September 2013 concerning investigations conducted by the European Anti-Fraud Office (OLAF) and repealing Regulation (EC) No 1073/1999 of the European Parliament and of the Council and Council Regulation (Euratom) No 1074/1999;

8.	Council Regulation (Euratom, EC) No 2185/96 of 11 November 1996 concerning on-the-spot checks and inspections carried out by the Commission in order to protect the European Communities' financial interests against fraud and other irregularities;

9.	Regulation (EC) No 45/2001 of the European Parliament and of the Council of 18 December 2000 on the protection of individuals with regard to the processing of personal data by the Community institutions and bodies and on the free movement of such data;

10.	Regulation (eu) no 236/2014 of the European Parliament and of the Council of 11 March 2014, laying down common rules and procedures for the implementation of the Union's instruments for financing external actions

11.	Regulation (eu) no 231/2014 of the European Parliament and of the Council of 11 March 2014 establishing an Instrument for Pre-accession Assistance (IPA II)

12.	Commission Implementing Regulation (EU) No 447/2014 of 2 May 2014 on the specific rules for implementing Regulation (EU) No 231/2014 of the European Parliament and of the Council establishing an Instrument for Pre-accession assistance (IPA II)

13.	Regulation (EU, Euratom) No 966/2012 of the European Parliament and of the Council of 25 October 2012 on the financial rules applicable to the general budget of the Union and repealing Council Regulation (EC, Euratom) No 1605/2002

14.	Commission delegated regulation (EU) No 1268/2012  of 29 October 2012 on the rules of application of Regulation (EU, Euratom) No 966/2012 of the European Parliament and of the Council on the financial rules applicable to the general budget of the Union

3.5	Results per component:

Component 1: 	Strengthening the institutional set up and the legal framework of AFCOS and AFCOS network

1.1. 	Institutional set up and legal framework of the AFCOS system analyzed and recommendations for improvement prepared.

1.2. 	Decision on establishing the AFCOS Network amended and operational/co-operation protocols drafted;

1.3. 	New National Anti-fraud Strategy in the field of protection of EU financial interests and its Action Plan drafted for period 2018-2020;

1.4. 	Guidelines for public officials on managing irregularities and fraud developed (including the prevention, detection, reporting and follow-up of irregularities/fraud). This should be done in alignment with the development of procedures for managing irregularities and fraud affecting national funds;

1.5. 	Available Risk Assessment Methodologies (e.g. in the area of national funds) regarding irregularities and fraud analyzed, adapted (if possible) or developed; risk assessment methodology disseminated among actors involved in the management and control of EU funds and its use encouraged, including in the preparation of an updated national anti-fraud strategy.

1.6. 	Handbook about functioning of AFCOS and the AFCOS Network in Montenegro developed.

Component 2: 	Increasing capacities and public awareness on anti-fraud issues

2.1. 	Representatives of the bodies of  the IPA structures, representatives of the bodies responsible for suppression of fraud, corruption and any other type of irregularity within the system and employees of the AFCOS office trained on new National Anti-fraud Strategy, on Law and procedures to manage irregularities and frauds;

2.2. 	Information materials for raising public awareness on anti-fraud issues prepared in electronic form;

2.3.	Seminar for raising public awareness implemented.

3.6       Expected activities:

Component 1: 	Strengthening the institutional set up and the legal framework of AFCOS and AFCOS network

1.1. 	Support in the analysis of the institutional set up and legal framework in Montenegro (laws, regulations, strategic documents, methodology, decisions, procedures, etc.) in the context of functioning of the AFCOS system, in order to identify shortcomings and deficiencies, and prepare a report with recommendations for improvements;

1.2. 	Support in drafting Amendments to the decision on the establishment of the AFCOS Network and operational/co-operation protocols between competent institutions;

1.3.    Support in drafting the new National Anti-fraud Strategy in the field of protection of EU financial interests for the period 2018–2020, including a detailed Action Plan. This should be based on the results of the implementation of the CIF strategy 2015-2017 as well as an updated fraud risk assessment;

1.4. 	Support in drafting guidelines for public officials on managing irregularities and fraud that will be used by all AFCOS system bodies. The guidelines will cover all aspects of the anti-fraud cycle (prevention, detection, reporting, investigation, recovery/sanctions) and will be linked to the national detection and reporting system;

1.5. 	Support in developing a Risk Assessment Methodology regarding irregularities and fraud which is line with the risk management methodology used for national funds;

1.6 	Support in drafting a Handbook about functioning of AFCOS and AFCOS Network in Montenegro.

Component 2: Increasing capacities and public awareness on anti-fraud issues

2.1. 	Training needs analysis of employees of the AFCOS network related to the protection of the EU financial interests regarding managing irregularities and fraud;

2.2.	Preparing training materials (PowerPoint presentations, exercises, case studies, workshop scenarios, etc.) for seminars organized for the AFCOS network bodies on, at least, the following topics:

- New National Anti-fraud Strategy in the field of protection of EU financial interests;

- Procedures for managing irregularities and fraud, including detection and reporting of irregularities/fraud;

- Cooperation with OLAF

The training materials will be printed by the beneficiary institution and distributed to the participants during the seminars.

2.3. 	Organization of seminars based on the outputs of the Activity 2.1. and 2.2. The seminars will be implemented through several modules. The target groups will be representatives of the bodies in IPA structures, representatives of the bodies responsible for suppression of fraud, corruption and any other type of irregularity within the system and employees of the AFCOS office (AFCOS Network);

2.4. 	Organization  of a study visit to an EU Member State of at least of 3 working days for 8 AFCOS network representatives (2 representatives of AFCOS office, 3 representatives of IPA structure and 3 representatives of AFCOS Network) and preparation of a report on the findings of the study visit. The objectives of the study visit are to exchange the know-how on prevention, detection, treatment, reporting and follow up of irregularities and fraud;

2.5. 	Preparation of information materials (leaflets and brochures) in electronic form for raising public awareness on anti-fraud. The materials will contain information about the new CIF Strategy and its Action plan, on the amended decision on establishing the AFCOS Network, drafted operational/co-operation protocols with competent bodies, etc.

2.6. 	Preparation and implementation of at least 1 seminar for general public and media presenting the new CIF Strategy and the amended decision on establishing the AFCOS Network.

Two visibility events will be organized during the implementation of the project; a kick-off meeting at the start of the implementation and the ceremony for the conclusion of the implementation of the project activities.

The MS State Partner Administration is welcome to suggest additional activities that would help in achieving the aforementioned specific objective.

3.7        Means/ Input from the MS State Partner Administration:

3.7.1      Profile and tasks of the Project Leader

Qualifications and skills:

- University degree or equivalent professional experience of 8 years

- Working level English language skills (oral and written)

- Good computer skills

- Good communication skills

- Presentation, communication and organizational skills

- Knowledge of Montenegrin is considered as an asset

General Professional experience

- At least 3 years of experience in implementing EU legislation on combating irregularities and fraud with purpose of protection of EU financial interests

- Experience in project management

Specific requirements:

- Experience in cooperation with OLAF

- Experience in drafting strategic documents in the field of protection of EU financial interests

Tasks of the Project Leader:

- Overall management and coordination of the project, in cooperation with the BC Project Leader

- Cooperation with the main beneficiary and representatives of bodies in the AFCOS system in undertaking all activities

- Undertaking all activities specified under the project and achieving the mandatory results

- Ensuring sound implementation of envisaged activities

- Providing professional advice to the main beneficiary and representatives of bodies in the AFCOS system during the project implementation period

- Organization of a study visit

- Ensuring backstopping and financial management of the project in MS

- Project reporting

3.5.2     Profile and tasks of the short-term experts

Qualifications and skills:

- University level education or equivalent professional experience of 8 years

- Computer literacy

- Working level of English language (oral and written)

- Presentation, communication and organizational skills

Specific requirements:

At least 3 years of experience in fields relevant to objectives and results of the project

Tasks of the Short-term experts:

- Provide practical expertise/advices and transfer knowledge to relevant staff for execution of all activities related to the results and objective required within the project;

- Preparing training materials, organizing trainings and workshops;

- Provision of practical support, advice, recommendations and reports as foreseen under the Project in close cooperation and coordination with the relevant institution;

- Participating in all relevant activities as determined during the implementation of the project.

One of the experts may act as the Project Leader responsible for general coordination.

4.        Budget

EUR 200,000

5.        Implementation Arrangements

5.1.     Implementing Agency responsible for tendering, contracting and accounting:

European Union Delegation to Montenegro

Mrs Eleonora Formagnana

Program Manager-Cooperation Section

Delegation of the European Union to Montenegro

Vuka Karadzica 12, 81000 Podgorica, Montenegro

Mobile phone: 00382 69 126 615

Office phone:00382 20 444 600

E mail address: Eleonora.formagnana@eeas.europa.eu

5.2      Institutional Framework

Beneficiaries of the project are institutions involved in the Montenegrin AFCOS network:

Ministry of Finance - Department for Combating Irregularities and Fraud (AFCOS office) is the main beneficiary administration of this Twinning light project. The AFCOS office has the coordinating role in the AFCOS network.

IPA structure - Appointed Irregularity Officers

Bodies within the AFCOS network

5.3      Counterparts in the beneficiary administration:

Contact person:

Ms Anja Pavličić

Advisor in Department for Combating irregularities and fraud /AFCOS office

Ministry of Finance

Stanka Dragojevica 2, 8100, Podgorica

Mobile phone: +382 67 506 765

Office phone: +382 20 224 480

E-mail address: anja.pavlicic@mif.gov.me

Project Leader counterpart:

Ms Nataša Kovačević

Head of Department for Combating irregularities and fraud /AFCOS office

Ministry of Finance

Stanka Dragojevica 2, 81000 Podgorica

6.      Duration of the project

6 months

7.      Sustainability

The project results will contribute to the consolidation of the AFCOS network and will be maintained as a permanent asset after the end of the project implementation, by contributing further to the efficient protection of EU financial interests. The development of a new strategy and action plan will undergo an impact assessment, an internal consultation involving all relevant bodies included in AFCOS network and an external stakeholders consultation, according to the country legislation

8.       Crosscutting issues

Equal participation of women and men will be secured during the implementation of the project.  Institutions benefiting from this Project are equal opportunity employers. Special attention to minorities and vulnerable groups will be an integral part of any activity. There will be regular monitoring to ensure these issues are given due prominence. The activities envisaged under the project should not negatively affect the environment. For this purpose, the production of printed material will be kept to the strictest minimum.

9.       Conditionality and sequencing

This project will contribute in setting up the strong AFCOS system and protection of the EU financial interests in general, which will lead to accomplishment of the benchmarks regarding Chapter 32 –Financial control and all requirements that IPA II regulations impose.

10.	Indicators for performance measurement

- Amendment to the decision on establishing the AFCOS Network submitted for adoption

- Operational cooperation among AFCOS members better defined

- National Anti-fraud Strategy ready for adoption

- Guidelines for managing irregularities and fraud available and in line with national procedures

- Risk Assessment Methodology available and in line with the methodology used for national funds

- Handbook on AFCOS available

- Capacities of AFCOS and AFCOS network increased

- Public awareness on AFCOS activities increased

11. 	Facilities available

The Beneficiary will provide the experts with the necessary working premises and all facilities for the implementation of the activities.

ANNEXES TO ACTION DOCUMENT

- Logical Framework Matrix

- SIGMA Monitoring Report 2017

- Strategy for Fight Against Fraud and Irregularity Management 2015-2017

- Decision on establishment of AFCOS

Institutions having their representatives in AFCOS network, in addition to representatives of IPA structure in National Fund and AFCOS office in the Ministry of Finance are: Ministry of Justice; Ministry of Interior; Police Administration; Public Procurement Administration; Tax Administration’ Customs Administration; State Audit Institution; Supreme State Prosecution; Directorate for Anti-Corruption Initiative; Administration for Inspection Affairs; Administration for Prevention of Money Laundering and Terrorist Financing.

The term "irregularity" - as defined in Article 51 (5)(b) of the IPA II Framework Agreement - also comprises cases of suspected or actual fraud: "irregularity means any infringement of a provision of applicable rules and contracts resulting from an act or an omission by an economic operator which has, or would have, the effect of prejudicing the general budget of the Union by charging an unjustified item of expenditure to the general budget". In other words, "fraud" and "suspected fraud" are subsets of the larger set of "irregularities". The main difference between fraud and a "simple" irregularity is the presence of intentional behavior.

The costs of printing the information materials, the purpose of which is related to the project’s visibility, is envisaged to be financed through the project’s visibility costs specified in the Twinning light contract budget.

Contracting authorities are invited to carefully consider the fact that no form of sub-contracting to the private sector is allowed, with the only exception of the hiring of translation and interpretation services, where necessary

Please see footnote no. 1.