| PROPOSAL OF THE ACTION PLAN 2018-2020 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Milestones (sub-activities) |  |  |  |  | Lead institution | Start date |  |  | Planned end date | Costs assessment |  |  | Source of financing | Indicator |  |
| 4.1. ORGANIZATION AND LIABILITY IN THE PUBLIC ADMINISTRATION SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 4.1.1. Improved control of legality and expediency of work of all authorities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.Prieparation of amendments to the Law on Public Administration aimed at setting up more efficient organization of the public administration system, by stipulation of clear criteria for the establishment and functioning of public administration authorities | a) Establish the inter-ministerial working group for the preparation of Draft Law b) Prepare the Draft Law c) Conduct the public hearing procedure on the Draft Law d) Prepare the Proposal for the Law based on the public hearing results |  |  |  |  | MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) | I quarter 2018 I quarter 2018 II quarter 2018 II quarter 2018 |  |  | I quarter 2018 I quarter 2018 II quarter 2018 II quarter 2018 | 18.000 € Funds not needed 7.000 € Funds not needed |  |  | Budget CG/SBS Budget CG/SBS | Working group established Draft Law prepared Public hearing report announced on MPA webpage Proposal for the Law prepared |  |
| 2. Change of the public administration organization on the basis of new solutions referred to in the Law on Public Administration | a) Prepare analysis on which administrative authorities should be independent and which should be reorganized as organizational units of line Ministries, in accordance with the laid down uniform rules for the establishment of public administration authorities b) Prepare the Proposal for the Decree on organization and method of work of public administration, based on the recommendations from the analysis |  |  |  |  | MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) | III quarter 2018 IV quarter 2018 |  |  | III quarter 2018 IV quarter 2018 | Funds not needed Funds not needed |  |  |  | Analysis prepared Proposal for the Decree prepared |  |
| 3. Build human resources capacities of the administrative inspectorate | a) Organize training for administrative inspectors in the area of their competencies b) Organize study tour to a relevant country |  |  |  |  | MPA(Section for Inspection Control),HRMA (Sector for training and human resource development) MPA(Section for Inspection Control) | I quarter 2018 I quarter 2019 |  |  | II quarter 2019 IV quarter 2019 | 19.440 € 24.000 € |  |  | Budget CG/SBS Budget CG/SBS | 8 administrative inspectors attended 3 trainings each Study tour organized |  |
| 4. Creating prerequisites for building the unique information system (UIS) of the Administration for Inspection Affairs (AIA) supporting the procedure of inspection control, monitoring and reporting on inspectorates’ work | a) Analysis of current status of information communication resource implemented in AIA which will be the basis for the preparation of a detailed plan of setting up a unique information system (UIS) b) I phase of implementation of UIS |  |  |  |  | UIP(Sector for the protection of market and economy, games of chance and public procurement) UIP(Sector for the protection of market and economy, games of chance and public procurement) | I quarter 2018 I quarter 2019 |  |  | IV quarter 2018 IV quarter 2020 | Funds not needed 50.000 € |  |  | Budget CG/SBS | Analysis prepared I phase of the UIS implemented |  |
| Objective: 4.1.2. More efficient exercise of rights to a free access to information |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.Prepare analysis of normative framework in the area of free access to information | Not relevant |  |  |  |  | MPA(Directorate for Public Administration) | III quarter 2018 |  |  | IV quarter 2018 | Funds not needed |  |  |  | Analysis prepared |  |
| 2. Prepare amendments to the Law on Free Access to Information, based on the recommendations of the analysis | a) Establish the inter-ministerial working group for the preparation of the Draft Law b) Prepare the Draft Law c) Conduct the public hearing procedure on the Draft Law d) Prepare the Proposal for the Law based on the public hearing results |  |  |  |  | MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) | I quarter 2019 I quarter 2019 III quarter 2019 IV quarter 2019 |  |  | I quarter 2019 II quarter 2019 III quarter 2019 IV quarter 2019 | Funds not needed 18.000 € 7.000 € Funds not needed |  |  | Budget CG/SBS Budget CG/SBS Budget CG/SBS | Working group established Draft Law prepared Public hearing procedure conducted Proposal for the Law prepared |  |
| 3. Conduct training of employees in authorities on the enforcement of the Law on Free Access to Information | Not relevant |  |  |  |  | HRMA (Sector for training and human resource development) | I quarter 2018 |  |  | IV quarter 2019 | 13.500€ |  |  | Budget CG/SBS | 150 officers of these authorities a year (2018, 2019) to attend training |  |
| 4. Conduct training for employees of the Agency for personal data protection and free access to information on the enforcement of the Law on Free Access to Information | Not relevant |  |  |  |  | HRMA(Sector for training and human resource development) Agency for personal data protection | I quarter 2018 |  |  | IV quarter 2018 | 1.800€ |  |  | Budget CG/SBS | 20 Agency officers who attended training |  |
| 5. Establishing the Open Data Portal | a) Adoption of bylaws b) Starting the initiative for publication of data in open format c) Analysis of readiness assessment of public administration for publication of data in an open format which will emphasize its initial position, current legal framework, possible obstacles for implementation of the project of publication of data in an open format d) Development of Open Data Portal www.datagov.me e) Adopt instructions for publication and use of the open data f) Education of state employees and civil servants in Ministries and other administrative authorities on the open data concept and instructions for their use and publication |  |  |  |  | MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security), HRMA(Sector for training and human resource development) | Activity started Activity started I quarter 2018 Activity started II quarter 2018 III quarter 2018 |  |  | I quarter 2018 I quarter 2018 II quarter 2018 II quarter 2018 III quarter 2018 III quarter 2018 | 1.500 € Funds not needed Funds not needed 25.000 € Funds not needed Funds not needed |  |  | Budget CG/SBS Budget CG/SBS | Bylaws adopted Cooperation with public administration authorities established Document of readiness assessment analysis prepared Open Data Portal established Instructions for the publication of open data adopted, in accordance with the Law on Free Access to Information The Plan is prepared |  |
| 6. Increase in number of information proactively published by Ministries | Increase of inspection control with regard to a proactive access to information |  |  |  |  | Agency for Free Access to Information(Department for Free Access to Information) | I quarter 2018 |  |  | IV quarter 2020 | Funds not needed |  |  |  | Control of all Ministries in annual level performed |  |
| Objective: 4.1.3.Strengthened managerial responsibility in the middle management level in public administration authorities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Prepare methodology for delegating authorities | a)Preparation of methodology b)Monitoring the methodology enforcement |  |  |  |  | MF(Directorate for Central Harmonization) MF (Directorate for Central Harmonization) | Activity started IV quarter 2018 |  |  | IV quarter 2018 IV quarter 2020 | 25.000€ Funds not needed |  |  | EU granted funds | Methodology is prepared Annual reports are prepared |  |
| 2. Conducting training of managers in accordance with the training programs in the area of internal financial controls system | Select lecturers to conduct training in accordance with the topics |  |  |  |  | HRMA(Sector for training and human resource development) MF(Directorate for Central Harmonization) | Activity started |  |  | IV quarter 2020 | 24.750 € |  |  | Budget CG/SBS | 150 managers (in central and local level) who attended training in annual level |  |
| 4.2. PROVISION OF SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 4.2.1. Improved efficiency, effectiveness and citizens’ satisfaction with the quality of provided administrative services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.Improve capacities of public administration for the enforcement of solutions from the Law on Administrative Procedure | a) Identify key authorities of public administration where it will be necessary to conduct the specialized training for the enforcement of the Law on Administrative Procedure (by areas) b) Identify employees in key public administration authorities and local self-governance to be trained by 2020. c) Train 600 identified employees for the enforcement of the Law on Administrative Procedure |  |  |  |  | HRMA(Sector for training and human resource development),MPA(Directorate for Public Administration) HRMA(Sector for training and human resource development),MPA(Directorate for Public Administration) HRMA(Sector for training and human resource development) | I quarter 2018 I quarter 2018 II quarter 2018 |  |  | I quarter 2018 I quarter 2018 IV quarter 2020 | Funds not needed Funds not needed 54.000 € |  |  | Budget CG/SBS | Key authorities identified Employees identified 600 employees have been trained for the enforcement of the Law on Administrative Procedure, 200 in 2018, 2019 and 2020 |  |
| 2.Set up the system of monitoring and evaluation of enforcement of the Law on Administrative Procedure | a) Prepare methodology for monitoring the enforcement of the Law on Administrative Procedure b) Train one or more employees in every public law authority in the enforcement of the Rulebook and Methodology c) Prepare a uniform annual report on the enforcement of the Law on Public Administration for the period: July 2017- December 2018, |  |  |  |  | MPA(Directorate for Public Administration) HRMA(Sector for training and human resource development)MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) all public law authorities | II quarter 2018 III quarter 2018 I quarter 2019 |  |  | II quarter 2018 IV quarter 2018 IV quarter 2020 | Funds not needed 4.590 € Funds not needed |  |  | Budget CG/SBS | Methodology is prepared 100 employees trained in enforcement of the Rulebook and Methodology Uniform annual reports on the enforcement of the Law on Administrative Procedure for the relevant period are prepared and announced on the MPA webpage |  |
| 3.Strengthen capacities of the Administrative court for the implementation of the new Law on Administrative Procedure | a) Conduct training of judges and advisors for the enforcement and reference to the practice of the European court–search and training for Article 1, 6 and8 of European Convention b) Preparation of analysis on the type of administrative acts where it came to the increase of appeals to the Administrative court c)Preparation of analysis on operating procedures of the Administrative court for determining measures for more efficient case management d) Organizing international conference of Administrative courts for the purposes of comparing the practice with regard to the trial within a reasonable time, with emphasize on ruling on the substance of questions e) Regional round table on the topic of enforcement of practice of the European court of Human Rights in administrative disputes in certain areas |  |  |  |  | Centre for training in judiciary and state prosecution, Administrative court Administrative court Administrative court Centre for training in judiciary and state prosecution, Administrative court Administrative court | II quarter 2018 II quarter 2018 II quarter 2018 II quarter 2018 II quarter 2018 |  |  | II quarter 2018 IV quarter 2018 IV quarter 2018 IV quarter 2018 IV quarter 2018 | 2.250€ Funds not needed Funds not needed Funds not needed Funds not needed |  |  | Budget CG/SBS | Special training conducted for90% of judges and advisors Analysis prepared Analysis prepared Conference held |  |
| 4.Establish regular measurement of citizens’ satisfaction with rendered administrative services in identified public administration authorities and local self-governance authorities | a) Prepare methodology for measuring citizens’ satisfaction with rendered services b) Identify public administration authorities and local self-governance authorities rendering administrative services to citizens c) Identify which public administration authorities and local self-governance authorities, in annual level, announce the measurement results in their webpages |  |  |  |  | MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) | II quarter 2018 IV quarter 2018 I quarter 2019 |  |  | IV quarter 2018 IV quarter 2018 IV quarter 2020 | 20.000 € Funds not needed Funds not needed |  |  | Budget CG/SBS | Methodology prepared Public administration authorities and local self-governance authorities rendering administrative services to citizens are identified Measurement results are announced on webpages of public administration authorities and self-governance authorities |  |
| 5.Set up the system for measuring citizens’ satisfaction with electronic services that can be found on eGovernment Portal | a) Increase the number of electronic surveys on eGovernment portal by public authorities (institutions) b) Provide users with a possibility of assessing and giving comments of all electronic services on eGovernment portal |  |  |  |  | MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) | I quarter 2018 I quarter 2018 |  |  | IV quarter 2020 IV quarter 2020 | Funds not needed 3 500 € |  |  | Budget CG/SBS | Number of announced surveys on eGovernment portal 2018 – 10 2019 - 20 2020 – 30 Electronic assessment system established |  |
| Objective: 4.2.2. Ensure interoperability of registers and availability of register data to their users |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.Set up a uniform information system for electronic data exchange between the public authorities and state administration authorities (JISERP) | a) Analysis of business processes and their preparation for electronic data exchange–Catalogue preparation b) Signing of Memorandum of Cooperation between the institutions that have to exchange the data c)Establishment of public meta register of services and data by appending of key registers to the existing infrastructure d) Defining the schedule of connecting the public authorities and public administration authorities to the platform –Exchange of data by uniform information system for electronic data exchange (JISERP) e) Training of users/preparation of instructions for using the UISEDE - training for handling the UISEDE f) Prepare analysis of possibilities of including other electronic registers |  |  |  |  | MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) MPA (Directorate for E-administration and Information Security) MPA (Directorate for E-administration and Information Security) | I quarter 2018 I quarter 2018 I quarter 2018 I quarter 2018 I quarter 2018 I quarter 2018 |  |  | I quarter 2018 I quarter 2018 I quarter 2018 I quarter 2018 II quarter 2018 I quarter 2018 | Funds not needed Funds not needed 500.000€ Funds not needed Funds not needed Funds not needed |  |  | Budget CG/SBS | System and application platform for interconnection and automatic data exchange is established Memorandum is signed Key registers appended to the existing infrastructure Connecting schedule defined All administrators in public administration authorities are trained Analysis prepared |  |
| 2.E-administration–office operations – implementation of eDMS in all Ministries and General Secretariat to the Government of Montenegro (Phase I) | a) Expand the eDMS applications to all the Ministries and General Secretariat of the Government and continuous system maintenance b) Continuous training and raising awareness of users c)Establishment of document exchange between the Ministries and the General Secretariat of the Government d) Analysis of status for document exchange with local self-governance |  |  |  |  | MPA (Directorate for E-administration and Information Security) all Ministries, General Secretariat of the Government and all administrative authorities MPA (Directorate for E-administration and Information Security) MPA (Directorate for E-administration and Information Security) MPA (Directorate for E-administration and Information Security) | Activity started Activity started II quarter 2018 II quarter 2019 |  |  | II quarter 2018 IV quarter 2020 IV quarter 2020 IV quarter 2019 | 400.000€ 1.080 € Funds not needed Funds not needed |  |  | Budget CG/SBS Budget CG/SBS | eDMS implemented in all Ministries in 2018, with continuous system maintenance Continuous conduct of training 2018: portal ESV 2019: portal of eGovernment and IS Official Gazette Analysis done |  |
| 3.Implementation of eDMS (Phase II) – administrative authorities | Setting up the system |  |  |  |  | MPA(Directorate for E-administration and Information Security) | I quarter 2019 |  |  | IV quarter 2019 | 550.000€ |  |  | Budget CG/SBS | 2019: the system is set up 2020: 20% of authorities connected to the system |  |
| Objective: 4.2.3 The eGovernment portal represents a unique point of access to electronic services offered by administrative authorities with high level of user experience and user satisfaction |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Setting up a unique point of access to services - One stop Government | a) Analysis of current status for setting up the One Stop Government b) Preparation of activity plan for setting up One Stop Government c) Implementation of the plan for setting up One Stop Government |  |  |  |  | MPA, Directorate for Public Works, Property Administration MPA(Directorate for E-administration and Information Security) MPA(Directorate for Public Works, Property Administration) | I quarter 2018 II quarter 2018 IV quarter 2018 |  |  | I quarter 2018 III quarter 2018 IV quarter 2020 | Funds not needed Funds not needed 4.000.000€ |  |  | Budget CG/SBS | Analysis prepared Plan for setting up One Stop Government prepared Plan for setting up One Stop Government implemented |  |
| 2.Analysis and creation of prerequisites for inclusion of local self-governments to eGovernment portal | a) Create the Catalogue of electronic services b)Creation of new electronic services in local level |  |  |  |  | MPA, institutions included in provision of selected services MPA, institutions included in provision of selected services | I quarter 2018 III quarter 2018 |  |  | II quarter 2018 III quarter 2019 | Funds not needed 200 000 € |  |  | Budget CG/SBS | Catalogue of electronic services prepared Number of electronic services on eGovernment portal for the specified year, out of the total number of services provided by local self-government units: 2019 - 10% 2020 – 30% |  |
| 3.Setting up a unique system for electronic identification on eGovernment portal | a) Analysis of technical and administrative prerequisites for setting up the system of electronic identification b) Setting up the system of electronic identification c) Preparation of procedures, technical standards and instructions manual for the electronic identification system |  |  |  |  | MPA and all institutions included in provision of selected services MPA and all institutions included in provision of selected services MPA and all institutions included in provision of selected services | I quarter 2018 III quarter 2018 I quarter 2019 |  |  | II quarter 2018 IV quarter 2018 I quarter 2019 | Funds not needed 170.000€ Funds not needed |  |  | Budget CG/SBS | Analysis prepared 2018: the system is implemented - 2019: documents prepared 2020: cca 1 500 users connected to the system |  |
| 4.Increase the number of electronic services and include a higher number of institutions | a) Creation of new electronic services on eGovernment portal by public authorities (institutions) b) Conduct the training for managerial staff and employees of the public administration and local self-government on significance and advantages of electronic services c) Promotion of e-services to users d) Training of administrators |  |  |  |  | MPA, All public authorities and public administration authorities HRMA(Sector for training and human resource development) MPA (Directorate for E-administration and Information Security) MPA (Directorate for E-administration and Information Security) | Activity started I quarter 2018 Activity started Activity started |  |  | IV quarter 2020 IV quarter 2018 IV quarter 2020 IV quarter 2020 | Funds not needed 20.250€ 210.000€ 1.080€ |  |  | Budget CG/SBS Budget CG/SBS Budget CG/SBS | Number of electronic services on eGovernment portal for the specified year: 2018 - 370 2019 – 450 2020 – 500 (Percentage of increase of institutions providing e/services on eGovernment portal compared to previous years: 2018 - 10 % 2019 – 10% 2020 – 20%) Number of public and local employees who have undergone the training: 2018: 150 Number of promotional events conducted for electronic services users: 2018 – 5 2019 – 8 2020 - 10 Number of trained administrators 2018 - 10 2019 - 15 2020 - 20 |  |
| 5.Set up a higher level of eDemocracy | a) Improvement of the project of ePetitions (in cooperation with the General Secretariat of the Government b) Increase the number of hearings published on portal of eGovernment by competent public authorities c)Improvement of sub-portal of eParticipations d) Promotion of eParticipation aimed at using the public hearings and submission of comments via portal |  |  |  |  | MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) | III quarter 2018 III quarter 2018 III quarter 2018 Activity started |  |  | IV quarter 2018 IV quarter 2019 IV quarter 2019 IV quarter 2020 | Funds not needed Funds not needed 50.000€ Funds not needed |  |  | Budget CG/SBS | Number of active petitions for the specified year 2018: 70% of total number of public hearings published by the Ministries 2019:80% of total number of public hearings published by the Ministries 2020: 90% of total number of public hearings published by the Ministries Solution with regard to the envisaged improvement is implemented Number of promotional events (including media appearance) conducted for citizens: 2018 – 2 2019 – 4 2020 - 6 |  |
| 4.3. CIVIL SERVICE SYSTEM AND HUMAN RESOURCES MANAGEMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective: 4.3.1. Strengthened professional abilities of heads of public authorities and high managerial staff with clearly defined criteria for their selection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Implement the competencies framework when selecting the heads of public authorities and high managerial staff | a) Prepare the bylaw on the basis of the new Law on State Employees and Civil Servants b) Implement the training of trainers in competencies framework, prepare the manual c) Train employees of the human resources units of public authorities d) Amend the acts on internal organization and systematization of job positions in public authorities and enter competencies for managerial job positions e) Advertise vacancies for managerial job positions in public authorities with verification of candidates’ competencies |  |  |  |  | MPA(Directorate for Public Administration) HRMA(Sector for Training) HRMA(Sector for Training) HRMA(Sector for advertising), all public authorities HRMA(Sector for Training) | I quarter 2018 II quarter 2018 II quarter 2018 II quarter 2018 III quarter 2018 |  |  | I quarter 2018 II quarter 2018 IV quarter 2020 III quarter 2018 IV quarter 2020 | Funds not needed 10.425€ 16.200 € Funds not needed Funds not needed |  |  | Budget CG/SBS Budget CG/SBS | Adopt the bylaw 1 training of trainers held for 15 participants 120 employees of human resource units of public authorities trained for one years Amended internal organization and systematization acts of all public authorities to which the Law on State Employees and Civil Servants applies All public announcements for vacancies in public authorities in 2019 and 2020 implemented with verification of candidates’ competencies |  |
| Objective: 4.3.2. Increased competition, reduced discretion when deciding through higher transparency and smaller number of candidates on the list for final choice |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Set up the system of electronic verification of candidates’ competencies | a) Prepare the questions base for the development of theoretic part of a written test b) Develop software and application for electronic verification of competencies and their maintenance c) Strengthen capacities of the HRMA in a part of the software support |  |  |  |  | HRMA(Sector for Training), (MPA) HRMA(Sector for Training), (MPA) HRMA(Sector for Training), (MPA) | I quarter 2018 III quarter 2018 I quarter 2019 |  |  | IV quarter 2018 IV quarter 2018 II quarter 2019 | Funds not needed 50.000 € 50.000 € |  |  | Budget CG/SBS Budget CG/SBS | Collection of questions prepared for every area which is a subject of theoretical and practical part of a written test in the procedure of competencies verification Server and 50 computers supplied Software developed |  |
| 2. Improve capacities of Competencies Verification Commission | a) Training of trainers, prepare the Manual b) Training of Commission members in annual level c) Change the decision on compensation for the members of the Competencies Verification Commission |  |  |  |  | HRMA(Sector for Training) HRMA(Sector for Training) HRMA(Sector for Training) | I quarter 2018 I quarter 2018 IV quarter 2018 |  |  | I quarter 2018 IV quarter 2020 IV quarter 2018 | 15.125€ 27.000€ Funds not needed |  |  | Budget CG/SBS Budget CG/SBS | Training completed, 10 trainers trained Number of the Selection Commission members who have gone through the annual training: - 2018 – 200 - 2019 - 200 - 2020 – 200 Decision changed |  |
| 3. Adopt the bylaw aimed at improving the process of candidates’ competencies verification, reduction of number of procedures and costs | a) Prepare the bylaw governing the procedures of competencies verification b) Establish methodology for submission of practical part of a written test by public authority and local self-government unit |  |  |  |  | MPA(Directorate for Public Administration), HRMA HRMA(Sector for advertising) | I quarter 2018 II quarter 2018 |  |  | I quarter 2018 II quarter 2018 | Funds not needed Funds not needed |  |  |  | Bylaw governing the procedures of competencies verification is prepared Methodology for submission of a practical part of a written test by public authority and self-government unit is established |  |
| Objective 4.3.3 Improved human resources management and established effective system of monitoring and optimization of number of employees and measuring the quality of their work |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.Improve human resources planning in public authorities and self-government units | a) Prepare the bylaw related to human resources planning b) Prepare the guidelines for human resources planning, implementation and monitoring c) Upgrade the Central human resources records d) Train employees of the HRMA and employees in the authorities that are responsible for human resources planning |  |  |  |  | MPA(Directorate for Public Administration), HRMA HRMA(Sector for human resource information system) HRMA(Sector for information system of personnel) HRMA(Sector for Training) | Activity started II quarter 2018 II quarter 2018 II quarter 2018 |  |  | I quarter 2018 II quarter 2018 II quarter 2018 IV quarter 2018 | Funds not needed Funds not needed 5.000€ 9.000 € |  |  | Budget CG/SBS Budget CG/SBS | 100% of public authorities prepared their human resources plans Guidelines prepared Central human resources records upgraded 150 employees of the HRMA and employees in authorities responsible for human resources planning are trained |  |
| 2. Implementation of an accredited training program for human resources management | a) Training of trainers of the HRMA who will implement the educational program for acquiring essential skills for human resources management b) Strengthen capacities of human resources employees in central and local level in accordance with accredited educational program for human resources management |  |  |  |  | HRMA(Sector for Training) HRMA(Sector for Training and Development | II quarter 2018 II quarter 2018 |  |  | II quarter 2018 IV quarter 2020 | 4.500 € 185.625€ |  |  | Budget CG/SBS Budget CG/SBS | 50 trainers trained 125 employees trained - 2018 - 25 - 2019 - 50 2020 - 50 |  |
| 3. Optimization of number of employees in public sector per line access | a) Establish targeted values for the optimization of number of employees in public sector in accordance with previously determined methodology and criteria, under line principle b) Prepare the Optimization Plan for number of employees in the public sector, in accordance with the determined targeted values c) Implementation of optimization plan d) Compile annual reports on implementation of Optimization Plan for 2018, 2019 and 2020. |  |  |  |  | MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) MPA(Directorate for Public Administration) MF MPA(Directorate for Public Administration) | Activity started II quarter 2018 III quarter 2018 I quarter 2019 |  |  | I quarter 2018 II quarter 2018 IV quarter 2020 IV quarter 2020 | Funds not needed Funds not needed 3.000.000€ Funds not needed |  |  | Budget CG/SBS Budget CG/SBS | Targeted values determined for each sector The Plan adopted by the Government Continuous implementation of measures from Optimization Plan Annual reports on implementation of the Plan for 2018, 2019 and 2020 implemented |  |
| 4.Increase the level of promptness in data entry into Central Personnel Records | a)Preparation of bylaw b)Raising awareness of high managerial personnel of promptness of Central Personnel records C) Increase the number of inspection controls in public authorities and local self-government units in order to secure they promptly enter data into the Central personnel Records |  |  |  |  | MPA(Directorate for Public Administration) HRMA(Sector for human resource information system) MPA(Section for Inspection Control), HRMA | I quarter 2018 II quarter 2018 I quarter 2018 |  |  | I quarter 2018 II quarter 2018 IV quarter 2020 | Funds not needed 4.500 € Funds not needed |  |  | Budget CG/SBS | Bylaw prepared Two events held Number of pronounced measures with regard to the number of inspection controls with established irregularities |  |
| 5. Prepare mandatory training programs for different categories of employees and civil servants (including HMP) | a)Prepare the bylaw on education and training b)Establishment of mandatory training program for HMP c)Establishment of mandatory training program for new employees “introducing to work” |  |  |  |  | MPA(Directorate for Public Administration) HRMA(Sector for training and human resource development) HRMA(Sector for training and human resource development) | I quarter 2018 IV quarter 2018 II quarter 2019 |  |  | I quarter 2018 IV quarter 2018 III quarter 2019 | Funds not needed Funds not needed 5.700 € |  |  | Budget CG/SBS | Bylaw adopted Mandatory training program for HMP established Mandatory training program for new employees established |  |
| 6. Establish measurement of satisfaction of employees and civil servants (“organizational climate”) | a) Prepare methodology for measuring satisfaction of employees and civil servants b) Perform measurement of satisfaction of employees and civil servants in public authorities, in annual level |  |  |  |  | MPA (Directorate for Public Administration) HRMA MPA (Directorate for Public Administration) HRMA | I quarter 2019 III quarter 2019 |  |  | II quarter 2019 IV quarter 2019 | Funds not needed Funds not needed |  |  |  | Methodology prepared Results of measurement published on webpage of the HRMA |  |
| 4.4. DEVELOPMENT AND COORDINATION OF PUBLIC POLICIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 4.4.1. Comprehensive and rational system of planning, coordination and monitoring the implementation of Government policies established |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Development of capacities for establishing a mid-term system of planning the performance oriented Government work | a) Establishing network of state employees for strategic planning in the level of Ministries b) Preparation and adoption of amendments to the Rules of Procedure of the Government of Montenegro c) Development of the Government Work Program 2018-2020 d)Preparation and implementation of acredited training program for state employees in the area of strategic planning |  |  |  |  | General Secretariat of Government (Sector for planning, coordination and monitoring the implementation of Government policies) MEP, MPA- HRMA General Secretariat of Government General Secretariat of Government (Ministries) GSG,MEP, MPA, HRMA | I quarter 2018 I quarter 2018 I quarter 2018 II quarter 2018 |  |  | I quarter 2018 I quarter 2018 I quarter 2018 IV quarter 2020 | Funds not needed 2.250 € Funds not needed 87.040 € |  |  | Budget CG/SBS Budget CG/SBS | Established network of state employees for strategic planning/ educational inter-ministerial working group Amendment to the Rules of Procedure of the Government of Montenegro adopted Government Work Program for 2018-2020 developed Training program for strategic planning accredited 2 trainings of state employees conducted |  |
| 2.Development of the annual work program of the Government and Ministries performance oriented | a) Development and adoption of methodology for the preparation of the Work Program of the Government and Ministries performance oriented b)Prepare the proposal for annual Work Program of the Government according to new methodology for selected pilot Ministries c) Prepare annual Work Programs of selected pilot Ministries according to the new methodology d) Prepare annual Work Program of the Government according to the new methodology e) Prepare annual Work Program of the Ministries according to the new methodology |  |  |  |  | General Secretariat of the Government (Sector for planning, coordination and monitoring of implementation of Government policies),MF General Secretariat of the Government ( Sector for planning, coordination and monitoring of implementation of Government policies), (pilot Ministries) General Secretariat of the Government (Sector for planning, coordination and monitoring of implementation of Government policies),(pilot Ministries) General Secretariat of the Government ( Sector for planning, coordination and monitoring of implementation of Government policies),(Ministries) | II quarter 2018 IV quarter 2018 IV quarter 2018 IV quarter 2019 IV quarter 2019 |  |  | III quarter 2018 I quarter 2019 I quarter 2019 I quarter 2020 I quarter 2020 | Funds not needed, EU/SIGMA (expert support) Funds not needed Funds not needed Funds not needed Funds not needed |  |  |  | Methodology prepared Proposal of annual Work Plan for 2019 developed for selected pilot Ministries Work programs for 2019 developed for selected pilot Ministries Work Program of the Government for 2020 developed according to the new methodology Work Programs of the Government for 2020 developed according to the new methodology |  |
| 3. Establishing a new information system for planning and reporting | a) Analysis of current information system b) Establish the information system for implementation of new system of planning and reporting |  |  |  |  | MPA (Directorate for E-administration and Information Security) MPA(Directorate for E-administration and Information Security) | II quarter 2018 IV quarter 2018 |  |  | III quarter 2018 I quarter 2020 | Funds not needed 80.000 € |  |  | Budget CG/SBS | Analysis prepared Established information system |  |
| 4. Strengthen capacities of the Sector for coordination and monitoring the implementation of policies | Implementation of training program |  |  |  |  | GSV (Sector for planning, coordination and monitoring of implementation of Government policies), HRMA | II quarter 2018 |  |  | IV quarter 2020 | Funds not needed |  |  |  | Sector employees undergone the training program |  |
| 5.Preparation of Manual for the preparation of strategic documents, with clearly defined procedures and minimum criteria | Not relevant |  |  |  |  | MEP(Directorate for coordination, monitoring the compliance and implementation of strategies establishing public policies) | I quarter 2018 |  |  | II quarter 2018 | 5.000€ |  |  | Budget CG/SBS | Manual for the preparation of strategic documents adopted |  |
| 6. Preparation of legal framework for the development of strategic documents, with clearly defined procedures and minimum criteria | Not relevant |  |  |  |  | MEP(Directorate for coordination, monitoring the compliance and implementation of strategies establishing public policies) | I quarter 2018 |  |  | II quarter 2018 | 10.000€ |  |  | Budget CG/SBS | Established legal framework for the development of strategic documents by clearly defined procedures and minimum criteria |  |
| 7. Preparation of information on analysis of enforcement of legislative act on strategic planning | Not relevant |  |  |  |  | MEP(Directorate for coordination, monitoring the compliance and implementation of strategies establishing public policies) | III quarter 2019 |  |  | I quarter 2020 | Funds not needed, EU/SIGMA (expert support) |  |  |  | Adopted information on analysis of enforcement of legislative act on strategic planning, in the Government session |  |
| Objective 4.4.2. Increased use of analytic tools for development of legislation and better quality of consultations between the stakeholders when developing policies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Increase the level of participation of interested public in the process of creating public policies acts (laws and strategic documents) | a) Prepare amendments to the Decree on the procedure and method of conducting the public hearing in the law preparation process and Decree on the method and procedure of establishing the cooperation between the public administration authorities and non-governmental organizations b) Conduct training of employees working on preparation of public policies acts on the method of involving the interested public in the procedure of their preparation c) Prepare annual reports on enforcement of the Decree on the procedure and method of conducting public hearing in the process of law preparation and Decree on the method and procedure of establishing the cooperation between the public administration authorities and non-governmental organizations |  |  |  |  | MPA(Directorate for Public Administration) HRMA(Sector for Training) MPA(Office for cooperation with the NGO) | I quarter 2018 II quarter 2018 I quarter 2018 |  |  | I quarter 2018 III quarter 2018 IV quarter 2020 | Funds not needed 4.500 € Funds not needed |  |  | Budget CG/SBS | Unique decree governing cooperation between the public administration authorities and NGO and the procedure for conducting the public hearing in the process of law preparation is adopted 50 employees working on preparation of public policies acts in the Ministries are trained Annual report on enforcement of the Decree is prepared |  |
| 2. Introducing full RIA through quality improvement of reporting aimed at understanding the context and regulations impact on environmental, social and other issues |  | Amendments to the Instructions on compiling report on performed regulations impact review |  |  |  | MF(Directorate for financial system and improving of business environment ) | IV quarter 2019 |  |  | IV quarter 2020 | Funds not needed |  | Budget CG |  | Instructions amended |  |
| 3. Implementation of specialist training for technical skills (economic and fiscal analysis) |  | Not relevant |  |  |  | MF, HRMA (Sector for Training) | II quarter 2018 |  |  | IV quarter 2020 | 47.960 € |  | Budget CG/SBS |  | 220 trained employees for using the standard cost model by the end of 2020 |  |
| 4. Publication of Final report on conducted analysis of regulations impact with the proposal for the law on Ministry website |  | Not relevant |  |  |  | GSG, MF, all Ministries | I quarter 2019 |  |  | IV quarter 2020 | Funds not needed |  | Budget CG/SBS |  | Percentage of RIA report that has been published (compared to all Draft Laws requiring the preparation of RIA) |  |
| 5. Prepare annual report on enforcement quality of RIA (quality, lessons learned) |  | Not relevant |  |  |  | MF(Directorate for financial system and improving of business environment ) | I quarter 2018 |  |  | IV quarter 2020 | Funds not needed |  | Budget CG/SBS |  | Reports are made and published on the Webpage of the Ministry of Finance -annually |  |
| 6. Preparation of analysis of implementation of guillotine regulations |  | Not relevant |  |  |  | MF(Directorate for financial system and improving of business environment) | I quarter 2019 |  |  | IV quarter 2020 | 20.000€ |  | Budget CG/SBS |  | Analysis of assessment of savings in time and money in accordance with implemented regulations, for a selected area |  |
| 4.5. PUBLIC FINANCES MANAGEMENT (activities for this area are defined by Action Plan for PFM Strategy) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.6. SPECIAL ISSUES OF THE LOCAL SELF-GOVERNMENT SYSTEM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective:4.6.1. Improvement of functionality of local self-government units (LSGU) and building their capacities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Adopt and implement the Law on local self-government |  |  |  | a) Prepare models of harmonized acts for the local self-government units b) Promotion of model of harmonized acts for local self-government units c) Adopt harmonized acts by local self-government units | MPA(Directorate for local self-government) Union of Municipalities of Montenegro and LSGU MPA(Directorate for local self-government) Union of Municipalities of Montenegro and LSGU |  |  | I quarter 2018 III quarter 2018 IV quarter 2018 | III quarter 2018 IV quarter 2018 I quarter 2019 |  | 18.000 € 5.000 € 24.000 € | Budget CG/SBS Budget CG/SBS Budget CG/SBS |  |  |  | Law on local self-government adopted Model promoted Adopt Statute, Rules of Procedure of the Parliament and Decision on organization and method of work of local self-government units (75 acts adopted in local self-government units) |
| 2. Implement the Law on Utility Activities |  |  |  | a)Adopt the bylaws b) Prepare models of acts for the local self-government units c) Promotion of model of acts for local self-government units d) Adopt acts by local self-government units | MSDT, Union of Municipalities of Montenegro and LSGU MSDT, UNION OF MUNICIPALITIES OF MONTENEGRO and LSGU MSDT, UNION OF MUNICIPALITIES OF MONTENEGRO and LSGU |  |  | Activity started I quarter 2018 I quarter 2018 I quarter 2018 | IV quarter 2018 IV quarter 2018 IV quarter 2018 IV quarter 2018 |  | Funds not needed 18.000 € 5.000 € 36.000 € | Budget CG/SBS Budget CG/SBS Budget CG/SBS |  |  |  | Implemented Law on Utility Activities 7 bylaws adopted by competent public authorities 350 acts adopted by LSGU Model promoted 120 acts adopted |
| 3. Development of unique IS for human resources management in local level |  |  |  | a) Analysis of status and collection of data to be used in human resources records b) Development of human resources records project c) Supply of equipment d) Software development | HRMA(Sector for human resource information system)MPA, Union of Municipalities of Montenegro, LSGU HRMA(Sector for human resource information system)MPA, Union of Municipalities of Montenegro, LSGU |  |  | II quarter 2018 I quarter 2019 II quarter 2019 IV quarter 2019 | II quarter 2018 II quarter 2019 II quarter 2019 I quarter 2020 |  | Funds not needed 10.000€ 40.000€ 40.000€ | Budget CG/SBS Budget CG/SBS Budget CG/SBS |  |  |  | Data collected Project developed Equipment supplied Software developed |
| 4. Organizing training for building capacities of municipalities for preparation of projects and using of assets from EU funds |  |  |  | Implement training for building capacities of municipalities for using assets from EU funds | HRMA(Sector for development and training of personnel), Union of Municipalities of Montenegro, LSGU |  |  | Activity started | IV quarter 2020 |  | 55.000 € | Budget CG/SBS |  |  |  | 12 implemented training for preparation of projects and using of assets from EU funds 100 employees trained for writing and implementation of projects |
| 5. Fostering inter-municipal cooperation on the basis of international practice analysis |  |  |  | a) Analysis of possible areas and mechanisms of cooperation between the LSGU and sources of funding b) Proposal of the Plan for incentive measures c) Implementation of the Plan | MPA(Directorate for Local Self-Government) MF, Union of Municipalities of Montenegro MPA(Directorate for Local Self-Government) MF, Union of Municipalities of Montenegro MPA(Directorate for Local Self-Government) MF, Union of Municipalities of Montenegro |  |  | I quarter 2019 III quarter 2019 I quarter 2020 | II quarter 2019 IV quarter 2019 IV quarter 2020 |  | 20.000 € 10.000 € 1.000.000€ | Budget CG/SBS Budget CG/SBS Budget CG/SBS |  |  |  | Adopted Analysis on possible circle of jobs that require mandatory functional cooperation and other types of municipality cooperation with recommendations Prepared Plan Continuous implementation of the Plan |
| 6. Fostering inter-municipal cooperation in preparation and implementation of EU projects through operation of Network of municipal project managers |  |  |  | a) Provision of direct support in writing and implementation of EU projects on municipalities’ request b)Preparation of joint projects by municipalities | HRMA(Sector for training and human resource development) other Ministries, Union of Municipalities of Montenegro,LSGU |  |  | I quarter 2018 I quarter 2018 | IV quarter 2020 IV quarter 2020 |  | 30.000€ 30.000€ | Budget CG/SBS Budget CG/SBS |  |  |  | 20 prepared projects List of project proposals |
| Objective 4.6.2. Tighten and rationalize criteria for the establishment of new municipalities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.Development of proposal of criteria for the establishment of new municipalities in terms of being more binding and tighter |  |  | Analysis of legislative framework with regard to the criteria for the establishment of new municipalities |  | MPA(Directorate for Local Self-Government) MF, other public administration authorities |  | I quarter 2019 |  | III quarter 2019 |  | 72.000 € | Budget CG/SBS |  |  |  | Prepared analysis |
| Objective 4.6.3.Provide financial sustainability and good financial capacity of municipalities by balancing local self-government incomes with their operations and legal obligations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.Adopt and implement the Law on Financing the Local Self-Government |  |  |  | Prepare bylaws for the implementation of the Law | MF(Directorate for financial system and improving of business environment ) |  |  | II quarter 2018 | IV quarter 2019 |  | 5.000 € | Budget CG/SBS |  |  |  | Law on Financing the Local Self-Government adopted and implemented |
| 2. Development of unique information system for administering local public revenues |  |  |  | a) Software development b) Training of employees for software use | UNION OF MUNICIPALITIES OF MONTENEGRO |  |  | II quarter 2018 IV quarter 2018 | III quarter 2018 IV quarter 2018 |  | 355.000€ 45.000 € | Budget CG/SBS Budget CG/SBS |  |  |  | Operational system developed 120 employees of the LSGU trained for using software |
| 3. Decreasing number of employees in LSGU, with determining targeted values for decreasing the number of employees by 2020 |  |  |  | a) determine targeted values for optimization of number of employees of the LSGU in accordance with previously determined methodology and criteria per line principle b) Prepare the Plan for optimization of number of employees in LSGU in accordance with the determined targeted values c) Implementation of optimization plan d) Compile annual reports of implementation of the Optimization Plan for 2018, 2019 and 2020 | MPA(Directorate for Local Self-Government), MF,LSGU MPA(Directorate for Local Self-Government),MF, LSGU MPA(Directorate for Local Self-Government), MF, LSGU MPA(Directorate for Local Self-Government), MF, LSGU |  |  | Activity started II quarter 2018 III quarter 2018 I quarter 2019 | I quarter 2018 II quarter 2018 IV quarter 2020 IV quarter 2020 |  | Funds not needed Funds not needed Note Funds not needed | Budget CG/SBS |  |  |  | Targeted values for each sector determined Adopted Plan Continuous implementation of measures from optimization plan Annual reports on implementation of the Plan for 2018, 2019 and 2020 are prepared 17 LSGU that decreased the number of their employees |
| 4.7. STRATEGIC MANAGEMENT OF PUBLIC ADMINISTRATION REFORM PROCESS AND FINANCIAL SUSTAINABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objective 4.7.1.Efficient management and coordination of PAR Strategy 2016-2020 enables attainment of majority of objectives |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Ensure the quality system of managing and coordinating the public administration reform |  |  |  | a) Establish a clear procedure for collecting data and reporting on the process of reform implementation b) Conduct training of employees of MPA related to the methodology of monitoring the public administration reform c) Establish information support for monitoring implementation | MPA(Section for process management Regional Public Administration) HRMA(Sector for Training) MPA(Division for managing the process Regional Public Administration) |  |  | I quarter 2018 II quarter 2018 III quarter 2018 | I quarter 2018 IV quarter 2018 IV quarter 2019 |  | Funds not needed 2.000 € 10.000€ | Budget CG/SBS Budget CG/SBS |  |  |  | Prepared guidelines for data collection 2 trainings conducted for new employees in MPA and contact persons in institutions Annual Report for 2019 prepared on the basis of established IT system |
| 2.Prepare annual reports for the Government every year by the end of the first quarter of the next year |  |  |  | a) Collecting data from all public authorities b) Preparation of Draft Report c)Organizing consultations among the public authorities d) Publishing Report on MPA website | MPA(Division for management of process RPA) MPA(Division for management of process RPA) MPA(Division for management of process RPA) MPA(Division for management of process RPA) |  |  | I quarter 2018 I quarter 2018 I quarter 2018 I quarter 2018 | IV quarter 2020 IV quarter 2020 IV quarter 2020 IV quarter 2020 |  | Funds not needed 6.000€ Funds not needed Funds not needed | Budget CG/SBS |  |  |  | Timely data collection Draft Report prepared Organized consultations among the public authorities Annual Reports prepared within the given period and published on MPA website |
| 3. Perform evaluation of PAR strategy and Program of reform of managing public finances |  |  |  | a) Preparation of methodology for evaluation b) Collection of data and preparation of Evaluation Report | MPA(Division for management of process RPA)MF(Directorate for financial system and improvement of business environment) |  |  | IV quarter 2018 II quarter 2019 | II quarter 2019 II quarter 2019 |  | 10.000 € 10.000 € | Budget CG/SBS Budget CG/SBS |  |  |  | Methodology prepared Report prepared and presented to the Council for public administration reform |
| 4. Development of Proposal for the Strategy of public administration reform 2021-2024 |  |  |  | a) Establish the inter-ministerial working group for the preparation of Draft Strategy b) Prepare the Draft Strategy c) Conduct the public hearing procedure on the Draft Law d) Prepare the Proposal for the Strategy | MPA(Division for management of process RPA) MPA(Division for management of process RPA) MPA(Division for management of process RPA) MPA(Division for management of process RPA) |  |  | II quarter 2020 II quarter 2020 III quarter 2020 IV quarter 2020 | II quarter 2020 III quarter 2020 III quarter 2020 IV quarter 2020 |  | Funds not needed 18.000 € 7.000€ Funds not needed | Budget CG/SBS Budget CG/SBS |  |  |  | Working group established Draft Strategy prepared Report from the public hearing published on MPA webpage Proposal of the Strategy prepared |

Reports for 2019 and 2020 will be prepared according to the same schedule.

Costs are envisaged through Objective 4.2.2, activity number 1 , sub-activity c)

sredstva su predviđena kroz Objective 4.2.3, aktivnost 4 - Povećati broj elektronskih servisa i uključiti što veći broj institucija

The line Ministry will propose the targeted values for the optimization of number of employees in the Ministry, public administration authorities it controls and public institutions acting in the respective sector

High managerial personnel

finansijska sredstva su predviđena kroz aktivnost 4.4.1 d)

A part of funds for the implementation of the optimization plan of LSGU will be provided from envisaged funds of Objective 4.3.3, activity 3) sub-activity c).