## Twinning Fiche Project title: Capacity Building of the Civil Service Bureau of Georgia to Implement the Civil Service Reform Beneficiary administration: Legal Entity of Public Law The Civil Service Bureau of Georgia Twinning Reference: GE 15 ENI OT 01 18 # Publication notice reference: EuropeAid/159964/DD/ACT/GE

EU funded project TWINNING INSTRUMENT

1.	Basic Information

1.1	Programme: Support to the Public Administration Reform in Georgia (PAR) ENI/2015/037832/ direct management

“For applicants from the United Kingdom: Please be aware that eligibility criteria must be complied with for the entire duration of the grant. If the United Kingdom withdraws from the EU during the grant period without concluding an agreement with the EU ensuring in particular that applicants from the United Kingdom continue to be eligible, the beneficiaries from the United Kingdom will cease to receive EU funding (while continuing, where possible, to participate) or be required to leave the project on the basis of Article 12.2 of the General Conditions[1] to the grant agreement."

1.2	Twinning Sector: other issues

1.3	EU funded budget: 1,200,000€

2.	Objectives

2.1	Overall Objective(s):

The overall objective of the project is to enhance the professionalism of the civil service in Georgia, in line with the Principles of Public Administration, aiming to develop professional standards, impartiality and accountability within the civil service and to improve transparency, accessibility and the quality of services to citizens.

2.2	Specific objective:

The specific objective of the project is to strengthen the institutional and Human Resource (HR) capacities of the Civil Service Bureau (CSB) to manage the implementation of the Civil Service Reform, through the reinforcement of the legal framework, introduction of modern Human Resource Management (HRM) information system, tools and techniques, development of training scheme for HR managers and improvement of Assets Declaration Monitoring system.

2.3	The elements targeted in strategic documents i.e. National Development Plan/Cooperation agreement/Association Agreement/Sector reform strategy and related Action Plans

The present Twinning project is fully in line with the strategic documents at national and international level:

Socio-Economic Development Strategy of Georgia – “Georgia 2020”

The Socio-Economic Development Strategy of Georgia, “Georgia 2020” explicitly states that: The successful implementation of the “Georgia 2020” Strategy will require co-ordinated work on behalf of various state agencies as well as co-operation with all stakeholders. Institutional capacities for public policy management—which include policy formulation, strategic planning, and the development of evaluation and monitoring mechanisms—will gradually be strengthened in the public sector. The Government will also facilitate the development of a human resources management system as part of efforts to ensure the stability of public service provision and the recruitment of qualified staff through relevant material and career motivation.

Government Platform 2016-2020

The document highlights the importance of the new Law on Civil Service, which provides grounds for gradual implementation of public service reform and “good governance” principles, a career model of the civil service is being developed and ensures the recruitment and promotion of servants in accordance with objective criteria. The implementation of a system for policy planning and monitoring will be continued throughout Georgia. The plan is based on the idea of developing a transparent, result-oriented public engagement principle of accountability. The entire system for policy planning and monitoring will provide grounds for the implementation of UN sustainable development goals on a national level and allow for their integration into national planning documents.

Within the framework of public governance reform, active work will continue concerning capacity building of self-governance with regard to the management of public finances, accountability, and governance, in order to ensure successful implementation.

Local self-governance will also be strengthened. The authority of the municipalities will be expanded based on a subsidizing principle, the implementation of which will be based on a continuous and consistent process of planning and social-economic development. The purpose of this is to ensure fiscal decentralization. The share of revenues in the local budget will gradually increase in the revenues of a consolidated budget. Additionally, the tools for public engagement in implementation of local governance will be strengthened. The territorial units of the municipalities will be equipped respectively, in order to improve the quality and accessibility of public services. The network of “public centres” will be expanded all over Georgia, providing state and local services to all big and/or remote settlements.

Respective steps will be made to ensure effective coordination of activities for combating corruption, increasing public engagement, raising public awareness, and implementing and strengthening anticorruption mechanisms. A system for monitoring property declaration will be implemented, which will facilitate proper monitoring – in particular, verification of the accuracy of the data provided in the declarations. Georgia, as a regional leader in combating corruption and a co-chair country of Open Government Partnership (OGP), will continue its work in this direction. With this in mind, Georgia will continue its close cooperation with OECD,12 GRECO, and other international organizations.

Public Administration Reform Roadmap 2020

The Government of Georgia (GoG) recognises the importance of the Public Administration Reform (PAR) in regards to the effective implementation of the EU-Georgia Agreements (AA, DCFTA and Visa Liberalisation Action Plan). To this end, the GoG has highlighted PAR as an essential component of its development strategy “Georgia 2020”, and adopted several sector strategies including PAR Roadmap 2020 and its action plan, in which the civil service is widely addressed. It is intended to create a sustainable environment in the civil service that guarantees constant professional development. The reform of the civil service will increase its efficiency to drive and coordinate the reform that is taking place in the civil service area.

Civil Service Reform Concept (CSRC)

In 2014, the civil service reform in Georgia transitioned into an active phase of development with the introduction of the CSRC, adopted by the GoG in November 2014. The CSRC embraces European principles of public administration and values of merit-based civil service, including legal predictability and accountability, impartiality, integrity, meritocracy and political neutrality. Formation of a solid and transparent civil service system is the basis for increasing the trust of population towards the state. Trust towards just and impartial civil service will result in the involvement of wide segments of the society in governance, which will ultimately ensure formation of just and unbiased policy.

Association Agreement (AA)

The proposed Twinning project is fully in line with the AA. The reference is made under General Principles to mutual commitment to good governance and fight against corruption, as well as to the need for Georgia to comply with the Copenhagen Criteria, one of which requires that the partner State has developed a governance system and public institutions capable of preserving democracy and ensuring human rights. Title II article 4 of the Agreement "Political dialogue and reform", precisely refers to the reform of civil service. The AA also includes a number of indirect references to the need to strengthen the governance system.

The European Commission, in collaboration with OECD SIGMA, issued the European principles of public administration in October 2014, which identify the EU expectations for PAR in candidate countries and aspirants to candidate status, one of the main principles relates to civil service and emphasises the importance of a professional civil service, capable of delivering high-quality services. Georgia as made the choice to refer to these principles as guidelines for the elaboration of its national PAR Roadmap in 2015.

Association Agreement Agenda 2017-2020

Public Administration Reform and Improvement in Public Services and anti-corruption Pursue public administration reform in line with the Principles of Public Administration and the newly adopted Law on Civil Service with emphasis on implementation monitoring and fostering an accountable, efficient, effective, transparent public administration system of selection, promotion and dismissal and on building a merit-based and professional civil service, specialised needs-based training for civil servants working in all public administration sectors, agencies as well as in state owned enterprises, on delivering quality public services and on improving management of public finances. Ensure effective implementation of the Anti-corruption National Strategy and Action plan to prevent, detect and address corruption, in particular complex corruption as well as implement the verification of the asset and income declarations of all relevant officials.

3.	Description

3.1	Background and justification:

Background

The Civil Service Bureau (CSB) is a Legal Entity of Public Law (LEPL) subordinated under the Prime Minister’s Office. The CSB is mandated to develop uniform civil service state policy as well as to draft regulatory legislation and ensure successful implementation of the civil service reform through coordinating necessary actions. The main functions of the CSB are to study and analyze the current situation in the area of public service; monitor implementation of a unified policy in the area of public service and the observance of normative acts related to the policy and prepare respective recommendations. The CSB also develops normative acts and drafts legislation proposals in the area of public service. In a close cooperation with HRM units of public institutions, the CSB prepares annual HRM plans and maintains a unified electronic Human Resources Management System (e-HRMS). Taking into account the current level of qualification and professional training in public service, the CSB develops unified standards for the professional development of civil servants and supervises observance of those standards.

The CSB is a relatively small public entity with up to 40 employees distributed among 5 departments within 3 main functions (please see Annex 1): analytical, asset declaration supervision and asset declaration monitoring. Since 2015 many important steps were made towards the enhancement of the CSB’s capabilities and resources. More specifically, the role, status and mandate of the CSB have been increased according to the new Civil Service Law (CSL). In 2015 the new Statute of the CSB was adopted which accordingly led to reorganization process. Namely, in 2015 two new departments (Civil Service Institutional Set-up and Practice Generalization Department and Civil Service Human Resources Management Department) were created to tackle issues of implementation of reform. In 2017, within the frame of anti-corruption mechanisms, another new department (Asset Declarations Monitoring Department) was created to monitor asset declarations and verify the accuracy of the information; also, while detecting the violations, to forward the declaration and materials of the proceedings to the relevant law enforcement body or issue an administrative fine in case of unintended offence of the rules of filling the asset declaration. In 2018 Civil Service Institutional Set-up and Practice Generalization Department was renamed into Analytical Department.

The priorities of the CSB are defined in accordance with the governmental policies and in line with the requirements of the EU-Georgia cooperation agenda.

With the view of successful implementation of the envisaged reforms in civil service and according to the Article 2 of the Decree N627 of the GoG on the Approval of the Civil Service Reform Concept and Some Other Related Measures, the CSB has been recognized as the authority for undertaking the management and coordination of civil service as an integrated system. Although the CSB is a main actor in coordinating the proper implementation of the reform, the Administration of Government (AoG), restructured in 2013, is reinforced with the mandate to coordinate Government's work and sector policies, drive the PAR process and the policy development reforms, and act as interface with the donor community.

The PAR is of utmost importance for the country and to this end, the Government has highlighted PAR as an essential component of its national development strategy “Georgia 2020” as well as its programme 2016-2020. It has adopted the PAR Roadmap 2015-2020 and its first action plan 2015-2016, the Policy Planning System Reform Strategy and Action Plan 2015-2017 and several sector and sub-sector strategies addressing various aspects of the PAR process. In addition to policy development, the PAR Roadmap also addresses: Civil service, accountability, public finance management, service delivery and decentralisation. Modern public finance management tools are progressively being introduced into the line Ministries (programme budgeting, performance indicators, and internal auditing). Accountability and transparency are other areas of priorities, through anti-corruption and open government strategies and commitments. Improving civil service is one of the key components of the ongoing PAR being implemented on an initiative of the GoG. The AoG consolidated these initiatives into an overarching strategy, which also includes key aspects of the CSRC.

The Civil Service Reform Concept highlights the major issues to be addressed during the Civil Service Reform process:

- Revision to the civil service legislation, regulations, code of conduct;

- Development of a centralised system of management, coordination and oversight of the civil service;

- Elaboration and implementation of civil service classification system/hiring and firing/career development pathways/promotion and performance indicators/grievance procedures/rights and responsibilities;

- Revision to the civil service remuneration scheme;

- Training and professional development, and the development of an induction and in-service training platform;

- Equal opportunities and gender mainstreaming.

As a part of Civil Service Reform, a new Law on Civil Service has been elaborated by the CSB on the basis of the CSRC. The law defines the general principles that will govern the civil service and will subsequently be translated into a comprehensive body of law through the elaboration and enactment of secondary and tertiary legislation and regulations. The Law of Georgia on Civil Service was adopted by the Parliament of Georgia on 27 October, 2015 and entered into force on 1 July, 2017.

Justification

The expansion of mandate of the CSB entails substantial revisions to the internal structure of the CSB and the management approach. If the CSB is to meet the demands placed upon it by the Government and at the same time address internal organisational matters, it will require substantial assistance to reinforce its staff capacity and structures in undertaking all tasks and responsibilities under the new civil service legal framework:

- The new Law on Civil Service foresees strong and unified HRM units. The CSB should be able to take a leading role to support such units as generally the strong and unified HRM units are the cornerstone for ensuring the proper implementation of legislation. Moreover, the HRM units serve as a main platform for elaboration of standards in appraisal systems, training needs assessment methods and etc. Strengthening the HRM units within public administrations is a priority as they are responsible for leading candidates’ selection process and promoting the professional advancement of civil servants.

- Process of functional/institutional analysis leads to the elaboration of the new principles of institutional and structural arrangements of governmental institutions. This obliges the CSB to monitor and evaluate if any future change/reorganization of public administration is in consistence with these principles.

- The latest amendments to the Law on Conflict of Interest and Corruption introduced monitoring of public officials asset declarations, which is completely new dimension and challenge for the CSB.

The CSB has an important role to coordinate the proper implementation of the new law and related secondary legislations by public institutions, in some cases monitor the process, and prepare respective recommendations. The CSB operates and fulfils its duties in accordance with the Civil Service law with the available resources (human and financial) and with the support of Twinning project MS partner intends to expand its outreach as well as strengthen institutional capacities.

The CSB conducts trainings on Ethics and novelties of the Law for representatives of public institutions on a regular basis. Taking into account the recently defined functions of the CSB, the present Twinning project would greatly improve the CSB’s performance and thus insure the successful implementation of the Civil Service Reform in the country.

In response to the challenges in the relevant sector, the CSB intends to acquire the EU knowledge and expertise; with this purpose the CSB outlined following main directions to be undertaken by the Twinning project:

- Approximation of the legal framework according to the EU standards;

- Fine-tuning the structure and functions of the CSB in compliance with the Law on Civil Service;

- Enhancing HRM methods and training system;

- Upgrading its IT systems and tools, as well as introducing better communication and information exchange approaches.

This Twinning project is  a part of the Financing Agreement for the programme “Support to the Public Administration Reform in Georgia” and  will contribute to the achieving main targets identified under the assistance like supporting the reform of the central public administration, through enhancing the policy-formulation, coordination and monitoring processes, modernisation and professionalization of the civil service, the introduction of a more policy driven-results-oriented management approach, and increased transparency accessibility and accountability. In addition, assistance will be given to enhance the fight against corruption and to improve the strategic framework for the introduction of decentralisation.

The project approach will be consistent with the Principles of Public Administration . Specific attention will be paid to ensuring that the policy development and legal approximation process supported under this Twinning project will be according to the national framework on policy and legislative development and to the better regulation approach, supported also at the EU level. A better regulation approach requires that policies and legislation are prepared on the basis of best available evidence (impact assessments) and according to an inclusive approach involving both internal and external stakeholders.

Pursuant to its horizontal functions, the CSB collaborates with and provides recommendations to all branches of government and line ministries. The Twinning project will seek to strengthen the institutional capacity of the main stakeholders and pay specific attention to accountability and reporting lines between concerned institutions (agencies and ministries).

3.2	Ongoing reforms:

To support the effective implementation of provisions under the new Law and relevant secondary legislation, the CSB is currently undertaking various initiatives to upgrade and standardize existing systems and introduce international best practices to the areas of organizational structure, administration, HR and management.

The CSB, with assistance from the USAID funded Good Governance Initiative (GGI) has developed a standard methodology (together with a set of common principles for macro and micro-organizational rules) for carrying out institutional reviews of all line Ministries, local self-governments and LEPLs. The CSB has already assessed the overall organization of the central public administration.

The institutional reviews will be used in the first instance to catalogue the different organisational arrangements, disposition of staffing, internal procedures within public entities and etc. The reviews will also provide relevant data for the AoG to conduct the comprehensive functional reviews of the line Ministries foreseen with the objective of introducing policy-driven, results-based management approach into the line Ministries.

3.3	Linked activities:

In the recent years, a number of projects financed by different donors have been contributing for development and strengthening of the CSB.

UNIATED STATES AGENCY FOR INTERNATIONAL DEVELOPMENT (USAID)

Good Governance in Georgia G3 (2011-2015)

- Assistance to the GoG in elaboration of the CSRC;

- Assistance to the GoG in elaboration of the key areas of the CSRC. GoG was provided with: Functional Analysis on the Structure of the LEPLs; Recommendations on classification of Civil Servants; Recommendations on ongoing training of the GoG civil servants; Study on mandatory pre-entry exams to Civil Service conducted;

- Assistance to the GoG in modernization of HR systems provided. In close coordination with the CSB skills of the GoG HR managers and staff strengthened in development of standardized job descriptions and carrying out job analysis. Guidebook for developing job descriptions produced. Job Analysis matrix for civil servants developed. The CSB was provided with recommendations for development of the Civil Servants Performance Evaluation System;

- Assistance with defining the structure and functions of the CSB. The CSB was provided with: Functional Review of the agency; Recommendations for the structure and staffing of the Strengthened CSB; Assistance to the CSB in outreaching citizens about the Civil Service Reform; GoG was provided with the public awareness campaign strategy on the reform along with its implementation action plan.

Good Governance Initiative (GGI) in Georgia (2015 – present)

- To prepare the public institutions for the changes envisaged by the new Law on Civil Service the process of functional analysis (FA) of central governmental institutions was launched early in spring 2015. With the support of GGI program the international experts have been hired who developed draft of methodology for functional analysis and conducted training for the members selected by the CSB.

- Assistance in delivering a series of Training for Trainers (ToTs) in performance evaluation system for local trainers (HR representatives of CSB and 19 ministries).

NATO – PROFESSIONAL DEVELOPMENT PROGRAM (PDP) (2012-2014)

- Assistance to the CSB in elaboration of the HRM Manuals for governmental agencies. In 2013-2014 the CSB published three editions, which brings together all HRM policies and practices across different governmental agencies, promotes similar principles and approaches in all public agencies and introduces the modern management approaches. The publication of manuals was followed by a special training session for HR managers of government agencies;

- Assistance to the CSB in implementing Knowledge Transfer Campaign aimed to develop HR function in the state agencies. This Knowledge Transfer Campaign aims to develop HRM systems in civil service agencies by fostering professional ties and sharing local knowledge and experience;

- Assistance to the CSB in implementing internal performance evaluation system;

- Assistance to the CSB in organization of public discussions about draft law on civil service;

- Assistance in conducting trainings in Ethics and Whistleblower Protection issues for representatives of central governmental agencies and LEPLs;

- Assisting in organizing the HR forum for representatives of human resources departments from public agencies;

- Assistance in delivering job description training for the representatives of the government of the Autonomous Republic of Abkhazia;

GERMAN SOCIETY FOR INERNATIONAL COOPERATION (GIZ) 2013 - present

- Assistance to the CSB in developing new competition and attestation procedures in the Civil Service to ensure a transparent, flexible and efficient recruitment system within the Civil Service. New regulations were approved by the GoG;

- Assistance to the CSB in developing Public officials Asset Declaration Monitoring system;

- Assistance to the CSB in developing Ethics handbook for Civil Servants and conducting Trainers of Trainers program. 8 local trainers were trained;

- Assistance in providing a series of job description training for local self-government bodies;

- Assistance in conducting trainings in Ethics and Whistleblower Protection topics for representatives of central governmental agencies;

- Assistance in developing the Code of Ethics for Civil Servants;

UNITED NATIONS DEVELOPMENT PROGRAMME (UNDP) 2015

- The project "Strengthening the Whistleblower Protection Institution in Georgia" has launched in 2015, Project aimed to conducting training and awareness raising activities on whistleblower protection mechanism. Within the framework of the project the ToT has been conducted as a result of which the trainers have gained skills and knowledge enabling them to disseminate information about the whistleblower protection institution;

- Since 2015, with the help of UNDP program - Fostering Regional and Local Development in Georgia, the CSB has provided trainings in Ethics and Whistleblower Protection issues for representatives of local self-government agencies;

- Assistance in organizing the HR forum for representatives of HR departments from public agencies.

UNDP Project Governance Reform Fund

Sub-project “Capacity Building in Civil Service and Anti-Corruption Area”. Duration: July-December 2017. The initiative aimed at increasing the level of awareness among civil servants and public officials on a) novelties of new Law on Civil Service and b) new Anti-Corruption mechanisms, including whistle-blowing mechanisms. The project covered the following activities:

- Providing training sessions for Public Officials on a) novelties of the new LCS and b) corruption prevention mechanisms;

- Updating the Handbook on Ethics and Code of Conduct in Civil Service; Developing Guidelines for the Code of Ethics and Guidelines for the new Law on Civil Service;

- Enhancing Communication on Civil Service Reform;

- Preparing e-learning training module for provision of online training in Ethics for civil servants and developing training module and training structure for political appointees (state political officials, political officials and administrative contract employees).

EUROPEAN UNION

Project title: “EU-Georgia E-Governance Facility” 2012-2014 .The overall objective of this project was to provide assistance to Georgian state institutions for the implementation of e-Government projects enhancing the functionality of Government and public institutions at central and local level to better serve the citizens and businesses. In 2013, within the project the CSB has trained 150 civil servants on e-governance related issues and issued Handbook on E-participation and E-petition.

Technical Assistance Information Exchange (TAIEX)

Three study visits were organized for representatives of the CSB in 2015-2017 – “Public Sector Electronic Human Resources Management Systems” (ref 57055) implemented in March- April 2015; “Study visit on Functional Analysis of Public Institutions” (ref 61463) implemented in October 2016; “Civil Servant Training System” (ref 65226) implemented in November 2017. The study visits gave opportunity to get better view and a broader understanding of the processes within the civil service and acquire better knowledge through well proven practices in MS countries. Three main topics have been covered during the visits – HR development, functional analysis of public institutions and civil servant training system.

Support in Improvement in Governance and Management (SIGMA)

SIGMA has been actively supporting the CSB in several directions since 2009 until now. SIGMA provided its support in the process of reform within the civil service. SIGMA experts reviewed also Anti-Corruption Strategy and Action plan. Within SIGMA intervention in March 2011 quite complex study visit was organized for the representatives of CSB to Estonia Department of Public Service Ministry of Finance, Latvia State Chancellery and Corruption Prevention and Combating Bureau and Lithuania Civil Service Department Ministry of Interior. The draft Civil Service Code and Draft Law on Protection of Whistleblowers were elaborated with the support of SIGMA. In addition, SIGMA experts provided valuable recommendations for the current civil service legislation which was adopted in 2015.

During recent years SIGMA was actively involved in development of the CSRC and new Law on Civil  Service based on the CSRC. Technical expertise and assistant was provided in elaboration of secondary legislation and corresponding legislative acts arising from the new civil service legislation.

Related Programmes and Projects

As already mentioned above the reform of Public Administration (PAR) is of utmost importance for the country and the process is supported through donor community.  The EU total contribution to the “Support to the Public Administration Reform in Georgia” 2016-2019, is EUR 30 000 000 euro. Out of which EUR 20 000 000 is budget support share and EUR 10 000 000 for complementary support. The objective of the programme is to improve the efficiency, accountability and transparency of the public administration of Georgia, in line with the key Principles of Public Administration that have been developed by OECD/SIGMA in close cooperation with the European Commission. It will have a particular focus on the improvement of the policy planning and coordination capacities and processes in the central public administration. The professionalization of the civil service (including the reform of the civil service training system) will also be supported through the programme.

Project Title: Facility for the implementation of the Association Agreement in Georgia; EU funded; Duration: 2015-2018; Description: the project provides policy advice and capacity building support to the Georgian Government in coordinating the implementation of the Association, strengthening the institutional capacities of the line ministries and other public institutions to carry out the required reforms, including on policy development and legal approximation processes.

Project Title:  Legislative Impact Assessment, Drafting and Representation; EU funded;

Duration: 2015-2018; Description: the project aims to improve the legal drafting process at the central level of government (through promoting better coordination among relevant entities, and introduction of the regulatory impact assessment of draft legislation) as well as the Government's international representation and reporting functions with special emphasis on the Ministry of Justice.

These two projects: AA Facility and Legal drafting supported the elaboration of unified methodologies, and provided capacity building to key institutions (government and parliament) in the legal approximation and Regulatory Impact Assessment (RIA) processes. These methodologies are to be formally approved by Government.

Two other projects, EU funded – implemented by GIZ, and USAID-funded ("G4G") also support LA and RIA but with focus on economic sphere.

Policy and legislative process

The National Policy Planning System Reform Strategy, adopted by the Government of Georgia in August 2015 recognises the current weak link between the policy planning process and legislation drafting, the absence of practice of legislative impact assessment and the weak institutional capacity of ministries in legal drafting. In the same line, the OSCE has published an assessment of the legislative process in Georgia in 2015, highlighting a number of weaknesses in the current (policy-making) and legislative process. The assessment specifically notes the reoccurring problem with implementation of laws, which can be attributed to the low quality of laws due to weaknesses in the law-making process. There is a pressure to complete numerous legal reforms in the shortest possible time: "This situation inevitably places enormous pressure on the combined law-making resources of the Government and the Parliament and leaves little time for essential elements of a well-ordered law-making process, such as regulatory impact assessments or proper consultation with civil society." Improvement of the legislative drafting process and quality of legislation is now a priority area of action for the Administration of Government under the Prime Minister (steering the policy-making process) and all line ministries. This primarily involves the Administration of Government, Ministry of Justice, and Ministry of Economy and Sustainable Development. The Government, with international support, is currently developing a uniform methodology for regulatory impact assessments, to be used by all legal drafters. Similar effort is being made with regards to developing a uniform approach to legal approximation.

To sustain the legal approximation process the Ministry of Justice (MoJ) with the support of the EU assistance (under above mentioned projects Association Agreement Facility and Legal Drafting projects) elaborated Legal Approximation Guidelines and Manual. These documents provide key principles and techniques of approximation that will guide and orient legal drafters throughout the approximation process.

These documents should be used consistently, not only by MoJ, but also by all line ministries, and institutions tasked with the approximation exercise. Such proceedings will help to ensure the achievement of a steady and sustainable approximation path.

3.4	List of applicable Union acquis/standards/norms:

The new Civil Service Law together with the secondary legislation is mostly in line with good EU practices and principles. However, in general additional changes will be needed to better streamline existing legal framework with the following requirements:

- the Principles of Public Administration

- EU Equal Opportunities Directives

3.5	Results per component

The Twinning project will provide advisory support to the CSB in five main directions:

Under this Twinning project a Twinning implementation Working Group will be created, composed by the EU MS Experts and representatives of the CSB, to insure effective implementation of project activities.

COMPONENT 1: Alignment of Civil Service Legislation to the Principles of Public Administration in accordance with provisions of the Preamble to the Association Agreement and the Directives of equal opportunity

The general legal framework is in compliance with the Principles of Public Administration but still the gap assessment of the compliance of existing primary and secondary Georgian legislation on Civil Service needs to be done, together with the recommendations for improvement and amendments; if needed based on the recommendations and findings regulatory impact assessment could be applied as well. It would be very helpful to conduct trainings for the members of the thematic working groups on alignment of Georgian legislation with the Principles of Public Administration. After introducing amendments to the respective parts of the legislation short-term training sessions for the HR unit representatives from line ministries and governmental agencies would be quite supportive, as the HR units are the first entry points in relation to the enforcement of the Civil Service Law. It would be very important that the twinning project provides the CSB with statistics related to trainings conducted through the project (e.g. who has been trained, how many people divided per position, how many working hours, topics, results of tests if envisaged, etc.).

Result 1.1 Contribution to the revision of the legal framework according to an inclusive and evidence-based approach and in compliance with emerging needs and the Principles of Public Administration

Indicators of Achievement:

- Secondary legislation assessed, and where needed revised, in an inclusive process using unified LA and RIA methodologies and compliant with the new Law on Civil Service (framework) and the Principles of Public Administration within 12 months from the start on the project;

- Amendments and novelties of the Civil Service legal framework introduced to the HR managers and other relevant stakeholders in close cooperation and coordination with the CSB in the second half of the project; and statistics on capacity building activities provided.

COMPONENT 2: Contribution to the revision of the structure and functions of the CSB in order to expend its role in management, coordination and oversight of the Civil Service as prescribed by the new Law on Civil Service

After the new Law on Civil Service entered into force in July 2017 it became obvious that the structure and functions of the CSB need to be analysed and relevant recommendations prepared in close cooperation with the Administration of Government (AoG). The analysis report will facilitate to define administrative and operational changes to be introduced within the CSB. The mission statement together with internal institutional regulation should be revised and the range of services offered by the CSB to the relevant public institutions redefined in order to meet new requirements. It would be very helpful to organise study visits for CSB staff to share practical experience and examine institution with similar functions and operational experience in MS partner country. The component should facilitate strengthening the CSB capacities in different directions to perform its functions/duties efficiently. Support would be needed to develop e-platform, formal and in service training programmes and materials as well as Quality Assurance plan and Quality Control mechanism.

Result 2.1 Functions and duties of the CSB redefined according to the New Law on Civil Service;

Indicators of Achievement:

- Functional analysis of the CSB prepared and analysis report presented to AoG within 6 months from the start of the project implementation;

- Recommendations for managerial/administrative and operational changes including range of services prepared and introduced to relevant parties within 12 months from the start of the project implementation;

- Institutional Reform Plan for the CSB developed and presented to AoG within 12 months from the start of the project implementation.

Result 2.2 Implementation of the institutional reforms within CSB envisaged by the new Law on Civil Service supported

Indicators of Achievement:

- The CSB Mission Statement and Regulations revised based on the outcome of Functional Analysis provided through Result 2.1 within 12 months from the start of the project implementation;

- The ranges of services to be offered by the CSB to relevant stakeholders redefined and introduced in 2nd half of the project period implementation;

- The CSB staff capable to perform their duties according to the job descriptions compliant to new functions by the end of the project period.

Result 2.3 Application of new services envisaged by the Law on Civil Service enhanced (including:, assisting other public institutions while reorganization, introducing training scheme for HR managers and assisting  HRM units, modifying training module in ethics for top managers, improving public officials assets declaration monitoring system, introducing e-platform for systematization and standardization of  trainings for civil servants).

Indicators of Achievement:

- Guidelines on institutional arrangements in line with the methodology of FA elaborated by the CSB available within 6 months from the start of the project implementation;

- Training schemes for HR and top managers with appropriate guidelines introduced in the middle of the project implementation;

- Existing tools for public official’s assets declaration monitoring systems assessed and, where needed, revised and available by the end of the project;

- Concept note on characteristics and functioning of e-platform presented to the relevant authorities by the end of the project period;

Result 2.4 Capacity and professional performance of the CSB staff enhanced through formal and in-service trainings

Indicators of Achievement:

- Formal and in-service training programs and materials developed in minimum following topics:  Legal and regulatory drafting; Modern management and administrative practices; Service design and delivery; Quality assurance and quality controls; Methodologies, tools and techniques for preparing monthly, quarterly and annual reports; Modern HRM theory and practice; performance evaluation, strategic HRM, change management within 6 months from the start of the project implementation;

- Formal and  in-service trainings delivered for CSB staff to enhance their professional knowledge and performance skills within 14 months from the start of the project implementation;

Result 2.5 Quality assurance plan and quality control mechanism with clear targets for the CSB’s internal and external management system developed and installed

Indicators of Achievement:

- Quality Assurance Plan and Quality Control measures with clear standards and targets introduced to relevant authorities in the second half of the project implementation;

- Data collection methodology, tools and templates, to permit the CSB collect data from the public institutions needed, available within 10 months from the start of the project implementation;

- New Procedures for the application of quality control measures introduced to the CSB management by the end of the project implementation;

Component 3: Preparation of comprehensive HRM policy, modern HRM techniques and establishment of HR training platform

The component will be focused on revision of the HRD policy in light of the requirements in the new Law on Civil Service. Along with the policy revision there is a real need to develop relevant training modules in accordance with training scheme including curricula, training materials and guidelines. In order to strengthen the capacities of the CSB staff together with the HR managers from public administrations to deliver different training modules it would be required to conduct ToT for selected future trainers in several topics like: modern HRM theory and practice, performance evaluation and TNA, strategic HRM, change management and etc. To conduct some joint pilot training sessions would give more confident to new trainers as well as giving the possibility to CSB relevant staff members to acquire practical knowledge in relation to the latest developments in HRM in MS partner country would be added value of the component.

Result 3.1 Contribution to the revision of the current Human Resource Development (HRD) policy in light of the requirements in the new Law on Civil Service

Indicators of Achievement:

- HRD policy revised and consulted with HR managers from different public administrations within 14 months from the start of the project implementation;

Result 3.2 HR training/retraining platform (ToT) focusing on following topics established modern HRM theory and practice, performance evaluation, Training Need Assessment, strategic HRM, change management.

Indicators of Achievement:

- Relevant new training modules in accordance with training scheme elaborated through Result 2.3 available within the first  half of the project implementation;

- Training programme including curricula, training materials and guidelines for each topic of HR trainings developed and available within 10 months from the start of project implementation;

- Selected CSB staff members and HR unit representatives from governmental institutions  trained and capable to deliver relevant training modules to  different stakeholders within the second half of the project implementation;

- Minimum 3 pilot training sessions conducted by new trainers for other HR unit representatives from different governmental institutions by the end of the project implementation;

component 4:  Revision of the CSB IT system and preparation for effective upgrade of IT tools

In order to have more sophisticated and user friendly IT system in place there is a need to make assessment of existing one (including web-portals www.hr.gov.ge; www.ehrms.ge and   www.declaration.gov.ge) and tools in close cooperation with relevant institutions and prepare recommendations for upgrading the portals. Relevant CSB staff should be trained to introduce new developments and tools for proper application of the CSB IT systems.

Result 4.1 IT System of the CSB including the web portals www.hr.gov.ge; www.ehrms.ge and www.declaration.gov.ge reviewed and capacity of relevant staff strengthened

Indicators of Achievement:

- Existing IT systems and tools including the web portals www.hr.gov.ge; www.ehrms.ge and www.declaration.gov.ge assessed and necessary steps for upgrade identified after 9 months from the start of the project implementation;

- Terms of Reference (ToR) and Technical Specifications Document on revision and upgrade of the existing IT systems developed and agreed with relevant responsible institutions after 10 months from the start of the project implementation;

- Relevant CSB staff aware of changes introduced and skilled in application of CSB IT systems and tools by the end of the project period.

COMPONENT 5: Contribution to the development of Effective Communication Tools and Materials for the Proper Delivery of Information

Under the component the CSB current communication practices targeted for public institutions and civil society need to be assessed. Recommendations for upgrading communication practices and tools of the CSB have to be redefined together with the communication tools and relevant visibility/information materials (like: leaflets, brochures, promotional articles, banners, videos and etc.).  Efficient communication strategies and Public Relation (PR) activities have to be introduced to the CSB staff. To raise awareness on on-going reforms in the field and expand the CSB measures in public outreach it would be advisable to organise promotional events for civil servants from central and local municipalities, civil society organisations and media representatives.

Result 5.1 CSB communication policies and public outreach tools strengthened

Indicators of Achievement:

- Contribution to the elaboration of the CSB communication and awareness raising strategy with relevant authorities in the second  half of the project implementation;

- Tailored consultative mechanisms for civil servants from central governmental and local municipalities and civil society organisations developed and operational in the second half of the project implementation;

- Communication tools and relevant visibility/information materials (like: leaflets, brochures, promotional articles, banners, videos and etc.) developed and disseminated to relevant stakeholders in the second half of project;

3.6	Means/input from the EU Member State Partner Administration(s)*:

Member State(s) is/are kindly requested to develop activities in the submitted proposal which are needed in order to achieve the results stipulated in the fiche.

The MS PL will be expected to devote a minimum of 3 days per month to the project in his/her home administration. In addition, he will coordinate from the Member state side the work of the Project steering Committee (PSC). MS Project Leader may participate in the project also as short-term expert (STE). In this case the MS Project Leader should satisfy requirements stipulated in the fiche for both the Project Leader and the relevant STE profile.

The RTA will be located in the premises of the CSB in the beneficiary country on a full time basis and will be responsible for the direct implementation of the project under the overall supervision of the MS Project Leader.

The RTA will maintain day-to-day cooperation with the beneficiary administration and coordinate the work performed by the STEs. The RTA will have a key role in the coordination of the inputs required for the successful implementation of all the project activities.

Minimum two visibility events will be organized in the course of the implementation of the project; Kick-off meeting at the start of the implementation and the Final meeting at the end of the implementation of the project activities.

The required MS experts must either be civil/public servants of the relevant MS administration or be permanent staff of authorised mandated bodies. All experts must comply with the requirements set in the Twinning Manual 2017.

The RTA should be supported by a permanent RTA Assistant. The RTA assistant should be in close collaboration with the BA. The RTA assistant will perform general project duties and providing translation and interpretation services as necessary, practical arrangements for the project, such as organizational issues of expert missions, conferences, training, seminars, maintaining project records and etc. Until the RTA can select and hire an assistant, the Beneficiary administration makes a member of its staff available to support the RTA in his/her daily tasks.

A full-time language assistant should also be recruited. She/he should perform most of the required interpretation/translation services. She/he will provide day-to-day interpretation/translation to the RTA and project experts during missions.

Whenever required and needed for simultaneous interpretation during seminars and workshops, translation of large volume of documents additional interpretation may be procured and funded by the project.

Proposals shall include only the CVs of the proposed PL, of the RTA and of the Component Leaders

3.6.1 Profile and tasks of the PL:

Profile:

- University level education in a relevant discipline (e.g. Public Administration, Economics, Law, Politics) or a recognised professional qualification or equivalent professional experience in a related field of minimum 5 years;

- Minimum of 3 years professional experience gained as a Civil Servant in a MS administration similar to CSB;

- High ranking official or assimilated agent from a full mandated body;

- Comprehensive knowledge of Civil Service policy, legislation and regulations in the EU MSs;

- Proven experience in designing or managing a similar to the CSB institution or a comparable structure would be an advantage;

- Excellent spoken and written English language skills;

- Good communications and inter-personal skills;

- Good leadership skills;

- Experience in project management would be an asset

Tasks:

- Overall direction,  supervision, guidance and monitoring of the project;  ability to mobilise the necessary expertise in support of the efficient implementation of the project;

- Signature of project progress reports and the final report prepared with the support of RTA;

- Timely achievement of the project results;

- Co-Chairing of project steering committees; Provision of legal and technical advice and analysis whenever needed.

3.6.2 Profile and tasks of the RTA:

Profile:

- University level education in a relevant discipline (e.g. Public Administration, Economics, Law, Politics) or a recognised professional qualification or equivalent professional experience in a related field of minimum 5 years;

- At least 3 years’ experience working within a similar to the CSB institution or a comparable structure in MS countries;

- Knowledge of EU laws and the best practices in Civil Service area;

- Excellent spoken and written English language skills;

- Good team-working, communications and inter-personal skills;

- Strong analytical and report writing skills;

- Computer literacy.

- Proven experience in project management, with a demonstrable record of organisational leadership and staff motivation;

Tasks:

- Overall coordination project implementation and of all activities ;

- Coordination of the activities of the team members in line with the agreed work plan to enable timely completion of project outputs;

- Provide technical input to the project whenever needed and provision of advice in his field of expertise;

- Liaise with MS and BC PLs and daily contacts with BC RTA counterpart;

- Preparation of the initial and subsequent work plan(s) and project progress reports, together with PL, to be submitted to the Steering Committees;

- Timely achievement of the project results;

- Liaison with EUD Project Manager and Programme Administration Office (PAO);

- Liaison with other relevant projects and relevant Georgian institutions;

3.6.3 Profile and tasks of Component Leaders:

Component 1: Alignment of Civil Service Legislation to the Principles of Public Administration in accordance with provisions of the Preamble to the Association Agreement and the Directives of equal opportunity

Profile:

- University degree in similar discipline relevant to the project or equivalent professional experience in a related field of minimum 5 years;

- Minimum 3 years of progressive experience in civil service comparable structure in MS countries;

- Excellent knowledge of EU laws and the best practices in Civil Service area;

- Sound knowledge in legal drafting principles and approximation techniques;

- Experience in preparing regulatory framework, including fiscal and regulatory impact assessments, public consultations and inter-institutional coordination;

- A good understanding of human resource management, training and professional development issues;

- Excellent spoken and written English language skills;

- Good team-working, communications and inter-personal skills;

- Strong analytical and report writing skills;

- Previous experience in similar projects would be an asset;

Tasks:

- Component coordination, guidance and monitoring;

- Conducting analysis of the area relevant to the component;

- Provision of legal and technical advice and analysis whenever needed;

- Training coordination and conduction based the practical needs of the beneficiary administration;

- Timely achievement of the component results;

- Timely proposals for any corrective measures;

- Liaise with MS and BC PLs and daily contacts with RTA and BC counterpart.

Component 2: Contribution to the revision of the structure and functions of the CSB in order to expend its role in management, coordination and oversight of the Civil Service as prescribed by the new Law on Civil Service

Profile:

- University degree in similar discipline relevant to the project or equivalent professional experience in a related field of minimum 5 years;

- Minimum 3 years of progressive experience in civil service comparable structure in MS countries;

- Experience in strengthening institutional and service delivery capacities of the institution similar to the CSB;

- Experience in leading organizational restructuring process;

- Good knowledge of Quality Assurance and Quality Control system and methodology;

- Excellent spoken and written English language skills;

- Good team-working, communications and inter-personal skills;

- Strong analytical and report writing skills;

- Previous experience in similar projects would be an asset.

Tasks:

- Component coordination, guidance and monitoring;

- Conducting analysis of the area relevant to the component;

- Provision of legal and technical advice and analysis whenever needed;

- Timely achievement of the component results;

- Training coordination and conduction based the practical needs of the beneficiary administration;

- Timely proposals for any corrective measures;

- Liaise with MS and BC PLs and daily contacts with RTA and BC counterpart.

Component 3: Preparation of comprehensive HRM policy, modern HRM techniques and establishment of HR training platform

Profile:

- University degree in similar discipline relevant to the project or equivalent professional experience in a related field of minimum 5 years;

- Minimum 3 years of progressive experience in civil service comparable structure in MS countries;

- Sound working experience in HRD and training;

- A good understanding of human resource management, training and professional development of personnel;

- Excellent spoken and written English language skills;

- Good team-working, communications and inter-personal skills;

- Strong analytical and report writing skills;

- Previous experience in similar projects would be an asset;

Tasks:

- Component coordination, guidance and monitoring;

- Conducting analysis of the area relevant to the component;

- Training coordination and conduction based the practical needs of the beneficiary administration;

- Timely achievement of the component results;

- Timely proposals for any corrective measures;

- Liaise with MS and BC PLs and daily contacts with RTA and BC counterpart.

Component 4: Revision of the CSB IT system and preparation for effective upgrade of IT tools

Profile:

- University degree in similar discipline relevant to the project or equivalent professional experience in a related field of minimum 5 years;

- Minimum 3 years of progressive experience in the area relevant to the project;

- Relevant experience in Information and Communication Technologies with specific experience in developing management information systems;

- Excellent spoken and written English language skills;

- Good team-working, communications and inter-personal skills;

- Strong analytical and report writing skills;

- Previous experience in similar projects would be an asset;

Tasks:

- Component coordination, guidance and monitoring;

- Conducting analysis of the area relevant to the component;

- Provision of technical advice and analysis whenever needed;

- Training coordination and conduction based the practical needs of the beneficiary administration;

- Timely achievement of the component results;

- Timely proposals for any corrective measures;

- Liaise with MS and BC PLs and daily contacts with RTA and BC counterpart.

Component 5: Contribution to the Development of Effective Communication Tools and Materials for the Proper Delivery of Information

Profile

- University degree in similar discipline relevant to the project or equivalent professional experience in a related field of minimum 5 years;

- Minimum 3 years of progressive experience in the area relevant to the project;

- Demonstrated understanding of communication tools and mechanisms;

- Excellent spoken and written English language skills;

- Good team-working, communications and inter-personal skills;

- Strong analytical and report writing skills;

- Previous experience in similar projects would be an asset;

Tasks:

- Component coordination, guidance and monitoring;

- Conducting analysis of the area relevant to the component;

- Training coordination and conduction based the practical needs of the beneficiary administration;

- Timely achievement of the component results;

- Timely proposals for any corrective measures;

- Liaise with MS and BC PLs and daily contacts with RTA and BC counterpart.

3.6.4 Profile and tasks of other short-term experts:

Specialist civil servants/staff of approved mandated bodies will be made available by the Twinning Partner (MS) to support the implementation of the activities and agreed with the beneficiary administration. Specific and technical matters relevant to this Twinning project will be taken over by a pool of STEs. The detailed expert input shall be established when drawing up the Twinning work plan.

Below some indicative qualifications and tasks: (NB: STEs CV should not be included in the MS proposal)

Qualifications and skills:

- University level education in a relevant discipline (e.g. Public Administration, Economics, Law, Politics) or a recognised professional qualification or equivalent professional experience in a related field of minimum 5 years;

- At least 3 years’ extensive working experience in the respective field relevant to the assignment;

- Relevant working experience in the ENI countries and/or a transitional economy would be an asset;

- Sound knowledge in legal drafting with specific knowledge of Civil Service Law;

- Experience in strengthening institutional and service delivery capacities of the institution similar to the CSB;

- Relevant experience in Information and Communication Technologies with specific experience in developing management information systems;

- Sound working experience in HRD and training;

- Demonstrated understanding of communication tools and mechanisms;

- Experience in preparing regulatory framework, including fiscal and regulatory impact assessments, public consultations and inter-institutional coordination

- Excellent spoken and written English language skills;

- Good team-working, communications and inter-personal skills;

- Strong analytical and report writing skills;

- Computer literacy;

- Previous experience as an STE in similar projects would be an asset;

Tasks:

- Contributing to the sustainability of the project by ensuring that aspects of the project related to their field of expertise are implemented timely;

- Supervision and on-site coordination of all activities related to their field of expertise and performed under this project;

- Timely proposals for any corrective measures;

- Assistance with drafting project related documents in accordance with the national rules for legislative development and preparation of trainings, study tours, workshops, seminars, etc.

- Liaise with RTA and BC counterparts;

4.	Budget

Maximum Budget available for the Twinning Grant 1, 200,000 €

5. Implementation Arrangements

5.1 	The European Union Delegation in Tbilisi, Georgia, will be responsible for the tendering, contracting, payments and financial reporting, and will work in close co-operation with the Beneficiary. The person in charge of this project at the Delegation of the European Union to Georgia is:

Ms. Sophie Huet-Guerriche

Thematic Sector Coordinator - Governance and Human Capital

Programme Officer – Public Administration Reform

Delegation of the European Union to Georgia

38 Nino Chkheidze Street, 0102 Tbilisi

Georgia

Tel: + 995 32 2943763

E-mail: Sophie.HUET-GUERRICHE@eeas.europa.eu

5.2 	Institutional framework

The main Beneficiary Institution (BI) is the CSB of Georgia, located in Tbilisi. The CSB currently has 27 full-time staff and 13 contract staff. The staff is presently divided between five Departments: Administrative Department, Asset Declarations Department, Asset Declaration Monitoring Department, HR Department and Analytical Department. For details regarding CSB organizational structure please see Annex 1 (although it is probable that the institutional arrangements will be adjusted in response to the outcomes of the project as new functions for the CSB are defined and introduced).

The beneficiary institution will dedicate all necessary human and financial resources in order to guarantee an effective implementation of the respective project.

Where necessary, other stakeholders at all levels will be involved in project activities and special attention shall be paid to accountability lines between relevant stakeholders.

Stakeholders involved in the project are:

- Administration of the Government of Georgia;

- Civil Service Council;

- Line Ministries;

- Governmental/Public Agencies;

- Local Municipalities;

- Civil Society Organisations.

5.3	Counterparts in the Beneficiary administration:

The PL and RTA counterparts will be staff of the Beneficiary administration and will be actively involved in the management and coordination of the project.

5.3.1	Contact person:

Ms. Irina Aghapishvili

Head of Institutional Set-up and Practice Generalization Department

Civil Service Bureau

7 Ingorokva str. 0105, Tbilisi

www.csb.gov.ge

5.3.2	PL counterpart

Dr. Catherine Kardava,

Head, Civil Service Bureau

7 Ingorokva str. 0105, Tbilisi

www.csb.gov.ge

5.3.3	RTA counterpart

Ms. Maia Dvalishvili

Deputy Head, Civil Service Bureau

7 Ingorokva str. 0105, Tbilisi

www.csb.gov.ge

6.	Duration of the project

Duration of the execution period: 24 months; the execution period will end 3 months after the implementation period of the Action (work plan) which will take 21 months.

7.	Sustainability

The sustainable development in all key areas of the proposed intervention is the principal aim of the CSB. Actions carried out within the framework of the project will support closer integration of the beneficiary institution in relevant European community in order to work towards more coherent strategic goals. The project forms an integral part of the CSB’s development plan, which is strongly reinforced by commitment from the political level.

The Beneficiary Institution is fully devoted to ensuring the long-term impact and sustainability of the Twinning Project. At the policy level, all activities are in line with the Government’s national priorities and on-going reforms in public administration, as well as with the existing CSRC.

At the project level, sustainability of project results will be guaranteed by ensuring that all procedures, management practises and tools, are embedded in the work routine of the CSB. The sustainability of the project will be achieved through a suitable implementation of the project activities and availability of trained personnel in different departments of the beneficiary.

Development of any strategic document and legislation/amendments will be carried out respecting all national procedures and practices. Any guidelines or procedures developed under this action will not contradict to any legal provision of the country.

In order to contribute to develop implementable legislation, the twinning project will support preparation of analytical prerequisites i.e. preparation of concept notes, impact assessments, estimation of implementation costs and will support CSB on conducting inter-institutional and public consultations.

In this regard, the project will promote close cooperation with the AoG of Georgia to ensure consistency of the legal framework and alignment of the regulatory strategy with the government programme and with provisions of the PAR.

8.	Crosscutting issues (equal opportunity, environment, climate etc…)

All activities under this project will be designed and implemented in accordance with principles of good governance and human rights and gender equality wherever these issues are of particular relevance to the CSB. Gender as well as ethnic minority related issues will be tackled through the establishment and implementation of equality-related criteria in the civil service, and in policy making, promoting gender-related issues in the production of data. The principle of non-discrimination, ensuring equitable access of job seekers to employment irrespective of gender, racial or ethnic origin, religion or belief, or sexual orientation, is embedded in the new Law on Civil Service and will be rigorously enforced by the CSB staff. Moreover, the principles will be applied within the CSB itself and reflected in the Procedures Manual.

Attention will be paid to ensuring access for vulnerable and marginalised groups to employment in the Civil Service.

The principle of implementation of this Twinning project will be based on environment friendly atmosphere. This in particular guarantees, minimising paper use during project implementation by the maximum feasible use of electronic tools and resources.

9.	Conditionality and sequencing

There is no precondition set for this twinning project as the new law on Civil Service entered into force in July 2017 giving the solid basis to the project to be implemented.

The CSB has expressed its full commitment to the objectives of the project and the actions designed to achieve those objectives. The CSB undertakes to:

- Assign appropriately skilled and competent staff at all levels to act as counterparts to the RTA and his/her colleagues;

- Release members of staff to participate in project activities (e.g. training workshops, study tours, communications actions);

- Ensure that the results of the project are fully integrated into the work routine of the CSB;

- Provide access to all relevant legislation, regulations, policies, strategies and supporting documentation relevant to the project;

- Provide facilities for the STEs to allow them to perform their work efficiently and effectively while on mission;

- Facilitate access to decision-makers at national, regional and local levels;

- Provide suitable venues for training workshops/presentations/meetings held within the framework of the project.

10.	Indicators for performance measurement

- Providing the information/documents in regards with the national regulatory basis and arranging the relevant informative meetings;

- Appropriate area and facilities prepared and provided in  project implementation process;

- Training facilities provided;

- Coordination and meetings with other donor organizations conducing the technical assistance programs for the CSB;

- Action Plan reports provided and updated.

11. 	Facilities available

The BC commits itself to deliver the following facilities:

- Adequately equipped office space for the RTA and the RTA assistant(s) for the entire duration of their secondment;

- Supply of office room including access to computer, telephone, internet, printer, photocopier;

- Adequate conditions for the STEs to perform their work while on mission to the BC;

- Provide suitable venues for the training sessions and meetings that will be held under the Project;

- Security related issues will be assured according to the standards and practices applicable for all Georgian public institutions;

List of Abbreviation

| AA | EU-Georgia Association Agreement |
| --- | --- |
| AoG | Administration of Government |
| BC | Beneficial Country |
| BDD | Basic Data and Directions document |
| CSB | Civil Service Bureau |
| CSL | Civil Service Law |
| CSRC | Civil Service Reform Concept |
| DCFTA | Deep and Comprehensive Free Trade Area |
| e-HRMS | Electronic Human Resource Management System |
| ENI | European Neighbourhood Instrument |
| EU | European Union |
| FA | Functional Analysis |
| GGI | Good Governance Initiative |
| GIZ | German Society for International Cooperation |
| GoG | Government of Georgia |
| GRECO | Group of States against Corruption |
| HR | Human Resource |
| HRD | Human Resource Development |
| HRM | Human Resource Management |
| IT | Information Technology |
| LEPL | Legal Entity of Public Law |
| MoF | Ministry of Finance |
| Moj | Ministry of Justice |
| MS | Member State |
| OECD | Organisation for Economic Co-operation and Development |
| OGP | Open Government Partnership |
| PAO | Programme Administration Office |
| PAR | Public Administration Reform |
| PDP | NATO Professional Development Programme |
| PL | Project Leader |
| PR | Public Relations |
| PSC | Project Steering Committee |
| RIA | Regulatory Impact Assessment |
| RTA | Resident Twinning Advisor |
| SIGMA | Support in Implementation in Governance and Management |
| STE | Short Term Expert |
| UNDP | United Nations Development Programme |
| TNA | Training Needs Assessment |
| TOR | Terms of Reference |
| ToT | Training of Trainers |

ANNEXES TO PROJECT FICHE

1. 	Organisational Structure of the CSB

2. 	Logical framework matrix in standard format

ANNEX 1: Organisational Structure of the CSB

| ANNEX 2: Logical Framework Matrix |  |  |  |  |
| --- | --- | --- | --- | --- |
| Project Title: Capacity Building of the Civil Service Bureau of Georgia to Implement the Civil Service Reform |  | Program name and number: | Support to the Public Administration Reform in Georgia (PAR) ENI/2015/037832 |  |
| Civil Service Bureau of Georgia |  | Total budget: 1,200,000 EUR | EU ENI financing (100%) 1,200,000 EUR |  |
| Overall objective (impact) | Objectively Verifiable Indicators | Sources of Verification |  | Assumptions |
| The overall objective is to enhance the professionalism of the civil service in Georgia, in line with the Principles of Public Administration, aiming to develop professional standards, impartiality and accountability within the civil service and to improve transparency, accessibility and the quality of services to citizens | - The relevant legislation amended in accordance with the EU provisions; - Quality of services provided to the relevant stakeholders enhanced; - Civil Service of Georgia operates in line with the principles of public administration; | - Reports on PAR implementation; - EU Regular Reports ; - OECD-SIGMA Reports; |  |  |
| Specific Objective(s ) (outcome) | Objectively Verifiable Indicators | Objectively Verifiable Indicators |  | Assumptions |
| The project purpose is to strengthen the institutional and HR capacities of the CSB to manage the implementation of the Civil Service Reform, through the reinforcement of the legal framework, introduction of modern HRM information system, tools and techniques, development of training scheme for HR managers and establishment of Assets Declaration Monitoring system | - Number of legal and regulatory amendments drafted in accordance with an inclusive and evidence-based approach; - Human capacity of the CSB enhanced in line to the new requirements; - HRM information system in place and operational; - CSB structure and functions revised; - Training scheme for HR managers effectively updated | - EU Regular Reports; - OECD-SIGMA Reports; - Reports of PAR implementation; - Annual Reports of the CSB. |  | - The government continues to meet the general and specific conditions set out in the technical and administrative provisions annexed to the financing agreement for the public administration sector reform contract; - The government maintains its commitment to reform the central public administration; - The government maintains its foreign policy objective of closer political and economic integration with the EU; |
| Mandatory Results (outcomes) | Objectively Verifiable Indicators | Source of Verification |  | Assumption |
| COMPONENT 1: Alignment of Civil Service Legislation to the Principles of Public Administration in accordance with provisions of the Preamble to the Association Agreement and the Directives of equal opportunity Result 1.1 Contribution to the revision of the legal framework according to an inclusive and evidence-based approach and in compliance with emerging needs and the EU Principles of Public Administration | - Secondary legislation assessed, revised in an inclusive process using unified LA and RIA methodologies and compliant with the new Law on Civil Service (framework) and the EU Principles of Public Administration within 12 months from the start on the project implementation; - Amendments and novelties of the Civil Service legal framework introduced to the HR managers and other relevant stakeholders in close cooperation and coordination with the CSB in the second half of the project; and statistics on capacity building activities provided | - OECD-SIGMA Reports; - Annual Reports of the Civil Service Bureau; - Minutes and feedback from stakeholder consultations; - Twinning project reports; - Revised Charter of the CSB; - NGO reports and official websites; - Copies of legislation and regulations; - Copies of Government Decisions; - Copies of Government/CSB Regulations; - Project documentation (list of participants, recommendations Copies of project training programmes & materials; Copies of post-training questionnaires); - Print out of CSB IT system; - Copies of communications / visibility materials; - CSB website; - Copies of CSB press releases; |  | - CSB willing and able to allocate appropriately skilled and experienced staff to act as counterparts to the project; - Readiness to pursue further measures to prevent and combat corruption in the public sector; - Government maintains its commitment to provide sufficient funds to the CSB to enable it to implement its reform agenda; - Assistance in cooperation with government authorities and other external stakeholders of the project; - Strong support and commitment from the senior management of CSB and AoG; - Good communication between the Beneficiary and other stakeholders; - Twinning MS partner commitment; - Good communication between the Beneficiary and MS partner(s); - All relevant documentation/information available. |
| COMPONENT 2: Contribution to the revision of the structure and functions of the CSB in order to expend its role in management, coordination and oversight of the Civil Service as prescribed by the new Law on Civil Service Result 2.1 Functions and duties of the CSB redefined according to the New Law on Civil Service; Result 2.2 Implementation of the institutional reforms within CSB envisaged by the new Law on Civil Service supported Result 2.3 Application of new services envisaged by the Law on Civil Service enhanced (including:, assisting other public institutions while reorganization, introducing training scheme for HR managers and assisting HRM units, modifying training module in ethics for top managers, improving public officials assets declaration monitoring system, introducing e-platform for systematization and standardization of trainings for civil servants). Result 2.4 Capacity and professional performance of the CSB staff enhanced through formal and in-service trainings Result 2.5 Quality assurance plan and quality control mechanism with clear targets for the CSB’s internal and external management system developed and installed | - Functional analysis of the CSB prepared and analysis report presented to AoG within 6 months from the start of the project implementation; - Recommendations for managerial/administrative and operational changes including range of services prepared and introduced to relevant parties within 12 months from the start of the project implementation; - Institutional Reform Plan for the CSB developed and presented to AoG within 12 months from the start of the project implementation - The CSB Mission Statement and Regulations assessed and, where needed, revised based on the outcome of Functional Analysis provided through Result 2.1 within 12 months from the start of the project implementation; - The ranges of services to be offered by the CSB to relevant stakeholders redefined and introduced in 2nd half of the project period implementation; - The CSB staff capable to perform their duties according to the job descriptions compliant to new functions by the end of the project period. - Guidelines on institutional arrangements in line with the methodology of FA elaborated by the CSB available within 6 months from the start of the project implementation; - Training schemes for HR and top managers with appropriate guidelines introduced in the middle of the project implementation; - Existing tools for public official’s assets declaration monitoring systems revised and available by the end of the project; - Concept note on characteristics and functioning of e-platform presented to the relevant authorities by the end of the project period; - Formal and in-service training programs and materials developed in minimum following topics: Legal and regulatory drafting; Modern management and administrative practices; Service design and delivery; Quality assurance and quality controls; Methodologies, tools and techniques for preparing monthly, quarterly and annual reports; Modern HRM theory and practice; performance evaluation, strategic HRM, change management within 6 months from the start of the project implementation; - Formal and in-service trainings delivered for CSB staff to enhance their professional knowledge and performance skills within 14 months from the start of the project implementation; - Data collection methodology, tools and templates, to permit the CSB collect data from the public institutions needed, available within 10 months from the start of the project implementation. - Quality Assurance Plan and Quality Control measures with clear targets and measures introduced to relevant authorities in the second half of the project implementation; - New Procedures for the application of quality control measures introduced to the CSB management by the end of the project implementation; |  |  |  |
| COMPONENT 3: Preparation of comprehensive HRM policy, modern HRM techniques and establishment of HR training platform Result 3.1 Contribution to the revision of the current Human Resource Development (HRD) policy revised in light of the requirements in the new Law on Civil Service Result 3.2 HR training/retraining platform (ToT) focusing on following topics established modern HRM theory and practice, performance evaluation, Training Needs Assessment (TNA), strategic HRM, change management | - HRD policy revised and consulted with HR managers from different public administrations within 14 months from the start of the project implementation; - Relevant new training modules in accordance with training scheme elaborated through Result 2.3 available within the first half of the project implementation; - Training programme including curricula, training materials and guidelines for each topic of HR trainings developed and available within 10 months from the start of project implementation; - Selected CSB staff members and HR unit representatives from governmental institutions trained and capable to deliver relevant training modules to different stakeholders within the second half of the project implementation; - Minimum 3 pilot training sessions conducted by new trainers for other HR unit representatives from different governmental institutions by the end of the project implementation; |  |  |  |
| COMPONENT 4: Revision of the CSB IT system and preparation for effective upgrade of IT tools Result 4.1 IT System of the CSB including the web portals www.hr.gov.ge; www.ehrms.ge and www.declaration.gov.ge reviewed and capacity of relevant staff strengthened | - Existing IT systems and tools including the web portals www.hr.gov.ge; www.ehrms.ge and www.declaration.gov.ge assessed and necessary steps for upgrade identified after 9 months from the start of the project implementation; - Terms of Reference (ToR) and Technical Specifications Document on revision and upgrade of the existing IT systems developed and agreed with relevant responsible institutions after 10 months from the start of the project implementation; - Relevant CSB staff aware of changes introduced and skilled in application of CSB IT systems and tools by the end of the project period. |  |  |  |
| COMPONENT 5: Contribution to the Development of Effective Communication Tools and Materials for the Proper Delivery of Information Result 5.1 CSB communication policies and public outreach tools strengthened | - Contribution to the elaboration of the CSB communication and awareness raising strategy with relevant authorities in the second half of the project implementation; - Tailored consultative mechanisms for civil servants from central governmental and local municipalities and civil society organisations developed and operational in the second half of the project implementation; - Communication tools and relevant visibility/information materials (like: leaflets, brochures, promotional articles, banners, videos and etc.) developed and disseminated to relevant stakeholders in the second half of project implementation; |  |  |  |
| Activities | Means | Specification of Costs |  |  |
| Member State(s) is kindly requested to develop activities in the submitted proposal which are needed in order to achieve the results stipulated in the fiche | Consultations, analyses, preparation of documentation, trainings, workshops, study visits, | Twinning project: 1.200.000,00 EUR |  | In line with the assumptions specified |

[1] Twinning manual Annex A2

The Parties shall cooperate on (…) on further pursuing the public administration reform and on building an accountable, efficient, effective, transparent and professional civil service; and on continuing effective fight against corruption (…).

e.g. support for good governance, fight against corruption and prevention of conflict of interests (General principles of the AA, including references to the Copenhagen Criteria, Article 17 and Article 391 of the AA); Protection of privacy, i.e. personal data protection (Article 14 of the AA); Public procurement (Article 143 of the AA); PFIC and external audit – specifically support for independence and capacity of the SAO (Article 279 of the AA); Cooperation in the field of statistics (Article 286 of the AA); Civil society cooperation and regular dialogue in this field, including establishment of the Civil Society Platform (Articles 369, 371, 409 and 410 of the AA); Strengthening of “multi-level governance” (Articles 372 and 373 of the AA).

The Civil Service Bureau of Georgia was established by the ordinance #472 of the President of Georgia, 29 October 2004.

http://ec.europa.eu/info/strategy/better-regulation-why-and-how_en

http://www.sigmaweb.org/publications/Principles-of-Public-Administration_Edition-2017_ENG.pdf

In order to support and foster the process thematic working groups will be established with the involvement of all relevant stakeholders (such as MoJ, AoG, MoF)

The exhaustive list of pieces of secondary legislation are given in the Article 126 of the New Law on Civil Service of Georgia

Process of functional/institutional analysis implies that Statute and Mission Statement of CSB, as well as management structure, the range of services offered, distribution of tasks and staffing analyzed.

For example, certification of civil servants, trainings for HR managers, monitoring of public officials assets declarations, promotion of integrity through awareness raising campaign and others as foreseen by the new Law on Civil Service.

Methodology have been elaborated by FA team within CSB with active support of international and local experts

Future trainers will be identified jointly by the project partners based on the observations from the staff of CSB and/or HR managers from other governmental administrations, ToT will include four one-day trainings

LEPL of the Ministry of Justice –Data Exchange Agency; LEPL of the Ministry of Finance - Financial Analytical Service

Promotional events and seminars will aim to deliver relevant information about Civil Service Reform and the changes introduced.

In order to support and foster the process thematic working groups will be established with the involvement of all relevant stakeholders (such as MoJ, AoG, MoF)

The exhaustive list of pieces of secondary legislation are given in the Article 126 of the New Law on Civil Service of Georgia

Process of functional/institutional analysis implies that Statute and Mission Statement of CSB, as well as management structure, the range of services offered, distribution of tasks and staffing analyzed.

For example, certification of civil servants, trainings for HR managers, monitoring of public officials assets declarations, promotion of integrity through awareness raising campaign and others as foreseen by the new Law on Civil Service.

Methodology have been elaborated by FA team within CSB with active support of international and local experts

Future trainers will be identified jointly by the project partners based on the observations from the staff of CSB and/or HR managers from other governmental administrations, ToT will include four one-day trainings