## Project title: Establishing Efficient Protection and Control System of Geographical Indications (GIs) in Georgia ## Beneficiary administration: National Intellectual Property Center of Georgia - Sakpatenti ## Twinning Reference: GE 16 ENI EC 03 18 ## Publication notice reference: EuropeAid/160650/DD/ACT/GE

EU funded project TWINNING INSTRUMENT

# List of Abbreviation

- AA - Association Agreement

- AO – Appellations of Origin

- AP – Action Plan

- BC – Beneficiary Country

- DCFTA - Deep and Comprehensive Free Trade Area

- DG – Director General

- EaP - Eastern Partnership

- ENPI - European Neighbourhood and Partnership Instrument

- EU – European Union

- EXBS – Export Control and Related Border Security

- GI – Geographical Indications

- G4G – Governing for Growth

- GoG – Government of Georgia

- GRS - Georgia Revenue Service

- IPR – Intellectual Property Rights

- MEPA – Ministry of Environment Protection and Agriculture

- PAO - Programme Administration Office

- PAR – Public Administration Reform

- PCA - Partnership and Cooperation Agreement

- STE – Short Term Expert

- TAIEX – Technical Assistance and Information Exchange instrument

- TEIPS - Trade-Related Aspects of Intellectual Property Rights

- TGD - The Department of Trademarks, Geographical Indications and Designs

- USAID – United States Agency for International Development programme

- WIPO - World Intellectual Property Organization

- WTO –World Trade Organization

1.	Basic Information

1.1	Programme: Technical Cooperation Facility II ENI/2016/039-337 / direct management

For applicants from the United Kingdom: Please be aware that eligibility criteria must be complied with for the entire duration of the grant. If the United Kingdom withdraws from the EU during the grant period without concluding an agreement with the EU ensuring in particular that applicants from the United Kingdom continue to be eligible, the beneficiaries from the United Kingdom will cease to receive EU funding (while continuing, where possible, to participate) or be required to leave the project on the basis of Article 12.2 of the General Conditions to the grant agreement.

1.2	Twinning Sector: Standardisation and certification, Trade & Industry (EC)

1.3	EU funded budget: 1.500,000 €

2.	Objectives

2.1	Overall Objective:

The overall objective of the project is to support development of Appellations of Origin and Geographical Indications (GIs) system in Georgia through creation of effective supporting tools with the provisions of the European Union’s GIs protection system.

2.2	Specific objective:

The purpose of the project is to assist National Intellectual Property Center of Georgia - Sakpatenti, together with other relevant stakeholders, to create legal, administrative and institutional mechanisms to enhance the GI protection and control systems and strengthen capacity of the national institutions to implement and adopt the best European practices.

2.3	The elements targeted in strategic documents i.e. National Development Plan/Cooperation agreement/Association Agreement/Sector reform strategy and related Action Plans

This Twinning project contributes to the implementation of some of the main goals described in the strategic documents of the Government of Georgia (GoG) as well as in international agreements:

Under the Georgian Social-Economic Development Strategy 2020 one of the main objectives is to strengthen the legislative and institutional framework relevant to the protection of intellectual property and introduction of the best European practices in accordance with the EU-Georgian Association Agreement.

The Government Platform 2016-2020 articulates Government’s priority directions for upcoming years. The Government of Georgia values strong trade relations and continues to see progress in this area. Consequently, the export potential of Georgian products and diversification will be improved.

Another key goal of Georgia’s economic policy is the effective and proper use of opportunities from free trade agreements. As a result, Georgia will continue the implementation of active policy, in particular: to maximize the opportunities provided by free trade agreements and to ensure compliance with the EU requirements.

The government will continue its agricultural policy agenda, aimed at improving competitiveness based on principles of sustainable development, increasing stable production of high quality products, and ensuring food security, food safety and rural development. Significant attention will be paid to the promotion of agricultural products in international markets.

The development of GIs protection system is reflected in the Rural Development Strategy of Georgia 2017-2020 of Georgia as well. The strategy emphasizes the role of geographical indications protection system for development of rural areas and considers it as a tool for increasing competitiveness of Georgian agricultural products, with the direct effect on the export volume.

The project aims to provide support in further effective and efficient implementation and fulfilment of the objectives set out in the EU-Georgia Association Agreement (AA), including Deep and Comprehensive Free Trade Area (DCFTA). Chapter 9 of the DCFTA refers to the Intellectual Property and the Sub-Section 3 of this Chapter is dedicated to GIs. Noteworthy is the “Agreement between the European Union and Georgia on protection of geographical indications of agricultural products and foodstuff”, which became the part of this chapter. AA Article 423 Relation to other agreements, (3). This Agreement replaces the Agreement between the European Union and Georgia on protection of geographical indications of agricultural products and foodstuffs, signed on 14 July 2011 in Brussels and which entered into force on 1 April 2012.The agreement applies to the recognition and protection of GIs which are originating in the territories of the contracting parties. Through this agreement more than 3500 EU originated GI products were protected in Georgia and 34 Georgian GI products got their protection in the EU.

In its turn the DCFTA envisages important administrative mechanisms, which guarantee the protection of GIs in the territories of parties from unauthorized registration and production of counterfeited goods and from their presence at the parties’ consumer markets.

Several multilateral agreements also provide for the protection of Geographical Indications and Appellations of Origin. Georgia is the contracting party of the Agreement on Trade-Related Aspects of Intellectual Property Rights (TRIPS), Lisbon Agreement for the Protection of Appellations of Origin and their International Registration and the Paris Convention for the Protection of Industrial Property.

The proposed project directly supports the priorities that have been specified in the Association Agenda (Trade and Trade-Related Matters; Intellectual Property Rights (IPR)) (2.5) namely:

- Ensuring rights holders from both Parties a high level of IPR protection and enforcement;

- Strengthening the enforcement capacity of relevant governmental bodies or executive agencies, as well as ensuring proper functioning of the judicial system to guarantee access to justice for rights holders and implementation of sanctions;

- Supporting functioning of the National Intellectual Property Centre of Georgia “Sakpatenti” in order to ensure protection of industrial property rights and copyright]; extending cooperation with third country authorities and industry associations;

- Taking measures to increase public awareness in the field of intellectual and industrial property protection and ensuring effective dialogue with rights holders;

- Taking effective measures against counterfeiting and piracy, including production of statistical information on those activities to be shared between the Parties.

In this regard it is very important to develop GI protection and control system and respective legislation in Georgia that will meet the EU standards.

Finally, the Government of Georgia approved the PAR Roadmap for 2015-20 in August 2015, along with its Action Plan for 2015-16. The Roadmap includes reforms in the area of policy development and co-ordination, human resource management, accountability, service delivery, public financial management, and local self-government. The Administration of Government (AoG) monitors the implementation of the roadmap. Mid-term reviews on the implementation of the Roadmap and a new action plan for 2019-2020 with clearer output and outcome indicators are under preparation.

3.	Description

3.1	Background and justification:

National Intellectual Property Centre of Georgia - Sakpatenti is a governmental agency - Legal Entity of Public Law, which determines state policy in all fields of Intellectual Property. Sakpatenti is in charge of development of Intellectual Property system in Georgia and is accountable before the Prime Minister of Georgia. According to the Art. 8 of the Patent Law of Georgia, Sakpatenti is headed by a Chairman, who is appointed and dismissed by the Prime Minister of Georgia.

Sakpatenti plays an important role in coordinating IP enforcement at all levels; inter alia through the Interagency Council on IP Rights Enforcement, which was created according to the decree of Prime Minister of Georgia and works under Sakpatenti. Members of the council are representatives of the different line Ministries: Ministry of Internal Affairs; Ministry of Economy and Sustainable Development; Ministry of Environmental Protection and Agriculture and Ministry of Finance; also representatives of other relevant governmental and private organizations.

Main functions of Sakpatenti include:

a)	Determining of the IP Policy of Georgia;

b)	Drafting of laws and other legislative acts related to intellectual property;

c)	Examination, granting protection and keeping register on intellectual property objects;

d)	Representing Georgia before international organizations;

e)	Implementation of projects and relevant activities on the local and international level in order   to fulfil its functions;

f)	Conducting public awareness activities in the field of IP etc.

Development and protection of intellectual property rights is one of the main priorities of the Government of Georgia. Paramount importance is granted to the protection and development of Geographical Indications in the country. The importance of geographical indications for Georgia is stipulated in many activities of the governmental institutions and is underlined in multilateral or bilateral agreements. It has to be highlighted that issues related to the protection of geographical indications are included in the agendas of all intergovernmental economic commissions with different countries.

Recently, international interest in one of the most important objects of intellectual property – GIs has grown significantly and keeps on growing. It is considered as an effective tool for increasing recognition and competitiveness of local products that are unique due to natural conditions of their place of origin or local traditions and knowledge.

Agriculture is a field where Georgia has a great export potential. So the agricultural products are the cornerstone of the development of the country’s “branding” strategy. Development of GIs system for agricultural products could become the most effective instrument for increasing of Georgian products’ export potential.

As the most of the traditional Georgian products (wine and various agricultural products) are export-oriented and they are often counterfeited in different European countries’ markets, which damages the reputation of the Georgian goods and consequently Georgian economy.

In 2015 the Government of Georgia and the World Intellectual Property Organization (WIPO) signed a Memorandum of understanding. Art.4 of the Memorandum states that both parties will cooperate for development of GIs system in Georgia.

Sakpatenti follows its 2014-2018 action plan, according to which, development of the GI system and elaboration of effective control mechanisms on GIs is one of the key priorities. For the purpose of development of the GIs system in Georgia, Sakpatenti helps private sector and relevant institutions:

- In the process of exploration and analysis of the potential GIs with the aim of their further registration;

- In establishment of GI control system and facilitation of its implementation.

As mentioned above the development of GIs protection system is reflected in the Rural Development Strategy of Georgia 2017 – 2020. Thus, development of the GIs protection system and introduction of efficient control mechanisms on GIs is one of the commitment of the country, which should be elaborated in cooperation with other stakeholders involved in protection and controlling of GIs; such as the National Wine Agency of Georgia and National Food Agency of Georgia, also the Ministry Environment Protection and Agriculture (MEPA) (former Ministry of Agriculture of Georgia) and the Unified National Body of Accreditation - Accreditation Centre.

Existing Georgian legislation on GIs is in conformity with the EU acquis. However, for the implementation of the relevant legislation it is necessary to develop more efficient control system and proper control mechanisms on GIs.

The proposed Twinning project will address some important issues such as the establishment of GIs control bodies, development and improvement of the legal framework, enhancement of institutional and administrative capacities of GI control systems.

As in all other IP fields, Sakpatenti determines the policy in the field of GIs and as the main counterpart of these project has a longstanding experience in the development of GIs system in the country. Sakpatenti with other relevant stakeholders applied for this programme to share the best European practice in the given field. The project will support to strengthen the capacity building of Sakpatenti and other relevant stakeholders.

The Law on Appellations of Origin of Goods and Geographical Indications of Georgia entitles Sakpatenti to carry out measures necessary for the registration and protection in another state of an appellation of origin or geographical indication, which is registered in Georgia, only if at the time of registration of an appellation of origin or geographical indication at Sakpatenti, the applicant is a public authority or legal entity of public law.

In recent years Sakpatenti has undertaken many actions towards protection of Georgian GIs in several countries but still needs further guidance to fully apply established EU standards. This Twinning project will be a complementary support along with other interventions provided in the respective field.

During the project implementation specific attention will be paid to ensure that legal approximation process supported under this Twinning project will be according to the national framework on policy and legislative development and to the better regulation approach supported also at the EU level. A better regulation approach requires that policies and legislation are prepared on the basis of the best available evidence (impact assessments) and according to an inclusive approach involving both internal and external stakeholders.

Furthermore, building on the lessons learnt and the Better Regulation agenda promoted at the EU level, this Twinning project will contribute to the overall public administration reform in Georgia by ensuring the introduction of an inclusive and evidence-based approach to policy-making and legal drafting in the respective sector. It will also pay specific attention to accountability and reporting lines between concerned institutions (agencies and ministries). Sakpatenti will ensure participation of the representatives of stakeholders in the activities that will be undertaken within the project (National Wine Agency, National Food Agency, Ministry of Economy and Sustainable Development, etc.)

3.2	Ongoing reforms:

During recent years Sakpatenti has implemented number of actions in relation to development of IPR in the country and special attention has been paid to GIs.

For the time being almost all Georgian geographical indications and Appellations of Origin (AOs) were applied for registration by the governmental institutions. In the case of wines, all Georgian AOs of wines were applied for registration by the National Wine Agency of Georgia. All other GIs and AOs like mineral waters and cheeses were applied for registration by the MEPA of Georgia.

It has to be highlighted that last four GIs were registered by producers associations, using EU practice. Different activities, namely, training of producers, public awareness raising campaigns, legislation reform etc. have been provided in order to increase the involvement of the private sector (GI producers, farmers etc.) in management of existing GIs and make attempts to replace governmental agencies gradually.

3.3	Linked activities:

The following projects directly or indirectly supported Sakpatenti during the past years.

Sakpatenti has applied and implemented several TAIEX  interventions during recent years but the following ones were related directly to protection of GIs. Study Visit –Experience sharing of INAO (National Institue of Origin and Quality of France) in the field of GIs protection and appilation of origin (ref 46862); Duration: 01.04.2012-06.04.2012; Main activities: In the framework of the visit, French experience in the field of GIs protection and enforcement was discussed. Georgian side was given answers to all important issues which were standing in the field of GI protection and enforcement mechanisms. As in April 2012 the Agreement between the European Union and Georgia on protection of geographical indications of agricultural products and foodstuff was signed, this study visit had utmost importance in terms of sharing European experience in the protection of GIs.

Study Visit - Building capacity in Management and Control of GIs of Foodstuffs (ref.63270); Duration: 07.11.2016 - 11.11.2016; Main activities: the event envisaged understanding legal and administrative requirements for controlling of production and marketing of agro products, among them nuts and fruits protected by GIs in Italy.

Project title – under ENPARD Georgia-Geographical Indications technical assistance; funded by EU;

Period: 2014; Main activities: Establishment of four GI associations and creation of specifications for four GI products (tea, greens, potato, honey). All these GIs were registered at Sakpatenti and later materials were sent to the European Commision for their protection through the mechanisms provided by the Association Agreement between Georgia and the EU.

Project title – FAO-EBRD project “Support to sustainable value chains through the development of geographical indications in the dairy sector”; EU funded; Duration: February 2017-February 2020; Main activities: Support provided as a part of the FAO-ENPARD programme: Technical capacity development of the Ministry of Environment Protection and Agriculture, the aim is the development of the suitable legal and institutional framework for geographical indications for cheeses in Georgia.

FAO has been assisting MoA on GIs since ENPARD I under their contract: Capacity Development of the Ministry of Environment Protection and Agriculture of Georgia (MEPA) (CRIS 317-764); Duration 23.05.2013 to 23.02.2017.

Under the ENPARD II contract - Technical Assistance to the Ministry of Environment Protection and Agriculture of Georgia (CRIS 358-831); Duration 17.03.2017 - 17.03.2019; Support is continued to the MEPA. Through the intervention following actions are envisaged: Drafting of a ministerial decree for certification and control; Procedure manual and guidelines for the assessment of GI request; Procedure manuals for GI applicant; Practical guidelines on how to develop sustainable GI, for value chain actors and facilitators

Project title - Founding of Nonprofit Organization OriGIn; Funded by: Sakpatenti, National wine Agency, Donors. Duration: 2016-ongoing; Main activities: OriGIn Georgia is mainly focusing on the exploration of potential Georgian GIs, helping producers of GI products to export their product on potential markets, enhancing the capacity building and the training capacities of the immediate beneficiaries who are the producers of GI products of Georgia. This is done mainly through: Specialist trainings; organizing various trainings/seminars etc. It has also to be mentioned that newly founded OriGIn Georgia signed a license agreement with the Organization for an International Geographical Indications Network OriGIn.

Project title – Experience sharing of INAO (National Institue of Origin and Quality of France) in the field of protection of Appellations of origin; funded by: WIPO; Duration: 01.06.2015 - 05.06.2015; Main activities: Workshop on understanding of the experience of INAO (National Institue of Origin and Quality of France) in the field of protection of Appellations of Origin. During the study visit important issues regarding protection of Appellations of Origin were considered, including the organization of quality signs in France and the EU, principles and regulations, support from the Member States, role of the Quality signs policy regarding rural development and economic issues and etc.

Related Programmes and Projects

The reform of Public Administration (PAR) is of utmost importance for the country and the process is supported through donor community.  The EU total contribution to the “Support to the Public Administration Reform in Georgia” 2016-2019, is EUR 30 000 000 Euro. Out of which EUR 20 000 000 is budget support share and EUR 10 000 000 for complementary support. The objective of the programme is to improve the efficiency, accountability and transparency of the public administration of Georgia, in line with the key Principles of Public Administration that have been developed by OECD/SIGMA in close cooperation with the European Commission. It will have a particular focus on the improvement of the policy planning and coordination capacities and processes in the central public administration. The professionalization of the civil service (including the reform of the civil service training system) will also be supported through the programme.

Project Title:  Facility for the implementation of the Association Agreement in Georgia; EU funded; Duration: 2015-2018; Description: The project provides policy advice and capacity building support to the Georgian Government in coordinating the implementation of the Association, strengthening the institutional capacities of the line ministries and other public institutions to carry out the required reforms, including on policy development and legal approximation processes.

Project Title:  Legislative Impact Assessment, Drafting and Representation; EU funded; Duration: 2015-2017; Description: The project aims to improve the legal drafting process at the central level of government (through promoting better coordination among relevant entities, and introduction of the regulatory impact assessment of draft legislation) as well as the Government's international representation and reporting functions with special emphasis on the Ministry of Justice.

Two other projects, EU funded – implemented by GIZ, and USAID-funded ("G4G") also support LA and Regulatory Impact Assessment (RIA) but with focus on economic sphere.

Policy and legislative process

The national Policy planning system reform strategy, adopted by the Government of Georgia in August 2015 recognises the current weak link between the policy planning process and legislation drafting, the absence of practice of legislative impact assessment and the weak institutional capacity of ministries in legal drafting. The OECD/SIGMA 2018 assessment in the policy development and coordination area highlights a number of weaknesses in the current (policy-making) and legislative process. The assessment specifically notes the reoccurring problem with implementation of laws, which can be attributed to the low quality of laws due to weaknesses in the law-making process. There is a pressure to complete numerous legal reforms in the shortest possible time: "This situation inevitably places enormous pressure on the combined law-making resources of the Government and the Parliament and leaves little time for essential elements of a well-ordered law-making process, such as regulatory impact assessments or proper consultation with civil society." Improvement of the legislative drafting process and quality of legislation is now a priority area of action for the Administration of Government under the Prime Minister (steering the policy-making process) and all line ministries. This primarily involves the Administration of Government, Ministry of Justice, and Ministry of Economy and Sustainable Development. The Government, with international support, is currently developing a uniform methodology for regulatory impact assessments, to be used by all legal drafters. Similar effort is being made with regards to developing a uniform approach to legal approximation.

To sustain the legal approximation process the Ministry of Justice (MoJ) with the support of the EU assistance (under above mentioned projects Association Agreement Facility and Legal Drafting projects) elaborated Legal Approximation Guidelines and Manual. These documents provide a group of key principles and techniques of approximation that will guide and orient legal drafters throughout the approximation process.

These documents should be used consistently, not only by MoJ, but also by all line ministries, and institutions tasked with the approximation exercise. Such proceedings will help to ensure the achievement of a steady and sustainable approximation path.

3.4	List of applicable Union acquis/standards/norms:

- Regulation (EU) No 1151/2012 on quality schemes for agricultural products and foodstuffs;

- Regulation (EU) No 608/2013 concerning customs enforcement of intellectual property rights and repealing Council Regulation;

- Regulation (EU) No 1308/2013 of the European Parliament and of the Council of 17 December 2013 establishing a common organisation of the markets in agricultural products and repealing Council Regulations (EEC) No 922/72, (EEC) No 234/79, (EC) No 1037/2001 and (EC) No 1234/2007;

- Regulation (EC) No 110/2008 of the European Parliament and of the Council of 15 January 2008 on the definition, description, presentation, labelling and the protection of geographical indications of spirit drinks and repealing Council Regulation (EEC) No 1576/89;

- Commission Regulation (EU) No 164/2012 of 24 February 2012 amending Annex III to Regulation (EC) No 110/2008 of the European Parliament and of the Council on the definition, description, presentation, labelling and the protection of geographical indications of spirit drinks;

- Regulation (EU) No 251/2014 of the European Parliament and of the Council of 26 February 2014 on the definition, description, presentation, labelling and the protection of geographical indications of aromatised wine products and repealing Council Regulation (EEC) No 1601/91;

- Commission Regulation (EC) No 607/2009 of 14 July 2009 laying down certain detailed rules for the implementation of Council Regulation (EC) No 479/2008 as regards protected designations of origin and geographical indications, traditional terms, labelling and presentation of certain wine sector products

3.5	Results per component

The Twinning project shall provide advisory support to Sakpatenti and other authorities for the implementation of key elements of the relevant EU legislations.

Component 1 - Approximation of primary and secondary legislation related to Geographical Indications GIs in accordance with the relevant EU directives

Despite the fact that Georgia has well established IPR system still there are directions to be enhanced and as already mentioned above advancement of the GIs field is one of the priorities. There is a need to assess the degree of compliance of existing primary and secondary legislation with the EU standards and requirements; develop the list of existing primary and secondary legislation related to GIs protection and quality control systems that should be abolished or revised and based on the assessment prepare relevant amendments to be presented to the Government of Georgia.

Result 1.1 – Contribution to the revision of the Legal framework on protection and quality control system of GIs in compliance with the EU legislation

Indicators of Achievement:

- Amendments to the relevant primary and secondary legislation (i.e. by-laws incorporating special rules and procedures), with explanatory note, including regulatory and fiscal impact assessments, prepared in an inclusive process, agreed with  corresponding authorities and accompanied with table of Concordance preferably within the first half of the project implementation.

Component 2 - Capacity building of relevant state authorities and private sector (producers and/or producers’ associations) for enhancing and developing GI protection system

Through the second component it is highly preferable to assess the administrative/institutional capacities of Sakpatenti and other stakeholder institutions. Develop relevant recommendations for improvement considering accountability lines between institutions. It is also very important to perform training needs assessment of all relevant parties and prepare short and long term training plans consistent with the general civil service training system, for Sakpatenti and other stakeholder institutions’ staff in order to fulfill their duties effectively. The producers and producers’ associations should also be targeted. In parallel with the capacity building activities relevant operational/procedural documents should be elaborated.

Result 2.1 - Capacity of the state authorities and private sector to implement the EU best practices strengthened and required strategies developed

Indicators of Achievement:

- Plan for improvement (e.g. requirements for re-structuring of administrative units, human/financial resources needed for permits issuing) of the administrative structure to enforce the EU regulations prepared preferably within the first half of the project implementation;

- Plan for improvement of resources and capacity of producers and producers’ association prepared and accepted by relevant parties, after completion of the draft of the secondary legislation indicated in Result 1.1;

- Sakpatenti and other relevant institutions’ staff trained and quality of their performance improved by the end of the project implementation.

Result 2.2 - Inter-institutional co-operation for the establishment of the functional GI protection system strengthened

Indicators for Achievement:

- Improvement plan for establishing efficient GI protection system implemented upon completion of the draft of the secondary legislation indicated in Result 1.1;

- General manual (“roadmap”) on GI protection system development in Georgia (to be specifically considered for its proper implementation) prepared and accepted by all involved parties upon completion of the draft of the secondary legislation indicated in Result 1.1;

- Number of joint actions by Sakpatenti and other relevant institutions increased in regards to protection of GIs.

Component 3 - Organization of quality control system of GIs in line with the EU regulations and EU best practices

In order to have well-organized quality control system of GIs, the existing administrative/institutional capacities of the inspecting bodies need to be analyzed in line with the EU legislation and requirements (staff, structure, trained experts in specific areas, equipment, documentation, coordination and competences, accountability lines between institutions); Report on the analysis of the capacity in the private sector (associations, producers, other relevant groups) would be very helpful together with the assessment of current network of certified laboratories and to provide recommendations for its improvement/expansion.

Enhancing knowledge and skills at the state and local authorities’ level, as well as producers and producers’ associations is of upmost importance, so relevant trainings/seminars need to be conducted.

Through the component the regional analysis regarding impact of the supply chains on regional economics, vision development, related to the introduction of products protected by AOs and GIs should be performed, and their potential to stimulate rural development should be clearly defined.

Result 3.1 - Existing institutional inspection and GI quality control system strengthened

Indicators of Achievement:

- Plan for establishing quality control and inspection schemes on state and producers’ level for GIs, namely drafting rules for providing control by relevant institutions, training of experts, etc. prepared preferably within the first half of the project implementation;

- Quality control and inspection schemes for GIs in conformity with the relevant plan mentioned above implemented upon completion of the draft of the secondary legislation;

- Quality of inspections carried by inspection bodies improved by the end of the project implementation;

- 4 specifications for registration of new GIs or already registered GIs incorporating control mechanisms (external and internal) for 4 different categories: dairy, meat, vegetables and wine products available by the end of the project implementation;

All relevant documentation developed within the Twinning project should be provided both in English and Georgian languages. Any internal procedure developed with the support of the project will not contradict existing procedures horizontally regulating the functioning of public institutions.

3.6	Means/input from the EU Member State Partner Administration(s)*:

Member State(s) is/are kindly requested to develop activities in the submitted proposal which are needed in order to achieve the results stipulated in the fiche.

The MS PL will be expected to devote a minimum of 3 days per month to the project in his/her home administration. In addition, he will coordinate from the Member state side the work of the Project steering Committee (PSC). MS Project Leader may participate in the project also as short-term expert (STE). In this case the MS Project Leader should satisfy requirements stipulated in the fiche for both the Project Leader and the relevant STE profile.

The RTA will be located in the premises of the SAKPATENTI in the beneficiary country on a full time basis and will be responsible for the direct implementation of the project under the overall supervision of the MS Project Leader.

The RTA will maintain day-to-day cooperation with the beneficiary administration and coordinate the work performed by the STEs. The RTA will have a key role in the coordination of the inputs required for the successful implementation of all the project activities.

Minimum two visibility events will be organized in the course of the implementation of the project; Kick-off meeting at the start of the implementation and the Final meeting at the end of the implementation of the project activities.

The required MS experts must either be civil/public servants of the relevant MS administration or be permanent staff of authorised mandated bodies. All experts must comply with the requirements set in the Twinning Manual 2017.

The RTA should be supported by a permanent RTA Assistant. The RTA assistant should be in close collaboration with the BA. The RTA assistant will perform general project duties and providing translation and interpretation services as necessary, practical arrangements for the project, such as organizational issues of expert missions, conferences, training, seminars, maintaining project records and etc. Until the RTA can select and hire an assistant, the Beneficiary administration makes a member of its staff available to support the RTA in his/her daily tasks.

A full-time language assistant should also be recruited. She/he should perform most of the required interpretation/translation services. She/he will provide day-to-day interpretation/translation to the RTA and project experts during missions.

Whenever required and needed for simultaneous interpretation during seminars and workshops, translation of large volume of documents additional interpretation may be procured and funded by the project.

Proposals shall include only the CVs of the proposed PL, of the RTA and of the Component Leaders

3.6.1 Profile and tasks of the PL:

Profile:

- A high ranking Member State official or assimilated agent with a sufficient rank to ensure an operational dialogue at political level;

- Considerable experience of at least 5 years in the field of Intellectual Property with good understanding of subjects related to project activities, including at least 3 years on a senior management position in a Member State institution/full mandated body;

- Deep understanding of the EU standards/requirement  in Intellectual Property right and especially Geographical Indications;

- Good leadership skills;

- Knowledge of English Working language;

- Experience in project management would be an asset;

Tasks:

- Overall direction,  supervision, guidance and monitoring of the project;  ability to mobilise the necessary expertise in support of the efficient implementation of the project;

- Signature of project progress reports and the final report prepared with the support of RTA;

- Timely achievement of the project results;

- Co-Chairing of project steering committees;

- Provision of legal and technical advice and analysis whenever needed;

- Ensuring sound implementation of the envisaged activities.

3.6.2 Profile and tasks of the RTA:

Profile:

- University level education in a relevant discipline or equivalent professional experience in a related field of minimum 7 years

- Minimum 3 years of experience in the field of Geographical Indications;

- Sound comparative knowledge of relevant EU legislative and institutional requirements related to the various components of this project;

- Wide knowledge of EU legislation in the field of Geographical Indications protection, controls systems/schemes;

- Good training, public speaking, and written communication skills;

- Excellent computer literacy (Word, Excel, Power Point etc.);

- Excellent command of spoken and written English;

- Previous experience in project management would be an asset;

Tasks:

- Overall coordination project implementation and of all activities;

- Coordination of the activities of the team members in line with the agreed work plan to enable timely completion of project outputs;

- Provide technical input to the project whenever needed and provision of advice in his field of expertise;

- Liaise with MS and BC PLs and daily contacts with BC RTA counterpart;

- Preparation of the initial and subsequent work plan(s) and project progress reports, together with PL, to be submitted to the Steering Committees;

- Liaison with EUD Project Manager and Programme Administration Office (PAO);

- Liaison with other relevant projects and relevant Georgian institutions.

He/she will be introduced to the BC stakeholders of the project, counterparts and staff. He/she will also hire a Project Assistant as well as a Language Assistant through an appropriate selection procedure.

3.6.3 Profile and tasks of Component Leaders:

3.6.3.1 Profile and tasks of Component Leader 1:

Profile:

- University degree in law, or similar discipline relevant to the project or equivalent professional experience in a related field of minimum 5 years;

- Minimum 3 years of progressively responsible experience in GI’s;

- Experience in standard setting or other relevant regulatory experience;

- Excellent knowledge of relevant International and European legal framework;

- Solid experience in legal drafting coordination process relevant to the project scope and fiscal impact assessments;

- Solid experience of developing and executing strategy and delivering results;

- Relevant experience in capacity building activities;

- Exceptional time management, organization, and prioritization skills;

- Fluency in written and spoken English;

Tasks:

- Component coordination, guidance and monitoring;

- Conducting analysis of the area relevant to the component;

- Preparing and conducting training programs;

- Timely proposals for any corrective measures;

- Liaise with MS and BC PLs and daily contacts with RTA  and BC counterpart;

Profile and tasks of Component Leader 2:

Profile:

- University degree in law, or similar discipline relevant to the project ; or equivalent professional experience in a related field of minimum 5 years;

- Minimum 3 years of progressively responsible experience in GI’s;

- Experience in standard setting or other relevant regulatory experience;

- Excellent knowledge of relevant International and European legal framework;

- Solid experience in legal drafting coordination process relevant to the project scope and fiscal impact assessments;

- Solid experience of developing and executing strategy and delivering results;

- Relevant experience in capacity building activities;

- Exceptional time management, organization, and prioritization skills;

- Fluency in written and spoken English;

Tasks:

- Component coordination, guidance and monitoring;

- Conducting analysis of the area relevant to the component;

- Preparing and conducting training programs;

- Timely proposals for any corrective measures;

- Liaise with MS and BC PLs and daily contacts with RTA  and BC counterpart;

Profile and tasks of Component Leader 3:

Profile:

- University degree or equivalent professional experience in a related field of minimum 5 years;

- Minimum 3 years of working experience in GI Association in EU country;

- Sound knowledge of GI Control system, including internal and external control;

- Experience in GI system development and implementation;

- Experience in GI control system development and implementation;

- Experience in marketing strategies and promotional activities;

- Exceptional time management, organization, and prioritization skills;

- Fluency in written and spoken English;

Tasks:

- Component coordination, guidance and monitoring;

- Conducting analysis of the area relevant to the component;

- Preparing and conducting training programs;

- Timely proposals for any corrective measures;

- Liaise with MS and BC PLs and daily contacts with RTA  and BC counterpart;

3.6.4 Profile and tasks of other short-term experts:

Specialist civil servants/staff of approved mandated bodies will be made available by the Twinning Partner (MS) to support the implementation of the activities and agreed with the beneficiary administration. Specific and technical matters relevant to this Twinning project will be taken over by a pool of STEs. The detailed expert input shall be established when drawing up the Twinning work plan.

Below some indicative qualifications and tasks: (STEs CV should not be included in the MS proposal)

Indicative Profile of STEs

- Minimum of 5 years of experience in the field of protection of GIs and GI control systems/schemes;

- Demonstrated good report writing and communication skills and be familiar with various approaches in implementation of the EU legislation;

- Experience in drafting of legislation, including regulatory impact assessment;

- An excellent knowledge of the EU GI control systems/schemes;

- Experience in preparing operational instructions;

- Excellent knowledge of written and spoken English;

- Excellent computer literacy (Word, Excel, Power Point etc.).

Tasks of short term experts

- Contributing to the sustainability of the project by ensuring that aspects of the project related to their field of expertise are implemented timely;

- Supervision and on-site coordination of all activities related to their field of expertise and performed under this project;

- Timely proposals for any corrective measures;

- Assistance with drafting of strategic documents and legislation as well as preparation of trainings, study tours, workshops, seminars, etc

- Liaise with RTA and BC counterparts;

4. 	Budget

Maximum Budget available for the Twinning Grant 1, 500,000 €

5. 	Implementation Arrangements

5.1 	The European Union Delegation in Tbilisi, Georgia, will be responsible for the tendering, contracting, payments and financial reporting, and will work in close co-operation with the Beneficiary. The person in charge of this project at the Delegation of the European Union to Georgia is:

Mr.Irakli Khmaladze

Project Manager, Economics, Regional Development and Public Finance

Delegation of the European Union to Georgia

38 Nino Chkheidze St, 0102 Tbilisi, Georgia

Tel: +995 32 2943 763

E-mail: irakli.khmaladze@eeas.europa.eu

5.2 	Institutional framework

The main beneficiary institution of the Twinning project is the National intellectual Property Center of Georgia Sakpatenti. As mentioned above Sakpatenti determines IP Policy and priority directions in the country and is in charge of development of Intellectual Property system in Georgia.

Sakpatenti Headquarter is located in Mtskheta, with its second office in Tbilisi. The majority of 90 employees of Sakpatenti work in Mtskheta.

In cooperation with other stakeholders, namely National Wine and Food Agencies of Georgia, Sakpatenti creates legal and regulatory framework.

In the given sphere Sakpatenti is responsible for maintenance of the following registries:

- State Register of the Applications of Origin and Geographical Indications of Goods;

- GIs users’ register.

The Department of Trademarks, Geographical Indications and Designs (TGD) has 21 employees. The department determines the priority directions in the field of GIs. It elaborates concrete measures for the development of GI system and is involved in the preparation process of laws and regulations. The TGD department is in charge of registration of new GIs, examination of applications, alterations and amendments to the existing GIs etc.

The Legal and international relations department (10 employees) is responsible for preparation of legal acts, representing Sakpatenti before the courts and international organizations. In order to ensure the harmonization of Georgian legislation with the EU legislation the department successfully managed to draft relevant amendments to the laws and bylaws in the field of intellectual property.

The project will be located in the premises of Sakpatenti which will also ensure providing the MS experts with the documents necessary for project implementation.

The beneficiary institution will dedicate all necessary human and financial resources in order to guarantee an effective implementation of the respective project. In particular, the beneficiary institution will insure the availability of the following provisions:

- Adequately equipped office space for the RTA and the RTA’s assistant for the entire duration of their secondment (in particular a desk, a telephone line, PC with e-mail account and internet access, possibility to use fax & copy services);

- Adequate conditions for the STEs to perform their work while on mission to the BC;

- Training and conference venues as well as presentation and interpretation equipment;

- Its active involvement in preparation of the Steering Committee meetings and participation of its members;

- The availability of the BC human resources (BC experts) during the implementation of the activities.

Main Stakeholders:

National Wine Agency, which is responsible for: regulation of viticulture - wine making industry in Georgia; state control of the appellations of origin of wines and wine brands; preparation of proposals and recommendations for functionality and development of the branch; interrelations with national and international organizations in the viticulture field.

National Food Agency, which is responsible for food/feed safety and quality assurance, as well as, carries out state control over the fulfillment of hygiene and phytosanitary rules and requirements; interrelations with national and international organizations in the food/feed safety sphere.

All stakeholder representatives will be involved in the project implementation according to their mandate and responsibilities.

5.3	Counterparts in the Beneficiary administration:

The PL and RTA counterparts will be staff of the Beneficiary administration and will be actively involved in the management and coordination of the project.

5.3.1	Contact person:

Ms. Ana Khoshtaria

Head, International Affairs Division,

5 Antioch St., 3300, Mtskheta, Georgia

5.3.2	PL counterpart

Mr. Nikoloz Gogilidze,

Chairman,

5 Antioch St., 3300, Mtskheta, Georgia

5.3.3	RTA counterpart

Ms. Ketevan Kiladze

Head, Legal and International Affairs Department

5 Antioch St., 3300, Mtskheta, Georgia

6.	Duration of the project

Duration of the execution period: 27 months. [The execution period will end 3 months after the implementation period of the Action (work plan) which will take 24 months].

7.	Sustainability

The achievements of the Twinning project will be maintained by the beneficiary institution even after finalization of the project operation phase. The sustainability of the project will be achieved through a suitable implementation of the project activities and availability of trained personnel in the sphere of Geographical Indications protection and quality control system. Training measures will be organised in accordance with the general requirements of the Civil Service.

The project will also promote close cooperation with the concerned institutions to ensure consistency of the legal framework and alignment of the system in support to development and protection of GIs. In order to contribute to develop implementable legislation, the twinning project will support preparation of analytical prerequisites i.e. preparation of concept notes, impact assessments, estimation of implementation costs.

The achievements of this Twinning project are anticipated to contribute to the development of the GI system in Georgia according to well established practices and standards of the EU, which in its turn creates favourable environment for economic development at the regional and state level in Georgia.

The Beneficiary Institution is fully committed to ensure the long term impact of the Twinning project. During the project implementation, the twinning partners should develop documents/hand-outs, guidelines that will be easily accessible for later use by the beneficiary administration. Staff benefiting from trainings/study visits shall transfer knowledge through subsequent trainings to their colleagues.

This means inter alia that efective mechanisms are put in place by the beneficiary institution to disseminate and consolidate project outcomes.

8.	Crosscutting issues (equal opportunity, environment, climate etc…)

Sakpatenti will ensure equal opportunities between male and female in the management and implementation of the project, including equal opportunities in training, site visits and participation in all of the Projects’ missions and events; contributing thus to the promotion of gender equality.

The principle of implementation of this Twinning project will be based on a paperless work environment. This means, in particular, minimising paper use during project implementation by the maximum feasible use of emails and, if available, project web-site and/or project electronic data base for co-operation between partners.

9.	Conditionality and sequencing

There is no precondition set for this twinning project but it is foreseen that a series of activities/ measures would have been undertaken by the Sakpatenti in order for the project to start in satisfactory conditions.

Sakpatenti commits itself to provide the contributions stated in the Fiche, project activities will follow the same pattern such as:

- Joint reflection of MS and Sakpatenti experts;

- Drafting of a documents jointly by MS and Sakpatenti experts;

- Opinion given by Sakpatenti and MS experts;

- Finalisation of a first draft and training delivered jointly;

- Application by Sakpatenti and other relevant institutions’ staff;

- Peer/review and possible revision of the document;

- Ensuring access to indispensable information and documents;

- Adequate conditions for the STEs to perform their work while on mission to the BI;

- Providing suitable venues and equipment for the training sessions and meetings that will be held under the Project;

10.	Indicators for performance measurement

- Relevant staff from Sakpatenti (higher management and filed specialists) will be involved in the project implementation and nominated for the overall coordination and project management;

- Providing the information/documents in regards with the national regulatory basis and arranging the relevant informative meetings;

- Appropriate area and facilities prepared and provided during the project implementation process;

- Training facilities provided;

- Coordination and meetings with other stakeholder organizations, donors or interested parties related to the Sakpatenti field of operation;

- Action Plan reports provided and updated;

11. 	Facilities available

The BC commits itself to deliver the following facilities:

- Adequately equipped office space for the RTA and the RTA assistant(s) for the entire duration of their secondment.

- Supply of office room including access to computer, telephone, internet, printer, photocopier.

- Adequate conditions for the STEs to perform their work while on mission to the BC.

- Provide suitable venues for the training sessions and meetings that will be held under the Project.

- Security related issues will be assured according to the standards and practices applicable for all Georgian public institutions.

ANNEXES TO PROJECT FICHE

- Organizational chart

- Logical framework matrix in standard format

- List of relevant laws and regulations

Annex 1: Organizational chart

National Intellectual Property Center of Georgia Sakpatenti

|  | N of staff |
| --- | --- |
| Administrative Department | 27 |
| Legal and International Relations Department | 10 |
| Trademarks, Geographical Indications and Designs Department | 21 |
| Inventions, New Plant Varieties and Animal Breeds Department | 22 |
| Management | 2 |
| Financial Department | 8 |
| Working on the basis of Temporary Agreements | 33 |
| Total | 123 |

Annex 2. Logical framework matrix

| Project title Establishing Efficient Protection and Control System of Geographical Indications (GIs) in Georgia |  | Programme name and number: | Technical Cooperation Facility II ENI/2016/039-337 |  |
| --- | --- | --- | --- | --- |
| National Intellectual Property Center of Georgia Sakpatenti |  | Total budget: 1.500,000.00 EUR | Financing: 100% 1,500,000.00 EUR |  |
| Overall objective | Objectively Verifiable Indicators | Sources of Verification | Assumptions |  |
| The overall objective of the project is to support development of Appellations of Origin and Geographical Indications (GIs) system in Georgia through creation of effective supporting tools with the provisions of the European Union’s GIs protection system. | - GI protection and control system in place and operational in compliance with EU standards; | - Relevant National Legislative acts; - Sakpatenti/Wine and Food agencies Reports; - Sakpatenti official buletin; - Monitoring/assessment reports by international organisations; - AA implementation reports; |  |  |
| Project purpose | Objectively Verifiable Indicators | Sources of Verification | Assumptions |  |
| The purpose of the project is to assist National Intellectual Property Center of Georgia - Sakpatenti, together with other relevant stakeholders, to create legal, administrative and institutional mechanisms to enhance the GI protection and control systems and strengthen capacity of the national institutions to implement and adopt the best European practices. | - Legal amendments in the field of GIs prepared and approved in accordance with an inclusive and evidence-based approach - Sakpatenti‘s and other relevant stakeholders‘ administrative procedures amended in accordance with the new requirements; - Quality of staff performance of Sakpatenti and other stakeholder representatives improved in application on new system; - 4 new GIs created in different fields; | - Amendment to the relevant primary and secondary legislation; - Assessment reports; - Guidelines and procedural documents; - Trainigs plans and materials; - Promotional materials; - 4 specifications of new GIs; | - Government commitment on Fulfilment of DCFTA requirements continued; - strong support and commitment from the senior management of Sakpatenti; - strong support and commitment from twinning partner(s); - Relevant staff of Sakpatenti and other stakeholder representatives available and involved in the process; |  |
| Results | Objectively Verifiable Indicators | Sources of Verification | Assumptions |  |
| Component 1 - Approximation of primary and secondary legislation related to Geographical Indications GIs in accordance with the relevant EU directives Result 1.1 – Contribution to the revision of the Legal framework on protection and quality control system of GIs in compliance with the EU legislation | - Amendments to the relevant primary and secondary legislation (i.e. by-laws incorporating special rules and procedures), with explanatory note, including regulatory and fiscal impact assessments, prepared in an inclusive and evidence based process, agreed with corresponding authorities and accompanied with Table of Concordance preferably within the first half of the project implementation; | - Legislative amendments; - Table of concordance; - Project documentation (list of participants, conclusions of stakeholder discussions, recommendations etc) ; - STE mission reports; | - Government commitment on Fulfilment of DCFTA requirements continued - Strong support and commitment from the senior management of Sakpatenti; - Availability of local staff; - Good communication between the Beneficiary and other stakeholders; - Twinning MS partner commitment; - All relevant documentation available. |  |
| Component 2 - Capacity building of relevant state authorities and private sector (producers and/or producers’ associations) for enhancing and developing GI protection system Result 2.1 - Capacity of the state authorities and private sector to implement the EU best practices strengthened and required strategies developed Result 2.2 - Inter-institutional co-operation for the establishment of the functional GI protection system strengthened | - Plan for improvement (e.g. requirements for re-structuring of administrative units, human/financial resources needed for permits issuing) of the administrative structure to enforce the EU regulations prepared preferably within the first half of the project implementation; - Plan for improvement of resources and capacity of producers and producers’ association prepared and accepted by relevant parties, after completion of the draft of the secondary legislation indicated in Result 1.1. - Sakpatenti and other relevant institutions’ staff trained and quality of their performance improved by the end of the project implementation; - Improvement plan for establishing efficient GI protection system implemented upon completion of the draft of the secondary legislation indicated in Result 1.1. - General manual (“roadmap”) on GI protection system development in Georgia (to be specifically considered for its proper implementation) prepared and accepted by all involved parties upon completion of the draft of the secondary legislation indicated in Result 1.1. - Number of joint actions by Sakpatenti and other relevant institutions increased in regards to protection of GIs. | - Proposal for restructuring; - Assessment reports; - Project documentation (list of participants, training materials, recommendations, ,stakeholder consultation conclusions etc) - Promotional materials; - STE mission reports; - Legislative amendments; - Capacity development plan for producers; - Guidelines and procedural documents; - Manual on GI protection system; |  | - Government commitment on Fulfilment of DCFTA requirements continued - Strong support and commitment from the senior management of Sakpatenti; - Availability of local staff - Good communication between the Beneficiary and other stakeholders; - Twinning MS partner commitment - All relevant documentation available |
| Component 3 - Organization of quality control system of GIs in line with the EU regulations and EU best practices Result 3.1 - Existing institutional inspection and GI quality control system strengthened | - Plan for establishing quality control and inspection schemes on state and producers’ level for GIs, namely drafting rules for providing control by relevant institutions, training of experts etc. prepared preferably within the first half of the project implementation; - Quality control and inspection schemes for GIs in conformity with the relevant plan mentioned above implemented upon completion of the draft of the secondary legislation; - Quality of inspections carried out by inspection bodies improved by the end of the project implementation; - 4 specifications for registration of new GIs or already registered GIs incorporating control mechanisms (external and internal) for 4 different categories: dairy, meet, vegetables and wine products available by the end of the project implementation; | - Twining documentation (list of participants, training materials, recommendations etc) - STE mission reports - Plans for quality control and inspection; - Quality control and inspection schemes; - Inspection reports; - 4 specifications of new GIs; | - Government commitment on fulfilment of DCFTA requirements continued - Strong support and commitment from the senior management of Sakpatenti; - Availability of local staff - Twinning MS partner commitment; - Good communication between the Beneficiary and other stakeholders - All relevant documentation available |  |
| Activities | Means | Specification of costs | Assumptions |  |
| Member State(s) is/are kindly requested to develop activities in the submitted proposal which are needed in order to achieve the results stipulated in the Fiche | Consultations, analyses, preparation of documentation, trainings, workshops, study visits | Twinning project: 1 500 000-, EUR | See assumptions to each results |  |

Annex 3: List of relevant laws and regulations administered by stakeholder institutions

National Intellectual Property Center of Georgia Sakpatenti

1. Georgian Law ,,On Appellations of Origin of Goods and Geographical Indications: 1999;

2. Decree of  The President of Georgia N88 ,,Concerning arrangements which are related to entering into force the Law on Appellations of Origin of Goods and Geographical Indications“  2002;

3. Resolution of the Government of Georgia N181 ,,On Approval of the Statute on the Legal Entity of Public Law – National Intellectual Property Center of Georgia “Sakpatenti" 2010;

4. Resolution of the Government of Georgia N182 “On Approval of Fees for the Service Related with Patenting, Registration and Deposition of Intellectual Property Subject-Matters” 2010.

National Wine Agency

1. Georgian Law ,,On Vine and Wine“ – 1998;

2. Resolution of the Government of Georgia N2 ,,On Approval of technical regulation regarding the list of processes, materials and substances permitted in winemaking practice“ 2014;

3. Resolution of the Government of Georgia N3 ,,On Approval of technical regulations regarding the general rules on grape wine production“ 2014;

4. Resolution of the Government of Georgia N45 ,,On Approval of fees and terms for the service provided by LEPL National Wine Agency“  2011;

5. Order of the Minister of Agriculture of Georgia N2-67 ,,On Approval of the Statute on Legal Entity of Public Law – National Wine Agency“ 2012;

7. Order of the Minister of Agriculture of Georgia N2-37 ,,On Approval of the procedure for specifying and examining the information necessary for registration of denominations of origin of wine and wine brandy and the procedure for state control over production of wine and wine brandy with a denomination of origin“ 2003;

8. Order of the Minister of Agriculture of Georgia N2-51  ,,Statute on Rules of Recording Technological Processes and Statute on Rules of Compulsory Notification of Activities Relating the Production and Selling of Commodity Output in the Fields of Viticulture and Winemaking“ 2003;

9. Order of the Minister of Agriculture of Georgia N2-220  ,,Regulation for the Technical and Phytosanitary Control of the Production of Vine Mother Plantations, Grafting material and Engrafted Seeding, Certification Rules for Vine Grafting materials and Engrafted Seedlings, Rules for Specifying the Special Zones and Grape-Growing Regions“ 2003;

National Food Agency

1. Law of Georgia ,,Regarding labeling of Genetically modified organisms and genetically modified food/feed produced from above mentioned organisms intended for human consumption/feed“ 2014;

2. Resolution of the Government of Georgia N185 ,,On the Approval of Technical Regulation on Hazelnuts“ 2016;

3. Resolution of the Government of Georgia N577 ,,On the Approval of General Traceability Principles and Requirements in Food/Feed Safety, Veterinary and Plant Protection Fields“ 2015;

4. Resolution of the Government of Georgia N719 ,,On the Approval of Technical Regulation on Packaged Mineral Water and Spring Water“ 2014;

5. Resolution of the Government of Georgia N198 ,,On Organic (Biological) Production“ 2013;

6. Resolution of the Government of Georgia N118  ,,On the Approval of Technical Regulation on Beef and Beef Product Labelling Rules“ 2016;

7. Resolution of the Government of Georgia N567 ,,On the Approval of Maximum Residue Limits For Certain Contaminants in Food“ 2015;

8. Resolution of the Government of Georgia N376 ,,On the Approval of Technical Regulation on Wheat Flour“ 2015;

9. Resolution of the Government of Georgia N639 ,,On the Approval of Technical Regulation on Pharmacologically Active Substances, Classification and  Maximum Residue Limits Thereof in Food of Animal Origin“ 2015;

10. Resolution of the Government of Georgia N152 ,,On the Approval of Technical Regulation on Milk and Milk products“ 2015;

11. Resolution of the Government of Georgia N72 ,,On the  Approval of Technical Regulation on sanitary-hygiene standards for tare connected with food“ 2014;

12. Resolution of the Government of Georgia N55 “On the approval of the Special Rule for the Implementation of Official Control on Food of Animal Origin“ 2015;

13. Resolution of the Government of Georgia N22 ,,On the Approval of Technical Regulation for the Control of Certain Substances and Residues Thereof in Certain Animal Products“ 2016;

14. Resolution of the Government of Georgia N90 ,,On approval of  Specific Hygiene Rule for Food of Animal Origin“ 2012;

15. Resolution of the Government of Georgia 
N173  ,,On approval of Food/Feed Hygiene Rules and simplified food/feed safety hygiene rules“ 2010.

16. Order N2-41 of the Minister of Agriculture of Georgia ,,On the Approval of Rules for Examining and Determining Data, as Required by Legislation, for the Registration of Designations of Origin and/or Geographical Indications of Food (With the Exception of Wine and Wine Brandy, Natural Mineral Water and Spring Water) and Persons Authorized to Use Registered Designations of Origin and/or Geographical Indications of Food (With the Exception of Wine and Wine Brandy, Natural Mineral Water and Spring Water) and for the Issuance of Relevant Summary Thereof“ 2014.

17. Order of the Minister of Agriculture of Georgia №2-49 ,,On Implementation of rules for Examining, Determining Data, as Required by Legislation, for the Registration of Designations of origin of mineral water and for registration of person authorized to use the designation of origin of mineral water and control to use of designation of origin of mineral water“ 2003.

18. Resolution of the Government of Georgia N-581 - “On approval of Technical regulations on microbiological indicators of food” 2015;

19.  Resolution of the Government of Georgia N-714 - “On approval of Technical regulations on Honey” 2014;

20.      Resolution of the Government of Georgia N-3 - “On approval of technical regulations for general rules of producing wine from grapes” 2014;

21.      Resolution of the Government of Georgia N-111 - “On approval of Rules for Issuing a Hygienic Certificate on Food and Food Related Packaging" 2007;

22.      Resolution of the Government of Georgia N-262 - “On approval of Norms of Trans fats in Food” 2016;

23.      Resolution of the Government of Georgia N-441 - “On approval of Regulations of Additional Requirements for Food Labeling" 2014;

24.      Resolution of the Government of Georgia N-508 - “On approval of Technical Regulations for granting of Rights for adding of vitamins, minerals and some other substances in food " 2016;

25.      Resolution of the Government of Georgia N-510 - “On approval of Regulations for Submission of Applications related with Food Nutritive value and Health" 2016;

26.  Resolution of the Government of Georgia N-15 - “On approval of Technical Regulations for potable water” 2014;

27.  Resolution of the Government of Georgia N-585 - “On approval of technical Regulations for Food Supplements” 2016;

28. Order of the Minister of Environment Protection and Agriculture of Georgia N2-106 - „On approval of Rules for granting of Right for using of Quality Signs“ 2018.

Twinning Manual Annex A2

http://www.sakpatenti.gov.ge/media/page_files/patent_law_2017_Iy62qmS.pdf

http://ec.europa.eu/info/strategy/better-regulation-why-and-how_en

http://ec.europa.eu/info/files/better-regulation-better-results-eu-agenda-0_en

Sakpatenti did not directly participate in this project. However, through this project were registered 4 GIs at Sakpatenti.

Sakpatenti was not involved in these activities.

http://www.sigmaweb.org/publications/Baseline-Measurement-Report-2018-Georgia.pdf