## ANNEX C1: Twinning Fiche Project title: Strengthening Capacities of Internal Control in the Fight against Corruption within the Ministry of Interior Beneficiary administration: The Ministry of Interior of the Republic of Serbia Twinning Reference: SR 15 IPA JH 01 18 Publication notice reference: EuropeAid/160768/DD/ACT/RS

EU funded Project TWINNING INSTRUMENT

1.	Basic Information

1.1	Programme:

National Programme for Serbia under the IPA – Transition Assistance and   Institution Building Component for the year 2015

1.2	Twinning Sector: Justice and Home Affairs

1.3	EU funded budget: € 1,000,000

2.	Objectives

2.1	Overall Objective(s):

To support Serbia’s commitment in the field of fighting corruption in line with the recommendations  of the Action Plans on Chapter 23 and Chapter 24.

2.2 Specific objective:

Support to on-going capacity building of the Internal Affairs Sector (hereinafter IAS), with focus on preventive mechanisms to fight corruption in the Ministry of Interior, as well as fulfilling activities defined in National Anti-Corruption Strategy and its Action Plan.

2.3 The elements targeted in strategic documents i.e. National Development Plan/Cooperation agreement/Association Agreement/Sector reform strategy and related Action Plans”

Stabilisation and Association Agreement (SAA), in its Article 80 committed to reinforcement of institutions and rule of law, states “In their cooperation on justice, freedom and security, the Parties shall attach particular importance to the consolidation of the rule of law, and the reinforcement of institutions at all levels in the areas of administration in general and law enforcement and the administration of justice in particular. Cooperation shall notably aim at strengthening the independence of the judiciary and improving its efficiency, improving the functioning of the police and other law enforcement bodies, providing adequate training and fighting corruption and organised crime”. In addition, Article 86 (Preventing and combating organized crime and other illegal activities) stipulates, “The Parties shall cooperate on combating and preventing criminal and illegal activities, organized or otherwise, such as: (C) corruption, both in private and public sector, in particular linked to non-transparent administrative practices”.

The Indicative Strategy Paper 2014-2020 for Serbia (the Strategy Paper) sets out that Corruption is prevalent in many areas of public and economic life and continues to be a serious cause of concern. Corruption in Serbia is a widespread social phenomenon which severely affects all sectors of life and negatively impacts the rule of law, legal certainty, economic development and overall stability and prosperity. With the result of 41 on the scale from 100-0, Serbia is placed as 77th out of 180 evaluated countries in 2017 by the Transparency International’s Corruption Perception Index (CPI).

According to the Transparency International Global Corruption Barometer 2016 the perception of corruption was associated mostly with business executive (35% of respondents), tax officials (34%), police (33%) local government representatives (33%), judges and magistrates (32%), government officials (32%), Parliament (28%), President / Prime Minister (27%) and religious leaders (20%).

Hence, the means and methods to fight corruption must be cross-sectorial and extend across all relevant stakeholders (government institutions, bodies, departments, organizations and society at large), enhance coordination of the anticorruption institutions and develop their capacities for implementation of the National Anti-Corruption Strategy and Action Plan and the Chapter 23 Action plan.

Corruption acts as a facilitator for оrganised crime and affects economic development and welfare. The legal and institutional framework for the prevention and fight against corruption is largely in place, but implementation is lagging behind. The administrative capacity of relevant authorities and especially inter-institutional cooperation and coordination among relevant authorities such as judiciary, prosecution, police, customs and tax authorities remains insufficient for proper joint investigations. The institutional set-up should be substantially strengthened, both in terms of staff and in terms of respecting the full independence of law enforcement and judicial bodies dealing with investigations especially into high level corruption.

The new strategy for the prevention and fight against corruption for the period 2013-2018 and its action plan have both a structural approach covering issues such as good governance, independent institutions, internal control and external audit, and protection of whistle-blowers, and a sector approach addressing corruption in most sensitive sectors such as public procurement, spatial planning, judiciary, police, education and health. To decisively impact on the level of corruption, strong political support will be needed for implementation of the strategy. A more detailed action plan needs to be elaborated in the framework of the negotiations for Chapter 23.

Serbia 2018 Report

https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/20180417-serbia-report.pdf

The current situation is extensively reported in section 2. "Fundamentals First: Political Criteria and Rule of Law chapters."

Applicants are requested to carefully read and take into consideration both above mentioned sections of the Serbia 2018 Report concerning track record, Anti-corruption policy, institutional framework, law enforcement, legal framework, strategic framework.

In particular the 2018 Progress Report states that Serbia should "further enhance the independence and capacity of the internal control sector of the police"

Anti-corruption policy

EU Common Position and the interim benchmarks for Chapters 23 which refers to anti-corruption:

http://data.consilium.europa.eu/doc/document/AD-20-2016-INIT/en/pdf

In particular Interim benchmarks under section "Fight Against corruption" (from no 22 to no 35)

EU Common Position and the interim benchmarks for Chapters 24:

http://data.consilium.europa.eu/doc/document/AD-21-2016-INIT/en/pdf

In particular Interim Benchmark 23 under section "Serbia enhances its efforts to ensure compliance with EU requirements in the field of police co-operation and the fight against organised crime":

- 23. Serbia conducts a comprehensive analysis and on that basis amends its action plan providing:

- a clear sequencing of steps needed to align with the EU police co-operation instruments;

- an overview of staffing and training needs, including, where relevant, steps to address critical gaps;

- clarifying procedures for operational co-operation between various departments in the Ministry of the Interior and with Intelligence Services;

- ensuring the material conditions for smooth and secure exchange of relevant data;

- cost details and sustainable financial sources required for effectively implementing these reforms;

- detailed steps for establishing robust safeguards to ensure that the police integrity is strengthened and that police services are operationally independent from political interests and shielded from criminal influence.

The National Anti-Corruption Strategy (NACS) in the Republic of Serbia for the period 2013-2018 along with the Action Plan for its implementation:

http://mpravde.gov.rs/en/vest/3369/the-anti-corruption-strategy-and-the-action-plan.php

In July 2013 the National Assembly of the Republic of Serbia adopted the National Anti-Corruption Strategy (NACS) in the Republic of Serbia for the period 2013-2018 along with the Action Plan for its implementation. The Ministry of Justice is responsible for coordinating implementation of the Strategy and the Action Plan, while the Anti-corruption Agency is responsible for monitoring them.

The general objective of the NACS is to eliminate corruption, as an obstacle to the economic, social and democratic development of the Republic of Serbia, as much as possible.

The NACS is cross-sectorial covering specific issues and good governance issues and needs an inter-institutional effort for its proper and effective implementation. It is structured around nine priority areas: Political activities, Public finances (including public revenues, public expenditures and internal financial audit, external audit, and protection of EU financial interests), Privatization and public-private partnerships, Urban and Spatial Planning, Justice, Police, Education and Sport, Health, Media. The action plan provides for detailed measures to implement the strategy, with a focus on most vulnerable areas, such as the improvement of financial investigation capacity and making illicit wealth a criminal offence.

In the implementation of this Strategy, authorities and holders of public powers that are involved in the prevention of and fight against corruption, are obliged to perform their duties in accordance with the general objective and principles of the strategy.

The National Anti-Corruption Strategy and its Action Plan, imposes activities to improve normative, organizational and technical capacities of the Internal Affairs Sector (IAS) of the Ministry of Interior, increase the number of employees and develop new preventive mechanisms in fight against corruption (risk analysis of corruption, integrity testing and implement measures for strengthening of integrity of employees who work on positions where there is a high risk of corruption).

Applicants are supposed to be fully acquainted with both NACS and AP.

The Action Plan for the Chapter 23:

http://mpravde.gov.rs/files/Action%20plan%20Ch%2023.pdf

Fight against corruption is in Section 2 at page 127.

Serbia adopted in 2016 the Action plan for the Chapter 23, which focuses on the implementation of the recommendations made in the Screening report for this chapter. The Screening report was adopted in May 2014, following the Explanatory meetings for the Chapter 23, which took place in September 2013 and the Bilateral meeting which took place in December 2013.

Serbia declared in the introduction to this Action plan that it is fully committed to the process of European integration and aware that this process requires substantial and fundamental changes in the judiciary, the anti-corruption system and the protection of fundamental rights, both at the normative and the implementation level. In this sense, in the process of developing the reform steps in Chapter 23, Serbia was primarily guided by the EU acquis. In areas where there is no acquis or it does not cover the whole area, the established standards and best comparative practices were used as a guide for creating reforms, particularly considering the legal heritage of the Republic of Serbia, as well as socio-economic factors conditioning the applicability of the solutions that provide good results in other legal systems.

The Screening report and consequently the action plan for the Chapter 23 set out a total of 4 recommendations for the implementation of the anti-corruption measures, 11 specific recommendations for prevention and 8 recommendations about repressive actions against corruption. The Action plan provides detailed measures for the implementation of each recommendation, with defined timelines, responsible institutions and budget for each, as well as outcome level indicators per recommendation

Specifically Action Plan for Chapter 23 foresees recommendation 2.2.10:  "Further develop, implement and assess the impact of specific measures to tackle corruption in other particularly vulnerable areas, such as health, taxation, education, police, customs and the local administration" Activities from 2.2.10.21 to 2.2.10.29 (at page 176) concern Police and in particular activities from  2.2.10.21 to 2.2.10.26 concern the Internal control in the police.

Applicants must be fully acquainted with the entire above document in particular  section 2.1 "implementation of Anti-corruption measures " including the 4 recommendations as well as the 11 recommendations concerning Prevention of Corruption listed in section 2.2 and the 8 recommendations concerning Repression of Corruption listed in section 2.3. Activities from  2.2.10.21 to 2.2.10.26 concern the Internal control in the police must be carefully taken into account.

The Screening Report and the Action Plan for the Chapter 24:

http://www.mup.gov.rs/wps/wcm/connect/36e98096-9938-4aaf-b36c-e413bfbcac57/Treca_verzija_AP_27_03_2015.pdf?MOD=AJPERES&CVID=kTXD4Ry

The Screening report for Serbia for Chapter 24 – Justice, freedom and security contains recommendations, in section External borders and Schengen, which Serbia has to implement during negotiation process.

Action Plan for Chapter 24 contains recommendation 4.4: "Outline a comprehensive set of measures to improve the fight against corruption at the borders, covering all agencies active at the border".

In the Action Plan, one of the activities for this recommendation is: 4.4.2. (A1) Revise Action plan of the National Anticorruption Strategy by the Ministry in charge of Interior based on the Border Police Corruption Risk Assessment by the end of second quarter of 2016.; (A2) Adopt Action Plan of the National Anticorruption Strategy by the Serbian Government through: (1) Introducing Integrity Test of the Border Police, (2) Strengthening integrity of the corruption high risk border police officers, (3) Monitoring the implementation of Police Code of Ethics by the end of second quarter of 2016.

Connected to anticorruption are also activities 4.4.3, 4.4.4, 4.4.5, 4.4.6.

(NPAA) National Programme of Serbia for the Adoption of the EU Acquis for the period 2016-2018

Within the National Programme of Serbia for the Adoption of the EU Acquis (NPAA) for the period 2016-2018, IAS defined activities in the period 2014-2018 to become responsible to control all employees of the Ministry in charge of Interior (not only police officers according to the current Law on Police) and introduce integrity test, conduct risk analysis of corruption. Also IAS proposes to increase human and technical capacities in order to have capacity to place technical devices into indoor and outdoor places, by establishment of operational analytics unit and strengthening of the Unit for Covert surveillance. The plan is to fill all available work positions (IAS has 94 work positions out of systematized 114) and increase the number of employees (20 each year from 2015-2018). The work position will be for inspectors, operational analytics officer and covert surveillance officers.

3. Description

3.1 Background and justification:

The Republic of Serbia is located at the crossroads of Central and Southeast Europe and is the central part of the Balkans.

The Republic of Serbia signed the Stabilization and Association Agreement with the EU on 29 April 2008 which, upon completion of the ratification process in the National Assembly of the Republic of Serbia, the Parliaments of EU Member States and the European Parliament, entered into force on 1 September 2013. The European Council granted the status of candidate country to Serbia in March 2012 and decided to open accession negotiations in June 2013.

Following the adoption of the framework for accession negotiations with Serbia by the European Council in December 2013, the first Intergovernmental Conference with Serbia was held in January 2014. The analytical examination of the EU acquis (screening process) started in September 2013 and it was completed in March 2015. Serbia remained committed to its strategic goal of EU accession and continued to build track record in implementing the obligations of the SAA. It is implementing an ambitious political and economic reform agenda and successfully finalized the action plans required for the opening of the rule of law negotiating chapters.

The Negotiation group for Chapter 23 coordinated by Ministry of Justice, prepared the Action plan for Chapter 23, through an inclusive process and following extensive consultations with the EC. Based on measures and activities in the AP Ch.23, the Negotiation group for Chapter 23 developed the Negotiation position, which was adopted by the Government on 25th of March 2016.

First two negotiation chapters 32 and 35 were opened in December 2015.

Accession negotiations for chapters 23 and 24 were opened in July 2016.

The opening of the two chapters represents an important milestone in the accession negotiations with Serbia. Under the new approach, both chapters are tackled early in the enlargement process to allow Serbia to develop a solid track record of reform implementation. This will ensure sustainable and lasting reforms in the area of the rule of law.

The EU developed its common positions on the basis of the Action Plans, which Serbia has elaborated in order to fulfil the opening benchmarks for the two chapters. The Action Plans will allow the EU to assess the substantial reforms Serbia is planning in the months and years ahead, inter alia in areas such as judiciary, fight against corruption, fundamental rights, migration, asylum, visa policy, external borders and Schengen, judicial and police cooperation, and the fight against organised crime and terrorism.

In line with the new approach, interim benchmarks were defined to assess further progress of Serbia. These include legislative amendments, robust monitoring mechanisms, institutional and coordination arrangements, initial track records as well as the administrative capacity and resources required to implement and enforce the relevant acquis in the respective chapters. There are 50 interim benchmarks for Chapter 23 and 41 interim benchmarks for Chapter 24 to be met by Serbia.

The comprehensive list of interim benchmarks for Chapters 23 and 24 are included respectively in the following documents:

Chapter 23: http://data.consilium.europa.eu/doc/document/AD-20-2016-INIT/en/pdf

Chapter 24: http://data.consilium.europa.eu/doc/document/AD-21-2016-INIT/en/pdf

With the adoption of the National Anti-Corruption Strategy and its Action Plan, activities are envisaged to improve the Internal Affairs Sector (IAS) in order to define normative, organizational  and technical capacities, increase the number of employees  and  develop new preventive mechanisms in fight against corruption (risk analysis of corruption, integrity testing and implement measures for strengthening of integrity of employees who work on positions where there is a high risk of corruption).

According to the previous Police Law (2005), IAS controlled the legality of work of only police officers and not all employees of MoI.  There was no obligation for MoI units to send intelligence regarding corruption committed by police officers and other employees of MoI to IAS. There was no clear coordination between IAS and other organizational units within the General Police Directorate that have competence to control the legality of work of police officers in the General Police Directorate in the area of disciplinary misconduct and control of the quality of work namely:

1) The Department for the control of the legality of police work, within the Uniformed Police Directorate,

2) the Department for the control of the legality of work and security, within the Gendarmerie and

3) the Department for the control of legality, within the City of Belgrade Police Directorate

Now the IAS needs to manage all complaints and intelligence regarding corruption of MoI employees.

3.2 Ongoing reforms

With the adoption of the new Police Law in January 2016 and amendments to the Law in 2018, IAS gained new competences in order to introduce new preventive mechanisms and to clearly define its competence:

- Increase competence of IAS to control police officers and all employees of the Ministry of Interior;

- IAS conducts integrity tests;

- IAS conducts checks of declaration of property of the managers in MoI (managers of strategic, high and middle level, also high-rick position for corruption in MoI which are determined by risk analysis of corruption);

- IAS conducts risk analysis of corruption and create corruption risk register in MoI;

- All organizational units of MoI have the obligation to send to the IAS intelligence, which they came across, that a police officer has committed a criminal offence while working or in relation with work, in 24 hours the latest from the moment when the  information was obtained;

- IAS conducts preventive controls of all organizational units of MoI;

- There is an obligation of the managers of the controlled units to be accountable for the implementation of  measures prescribed by IAS authorised police officers;

- Serious violations of official duty  are envisaged for all above points;

- IAS will conduct second and third level of security checks for managers of strategic, high and medium level;

- IAS secured by the new Law to have fund for operational purposes.

The Ministry of Interior is in the process of adopting secondary legislation that will regulate the method and manner of conducting internal control within MoI and coordination between IAS and other units within the General Police Directorate that control the legality of work of police officers in order to fully implement preventive and coordinated mechanisms.

According to new powers and competences, IAS established two new operational divisions: 1) the Division for operational analytics and use of special investigative techniques and 2) the Division for control of the legality of work and check of asset declaration. The Division for covert audio and video surveillance was transformed into the Division for Observation and Integrity test.

The Division for Observation and Integrity Test should have nine police officers and one head; the Division for operational analytics and use of special investigative techniques should have five police officers and one head; the Division for control of the legality of work and check of asset declaration should have five police officers and one head. IAS will reorganize administrative and logistics staff and will set up the Division for support and logistics that will provide expert and logistic help to all units in IAS. Total number of staff should be 127 employees.

In 2017, IAS filed 171 criminal charges against 149 police officers and 80 citizens for 481 committed criminal offences. The number of filed criminal charges increased comparing to the statistics in previous years (filed criminal charges 2016 - 201, 2015-168, 2014 - 148, 2013- 116, 2012 – 133, 2011-124, 2010 – 111).

Bearing in mind that the new Criminal Procedure Code adopted in 2013("Official Gazette RS", number 72/2011, 101/2011, 121/2012, 32/2013, 45/2013 and 55/2014) introduced the prosecutor-led investigation within national the legal system, there is a need of further specialisation and modern equipment for internal control police officers for acquiring high-quality evidence related to corruption criminal offences which will be used by the prosecutor during the court trial. For this reason the Prosecutor should be involved already at an early stage of investigation/intelligence.

Main beneficiaries of the project will be all IAS Divisions as well as IT experts in charge of maintenance of IAS databases and hardware.  Other inspectors from IAS who conduct corruption investigations will also participate in the trainings, especially those ones related to proactive investigations of corruption.

In order to fight police corruption in the MoI in an efficient manner, IAS needs to have complete operational independence both in the use of special investigative techniques and in the implementation of preventive measures (integrity test), which is not the case at the moment.

In the investigation of major corruption cases (bribery, smuggling of goods and people on the border, etc.), where perpetrators need to be caught “in flagrante” and where advanced technical covert devices need to be used, Division for Observation and Integrity test within IAS has to borrow specialized equipment for audio and video surveillance from surveillance units within Criminal Police Directorate to record necessary material for proving criminal offences. The Division also doesn’t have the technical capacity to place audio or video surveillance devices in premises like police stations or border crossing points. Comparative legal solutions of internal control departments in the region show that necessity of having this kind of skills and equipment is a pre-condition to conduct proactive investigations. The equipment is part of a supply contract funded by the EU under the same IPA 2015 programme.

Currently IAS is unable to conduct integrity testing which represents the most efficient tool in prevention of police corruption in many EU countries. IAS should implement new preventive mechanism according to the new Law on Police. IAS is at the moment drafting sub-laws to define integrity tests with proper methodology and procedures for improving preventive mechanism for countering corruption and in particular to work independently without the need of relying on Criminal Police equipment and resources.

The issue of Integrity test concerns both random and targeted test:

Random tests would have the greatest impact in terms of prevention. They are designed to observe and evaluate officers' conducts' in situations in which a specific set of circumstances has been created that requires police intervention. Police Departments should routinely conduct random integrity of their officers to determine if their conduct in handling their official duties is appropriate. An annual plan for random tests as well as a mechanism to protect the confidentiality of the tests should be implemented. High level officials should also be included in the plan.

Targeted tests should be carried out after a certain officer or office has been identified as being at high risk of corruption and misconduct. If there are already elements to open a criminal pre-investigation, integrity tests should be used as an ordinary procedural investigative tools (led by the prosecutor).

Concerning Integrity tests the legal framework should also be addressed in order to solve crucial problems such as:

- possibility to use integrity testing for any kind of misconduct or just limitations to corruption and serious criminal actions;

- level of information required to conduct a targeted integrity test;

- admissibility as evidence in criminal proceedings of materials collected during integrity tests, even those materials accidentally gathered;

- definition of possible limits for the testers (incitement, entrapment etc);

- possibility of preventive signed agreement from all police officers, where they consent in advance in being tested , either randomly or in a targeted way , even unbeknownst to them.  This mere fact would have already a deterrent effect and could solve, at least partially, the problem of evidence admissibility;

- supervision of a prosecutor for targeted tests.

Current staff received basic training in use of the equipment. Three police officers are currently using I2 software, however just for the creation of basic charts. They received basic training from the Criminal Police directorate and OSCE.

Since IAS will be a separate and independent Division, there is a need for specialized training in the areas of operational analysis, processing corruption data and in the preparation of relevant documentation for the prosecutor.

The new Law on Police stipulates that IAS will be responsible to control all employees of the Ministry of Interior. The office will gain responsibilities to control also Finance and Human resource sector Unit, Emergency management Sector (Fire Unit) and Analytics, IT and telecommunications. Also for this reason advanced training for inspectors in financial investigations, control of supplies, abuse of IT system, etc are needed.

IT and Analytics Unit within IAS is responsible for maintenance of the current IT databases and IT system. The current IT equipment is technically obsolete and maintenance is unfeasible due to the lack of spare parts on the IT market. Some of the existing problems include malfunction of data storage devices, malfunction of optical devices that disables server installation after system failure, low capacity of hard discs, and failure of RAID controllers that brings system to crash and/or to lose data. These problems have been confirmed in the recommendations given by the IPA 2007 twinning project “Police reform: internal control” – assessment of IT.

IAS already created network which connects headquarters of IAS with 4 regional centres (Belgrade, Nis, Kragujevac, Novi Sad) in line with the new "Law on organization and jurisdiction of government authorities in suppression of organized crime, terrorism and corruption".  The aim is to have secure network, where all databases will be integrated into one application system (risk analysis, operational analytics, current IAS database, asset declaration database, etc.), accessible to all inspectors of IAS, secure and protected system of sensitive corruption data. The application will be created in line with the existing format of created applications in MoI.

The ongoing IPA 2015 EU funded Procurement for IAS will significantly strengthen IT infrastructure and capacities. The delivery of the equipment is a precondition for the implementation of the twinning.

This twinning will train IAS police officers in the use of the new equipment. IT experts will be trained to autonomously and independently provide services to users (IAS employees) and trained to manage soft wares for the protection of the system. This should also lead to a reduction of expenditures for maintenance of the IT infrastructure.

This twinning is also meant to draft operational procedures for conducting  integrity tests and to apply special investigative techniques such as the use of cover audio and video devices in cars and premises like police station where corrupt police officers can be caught “in flagrante” for bribery or misuse of office.

The aim of the twining project is also to develop manuals on corruption investigation cases, special investigative techniques and integrity tests.

3.3 Linked Activities

EU funded projects:

IPA 2007 "Police Reform - Internal Control" (2010-2012)

The project purpose was to enhance operational independence, professionalism and capabilities of Internal Affairs Sector. The project drafted the first Strategic analysis of corruption in MoI,  Anti-Corruption Manual and a manual on the  work of IAS.

Infrastructure report was drafted that reviewed current IT system and made recommendations on enhancing the IT infrastructure.

4 study visits and a number of  basic trainings were held to increase capacities of  internal control police officers to use special investigative techniques and conduct investigation of corruption.

10 key IAS police officers within Division for Audio and Video Surveillance (now Division for Observation and Integrity test) were trained in special investigation techniques at basic level as well as in the use of equipment. However, considering that the equipment was not procured, the project didn’t have final results and the team still has problems in everyday work to implement special investigative techniques.

"Support to Anti - Corruption Agency in Fight against Corruption” (Norway).

This is a 390.000 euro funded project, covering the period December 2010 - January 2013,which focuses on increasing the professional knowledge and skills of employees of the Anti Corruption Agency (ACA); The ACA provided instructions and trainings on the integrity plan for relevant institutions that are directly referred to in the law; initiated amendments to the anti-corruption regulations, the National strategy and Action plan; applicative software developed; automatisation of working processes in the Agency; staff trained to work in a new IT system; interns acquainted with the Agency's mission and competencies; interns gained general knowledge on the anticorruption values.

IPA Regional Programme “Fight against Organized Crime and Corruption: Strengthening the Prosecutors' Network” (2012-2014).

The purpose of this project is to contribute to the improved cross-border and international judicial cooperation of the beneficiaries to investigate and prosecute cross-border crime, in particular organized crime and corruption. Implementing Agency for this project is GIZ. Total Amount: 5.000.000 EUR

IPA 2008 “Fight against Corruption” (2010 - 2012).

The project contributed to reducing the level of corruption by supporting the functioning of the ACA. The project aimed to train staff at all levels in line with the EU best practice in the anticorruption area; establish an IT system for the ACA with appropriate software for management and tracking of cases and complaints; increase coordination amongst relevant state bodies involved in the fight against corruption; assist with drafting the Anti-Corruption Strategy, and increase the understanding of corruption and mechanisms for its prevention by the citizens and other relevant target groups. Furthermore the project ensured the supply, delivery, installation, commissioning and training of supplies related to Date warehouse platform, Data warehouse external storage, Document management system and reporting Analytics Platform, video conferencing system, backbone router and other equipment.

IPA 2010 “Project against Money Laundering and Terrorist Financing in Serbia”(2011-2014) (MOLI-Serbia).

The project aimed to improve Serbia’s anti-money laundering and countering the financing of terrorism (AML/CFT) capacities in terms of legislative provisions, professional training and operational capacities. In addition to the APML as the main beneficiary, other beneficiaries include law enforcement authorities, supervisory and judicial bodies, as well as professional associations and the NGO sector. The main objectives of the MOLI project is to improve democracy and rule of law through the prevention and control of money laundering and terrorist financing, and other forms of economic and financial crime in Serbia, in line with European and other international standards. Even though not concerned directly with anti-corruption issues, MOLI-Serbia supported the Money Laundering National Risk Assessment, one of the findings of which was that corruption affects the entire AML/CFT system, which is why there needs to be close coordination (exchange of information) between the systems, especially through communication between the respective bodies designated to supervise the implementation of the AML and anti-corruption strategies.

IPA 2011 PACS-Serbia - Strengthening the capacities of law enforcement and judiciary in the fight against corruption in Serbia

http://www.coe.int/t/dghl/cooperation/economiccrime/corruption/Projects/PACS-Serbia/PACS_default_en.asp

The Council of Europe and the European Union launched, in December 2012, a joint project “Strengthening the Capacities of Law Enforcement and Judiciary in the Fight against Corruption in Serbia” (PACS). With duration of 28 months, the project encompassed specialised training designed for the judiciary, prosecution and law enforcement officers; introduce new IT tools to investigate corruption and white collar crime, conducted risk analyses and provided recommendations aimed at improving the efficiency of criminal investigations and proceedings. The Methodology recommendation and guidance provided with this project aim to give advice on how to create and keep track record in line with the observation of the European Commission “Staff Working Paper: an Analytical Report with the “Commission Opinion on Serbia’s application for membership of the European Union”.

Among others the project implemented the following activities:

- Making an analysis of corruption in the police - conducted in 2013, 2014, a report released in early 2015

- Production of Opinion about the Police Code Ethics and conducted training in the field of ethics for members of the MUP - implemented in March 2015

- Development of guidelines for corruption risk analysis in the MoI and making risk analysis for border police - conducted at the end of 2015

- Meeting with British experts to assist in the development of procedures for the use of integrity test  and conference was held at the end of 2015 where  experiences in the implementation of the integrity test were presented

Support to the strengthening corruption prevention mechanisms and institutional development of the Serbian Anti-Corruption Agency (December 2013 - December 2015)

The project was aimed at strengthening preventive anti-corruption mechanisms, good governance principles and building capacities of the ACA to combat corruption and properly pursue tasks envisaged in the Law on ACA, the National Anti-Corruption Strategy (NACS) and Action Plan.

Key activities implemented during the first project year (December 2013 - December 2014) included development of two software applications which should improve monitoring of integrity plans (IPs) and reporting on implementation of the NACS and the Action Plan. Also, during the first project year 53 institutions in 9 towns and municipalities were visited by the ACA team which carried control of IPs quality. One of the key project activities during the first project year was preparation and conduct of the first call for CSOs in regards to alternative reporting, as well as preparatory work on alternative reporting methodology. The 3 grants have been allocated to three selected CSOs which have done independent assessment of NACS implementation and have submitted their reports in January 2015. More information on this activity is available on ACA web-site: http://www.acas.rs/en/

During the second project year, the project team paid visits to the selected sample of public institutions in Belgrade and other towns and municipalities in regards to the IPs implementation. Also, second round of CSOs grants for the NACA alternative reporting will be organized, while two software applications are expected to become operational. Also, the 2015 Annual Report on the Implementation of the NACA and the Action Plan will be translated and prepared for printing.

IPA 2013 - Service contract "Prevention and Fight against corruption" – Ongoing /30 months as of July 2017

This contract has 3 main expected results:

## Result 1

Strengthened transparency, efficiency and coordination of anti-corruption institutions and policies in the area of prevention and fight against corruption as envisaged by the National Anti-corruption Strategy and Action Plan and the Action Plan for Chapter 23 (Chapter 2. Fight against Corruption)

## Result 2

Strengthened capacities for prevention of corruption in line with the Strategy and Action Plan and the recommendations of the Action Plan for Chapter 23 (Chapter 2 Fight against corruption)

Result 3

Strengthened capacities for repression of corruption by improving quality of investigation, prosecution and trial of corruption-related cases in line with the Strategy and Action Plan and the recommendations of the Action Plan for Chapter 23 (Chapter 2 Fight against Corruption) as well as with the Financial Investigation Strategy and the newly adopted "Law on organization and jurisdiction of government authorities in suppression of organized crime, terrorism and corruption". In this component the project already delivered relevant training on financial investigations to Police, Prosecutors and Judges

IPA 2013 “Prevention and Fight against Corruption” (Twinning) – ONGOING

This twinning started on July 2016 and it has an implementation period of 24 months.

The overall objective of the Project is to improve the efficiency in fight against corruption and to reduce all forms of corruption. The main purpose of the project is to strengthen national mechanisms for prevention and fight against corruption in accordance with the National Anti-Corruption Strategy and the Action Plan for its implementation.

The project has 2 components:

Component 1: to enhance capacity, efficiency and coordination role of the Anti-Corruption Agency (ACA) in order to efficiently pursue its statutory competences in implementing and monitoring measures defined in the National Anti-Corruption Strategy and Action Plan.

Component 2: to strengthen corruption prevention mechanisms in line with the best EU Member States' practices and in accordance with the National Anti-Corruption Strategy and Action Plan

IPA 2015 "Enhancing the quality and efficiency of Suspicious Transactions Reporting (STR) and Administration for the Prevention of Money Laundering (APML) core functions"

The purpose of this project is to improve the effectiveness and efficiency of the AML/CFT system by enhancing the quality and efficiency of Suspicious transactions reporting (STR) and strengthening the core functions of the Administration for the Prevention of Money Laundering (APML) (receipt, analysis and dissemination of financial disclosures)

Other donors

The Internal Affairs Sector in 2010 implemented the project “Strengthening of capacities of regional centers of Internal Affairs Sector” together with the OSCE Mission to Serbia. The project was financed by the government of the Kingdom of Norway. The aim of this project was to strengthen capacities of IAS regional centers, the supply of IT equipment and the supply of 4 vehicles for the Sector’s regional centers in Belgrade, Novi Sad, Nis and Kragujevac.

3.4 List of applicable Union acquis/standards:

Relevant EU acquis is as follows:

Criminal Law Convention on Corruption and Additional Protocol (Council of Europe)

Convention on fighting corruption involving officials of the EU or officials of member states (1997)

Council Decision 2008/852/JHA of 24 October 2008 on a contact-point network against corruption

Communication on Fighting Corruption in the EU (COM(2011) 308 final of 6 June 2011)

Resolution (97) 24 on the twenty guiding principles for fight against corruption (Council of Europe Committee of Ministers)

Recommendation No. R (2000) 10 of the Committee of Ministers on codes of conducts for public officials

Police oversight Standards set by EPAC/EACN  (European partners against corruption/European contact-point network against corruption (Handbook for evaluating the effectiveness / efficiency of police oversight bodies https://www.epac-eacn.org/images/HANDBOOKVAV3.pdf)

Handbook on Police Accountability, Oversight and Integrity (UNODC) https://www.unodc.org/pdf/criminal_justice/Handbook_on_police_Accountability_Oversight_and_Integrity.pdf

3.5. Results per component

3.5.1 Enhanced capacity of IAS to efficiently use special investigative techniques in proactive investigations of corruption and integrity testing.

3.5.2. Improved IT systems of IAS to protect and manage data during investigations

3.5.3. Enhanced internal investigation capacity of the IAS and enforced asset/property declaration checks of employees of MoI.

3.5.4. Established capacities of IAS to process intelligence and operational data as well as to conduct corruption risk analysis.

3.6 Means/input from the EU MS Partner Administration(s):

The Project Leader and RTA (Resident Twinning Adviser) shall provide support to the responsible Serbian authorities in strengthening their capacities as well as in the implementation of this project.

During the implementation of this project, the RTA will be hosted in the premises of the Ministry of Interior.

3.6.1 Profile and tasks of the Project Leader:

The MS Project Leader will manage the project team of selected member state(s) and co-ordinate the implementation of activities.

a) Qualifications:

Requirements:

- University degree in a field relevant to this project;

- High-ranking official currently working in a MS administration

- At least 3 years of professional experience in an area relevant to the project;

- Project management experience;

- Fluency in written and oral English language;

- Computer literacy;

- Good knowledge from EU legislation regarding fight against organized crime and corruption

- Proven contractual relation to public administration or mandated body, as defined under twinning manual 5.4.5

Assets:

- Working experience as an expert in and providing technical assistance on corruption in public institutions

- Experience with twinning rules and procedures;

- Experience in managing or assisting in management in at least 1 project in the area of Fight against organised crime and corruption;

- Experience in transition countries in Europe;

Tasks of PL:

- Overall management and coordination of the project with MS, MoI, other partners and stakeholders;

- Project reporting;

- Ensuring backstopping and financial management of the project in the MS;

- Ensuring timely, effective and efficient implementation of the project and achievement of results, through proposed activities;

- Coordination of deployment of short-term experts;

- Coordination with RTA from the Member State side, the Project Steering Committee meetings, which will be held in Serbia every three months;

- Participation in the Steering Committee meetings (every three months);

- Assuring compatibility with EU requirements;

3.6.2. Profile and tasks of the RTA:

a) RTA qualifications

- University degree in law or any other relevant fields

- At least 7 years of general professional experience in the field of Home Affairs

- At least 3 years of specific experience in police work, including experience in investigation of organized crime and/or corruption with the use of SIMs (Special Investigative means)

- Proven contractual relation to public administration or mandated body, as defined under twinning manual 5.4.5

- Fluency in English language

- Computer literacy

Assets:

- Working experience in internal control unit within the police

- Specific experience in conducting Integrity testing

- Working experience in organizational management and Human Resources within Home Affaires sector

- Experience in organizing and conducting trainings

b) RTA tasks

Tasks of the RTA:

- Responsible for monitoring project implementation and proposing corrective management actions if required;

- Support and coordination of all project activities in the Beneficiary Country in line with the agreed work plan to enable timely completion of project results and delivery of the outputs;

- Nomination, mobilisation and supervision of the short-term experts, together with the Project Leader;

- Advise on related EU policies and best practice, legislation and regulation;

- Establish and maintain cooperation with all beneficiaries involved in the implementation of the project and other related projects (ensuring the avoidance of overlapping), in close coordination with the Project Leader;

- Facilitation of the contacts with peer institutions in EU member states in order to stimulate a proper exchange of information, data and experience;

- Organization of visibility events (kick-off and final event);

- Responsible for organisation of the Project Steering Committee meetings and reporting on the project progress in cooperation with Project Leader;

- Identifying and reporting to the Contracting Authority, at an early stage, all difficulties that may jeopardize the implementation of the project and the achievement of its results.

3.6.3 Profile and tasks of Component Leaders:

This project is structured in 4 Components,  each one linked to one of 4 results:

- Component Leader 1 (Result1) -Component Leader 1 profile: The profile of the Component Leader 1 should combine both technical competence and practical experience in the field of prevention and fight against corruption, especially in law enforcement agencies and to have experience in conducting integrity tests. Component Leader 1 tasks:  The Component Leader 1 will be responsible for the implementation of activities related to Result 1. Support and coordination of all project activities in line with the agreed work program to enable timely completion of project mandatory results and delivery of the outputs; Establish and maintain cooperation with all beneficiaries involved in the implementation of the project, and with other related projects (ensuring the avoidance of overlapping), in close coordination with the RTA and Project Leader.

- Component Leader 2 (Result 2)-Component Leader 2 profile:The profile of the Component Leader 2 should combine both technical competence and practical experience in the field of data protection, managing and developing IT security measures to protect operational data and intelligence. Component Leader 2 tasks:  The Component Leader 2 will be responsible for the implementation of activities related to Result 2. Support and coordination of all project activities in line with the agreed work program to enable timely completion of project mandatory results and delivery of the outputs; Establish and maintain cooperation with all beneficiaries involved in the implementation of the project, and with other related projects (ensuring the avoidance of overlapping), in close coordination with the RTA and Project Leader.

- Component Leader 3 (Result 3)-Component Leader 3 profile:The profile of the Component Leader 3 should combine both technical competence and practical experience in proactive investigations of corruption and checking declarations of assets. Component Leader 3 tasks:  The Component Leader 3 will be responsible for the implementation of activities related to Result 3. Support and coordination of all project activities in line with the agreed work program to enable timely completion of project mandatory results and delivery of the outputs;  Establish and maintain cooperation with all beneficiaries involved in the implementation of the project, and with other related projects (ensuring the avoidance of overlapping), in close coordination with the RTA and Project Leader.

- Component Leader 4 (Result 4)-Component Leader 4 profile:The profile of the Component Leader 4 should combine both technical competence and practical experience in operational analytics, experience in conducting risk analysis of corruption would be considered an advantage. Component Leader 4 tasks:  The Component Leader 4 will be responsible for the implementation of activities related to Result 4. Support and coordination of all project activities in line with the agreed work program to enable timely completion of project mandatory results and delivery of the outputs;  Establish and maintain cooperation with all beneficiaries involved in the implementation of the project, and with other related projects (ensuring the avoidance of overlapping), in close coordination with the RTA and Project Leader.

3.6.4 Profile and tasks of other short-term experts:

- University degree or equivalent professional experience of X years

- Minimum 3 years of relevant experience

- Knowledge of legislation necessary for legal drafting

- Operational experience in investigations to detect and prove serious cases of crime and corruption (criminal offences with elements of corruption and organized crime) perpetrated by police officers or employees of law enforcement agency

- Analysis of needs for training and its implementation

- Planning in human resources management

- Information management and systems of reporting

- Internal and external communication systems

- Excellent  communication skills and presentation skills

- Experience in  using special investigative techniques and equipment is considered and advantage

- Experience in implementation of integrity tests, control of assets declaration, risk analysis of corruption or operational analytics is considered and advantage.

- Experience in IT protection of sensitive operational data is considered and advantage.

Tasks of short-term experts:

Number, frame, duration and specific tasks of short-term experts will be defined in the Work plan of twining project. It is expected of short-term experts to support all the above activities, secure implementation stated above in following areas:

- Planning and reporting, administrative procedure, communication demands and human resources management. Expert must have direct experience and skills in management and contribution to professional development of different teams investigators, which need  functional management and help in their  professional discipline with management of unit where he/she works (“management of line of work”)

- Procedure and skills, compatibility analysis of domestic legislation with rules, standards of EU MS and international standards

- Skills and experience in improvement of capacities of national departments for police  internal affairs or control

EU Member states should specify in their proposals availability of short-term experts, in order to give support to these tasks.

All short-term experts engaged on the project will be citizens of MS EU.

4. Budget

The total budget for this Twinning project is 1.000.000 EUR.

| Strengthening capacities of Internal Control in the fight Against corruption within the Ministry of Interior | EU Contribution | National Co - Financing | TOTAL |
| --- | --- | --- | --- |
| Twinning contract | EUR 1.000.000 | EUR NA | EUR 1.000.000 |

It is recommended that the costs for the project translation will cover not more than 6% of the budget of the project, which should be calculated in the twining working plan budget.

5. Implementation Arrangements

5.1 Implementing Agency responsible for tendering, contracting and accounting including contact person and full contact details.

The Delegation of the European Union to the Republic of Serbia will be responsible for tendering, contacting and accounting.

EUD Contact person:

Gerhard Salzer, Project Manager

Address: Vladimira Popovica 40, block 19a,  11070  New Belgrade

Tel: +381 11 3083 200

E-mail: Gerhard.Salzer@eeas.europa.eu

5.2 Main counterpart in the BC

Senior Programme Officer (SPO):

Mr Željko Kojić, Advisor to Minister

2 Blvd Mihaila Pupina Str.

SRB – 11070 Belgrade

Phone: +381 64 892 7277

E-mail: zeljko.kojic@mup.rs

Project Leader Counterpart:

The BC Project Leader will manage a project team on the Serbian side and will assure that  decision makers at the national level will be informed properly on the implementation of the project. He will ensure close co-operation and overall steering and coordination of the project. He will also be responsible for drafting reports and other documents, related to project management at the Serbian side and will chair Steering Committee meetings.

Mr. Dragan Kujundžić,

Internal Control Sector, Head of Internal Control Sector

Ministry of Interior

Boulevard Mihaila Pupina 2

SRB – 11070 Belgrade

Phone: +381 648921447

E-mail: dragan.kujundzic@mup.gov.rs

RTA counterpart:

Mrs Ana Petrović,

Internal Control Sector

Ministry of Interior

Boulevard Mihaila Pupina 2

SRB – 11070 Belgrade

Phone: +381 64 8920 439

E-mail: ana.petrovic@mup.rs

6. Duration of the Project

18 (+3) months

7. Sustainability

The activities envisaged by the Twinning fiche are based on the Action Plan for the National Anti-Corruption Strategy and Action Plan for Chapter 23.

The Project will be fully implemented in line with strategic objectives and guidelines defined above in order to contribute to strengthening investigative and IT capacities of IAS to independently investigate cases of corruption. It will also enhance the quality of evidence gathering gained by special investigative techniques.

Under the project, the protection of corruption data in the IAS system and exchange of data in IAS will be significantly improved.

IAS police officers will be trained to use new preventive mechanisms to fight corruption like integrity testing and checking declarations of assets. IAS police officers will also improve knowledge in the use of special investigative techniques to investigate corruption offences and operational gathering and processing of data will be also be improved.

8. Crosscutting issues

Equal opportunities

Based on the fundamental principles of promoting equality and combating discrimination, participation in the project will be guaranteed on the basis of equal access regardless of sex, racial or ethnic origin, religion or belief, disability, age or sexual orientation. Ministry of Interior of the Republic of Serbia is committed to promoting equality of opportunity for women and men in terms of employment, service delivery and involvement. This project should ensure adequate representation of women in the activities of the project.

Environment

The environmental impact of this project will be limited. It will not have a negative impact on the environment nor jeopardise environment, health and security in the future. The project will be delivered in the most environmentally friendly way possible, including the recycling of paper and the reduction of paper-based activities to the absolute minimum, including through distribution of project materials through uploading them on intranet/internet. The project has no negative effect on the environment.

Minorities

Inclusion of more minority group police officers in the Internal Affairs Sector will add to its reputation as being fair and unbiased. The Ministry of Interior encourages promotion of diversity within the police and especially in Internal Affairs Sector.

9. Conditionality and sequencing

Strong cooperation and commitment of the beneficiary institution is expected in order to achieve project objectives.

IAS  is ready to commit the necessary time and resources to maximize the benefits of the Twining project. Significant staff time will be required from the BC in all aspects of the project.

At both senior an operational level there must be strong commitment and support provided by the beneficiary institution for smooth implementation of the project.

10. Indicators for performance measurement

- Manual and procedures for using special investigative techniques prepared;

- Operational procedure prepared for conducting integrity test adopted

- At least 10 IAS police officers trained to conduct integrity test and advanced surveillance techniques

- Operational procedures for IT anti-corruption data protection and security developed

- At least 5 Trained IT experts from IAS  to secure and manage confidential corruption data

- At least 40  IAS officers trained to conduct proactive investigations of corruption

- At least 20 IAS police officers trained to check declaration of assets/property

- Operational procedures prepared for conducting corruption investigations and  check declaration of assets/property

- At least 10 IAS police officers trained to process intelligence and analyse operational data

- At least 15 IAS police officers trained to conduct risk analysis of corruption and create risk register of corruption

- Operational procedures prepared for corruption intelligence gathering, processing and transforming it into evidence

- Operational procedure prepared for creating corruption risk register

11.Facilities available

The beneficiary will provide the MS twinning partner with adequate office space for RTA and experts, meeting rooms and equipment necessary for relevant everyday activities and trainings foreseen.

ANNEXES TO ACTION DOCUMENT

ANNEX 1. Logical framework matrix in standard format (compulsory)

| OVERALL OBJECTIVE | OBJECTIVELY VERIFIABLE INDICATORS (*) | SOURCES OF VERIFICATION |  |
| --- | --- | --- | --- |
| To support Serbia’s commitment in the field of fighting corruption in line with the recommendations of the Action Plans on Chapter 23 and Chapter 24. | - Number of activities within Action Plan for Chapter 23 and Chapter 24 implemented | - EU Progress reports - Reports of Ministry in charge of Chapter 23 - Reports of Ministry in charge of Chapter 24 |  |
| SPECIFIC OBJECTIVE | OBJECTIVELY VERIFIABLE INDICATORS (*) | SOURCES OF VERIFICATION | ASSUMPTIONS |
| Support to on-going capacity building of the Internal Affairs Sector, with focus on preventive mechanisms to fight corruption in the Ministry of Interior, as well as fulfilling activities defined in National Anti-Corruption Strategy and its Action Plan. | - New preventive mechanisms in fight against corruption are implemented in IAS - Number of filed criminal charges by IAS against employees in MoI and quality of gathered evidence - IAS activities arising from the Action Plan for Implementation of the National Anti corruption strategy implemented. | - EC Report on Chapter 23 - Project implementation and evaluation reports - Annual report of Internal Affairs Sector - Implementation of National Anticorruption Strategy and Action Plan and Action Plan for Chapter 23 | - Law on Police implemented - Supplies duly delivered |
| RESULTS | OBJECTIVELY VERIFIABLE INDICATORS (*) | SOURCES OF VERIFICATION | ASSUMPTIONS |
| Result 1.1. Enhanced capacity of IAS to efficiently use special investigative techniques in proactive investigations of corruption and integrity testing. | - Manual and procedures for using special investigative techniques prepared; - Operational procedure prepared for conducting integrity test adopted - At least 10 IAS police officers trained to conduct integrity test and advanced surveillance techniques | - Twining quarterly report, EC Report on Chapter 23 - Annual report of Internal Affairs Sector | - Strong support to implementation of activities with Chapter 23 and 24 - Willingness of IAS staff to accept changes |
| Result 1.2. Improved IT systems of IAS to protect and manage data during investigations | - Operational procedures for IT anti-corruption data protection and security developed - At least 5 Trained IT experts from IAS to secure and manage confidential corruption data | - MoI reports, Twining quarterly report, - EC Report on Chapter 23 - Annual report of Internal Affairs Sector | - New VMware technology in the IAS IT system established |
| Result 1.3. Enhanced internal investigation capacity of the IAS and enforced asset/property declaration checks of employees of MoI. | - At least 40 IAS officers trained to conduct proactive investigations of corruption - At least 20 IAS police officers trained to check declaration of assets/property - Operational procedures prepared for conducting corruption investigations and check declaration of assets/property | - MoI reports, Twining quarterly report, - EC Report on Chapter 23 - Annual Report of Internal Affairs Sector |  |
| Result 1.4. Established capacities of IAS to process intelligence and operational data as well as to conduct corruption risk analysis. | - At least 10 IAS police officers trained to process intelligence and analyse operational data - At least 15 IAS police officers trained to conduct risk analysis of corruption and create risk register of corruption - Operational procedures prepared for corruption intelligence gathering, processing and transforming it into evidence - Operational procedure prepared for creating corruption risk register | - MoI reports, Twining quarterly report, - EC Report on Chapter 23 Annual Report of Internal Affairs Sector |  |