ANNEX C1: Twinning Fiche

Project Title: Further Strengthening the Competition Authority’s capacities to protect the free and effective competition in the market

Beneficiary Administration: Albanian Competition Authority (ACA)

Twinning Reference: AL 15 IPA FI 02 18

Publication notice reference: (The publication notice reference will be completed by the European Commission)

EU funded project

TWINNING INSTRUMENT

- Basic Information

1.1 Programme: IPA 2015 Action Programme for Albania (Indirect Management) 2015/038715

For British applicants: Please be aware that eligibility criteria must be complied with for the entire duration of the grant. If the United Kingdom withdraws from the EU during the grant period without concluding an agreement with the EU ensuring in particular that British applicants continue to be eligible, you will cease to receive EU funding (while continuing, where possible, to participate) or be required to leave the project on the basis of Article 12.2 of the General Conditions to the grant agreement.

1.2 Twinning Sector: Finance, Internal market and economic criteria

1.3 EU funded budget: 700,000 EUR

- Objectives

  - Overall Objective(s):

To provide support and contribute in strengthening the administrative and institutional capacities of the Albanian Competition Authority (ACA)

  - Specific objective:

Provide support to ACA in order to ensure its mission to protect the free and effective competition in the market based on legal framework in force and Union Acquis. More specifically, it aims to provide support to the Albanian Competition Authority (ACA) to increase their skills for planning and conducting inspections and solve competition cases, to support the full harmonization of the Albanian legislation with the relevant EU rules in the area of competition law and policy, and capacity building actions in order to prepare accession negotiations (particularly chapter 8 Competition policy).

2.3 Contribution to National Development Plan/Cooperation agreement/Association Agreement/Action Plan

This Project will directly contribute to the objectives mentioned in the following strategic and/or programming documents:

National Strategy for European Integration set in a certain pillar of the document “Increasing economic growth through Competitiveness and Innovation” , the protection of competition and provisions of state aid control, where are defined the Strategic objectives in the field of competition. Among the other objectives, are emphasized the  completion of harmonization of primary and secondary legislation with European law to  meet obligations arising from EU integration, the strengthening of investigative capacities through investments to optimize infrastructure information and increase the level of expertise and number of experts on competition, increasing the culture of competition by strengthening law enforcement and cognitive activities such as roundtables, publications in the media, emphasizing the public interest and the benefits  that brings competition not only for end consumers but also for businesses.

Indicative Country Strategy Paper (adopted on the 18.08.2014) sets out the priorities for EU financial assistance for the period 2014-2020 to support Albania on its path to EU accession.

National Plan for European Integration 2016-2020 sets that Albania has made progress in terms of free market competition. The Competition Authority has intervened in many sectors of the economy where anti-competitive practices have been identified and detected, taking appropriate measures to restore competition in the market. Tools have been used to increase the culture and advocacy of competition, with the goal of raising the awareness of actors in the market of competition rules and principles. The Competition Authority has continued the process of the approximation of legislation with the EU acquis, aiming at a comprehensive legal framework for competition, process that will follow even in the future.

One of the Albanian Competition Authority's priorities is to maintain free and effective competition in the market, through the application of competition rules and principles, applying the provisions of law.

In order to achieve the goals of organic law and National Competition Policy, the enforcement activities of the institution will be extended in the following fields:

- Enforcement of antitrust law, detecting prohibited agreements, abuse of dominant position and control of Mergers and Acquisitions(M&A);

- Competition advocacy, by providing recommendations to increase competition in sectors/markets which have exclusive rights/special, market entry barriers, natural monopolies;

- Information on special and exclusivity rights, with the main aim to recommend necessary interventions for market liberalisation to increase competition in the relevant markets;

- strengthening administrative capacities;

- Market monitoring;

- General investigation of the sectors of economy;

- Preliminary and in-depth investigation with the intention of protecting free and effective competition in the market;

- Legal approximation of primary/secondary laws with the EU acquis;

- Organisation of seminars and workshops to enhance administrative capacity;

Commission Report for Albania on 2015, sets that Albania has made moderate progress in the Competition policy field. In the field of anti-trust and mergers, the ACA has adopted guidelines for the evaluation and abuse of dominant position in the market and has developed new guidelines for remedies based on the notice of the European Commission for remedies. The administrative capacity of the ACA is sufficient and its staff has a good level of expertise. However, delays in court proceedings are too long and further efforts should be made to increase the availability and quality of training for judges on competition policy.

The Twinning Project “Support for Competition and State Aid in Albania” part of IPA 2008, which was implemented by the Italian Competition Authority and Hungarian Competition Authority during the period 01 November 2010-31 October 2012, recommended that greater caution should be exercised when considering the level of in-house understanding (in the area of competition) and inter-government connectivity (this is vital when competition policy cuts across other government policy areas such as infrastructure, business support programs and transport). The future projects should endeavor to ensure that in-house technical competences are consistent with proposed project. Otherwise valuable time will be spent or lost recalibrating the project activities to match the real needs for the Beneficiary Institution.

3. Description

3.1 Background and justification:

The competition policy enforcement in Albania is performed by ACA which was established on 1 March 2004 on the basis of the Law No. 9121, “On Competition Protection”, of 28.07.2003. ACA is also the national authority responsible for the enforcement of the Union acquis in the process of the Albania’s integration to the EU. ACA is an independent institution as stated in Article 18 of the law no 9121 dated 28.07.2003 “On Protection of Competition” (as amended) (herein and after the law): “ACA is a public body, independent in fulfilling its duties. ACA is a judicial person, based in Tirana”.

The law no 9121/2003 was amended in 2010 with a view to achieving further approximation with the EU legislation and to improving its practical implementation.

Similarly to Art.106 of the Treaty on the Functioning of the European Union (TFEU), the Albanian competition law is applicable to public undertakings and undertakings granted by the State with special or exclusive rights to perform certain economic activities. In accordance with the amendments, the competition rules apply to undertakings entrusted with the performance of services of general economic interest or having the character of a revenue-producing monopoly, as far as the competition law enforcement does not obstruct the fulfillment of the tasks assigned to them. In practice, ACA has been empowered to assess public contracts and concessions granted by the State to certain undertakings and to possibly exempt them from the application of competition rules provided that the legal requirements for exemption are met in particular cases.

In the field of prohibited agreements, the competition law has been amended in order to empower the national competition authority with the ability to grant not only individual exemption from the general prohibition but to also block exemptions to certain categories of agreements between undertakings as well as to apply de minimis rules towards the agreements of minor impact on competition.

As regards the unilateral conduct by dominant undertakings the amendments of 2010 removed the legal provision, with no analogue in the EU law, which allowed the abusing undertaking to prove that its practice was committed for objective reasons of legal or economic nature and thus it did not constitute an infringement.

In the sphere of merger control, following the EU development, a new test for merger appraisal has been introduced as the previous ‘dominance’ test has been replaced by the ‘significant impediment of the effective competition’ test. This amendment has significantly increased the role of economic analysis in merger cases. In addition, the threshold of the turnover required for merger notification has been decreased and certain improvements in the merger proceedings have been put in place.

The sanctioning policy has also been amended by removing the previously existing minimal level of 2 % of the undertaking’s turnover for setting the sanctions and the fines are now determined with higher degree of flexibility up to 10 % of the infringer’s turnover. In practice, the authority has also been empowered to impose symbolic sanctions in cases where such sanctions would guarantee adequate deterrent effect.

In May 2017, the new organization structure of ACA was approved by the Parliament with the decision 43/2017. New positions have been established, like new directorates and chief economist, and job description changes are taking place in different directorates, which require further trainings and exchange of experience between homologue authorities.

This project is necessary for the institution because, from past experience and the cases faced in the last years, ACA has concluded that cases have been more complex than in the past: multi-national companies (the parties under investigation are represented by legal multi-national companies specialized in competition issues) have been involved and as consequence further support is needed in order to increase the professional capacities and techniques in dealing with these cases.

This project will provide support and facilitation, regarding the joint cooperation between ACA and other institutions, especially governmental (regulatory entities) bodies in certain sectors of the economy, in solving competition concerns in the market.

The main beneficiary of this project is ACA’s staff.  Due to the rapid developments in markets,

digital economy, economic growth, changes in the structural organization of the authority, new markets and sectors are under assessment. Other relevant stakeholders will be the business environment, public central and local institutions, regulatory bodies, academia, and court systems. etc.

3.2 Ongoing reforms:

According to the INDICATIVE STRATEGY PAPER FOR ALBANIA (2014-2020) point 5.Competitiveness and innovation, the EU will assist Albania in achieving the objective to enhance the competitiveness of the Albanian economy, in particular by developing competitive SMEs, enhancing market integration and the role of competition in market surveillance.

3.3 Linked activities

IPA 2008. ACA has been the beneficiary institution in a Twinning Project, financed by IPA 2008, “Support for the Albanian Competition Authority and State Aid Department”, implemented by the consortium formed by the Italian Competition Agency and Hungarian Competition Agency for the competition part. The project lasted 24 months, from 01 November 2010 to 31 October 2012. The headline objectives were to strengthen the technical capacity and case handling skills, to improve the enforcement capabilities, to raise the competition awareness. Some concrete recommendations are left regarding to the level of the in-house understanding in the area of competition and also inter government connectivity. Some of the recommendations given by the Expert Mission Project are as following:

1. To continue the process of bringing competition law in line with the EU competition acquis;

2. To increase the number of ACA’s staff;

3. To further train ACA’s staff in competition law and policy; etc.

UNCTAD Project. ACA is the beneficial institution of a project from UNCTAD (United Nations Conference on Trade and development)   in the amount of 75 000 Dollars. ACA has been part of a voluntary peer review report performed by UNCTAD, which has been concluded with some recommendations, based on which a project proposal has been drafted. The project implemented focused mainly on the training of judges on competition legal aspects, offering some assistance to ACA staff etc. Some of the recommendations are the following:

- Continue to align the national competition framework with European Union standards in competition policy

- Increase public awareness of anti-cartel policy

- Enhance leniency policy in cartel cases

- Fight against bid rigging by coordinating actions with the relevant authorities dealing with public procurement and anti-corruption policies

- Continue strengthening tools for competition advocacy etc.

3.4 List of applicable Union acquis/standards/norms:

- Law no 9121/2003 “On competition Protection” as amended and secondary legislation of competition law are broadly approximated with TFEU articles 101&102, and with the EU legal framework.

3.5 Results per component

The project will aim to achieve the following results:

Result 1 (Component 1). Legal framework and  approximation with the EU legislation improved

The following indicative results will be achieved: The main indicators of achievement for this result are:

- Contribution to the revision of the Law no. 9121 date 28.7.2003 “ On protection of competition” in line with EU legislation

– New amendments drafted.

- Prepared and published Commentary of the Law no. 9121 date 28.7.2003 “ On protection of competition based on  the European best practices

- Commentary prepared and published

- Prepared and published manuals on the procedures followed by Competition Authority based on  the European best practices

- Number of manuals published.

- Normative acts (secondary legal normative acts) drafted/approved  on competition (regulations and guidelines)

Number of normative acts drafted

- Number of staff trained on theoretical aspects for RIA (Regulatory Impact Assessment)

- Number of staff trained on the methodology and techniques of legal approximation of the national law with the EU Acquis

Result 2 (component 2). Administrative capacities of the ACA strengthened

The following indicative results will be achieved:

- Trained staff with the best practices and the recent methodologies used by EU competition member states authorities, applicable to the Albanian competition cases on (but not limited to):

  - Prosecuting Cartels without direct evidence of prohibited agreements

  - Best bid rigging cases in recent years

  - FIT (Forensics IT),  sealing of documents

  - National and European legislation related to FIT

  - Protection of Personal Data in competition cases

  - Application of SSNIP test on M&A (Merger and Acquisition)  and abuse of dominant position cases

  - Effect of post-merger analysis

  - Methodologies used in analyzing abuse of dominant position in exclusive rights cases

  - Methodologies used in analyzing abuse of dominant position in essential facilities cases

  - Planning and conducting Merger Investigations;

  - Market Survey on Analyzing Relevant Market;

  - Diversion Ratios in merger analysis;

  - Pricing pressure Analysis (IPR, UPP, GUPPI) in merger assessment;

  - Turnover calculation in cases of offshore companies;

  - Remedies, cases with remedies (carve outs/ crown jewels cases; negotiation process, best buyer selection process etc.)

  - Abuse of dominance cases: In depth analysis for Predatory and Excessive prices, Analysis of Margin Squeeze: The Equally Efficient  Competitor, Cost Analysis and Discount Cash Flow Methods

  - Theory of Game & Oligopolistic Behavior

  - Gathering Data for Market Studies/ Sector Inquiries through surveys, questionnaires and usage of Social Media: quantitative and qualitative data, Data cleaning& Manipulation

- -No. of staff trained;

- Study visits and internships organized to the MS Agency to gain experience through day to day work

- Number of study visit and internships days organized

- Trainings provided in order to strengthen the capacities of the staff:

- Number of cases handled by ACA Secretariat;

- Number of Decisions taken by ACA Commission;

- Number of Recommendations given by ACA Commission

Result 3. (component 3) Authority capacity to reach out to different relevant stakeholders

increased

The main indicators of achievement for this result are:

- Number of workshops organized with regulatory bodies for competition matters in different sectors of economy; Variety of regulatory bodies involved.

- Conducted analyses of the effects of the recommendations of the Competition Commission and establishment of the right mechanisms to make them obligatory for central and local government/independent institutions/market regulatory bodies.

- Assistance provided on drafting a methodology for measuring the effects of CC recommendations.

- Number of joint meetings between ACA, regulatory bodies and the Parliament on the stage of implementation of the Competition Commission decisions.

- Analyses conducted on the stage of implementation of the Competition Commission.

- Joint meetings carried out between ACA, regulatory bodies and the Parliament regarding effects of the recommendations of the Competition Commission;

- Number of meetings organized with regulatory bodies.

4.  Raised awareness on the recent development of competition.

– Level of the application of the CC recommendations

5. Increased competition awareness in business environment, chambers of commerce, consumers associations, NGO-s, legal firms and administration in central/local level.

- Number of joint meetings between ACA and the mentioned third parties.

6. Increased cooperation with the court system regarding the juridical review of ACA decisions and private claims.

- Number of trainings with judges on competition legal framework and cases

7. Improved capacity of relevant public institutions in handling competition issues.

- Number of Joint meetings between ACA, regulatory bodies and relevant public institutions to improve capacity of the latter in detecting anticompetitive practices.

8. Increased competition culture in different regions in Albania (conferences in different cities).

- Number of workshops with legal firms;

- Number of workshops with trade associations;

9. Increased competition culture in academia and education system.

- Number of workshops with the academic bodies aiming at increasing the competition culture.

- Number of brochures/leaflets published for increasing competition culture, targeting academia;

10. Increased competition culture in business environment, etc.

- Number of workshops with business environment;

- Number of brochures/leaflets published for increasing competition culture, targeting the business environment.

11. Awareness activities organized with respect to the ACA mission activities

- Number of awareness activities organized

3.6 Means/ Input from the EU Member State Partner Administration:

The project is envisaged to provide exchange of experience and know-how with a MS Institution with good practice in the required area.

The implementation of the project requires a Project Leader who will be responsible for the overall coordination of the project activities. The Project Leader is expected to closely work with the Resident Twinning Advisor (RTA) and the short-term experts as well as with the counterpart of the Albanian Competition Authority (Beneficiary Institution).

3.6.1 Profile and tasks of the Project Leader

- University Degree in Economics and/or Law or equivalent professional experience of 8 years.

- High-level civil servant official from a Member State administration

- Proven contractual relation to a public administration or mandated body (see Twinning Manual 4.1.4.2)

- At least 3 years of experience in EU competition area

- Experience in implementing EU funded projects will be considered an asset;

- Managerial experience will be considered an asset

- Excellent English skills (oral and written);

- Excellent computer skills.

Tasks:

- Overall project co-ordination and monitoring,

- Supervision of the implementation of the project in coordination with the Albanian Project Leader counterpart,

- Coordinating work with other MSs in case of consortium of MSs

- Mobilizing and coordinating short-term experts,

- Closely working with the RTA and the short term experts,

- Executing administrative issues (i.e. signing reports, side letters etc.),

- Monitoring and evaluating the needs and priorities in the respective sector,

- Undertaking all activities specified in the project and achieving the mandatory results

- Ensuring backstopping and financial management of the project in the MS

- Organization of study visits

- Participation in Steering Committee meetings

3.6.2 Profile and tasks of the RTA

This project requires a Resident Twinning Advisor (RTA) as well as short term experts to implement the project.

The RTA will work on a day-to-day basis in the Competition Authority of Albania and support the co-ordination of different actions. RTA should be familiar with the legislative procedures both in the Competition Authorities of EU Member States and European Institutions as well as with the methods and techniques of legal harmonization.

The Resident Twinning Advisor will have a key role in the coordination of inputs required for successful implementation of the project activities. He/she shall be supported by short – term experts from the European Union Member State(s).

Profile:

- University Degree (preferred in Law and/or Economics) or professional experience of 8 years in public administration.

- Proven contractual relation to a public administration or mandated body (see Twinning Manual 4.1.4.2)

- At least 3 years of professional experience in EU competition area

- Experience in implementing EU funded projects will be considered an asset;

- Excellent English skills (oral and written);

- Excellent computer skills.

The RTA will be located within the premises of the Competition Authority and for 12 months period will be responsible for the following key activities:

Tasks

- Daily co-ordination of the project;

- Communication with the RTA counterpart and Beneficiary Project Leader on project activities,

- Coordination and briefing of the short term experts in situ;

- Permanent contacts with the main BC component counterparts;

- Undertaking all activities specified in the project implementation, achieving the mandatory results, proposing corrective actions if required;

- Preparation of projects progress reports

- Advising on EU policies and best practices, related legislation and regulations in competition field;

- Planning and organization of the study visits, training activities and the visibility events of the project (kick-off, final event, thematic events).

- Liaison with CFCU and EU Task Manager.

3.6.3 Profile and tasks of Component Leaders:

Component leaders will ensure the implementation of the project components and plan the agreed activities in a timely manner with high quality. They report to the RTA and liaise with the RTA counterpart.

Component Leader 1 for result 1: Improved legal framework and further approximation with the EU legislation

Profile

- University Degree in Law or similar discipline relevant to the project or equivalent professional experience of 8 years in public administration.

- At least 3 years of professional experience in EU competition area

- Excellent English skills (oral and written);

- Excellent computer skills.

Tasks:

- Undertaking all activities and achieving mandatory results;

- Conducting analysis on the area of the project components;

- Preparing and conducting training programs;

- Elaborating and presenting the proposals on the area of the project components

Component Leader 2 for result 2: Strengthened administrative capacities of the ACA

Profile

- University Degree in Law/Economy or similar discipline relevant to the project or equivalent professional experience of 8 years in public administration.

- At least 3 years of professional experience in EU competition area

- Excellent English skills (oral and written);

- Excellent computer skills.

Tasks:

- Undertaking all activities and achieving mandatory results;

- Conducting analysis on the area of the project components;

- Preparing and conducting training programs;

- Elaborating and presenting the proposals on the area of the project components

Component Leader 3 for result 3: Authority capacity to reach out to different relevant stakeholders increased

Profile

- University Degree in Law/Economy or similar discipline relevant to the project or equivalent professional experience of 8 years in public administration.

- At least 3 years of professional experience in EU competition area

- Excellent English skills (oral and written);

- Excellent computer skills.

Tasks:

- Undertaking all activities and achieving mandatory results;

- Conducting analysis on the area of the project components;

- Preparing and conducting workshops;

- Elaborating and presenting the proposals on the area of the project components

3.6.4 Profile and tasks of the short-term experts

The PL and the RTA will be assisted by international short-term experts (STEs). Their “mix” should be identified by the Project Leader/RTA in the course of defining the operational side letters (OPS). The short-term expert shall assist the PL and the RTA in delivering the activities within the project. STEs that will be engaged should be professionals with competition work background. This Twinning project should be implemented by a MS competition administration. Tasks for short-term expert(s) will be elaborated by Project Leader/RTA and the beneficiary counterpart at the work plan preparation stage.

Profile

- University Degree in Law, Economics or similar discipline relevant to the project or equivalent professional experience of 7 years in public administration.

- At least 3 years of professional experience in EU competition area

- Excellent English skills (oral and written);

- Excellent computer skills.

Tasks:

- Undertaking all activities and achieving mandatory results;

- Conducting analysis on the area of the project components;

- Preparing and conducting training programs;

- Elaborating and presenting the proposals on the area of the project components

4. Budget

The budget for the project is EUR 700,000 which will be covered by IPA contribution, in line with the Twinning Manual.

5. Implementation Arrangements

5.1 Implementing Agency responsible for tendering, contracting and accounting.

General Directorate for Financing and Contracting of EU, World Bank and Other Donor Funds/ Central Finance and Contracting Unit (CFCU) in the Ministry of Finance and Economy

Mrs. Enkelejda Kokthi

General Director

Email: Enkelejda.Kokthi@financa.gov.al;

"Dëshmorët e Kombit"Blvd.  No.3,

Tirana – Albania

Delegation of the European Union to Albania

Mr. Enzo Damiani The Project Manager at the EU Delegation

5.2 Institutional framework

ACA is composed by the Competition Commission, the decision-taking body, and the Secretariat, the operational body of the authority. The competence of ACA, which is exercised by the decision-taking body, includes the following duties:

- Outlines the national competition policy;

- Approves regulation on the internal functioning of ACA;

- Supervises the Secretariat in the application of the competition law;

- Takes decisions on the basis of the competition law;

- Issues regulations and guidelines for the implementation of the law;

- Submits ACA’s annual report to the Parliament;

- Gives opinions to the Parliament on competition-related issues;

- Gives recommendations to public administration and NGOs on competition;

- Represents ACA in its relationships with its counterparts;

- Sets the priorities of investigations and the related deadlines.

ACA is composed by a decision-making body and an investigative body so that both of them are functionally separated within the ACA unitary organizational structure which is approved by the Albanian Parliament. The functional separation between the ACA two composing elements, namely the Competition Commission and the Secretariat, is established with a view to guaranteeing procedural fairness and effectiveness in the competition law enforcement.

The Competition Commission is a permanent collegial body consisting of 5 members which exercise the decision-making powers of ACA.

The Commission’s members are elected by the Parliament for 5 years fixed term of office with the possibility to be re-elected not more than twice consecutively. The Parliament takes the election decision by simple majority of the votes, in the presence of more than half of all the members of the Parliament. One member is proposed by the President of the republic, two members are proposed by the Council of Ministers and two members are proposed by the Parliament. The Commission’s chairperson is elected by the Parliament amongst the elected members of the Commission and the deputy chair is subsequently elected by the majority of the votes of all the Commission’s members in its first sitting. The new chairwoman of ACA has been appointed on December 2016.

The criteria for election of the members are provided for in the law and include: Albanian citizenship; at least 15 years of working experience; at least a doctorate (PhD) degree or being an university lecturer in law or economics; and lack of disciplinary dismissals from work. In fact, finding candidates that meet the election requirements has proven challenging for the Parliament and during most of the time of the Commission’s functioning (2006-2012) it had at least one vacant position for a member.

The Competition Commission is headed by the Chairperson, who is elected by the Parliament. The Chairperson exercises the executive management of the daily work of ACA, chairs the meetings of the decision-making college, and ensures the implementation of the law. In case of the Chairperson’s absence, the Deputy Chairperson is in charge of the duties of the Chairperson. In the case that both the Chairperson and the Deputy are absent from work, one of the members of the Commission is to implement the tasks as defined in Art. 25 of the law, namely:

- Prepares, calls and leads the Commission meetings;

- Coordinates work amongst the Commission members;

- Signs Commission’s acts, except for the decisions signed by the whole college;

- Represents authority in relation with third parties.

The Secretariat is the Authority’s investigatory body which conducts the administrative investigations and studies under the competition law in accordance with the Code of Administrative Procedures. The Secretariat officials have the status of civil servants, organized in departments and sectors, which are headed by the Secretary General, who is elected by the Competition Commission. The main responsibilities of the Secretariat connected with the competition law enforcement are explicitly provided for in the Law:

- Monitors and analyzes the conditions on the market to the extent necessary for the development of free and effective competition;

- Conducts investigations as to competition law infringements;

- Drafts and submits investigation reports to the Commission for decision-taking;

- Ensures publishing the decisions, by-laws and the annual report of the authority;

- Supervises the implementation of the decisions taken by the Commission.

The organizational structure of the Secretariat is approved by the Albanian Parliament with the decision no.43/2017 and currently consists of 6 (six) directories.

- The “Market Analysis and Methodologies“ Directorate conducts sector inquires and monitors the market conditions with a view to enhancing competition in the country and is committed to assess the market conditions through complex economic analyses in concentration case, when granting exclusivity rights, in abuse of dominant position cases and in assessing horizontal and vertical agreements. The new position of chief economist, a key position in this directory, has been created and will realize in particular manner in depth economic and econometric analyses regarding the markets.

- The “Production Markets Surveillance” Directorate will deal with the surveillance of the production markets, as the energy market, liquid gas and fuel, construction, forest, minerals, agriculture, etc. This directorate is in charge of the assessment of the cases of dominant position in the relevant markets. Special attention should be given also to vertical and horizontal agreement.

- The “Non-Production/Services, Markets Surveillance” Directorate will deal with the surveillance of the non-production markets where takes part those sectors of economy that offers services and other non- production activities such as the electronic telecommunication, media, financial markets, health, tourism, transport and others. This directorate is in charge with the assessment of the cases of dominant position in the relevant markets. Also special attention would be given to the vertical and horizontal agreement.

- The “Legal and Judicial Affairs” Directorate deals with legal opinions, giving comments and pinions on draft legal acts, taking part in different sector investigations, being part of different working groups on competition cases, studies of draft or effective legal acts of central or local authorities with a view to assessing their compliance with the competition law. It is also responsible for the procedural representation relevant to the court proceedings as to which the authority is a party.

- The “Integration and Communication: Directorate deals with the harmonization of domestic legislation with the EU law in the field of competition, the European integration process, the internal and international cooperation and communication with third parties. The Competition Authority is leader and coordinator of Chapter 8 “On Competition Policy” of Acquis, has special responsibility in compiling all the EU requirements in competition field.

- The “Support Services” Directorate deals with the human resource management, payment, training, as well as support internal services and financial issues.

5.3 Counterparts in the Beneficiary administration:

# 5.3.1 Contact person:

# 5.3.2 Project Leader counterpart

# Albanian Competition Authority

# Rruga “Sami Frashëri”, Nr 4, Kati IV

# www.caa.gov.al

Tirana, Albania

5.3.3   The Resident Twinning Adviser counterpart:

IPA Unit

Albanian Competition Authority

# Rruga “Sami Frashëri”, Nr 4, Kati IV

www.caa.gov.al

Tirana, Albania

6.  Duration of the project

Duration of the execution period: 15 months. The execution period will end 3 months after the implementation period of the Action (work plan), which will take 12 months.

7. Sustainability

The successful implementation of the project will further improve the regulatory and oversight functions of the Competition Authority in general and in the EU-related issues in particular. The successful implementation of the project will bring a more efficient and qualitative approximation of Albanian legislation to the EU acquis, strengthen   the administrative capacities of the institution.

The sustainability of this project's results will be ensured by the continuation of the reforms and efforts to further strengthen the capacities of Competition Authority for more efficient approximation of domestic legislation to EU law and improved oversight functions.

The results of the project and the know-how that will be acquired through the implementation of the Twinning Project will be maintained, disseminated and further developed in order to ensure the long-term sustainability of this Twining project. The training manuals and guidelines elaborated under the Twinning Project will continue to be used and updated by the Competition Authority after the project's completion.

8. Crosscutting issues (equal opportunity, environment, etc.)

Equal access in compliance with the constitutional principal of equality will be guaranteed for participation in this project. The selection of the training participants in this twinning program will be made on non-discriminatory criteria regarding to men, women, administration staff.

The project has no evident effect on the environment.

9. Conditionality and sequencing

9.1 Conditionality

A key condition for the implementation of the Twinning Project is the full support of the ACA staff to the execution of this twinning project.

Additional conditionality includes:

- Co-operation and transparency among all partners and stakeholders involved in the implementation of the project.

- Full commitment of both the Albanian Competition Authority and the twinning counterpart to mobilize all appropriate human and financial resources for a successful implementation of the project.

# 9.2   Sequencing

Keys milestones will be:

- Successful selection of a Twinning partner

- Signature of the Twinning contract, including the Twinning Work Plan;

- Start of the twinning partnership (inter alia, the arrival in the country of the Resident

Twinning Advisers);

- End of the implementation period;

- Submission of the final report.

10. Indicators for performance measurement

The indicators are provided in the log-frame.

11. Facilities available

- Support the RTA with office accommodation, trainings rooms and logistical assistance

- Ensure that appropriate staff is made available to work with the EU twinning partner(s). Counterparts for each of the objectives will be appointed to facilitate the implementation of the respective activities of the twinning project;

- Be responsible for providing the EU experts with legislation and any other documents necessary for the implementation of the project;

- Ensure that staff trained under this project is encouraged to increase its capacity according to the tasks specified in the job description and to its promotion based on the merit. In this context a data base of what training was provided to which person should be maintained by the implementing partner for future monitoring.

- Provide all possible assistance to solve any unforeseen problem that the EU twinning partner(s) may face;

- Equally, the Twinning team, as led by the Twinning Resident Adviser must ensure full collaboration with the counterparts of the institution. Communications should be open and consistent. The Twinning team must carry out activities in the interest of the institution, and maintain its involvement at all stages of activities.

ANNEXES TO PROJECT FICHE

- Logical framework matrix in standard format

- Detailed implementation chart

- Contracting  and  disbursement  schedule  by  quarter  for  full  duration  of  programme  (including disbursement period)

- List of relevant Laws and Regulations

# ANNEX 1: Simplified Logical Framework

|  | Description | Indicators (with relevant baseline and target data) | Sources of verification | Risks | Assumptions (external to project) |
| --- | --- | --- | --- | --- | --- |
| Overall Objective | To provide support and contribute in strengthening the administrative and institutional capacities of the Albanian Competition Authority (ACA). |  | EU Progress Report for Albania |  |  |
| Specific (Project) Objective(s) | Provide support to ACA in order to ensure its mission to protect the free and effective competition in the market based on legal framework in force and Union Acquis. More specifically, it aims to provide support to the Albanian Competition Authority (ACA) to increase their skills for planning and conducting inspections and solve competition cases, to support the full harmonization of the Albanian legislation with the relevant EU rules in the area of competition law and policy, and capacity building actions in order to prepare accession negotiations (particularly chapter 8 Competition policy). |  |  |  |  |
| Mandatory results/outputs by components | Result 1 Legal framework and approximation with the EU legislation improved | -New amendments of the Law no. 9121 date 28.07.2003 “On protection of competition” drafted; -Commentary of the Law on Protection of competition prepared and published; -No. of manuals of procedures prepared and published; -No of secondary legal normative acts drafted; -No. of staff trained; | EU Progress Reports on Albania | Delays of the project implementation will cause the non-fulfillment of the result 1 | Political commitment. -Full commitment of the twinning project partners (MS and BC). -Optimal collaboration and transparency between twinning partners (MS and BC teams). -Relevant training materials |
|  | Result 2. Administrative capacities of the ACA strengthened | - Trained staff with the best practices and the recent methodologies used by EU competition member states authorities, applicable to the Albanian competition cases; -No of study visit and internships days organized to the MS Authorities; -No. of cases handled by ACA Secretariat; -No. of Decisions taken by ACA Commission; - Number of Recommendations given by ACA Commission | EU Progress Reports on Albania | Lack of staff training might cause inefficient final reports and low decision making effectiveness | -Relevant training materials. -Sustainability of staff. |
|  | Result 3. Authority capacity to reach out to different relevant stakeholders increased | - Number of workshops organized with regulatory bodies for competition matters in different sectors of economy; - Conducted analyses of the effects of the recommendations of the Competition Commission and establishment of the right mechanisms to make them obligatory for central and local government/independent institutions/market regulatory bodies; - Joint meetings carried out between ACA, regulatory bodies and the Parliament regarding effects of the recommendations of the Competition Commission; - Number of meetings organized with regulatory bodies; - Raised awareness on the recent development of competition; | EU Progress Reports on Albania | The non-fulfillment of the result 3, will take the ACA of not implementing the fourth pillar of the Law 9121/2003, the Competition Advocacy. | Availability and Good will of regulatory bodies to participate in meetings and workshops. |
|  |  | - Number of joint meetings between ACA and the mentioned third parties. - Number of trainings with judges on competition legal framework and cases; -Number of Joint meetings between ACA, regulatory bodies and relevant public institutions to improve capacity of the latter in detecting anticompetitive practices. - Number of workshops with legal firms; - Number of workshops with trade associations - Number of workshops with the academic bodies aiming at increasing the competition culture. - Number of brochures/leaflets published for increasing competition culture, targeting academia; -Number of workshops with business environment; |  |  |  |
|  |  | -Number of brochures/leaflets published for increasing competition culture, targeting the business environment. - Number of awareness activities organized |  |  |  |

ANNEX 2: Detailed Implementation chart (indicative)

2019

| T | T | T | T | C | C | C | I | I | I | I | I |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

2020

| I | I | I | I | I | I | I | R | R | R |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

T = Tendering

C = Contracting period

I = Implementation

R=Report

# ANNEX 3: 	Contracting and Disbursement Schedule by Quarter for full duration of programme (including disbursement period) (indicative)

|  |  | Quarter 3 2019 | Quarter 3 2020 |
| --- | --- | --- | --- |
| Contract Twinning | Contracted € 700,000 | 80% | 20 % |
|  | Disbursed | € 560,000 | € 140,000 |

# Annex 4:  List of Laws and Regulations

Competition legal framework

- Law no. 9121, date 28.07.2003 “On Competition Protection”, amended with Law no. 9499, date 03.04.2006 “On some changes of law 9121”, date 28.07.2003 “On competition protection”, Law no. 9584, date 17.07.2006 “On salaries, rewards and structures of independent constitutional institutions and other independents institutions, created by law”, law no. 10317, date 16.09.2010 “On some additions and changes to law no. 9121, date 28.07.2003 “On competition protection”

- Regulation “On functioning of the Competition Authority” approved with decision no. 58, date 15.10.2007, amended with decision no. 115, date 26.05.2009 “On some additions and changes in the regulation “On functioning of the Competition Authority”, changed with decision no. 168, date 21.12.2010 “On a change in regulation “On functioning of the Competition Authority”, and decision no. 189, date 26.05.2011 “On some changes in regulation “On functioning of the Competition Authority”

- Regulation “On exemptions of the categories of specialization agreements” approved with decision no. 190, date 26.05.2011

- Regulation “On exemptions of the categories of research and development agreements” approved with decision no. 187, date 03.05.2011

- Regulation “On categories of technological transfer agreements” approved with decision no 179, date 02.03.2011

- Regulation “On investigative procedures of the Albanian Competition Authority” approved with decision 176, date 24.02.2011

- Regulation “ On implementation of procedures for concentrations of undertakings”, approved with decision 80, date 05.06.2008; amended with decision no. 165, date 14.12.2010 “On some changes in regulation “On implementation of procedures for concentrations of undertakings”

- Guideline “On the form of concentration notifications” as well as the relevant annexes I and II approved with decision no. 82, date 23.06.2008

- Guideline “On assessment of horizontal concentrations between undertakings, approved with decision no. 131, date 07.12.2009

- Guideline “On the assessment of non-horizontal mergers and conglomerate mergers between undertakings” approved with decision no. 132, date 07.12.2009

- Regulation “On agreements of minor importance, de minimis” approved with decision no. 121, date 10.09.2009, amended with decision no. 164, date 14.12.2010

- Regulation “On fines and leniency” approved with decision no. 120, date 10.09.2009

- Guideline “On market definition” approved with decision no. 76, date 07.06.2008

- Guideline “On assessment of consequences in the competition legislation” approved with decision no. 68, date 24.12.2007

- “Ethics Code of the Competition Authority” approved with decision no. 69, date 24.12.2007

- Regulation “ On prevention of conflict of interest in performing public functions in the Competition Authority”

- Regulation “On determining expenses for following procedures at the Competition Authority, approved with decision no. 10, date 29.06.2004; amended with decision no. 167, date 21.12.2010; amended with decision no. 242, date 03.09.2012

- Guideline “On the form of notification of agreements and the form of notifying agreements” approved with decision no. 14, date 26.01.2005

- Regulation “On block exemption of categories of vertical prohibited agreements coordinated practices” approved with decision no. 234, date 19.07.2012

- Regulation “On block exemption of categories of vertical prohibited agreements coordinated practices in the sector of motorized vehicles” approved with decision no. 235, date 19.07.2012

- Guideline “On control of concentration between undertakings” approved with decision no. 236, date 19.07.2012

- Regulation “On implementation of article 6 of LPMK towards some categories of agreements, decisions and practices in the insurance sector” approved with decision no. 276, date 18.03.2013

- Regulation “On categories of agreements and coordinated practices in the sector of air transport” approved with decision no. 286, date 21.05.2013

- Guideline “On assessment of horizontal agreements” approved with decision no. 295, date 14.11.2013

- Regulation “On categories of agreements, decision and coordinated practices in the sector of naval transportation of goods” approved with decision no. 322, date 03.07.2014

- Guideline “On assessment of dominant position and abuse of dominant position” approved with decision no. 332, date 09.10.2014

- Guideline “On assessment of vertical restrains” approved with decision no. 352, date 03.03.2015

- Leniency Program, Approved with decision no. 382  date 17.11.2015

- Guideline "Conditions and obligations in cases of mergers", approved by  Decision no.374 dated 08.10.2015, of the Competition Commission;

- Regulation "On approval of the Regulation" On protection, processing, storage and security of personal data", approved by Decision No. 397, dated 02.02.2016, of the Competition Commission;

- Regulation “On Electronic data management during inspections by the Competition Authority", approved by Decision No. 410, dated 31.03.2016, of the Competition Commission;

- Regulation "On management of electronic systems and databases to the Competition Authority", approved by Decision No. 411, dated 31.03.2016, of the Competition Commission;

- Guideline "On simplified - from procedures on the assessment of concentrations ", approved by  Decision no. 419, dated 06.08.2016 of the Competition Commission.

http://unctad.org/en/PublicationsLibrary/ditcclp2015d1_en.pdf