Annex 1: Simplified Logical Framework

|  | Description | Indicators (with relevant baseline in 2019 (B) and end of project target data (T) | Sources of verification | Risks | Assumptions (external to project) |
| --- | --- | --- | --- | --- | --- |
| Overall Objective | To increase effectiveness, transparency and consistency of the competition policy in Ukraine on the basis of closer alignment with the EU competition framework, as required by AA/DCFTA (Title IV, Chapter 10). | Level of compliance of the legislative framework and law enforcement practices in Ukraine and EU (scale*) (*B: partial compliance; T: full compliance) Level of satisfaction of key stakeholders with competition framework (B: low; media tonality mostly negative; T: improved; media tonality neutral or positive) Level of integration of Ukraine's NCA into the EU's and international competition networks (B: good level of cooperation; T: very high level of cooperation) | Competition laws of Ukraine and AMCU regulations; Decisions of AMCU and national courts; Media reports; Peer reviews; Official reports on AA implementation. | Changes in AMCU leadership and strategic priorities; Low commitment of AMCU staff. | Overall political situation in the country is stable; Government is committed to continue reforms and EU integration; AMCU is committed to action. |
| Specific (Project) Objective(s) | • To ensure further alignment of the Ukrainian economic competition legislation with the EU competition laws in the field of antitrust and merger control. | Existence of legislative alignment action plan (B: no action plan; T: action plan in place with clear actions and timelines) Assessment of improved policy approximation by public and private stakeholders (B: 0; T: better comparability of EU-UA policy framework) | Competition laws of Ukraine and AMCU regulations; Decisions of AMCU and national courts; Media reports; Peer reviews; Official reports on AA implementation. | Changes in AMCU leadership and strategic priorities; Low commitment of AMCU staff. | Overall political situation in the country is stable; Government is committed to continue reforms and EU integration; AMCU is committed to action. |
|  | • To improve the institutional capacity of AMCU for competition law enforcement and competition advocacy. | Quality of AMCU decisions (assessed for their structure, clarity and quality of proof) (B: existing standard to be described at project start; T: 90% positive assessments of AMCU decisions on structure, clarity and supporting evidence) Percentage of AMCU decisions contested in courts (B: to be analysed at project start; T: at least 10% decrease) Number and type of public dialogue tools used by AMCU (B: to be described at project start; T: at least 3 more tools used by AMCU) Extent to which AMCU (and other relevant GoU stakeholders) undertake competition advocacy to promote competition among other economic policies (B: no/ad hoc advocacy efforts: T: evidence of competition advocacy strategies and tools at AMCU (and wider GoU level). |  |  |  |
| Mandatory results/outputs by components | Mandatory result 1 (Component 1): Action plan with the prioritised sequence of actions to address the remaining inconsistencies in the substantive and procedural rules Mandatory result 2 (Component 1): Proposals of legal acts (primary and secondary) addressing principal non-conformities of current Ukrainian competition legislation and promoting improvement of the economic competition protection regime in Ukraine. | Accuracy and usefulness of legislative gaps/ non-conformities analysis Presence of the action plan with clear priorities and sequence of actions Number and type of legislative proposals Level of adoption of legislative proposals Satisfaction rate of participants in capacity building activities | Project reports; Satisfaction surveys; Peer reviews; Official reports on AA implementation. | Risk Competition improvement is not a priority for Parliament and Government of Ukraine; Weak cooperation between AMCU and GoU in improvement of the competition legislation. | Assumption The Parliament and Government of Ukraine supportive of improvement of the economic competition protection regime in Ukraine; AMCU is committed to action. |
|  | Mandatory result 3 (Component 2): Improved guidelines, internal rules and procedures on handling cases, carrying out investigations, holding AMCU sessions and hearings, and other procedural actions. Mandatory result 4 (Component 2): Enhanced AMCU capacity for enforcement in individual cases by ensuring high standards (legal and economic) of decisions. | Quality and usefulness of analysis of existing AMCU rules and procedures Number and type of recommendations on new/amended rules and procedures Level of acceptance of revised procedures/rules/staff roles/organisational changes Satisfaction rate of participants in capacity building activities | Project reports; Satisfaction surveys; Peer reviews; Official reports on AA implementation. | Risk Weak absorption capacity of AMCU and low commitment of staff to changes. | Assumption AMCU is committed to organisational reforms and improvement of procedural actions. |
|  | Mandatory result 5 (Component 3): AMCU public outreach and advocacy strategies and action plans are developed and implemented. Mandatory result 6 (Component 3): AMCU's staff capacity for public outreach and advocacy is increased. | Quality and usefulness of analysis of existing AMCU communications and outreach functions Number and type of recommendations/strategic documents on public outreach and advocacy actions of the AMCU Level of acceptance of new public outreach and advocacy strategies/tools Satisfaction rate of participants in capacity building activities | Project reports; Satisfaction surveys; Peer reviews; Official reports on AA implementation; Media reports. | Risk Weak absorption capacity of AMCU and low commitment of staff to changes. | Assumption AMCU is committed to organisational reforms and improvement of public advocacy actions. |