REPUBLIKA E KOSOVËS/REPUBLIKA KOSOVA/ REPUBLIC OF KOSOVA QEVERIA E KOSOVËS / VLADA KOSOVA /GOVERNMENT OF KOSOVA ## Ministria e Ekonomisë, Punësimit, Tregtisë, Industrisë, Ndërmarrësisë dhe Investimeve Strategjike ## Ministarstvo Ekonomije, Zapošlavanja, Trgovine, Industrije, Preduzetništva i Strateških Investicija ## Ministry of Economy, Employment, Trade, Industry, Entrepreneurship and Strategic Investments

## DEPARTAMENTI I TREGTISË/ DEPARTAMENT TRGOVINE/DEPARTMENT OF TRADE

CONTACT POINT ON SERVICES AND THE POINT OF SINGLE CONTACT

Kosovo has adopted closely interrelated commitments both under AP6 and through the Law on Services in terms of providing transparency and facilitating the procedures for services suppliers intending to enter and operate in the market. It is important to implement these commitments in a synchronized manner and avoid any duplication of institutional frameworks to comply with the obligations.

A per the provisions of CEFTA 2006 and the AP6 Kosovo is bound to establish an institutional framework, a Contact Point for Services (CPS), that should perform three different functions:

- To provide answers to requests by other CEFTA members on issues related to its laws, regulations and administrative guidelines affecting trade in services [CEFTA Article 44.2]

- To inform the Subcommittee on Trade in Services (SCT) promptly, and at least annually, on any new laws, regulations and administrative guidelines affecting trade in services, and of any changes to existing ones;

- To provide advance information to the STS on any relevant measure of general application affecting trade in services it intends to adopt to allow opportunity to other parties to comment on the measure (advance notification).

There is no obligation whatsoever on the shape or structure that the CPS should have. The national government has full discretion on decisions regarding the shape or structure of the CPS.

On the basis of the Law on Services, Kosovo is bound to implement a Point of Single Contact (PSC) for services, which should be established and managed by the MTI. The PSC functions goes beyond those of the CPS, as it shall allow applicants to undertake electronically all the procedures required to enter and operate in the market. On the other hand, the CPS has a wider coverage than the PSC, as the Services Law includes important sectoral exceptions.

Given these commitments is important that the establishment of an institutional framework to comply with the different obligations is coordinated and incorporated in a single undertaken. There is no need to establish two different bodies. The implementation of the CPS should be a first step towards the full implementation of the PSC.

The work program suggested aims at achieving the objective of establishing a single institutional framework that will allow Kosovo to fulfil its obligations both under AP6 and Law on Services.

In addition, the color coded Action Plan, table with tasks and Work Programme is appended.

| Action Plan on establishing Point of Single Contact (PSC) under Services Directive 123/2006/EC |  |  |  |  |
| --- | --- | --- | --- | --- |
| OBJECTIVE | Planned Activity | Relevant Institutions | Time-frame | Budget |
| 1. Establish service contact point | 1a. Review and update Trade in Services Database | MEETIES (Department of Trade) | March 2020 |  |
|  | 2b. Determine the structure by elaborating on each law and procedure |  |  |  |
| 2. Define basic architecture of PSC (review some examples of PSC on EU) Including establishment or inclusion of freedom to provide services. | 2a. Review PSC formats in EU Members | MEETIES (Department of Trade) | March 2020 | Financed to provided by the EU twinning project |
|  | 2b. Find a role-model country as a reference point and example for a PSC in Kosovo |  |  |  |
|  | 2c. Identify the preferable structure of the PSC for Kosovo |  |  |  |
| 3. Identify all the entities that are going to participate on PSC, central and local level | 3a. Make a list of the relevant institutions and disaggregate them on a central and local level | MEETIES (Department of Trade) | November 2020 | Financed to provided by the EU twinning project |
|  | 3b. Identify specific procedures on each entity |  |  |  |
|  | 3c. Identify the function of listed institutions in PSC |  |  |  |
| 4. IT capabilities and gap analysis for each entity involved in PSC | 4a. Create an evaluation criteria for an assessment on IT Capabilities gap analysis | MEETIES (Department of Trade) | January 2021 | Financed to provided by the EU twinning project |
| 5. Define what to be done on each entity in order to be ready to be member of PSC | 5a. Create an evaluation criteria for assessment on institutional capability to become a member of PSC | MEETIES (Department of Trade) | July 2021 | Financed to be provided by the EU twinning project |
|  | 5b. Create a work-program for each institution respectively |  |  |  |
| 6. Implementation of the work-program in each entity as appropriate | 6a. Design the monitoring instruments on work-program for relevant institutions | MEETIES (Trade Department) | September 2021 | Financed to be provided by the EU twinning project |
| 7. Define the software on PSC, software specialist support (tools available at EU level (open source)) | 7a. Shortlist the relevant suitable software for PSC | MEETIES (Trade Department) | January 2022 | Financed to be provided by the EU twinning project |
| 8. Establishing the Point of Single Contact | Launching the work programme for the implementation of the Point of Single Contact | MEETIES (Trade Department) | June 2022 | Budgetary implications will be provided by the assessment undertaking under the EU twinning project |

| Task Name | Start (dd/mm/yyyy) | End (dd/mm/yyyy) | Approximate Duration (days) |
| --- | --- | --- | --- |
| 1. Establish service contact point | 13/01/2020 | 12/03/2020 | 69 |
| 2. Define basic architecture of PSC | 13/01/2020 | 12/03/2020 | 69 |
| 3. Identify all the entities that are going to participate on PSC, central and local level | 15/04/2020 | 27/11/2020 | 170 |
| 4. IT capabilities and gap analysis for each entity involved in PSC | 01/12/2020 | 11/01/2021 | 30 |
| 5. Define what to be done on each entity in order to be ready to be member of PSC | 11/02/2021 | 01/07/2021 | 120 |
| 6. Implementation of the work-program in each entity as appropriate | 02/08/2021 | 01/09/2021 | 45 |
| 7. Define the software on PSC, software specialist support (tools available at EU level (open source)) | 01/10/2021 | 17/01/2022 | 79 |
| 8. Establishment of PSC system. Train public officials how to use the system in each ministry and entity | 01/02/2022 | 01/06/2022 | 74 |