|  | Description | Indicators (with relevant baseline and target data) | Sources of verification | Risks | Assumptions (external to project) |
| --- | --- | --- | --- | --- | --- |
| Overall Objective | Progress in negotiations on chapter 1 – Free Movement of Goods To assist Montenegro in the process of accession to EU by contributing to legislation alignment and enforcement in the field of free movement of goods, with special focus on finalizing transposition of EU acquis and supporting the application of EU and international good practices in the field of pharmaceutics and medical devices | / | EC Progress Reports | / | / |
| Specific (Project) Objective(s) | To enhance and consolidate the institutional and operational capacities of the Agency for Medicines and Medical Devices of Montenegro to perform its statutory duties and contribute to health care system improvement and patients’ protection, by ensuring compliance with EU standards, guidelines and good practices relevant to Chapter 1 of EU acquis – ‘Free Movement of Goods’ concerning registration, marketing and consumption of medicines and medical devices | Increased number of Montenegrin legislation aligned with the Union acquis in the field of Medicines and Medical Devices Strengthened capacity of Agency of Medicines and Medical Devices | Reports on Parliament Activity. Official Gazette of Montenegro EC Progress Report CALIMS Yearly Activity reports Twinning Project periodic Reports | Lack of political support for adoption and enforcement of legislation Legislation is not swiftly approved by relevant Ministries/Government due to heavy workload on legislation harmonization within accession process Stakeholders not willing to implement newly introduced legislation Conditions for employees in public sector are worsened and Agency is not able to maintain its stuff due to better conditions offered by the pharmaceutical industry | EU integration process remains a priority issue in Montenegro’s Agenda. The new Law of Medicines of Republic of Montenegro is timely approved. Full commitment and motivation of the parties involved and good cooperation among twinned institutions and project teams in project implementation. CALIMS staff turnover remains within levels that do not threaten the delivery and the sustainability of capacity building efforts |
| Result 1- Component 1 – CALIMS Institutional Capacity and Visibility strengthened |  |  |  |  |  |
| Mandatory results/outputs by Component 1 | Sub-result 1.1: Enhanced background knowledge on good practices in the implementation of EU acquis and international guidance in the field of medicines and medical devices leads to improved strategic planning capacity at institutional level, based on tailored support and exchanges of experience delivered by twinning partners to CALIMS staff | Number of Training Needs Assessment (TNA) Baseline: 0 Target value: 1 Number of training programmes based on TNA Baseline: 0 Target value: 1 Number of strategic documents developed Baseline: 0 Target value: 1 Number of Action plans developed Baseline: 0 Target value: 1 | Twinning Project periodic Reports Mission Reports by Twinning Experts and their Annexes Minutes of CALIMS Steering Board Meetings | Conditions for employees in public sector are worsened and Agency is not able to maintain its stuff due to better conditions offered by the pharmaceutical industry. Strategic documents not approved Agency Steering Board Lack of political support for adoption and enforcement of legislation Legislation is not swiftly approved by relevant Ministries/Government due to heavy workload on legislation harmonization within accession process Stakeholders not willing to implement newly introduced legislation | The new Law of Medicines of Republic of Montenegro is timely approved. Full commitment of the parties involved and good cooperation among twinned institutions and project teams in project implementation. Human resources mobilized by Twinned MS Institution hold competencies and expertise that are relevant to the nature of the mission. Twinned MS institutions ensure continuity of assistance - i.e. no excessive turnover of Twinning Experts, when not required by project needs and activities. Heavy daily workloads do not limit the availability of CALIMS employees to participate in training and other capacity building activities. Absorption of capacity building inputs by CALIMS staff is not affected by high staff turnover and/or lack of interest in Twinning activities. |
|  | Sub-result 1.2: Secondary legislation in the field of Medicines as well as in the field of Medical Devices (MD) aligned with the Union acquis following the approval of the relevant Laws. | Number of Assessment reports (analysing harmonization of in-force secondary legislation) developed Baseline: 0 Target value: 1 Number of Rulebooks/Guidelines on GVP, GMP, GDP, GCP, marketing authorisation, advertising, manufacture, wholesale, prepared/revised Baseline: 0 Target value: 10 Number of Rulebooks/Guidelines on MD Surveillance developed Baseline: 0 Target value: 10 Number of existing Guidelines on MD reviewed and harmonized with the new legal framework Baseline: 0 Target value: 5 | Twinning Project periodic Reports Mission Reports by Twinning Experts and their Annexes CALIMS Website |  |  |
|  | Sub-result 1.3 CALIMS capacity to effectively communicate with stakeholders and to promote institutional visibility increased | Number of Communication Action Plans developed Baseline: 0 Target value: 1 Number of training seminars or workshops delivered to at least 8 CALIMS employees Baseline: 0 Target value: 2 Number of leaflets or promoting material designed for promoting CALIMS contribution to public health designed (in electronic format) Baseline: 0 Target value: 3 | Twinning Project periodic Reports Mission Reports by Twinning Experts and their Annexes Training/Workshop Agendas and Support materials Training/Workshop Attendance Lists Training/Workshop Reports Communication Materials prepared and disseminated Minutes of CALIMS Steering Board Meetings CALIMS Website |  |  |
| Result 2 - Component 2 – Post-Marketing Pharmacovigilance System and Medical Devices Surveillance System in Montenegro enhanced |  |  |  |  |  |
| Mandatory results/outputs by Component 2 | Sub-result 2.1: Enhanced administrative capacity of CALIMS staff to fulfil its legal tasks and responsibilities in relation to PV and MD surveillance in the post-marketing phase, by managing and maintaining a comprehensive and effective supervision system of safety of authorized medicines and medical devices that encourages ADR and medical devices AR reporting and allows prompt detection of any change to their risk-benefit balance | Number of training seminars/workshops in the area of ADR reporting, assessment, decision making, signal detection, crisis management, promotion of “reporting culture” delivered to at least 30 CALIMS employees and healthcare professionals Baseline: 0 Target value: 2 Number of training seminars/workshops on MD Surveillance Systems, reporting and assessment of AR, decision making, promotion of “reporting culture” Baseline: 0 Target value: 1 Number of training seminars/workshops on EU MD legislation and good practices in its application delivered to at least 3 CALIMS employees Baseline: 0 Target value: 2 Number of training seminars/workshops on informing and communication to the stakeholders of PV and MD Surveillance (Health Care Professionals, patients, pharmaceutical industry and the academia), delivered to at least 5 CALIMS employees Baseline: 0 Target value: 2 Number of knowledge-exchange workshops on Member State practices regarding the use of IT tools in PV and MD Surveillance Baseline: 0 Target value: 1 Number of knowledge-exchange workshops on Member State practices regarding quality assurance system in PV (SOPs) Baseline: 0 Target value: 1 Number of awareness raising meetings for media representatives, communication professionals and all other stakeholders Baseline: 0 Target value: 1 Number of ‘pilot’ communication tools developed (in electronic format) to raise healthcare professionals’ awareness on the importance of AR reporting Baseline: 0 Target value: 1 | Twinning Project periodic Reports Mission Reports by Twinning Experts and their Annexes Training/Workshop Agendas and Support materials Training/Workshop Attendance Lists Training/Workshop Reports CALIMS Website | Conditions for employees in public sector are worsened and Agency is not able to maintain its stuff due to better conditions offered by the pharmaceutical industry Target audience is not motivated to participate in the awareness events | The new Law of Medicines of Republic of Montenegro is timely approved. Full commitment of the parties involved and good cooperation among twinned institutions and project teams in project implementation. Human resources mobilized by Twinned MS Institution hold competencies and expertise that are relevant to the nature of the mission. Twinned MS institutions ensures continuity of assistance - i.e. no excessive turnover of Twinning Experts, when not required by project needs and activities. Heavy daily workloads and low number of employees in PV Dept. do not limit the availability to participate in training and other capacity building activities. Absorption of capacity building inputs by CALIMS staff is not affected by high staff turnover and/or lack of interest in Twinning activities |
| . |  |  |  |  |  |
|  | Sub-result 2.2: Administrative capacity of CALIMS staff to perform PV inspections enhanced | Number of operational procedures on planning of PV inspections, including a tailored risk-assessment methodology Baseline: 0 Target value: 1 Number of operational manuals for executing PV Inspections, including a full set of relevant checklists and reporting templates, Baseline: 0 Target value: 1 Number of CALIMS employees trained through seminars / workshops on: PV inspection planning, preparing and conducting Baseline: 0 Target value: 2 Number of simulation of desk and on-the-spot checks and train on-the-job inspectors on checklist use Baseline: 0 Target value: 1 | Twinning Project periodic Reports Mission Reports by Twinning Experts and their Annexes Training/Workshop Agendas and Support materials Training/Workshop Attendance Lists Training/Workshop Reports Minutes of CALIMS Steering Board Meetings |  |  |
| Result 3 - Component 3 –Authorization and Inspection Systems for Medicines and Clinical Trials in Montenegro improved |  |  |  |  |  |
| Mandatory results/outputs by Component 3 | Sub-result 3.1: Strengthened capacity of CALIMS staff to professionally and effectively assess Marketing Applications for Human and Veterinary Medicines, in compliance with EMA Marketing Authorization Guidance Documents. | Number of CALIMS employees trained on assessing of validity of marketing authorisation application, variations/renewals for human and veterinary medicines Baseline: 0 Target value: 10 Number of CALIMS employees trained on assessing of documentation on quality, safety and efficacy of human and veterinary medicines and application of EMA and ICH scientific guidelines in the area Baseline: 0 Target value: 10 Number of CALIMS employees trained through training seminars/study visits on classification and assessment of ‘border-line’ products Baseline: 0 Target value: 2 Number of CALIMS employees trained through training seminars/study visits on assessment of herbal and homeopathic medicines Baseline: 0 Target value: 2 Number of training seminars/workshops on the assessment of bioequivalence studies Baseline: 0 Target value: 1 Number of training seminars/workshops on the Decentralized Procedure and Mutual Recognition MA Procedure in EU Baseline: 0 Target value: 1 | Twinning Project periodic Reports Mission Reports by Twinning Experts and their Annexes Training/Workshop Agendas and Support materials Training/Workshop Attendance Lists Training/Workshop Reports Internship Agendas and Support materials Internship Attendance Lists Internship Reports | Conditions for employees in public sector are worsened and Agency is not able to maintain its stuff due to better conditions offered by the pharmaceutical industry | The new Law of Medicines of Republic of Montenegro is timely approved. Full commitment of the parties involved and good cooperation among twinned institutions and project teams in project implementation. Human resources mobilized by Twinned MS Institution hold competencies and expertise that are relevant to the nature of the mission. Twinned MS institutions ensures continuity of assistance - i.e. no excessive turnover of Twinning Experts, when not required by project needs and activities. Heavy daily workloads do not limit the availability of CALIMS employees to participate in training and other capacity building activities. Absorption of capacity building inputs by CALIMS staff is not affected by high staff turnover and/or lack of interest in Twinning activities. |
|  | Sub-result 3.2: Enhanced CALIMS capacity to perform inspections of medicines manufacturers and wholesalers, in full compliance with EU GMP and GDP guidelines | Number of basic trainings on EU GMP inspection procedures and good practices in their application Baseline: 0 Target value: 1 Number of basic trainings on EU GDP inspection procedures and good practices in their application Baseline: 0 Target value: 1 Number of GMP on-the-spot inspections to a Montenegrin manufacturer or a manufacturer in EU twinning partner Baseline: 0 Target value: 1 Number of GDP on-the-spot inspections to a Montenegrin wholesaler or a wholesaler in EU twinning partner Baseline: 0 Target value: 1 Number of follow-up workshops to discuss procedures improvement and weak points detected during GMP/GDP inspections Baseline: 0 Target value: 2 GMP/GDP inspection checklists analysed and reviewed Baseline: 0 Target value: 2 | Twinning Project periodic Reports Mission Reports by Twinning Experts and their Annexes Training/Workshop Agendas and Support materials Training/Workshop Attendance Lists Training/Workshop Reports Reports from simulation visits. |  |  |
|  | Sub-result 3.3: Enhanced administrative capacity of CALIMS staff to perform risk-benefit assessment process for clinical trial approvals with professionalism and impartiality, and ensuring full compliance with in-force legislation and internationally recognized Good Clinical Practice Guidelines (GCP). | Number of training seminars/workshops on EU regulatory and procedural guidance, international GCP and their application delivered to at least 2 CALIMS employees Baseline: 0 Target value: 2 Number of CALIMS employees trained through training seminars/workshops on assessment of CT application, particularly Informed Consent Form, Brochure for the Investigator and Protocol Baseline: 0 Target value: 2 | Twinning Project periodic Reports Mission Reports by Twinning Experts and their Annexes Training/Workshop Agendas and Support materials Training/Workshop Attendance Lists Training/Workshop Reports |  |  |
|  | Sub-result 3.4: Enhanced administrative capacity of CALIMS staff to adequately monitor ongoing clinical trials in compliance with Good Clinical Practice Guidelines (GCP). | Number of operational procedures on planning of CT inspections, including a tailored risk-assessment methodology Baseline: 0 Target value: 1 Number of operational manuals for executing CT Inspections, including a full set of relevant checklists for inspections and reporting templates Baseline: 0 Target value: 1 Number of CALIMS employees trained through training seminars/workshops in the area of CT ADR reporting, assessment and decision making Baseline: 0 Target value: 2 Number of basic trainings on CT inspections performing delivered to at least 2 CALIMS employees Baseline: 0 Target value: 1 Number of advanced training seminars on CT risk-based inspections planning, preparation, execution, irregularities, reporting and follow up Baseline: 0 Target value: 2 Number of GCP on-the-spot inspections to a clinical trial in Montenegro or participation in clinical trial control in EU twinning partner Baseline: 0 Target value: 1 | Twinning Project periodic Reports Mission Reports by Twinning Experts and their Annexes Training/Workshop Agendas and Support materials Training/Workshop Attendance Lists Training/Workshop Reports |  |  |
| Sub-results per component (optional and indicative) | / | / | / | / | / |