## EU Twinning Project
Ref. | Results | Sub. Ref. | Results | Leading Agency | Task | Indicator | Baseline | Year 1 | Year 2
Objective of EU Twinning Project: Strengthened capacity of the Ministry of Education to deliver the priority reforms for Early Childhood Education and Community Support for learning.
| Overall Objective | Enhance learning outcomes at the foundational level through improved access to quality early childhood education services and enhanced parental and community support for early learning.
| Specific Objective | Strengtheneg capacity of the Ministry of Education to deliver priority reforms and achieve the national targets for Early Childhood Education and Community Support for learning
| Component.1: Increased access to formal ECE services and community-based ECD programs | 1.1 | An expansion plan for pre-primary/Early Childhood Education is developed and is guiding the work of the Ministry of Education and Development Partners | MINEDUC | Evidence-based research on best investments in early childhood education, to help achieve national targets. Development, approval and dissemination of expansion plan for pre-primary education, together with relevant stakeholders, including development partners, and based on new ESSP targets. | 1. ECE expansion plan in place, guiding the work of the Ministry and all development partners 2. Monitoring and reporting system in place to track progress in implementing the expansion plan. | ECE Expansion Plan under development, based on the new ESSP Targets | ECE Expansion Plan developed and disseminated | Report developed and disseminated documenting progress in implementing the plan
|  | 1.2 | Capacity of the MINEDUC Pre-Primary and Primary Analyst and selected NCDA and REB staff enhanced to support the development, coordinated delivery, monitoring and reporting of ECE expansion plan | MINEDUC | Training plan developed and delivered to support the development, coordination, monitoring and reporting of the ECE expansion plan. | Number of MINEDUC and sector staff with enhanced capacity on planning for, implementing, monitoring and reporting on the expansion of ECE services | MINEDUC Pre-Primary and Primary Analyst to be recruited, based on new MINEDUC Structure. REB has focal points for ECE and NCDA has several relevant staff. | Capacity Needs Assessment completed and capacity development plan designed | Capacity development plan implemented and monitored
|  | 1.3 | All development partners contributions are effectively aligned and coordinated towards achieving the sector targets for increasing access to Early Childhood Education services. | MINEDUC-NCDA | Assessment of coordination framework for development partners and other donors and development of tools to map DP programme support; Development of new partnerships to support the implementation of pre-primary expansion plan. | 1. Number of new partnerships developed to support increased access to ECE. 2. Effective mapping tools for DP programme and budget support | ECD Working Group is functioning well as an information sharing forum and to guide ECD stakeholders and partners | DP Partner mapping exercise completed, with key areas of gaps identified | At least two new partnerships leveraged to support achievement of results
|  | 1.4 | Mechanism developed to increase coordination between MINEDUC and NCDA on ECE and ECD to expand coverage and access to ECE services | MINEDUC/REB, NCDA | Formalized coordination forum between the leadership of NCDA and MINEDUC on ECD/ECE is established, operationalised and strengthened to expand coverage of ECD services | 1. # of children attending at least one year of pre-primary | Coordination mechanism between NCDA and MINEDUC not formalised | Formalised coordination forum between NCDA and MINEDUC on ECD/ECE is established and operationalised | Monitoring progress towards a phased scale up.
|  | 1.5 | Enhanced coordination between MINEDUC and NCDA to invest in ECD caregiver training | MINEDUC, MIGEPROF, MINALOC | Provide oversight and support to existing programmes (and contribute to the development of new programmes) supporting capacity building support of ECD caregivers. | 1. # of ECD caregivers trained 2. # of caregivers transitioned to pre-primary teaching roles | Development of a training and transition plan. | Monitoring progress. | Monitoring progress.
| Component 2: Improve instructional quality at pre-primary education through teacher development and provision of effective teaching and learning materials for pre-primary education | 2.1 | Training programmes for pre-primary teachers have a focus on play based foundational learning as well as the effective use and management of play based learning materials | REB-TDM | Provide technical guidance to the design of Training programmes and training materials for pre-primary teachers, together with REB and other key stakeholders, with a focus on play based learning as well as to effectively use and manage play based learning materials. Development of budget estimate, implementation plans and strategy for scale up of training. | 1. A multi-year implementation and monitoring plan is developed. 2. Number of teachers trained 3. Monitoring reports of training quality | In-service training of ECE teachers is uneven and under-resourced. | Medium-term training plan developed, with costing and implementation arrangements | Report on ECE teacher training developed, with recommendations on strategies to scale up.
|  | 2.2 | Review of the Early Childhood and Lower Primary Education (ECLPE) option in TTCs completed, identifying strategies and actions to strengthen its focus on school readiness and play based learning | REB-CTLR | Review and assessment of the current curriculum for Early Childhood and Lower Primary Education (ECLPE) option in TTCs completed, identifying strategies and actions to strengthen its focus on school readiness. Make recommendations on potential revisions to the ECLPE curriculum, based on the assessment. | 1. Review conducted 2. Strategies to strengthen ECLPE school readiness being implemented | Development of curriculum review framework. | School Readiness focus incuded in the review of the ECLPE | Monitoring on impact of review on school readiness approach.
|  | 2.3 | Plan to increase regularity of investment in curricular play-based learning for TTCs and demonstration schools developed, especially the ECLPE option | REB-CTLR | Develop a five-year resourcing plan for TTCs Develop a framework for monitoring availability and provision of play based resources to TTCs. | 1. Annual budget made available 2. Resources provided to TTCS 3. Monitoring reports of usage | Resource provision does not occur on a regular cycle and is difficult for TTCs to predict. | Develop 5 year resourcing plan.. | Monitor receipt and use of resources
|  | 2.4 | Set of cost-effective play-based materials for pre-primary classrooms, including digital materials, identified. | REB-CTLR | Together with REB, identify a set of cost-effective play-based materials for pre-primary classrooms | 1.establishment of a set of cost-effective play-based materials for pre-primary classrooms. | Play based materials are scarcely found in classrooms. | Identify core play based materials package and cost per pupil and classroom. | Monitor and adjust where necessary.
|  | 2.5 | Development partner and other stakeholder support to play based teaching and learning materials provision and replacement maximised, through a mapping exercise and engagement in the ECD Technical Working Group | REB-CTLR | Provide analysis on overall requirements and funding mechanisms to provide appropriate levels of play based materials to all primary schools, including funding gaps. Develop a mapping of Development Partner support to provision of play based teaching and learning materials against the overall requirements and funding gaps Engage with Development Partners to support coordinated alignment and support to the procurement of play based materials, based on supply and funding gaps. | 1. # of partners providing financial support to play based learning materials provision 2. # of materials distributed to schools with partner support | Foundational Learning Strategy has identfied capitation grant as one source of funding. Ad hoc support for development partners. | Identify costing and implementation strategies to provide play based materials Develop a shared costing plan for play based learning material provision. | Procure, distribute and monitor.
|  | 2.6 | Capacity of local publishing and creative industry to produce quality play-based learning resources enhanced, including response to market need | REB-CTLR | Assess the current market and capacity of local publishers and creative industries to develop play based materials, as well as market and other barriers they encounter. Identify support required to local publishers to stimulate the local sector to develop quality cost-effective play based materials | 1. # of materials procured by local TLM suppliers | Local publishers are not consistently involved in the development or provision of the current TLM package. | Identify support required to stimulate the local sector to develop quality, cost-effective play based materials. | Provide support, monitor and adjust.
| Component 3: Strengthen systematic quality assurance and performance management of pre-primary education. (Year 2). | 3.1 | Development/update and use of the inspection framework for pre-primary education to include key metrics on monitoring play-based pre-primary teaching practices | NESA | Together with NESA, and coordinating with an EU direct grant to this agency, contribute to the update of the inspection framework to include key metrics on monitoring school and classroom support for play-based pre-primary teaching practices. Together with NESA, and coordinating with an EU direct grant to this agency, develop classroom observation tools to help monitor play based teaching and learning. Together with NESA, and coordinating with an EU direct grant to this agency, develop performance management and observation tools with metrics on usage of play based materials. | 1. Inspection framework updated to include key metrics on monitoring school & classroom support for foundational skills, play-based pre-primary teaching practices 2. Classroom observation tools developed for pre-primary 3. # of performance management and observation tools with metrics on usage of play based materials | Inspection framework was finalized in 2022 but does not include metrics specific to play based learning. Classroom observation tools are generic and not effective for monitoring pre primary play bassed learning. |  | Revisions/ annexes included in inspection framework. Development & piloting of a classroom observation tool. Review teacher, school leader & inspectorate tools to include a TLM (including play based materials) use metric
|  | 3.2 | Capacity of district inspectors and sector education officers to effectively inspect key elements of play based pre primary education enhanced | NESA | Together with NESA, and coordinating with an EU direct grant to this agency, develop a set of school inspection protocols and related data collection templates and training plan local Education Officer’s on using these resources for system monitoring. | 1. # of trainings conducted to NESA staff | District inspectors are placed but haven't received specialized training on play based pre primary education |  | Development of training tools and plan. Phased training roll out and monitoring.
| Component 4: A culture of parental support for learning developed, including increased time children spend reading and learning out of schooll | 4.1 | Engagement plan developed and implemented for MINEDUC and REB to lead initiatives on parental engagement for learning | MINEDUC, REB | Train identified MINEDUC and REB staff in parental support engagement Identify strategies at the school level for the School General Assembly Executive Committees (SGAECs) to strengthen structured parent engagement mechanisms to support parent contribution to home learning. | 1. Existence of a dedicated trained staff for parental support 2. # of parental engagement campaigns conducted 1. # of schools initiating structure to engage the parents in supporting children's learning | MINEDUC/REB don't have a dedicated department or focal point to coordinate and strengthen parental support for learning efforts. | Identification of position/unit in REB organogram. | Position/unit trained Work plans developed and monitored.
|  | 4.2 | Behavior change communication initiatives to sensitize parents on supporting foundational learning coordinated across different agencies | REB/NCDA | Together with the NCDA project manager, under the EU direct grant, support the development of a new evidence-informed behavior change communication campaign (activity coordinated under EU grant to NCDA). Review of communication products available and propose additions or revisions to NCDA and other partners. | 1. Availability of a Social Behaviour Change Communication strategy 2. Number of communications initiatives including the elements of play based learning and school readiness | Parental support for learning is low. Targeted efforts by schools to engage parents is inconsistent. A SBCC strategy has been initiated. | Finalization of strategy. Development of a M&E plan. | Phased roll out. Adjust, implement and monitor.
|  | 4.3 | Resourced plan developed to strengthen the Kigali Public Library's mandate to oversee the expansion of community reading structures, including libraries, reading clubs and literacy outreach activities | MINEDUC | Support the development of a costed plan to strengthen community reading structures, including identification of potential funding sources. | 1. Budget availability for KPL to support community libraries 2. # of trainings conducted by KPL to support community libraries 3. # of books distributed by KPL to support community libraries | There are only around 60 active community libraries across the country. KPL has the mandate to oversee community libraries, but does not receive dedicated financing to enable expansion of libraries. |  | Resourced expansion plan is developed with relevant stakeholders. Reporting mechanisms established.
|  | 4.4 | Plans operationalised to provide material support to schools to implement the school library guidelines and greater opportunities for students to access books in and out of school | MINEDUC, REB | Coaching plan for schools to operationalize libraries is developed in partnership with REB | 1.Coaching/ training support to schools 2. Inspection reports on library setup, stock and use | Guidelines are approved and available, but not widely accessed or implemented by schools. | Coaching plan for schools to operationalize libraries is developed | Phased roll out. Adjust, implement and monitor.
|  | 4.5 | Strategy developed to effectively disseminate and use engaging educational entertainment content to supplement foundational learning | MINEDUC, REB | Strategy for dissemination of edutainment materials to schools, libraries and ECD Centres, developed. Report on availability and use of edutainment materials developed. | 1. # and types of materials developed 2. # of platforms, including low-tech options, disseminate content 3. Monitoring report on impact | Online edutainment materials have been developed but internet & device accessibility limits usage. | Existing materials reviewed and dissemination strategy developed. | Targeted development of new materials. Dissemination & monitoring.