Phase II du Programme d’appui à la réforme de la justice

« NDICI-GEO-NEAR/2022/ACT 61201 »

Jumelage standard

Renforcement des capacités du Supérieur du Pouvoir Judiciaire à contribuer à l’amélioration de l’efficacité du système judiciaire

Calendrier de lancement et de mise en œuvre (INDICATIF)

| Action délai | Mois | Date |
| --- | --- | --- |
| Finalisation fiche : | 0 | 20/12/2024 |
| Lancement de l’appel à propositions: | M+1 | Mercredi 02 avril2025 |
| minimum 8 semaines |  |  |
| Information day + vc |  | Semaine du 28 avril |
| Q&A à publier le cas échéant |  | Avant le 16 mai |
| Réception des propositions : | M+3 | Vendredi 30 mai 2025 |
| Réunions de sélection : |  | Lundi 16 juin 2025 |
| idéalement 2 semaines exceptionnellement jusque 4 semaines |  |  |
| Notification des Etats membres : | m+4 | Lundi 30 juin 2025 |
| 1 semaine maxi |  |  |
| Confirmation Etat membre sélectionné : |  | Lundi 07 juillet 2025 |
| maximum 3 mois après notification |  |  |
| Signature du contrat de jumelage: | m+7 | Lundi 22 septembre 2025 |
| maximum 3 mois après notification |  |  |
| Démarrage des activités du projet de jumelage: Au plus tard |  | Lundi 03 novembre 2025 |
| 24 mois |  |  |
| Date de fin du projet: |  | Mercredi 03 novembre 2027 |

As per standard grants rules, during the time between the publication and the deadline, Member States should be able to ask questions. The answers provided on points that may be of interest to other Member States should be shared with all of them (see PRAG 6.5.4).