Simplified Logical Framework

|  | Description | Indicators (with relevant baseline and target data) | Sources of verification | Risks | Assumptions (factors external to the project) |
| --- | --- | --- | --- | --- | --- |
| General objective | Contribute to the preservation of human and animal health in line with the One Health approach and to the improvement of food safety in Côte d’Ivoire | (a) Reduction of food-borne diseases Baseline (2023): 12 % of the reported diseases are related to the consumption of contaminated food. Target (2028): 8 % of the reported diseases are related to the consumption of contaminated food. (b) Improving the monitoring of zoonoses Baseline (2023): 40 % of regions report on zoonoses. Target (2028): 80 % of regions report on zoonoses. (C) TIAC management capacity Baseline (2023): NA not available Target (2028): 100 % of adequate responses (in line with plans and across sectors) to reported TIACs. | (a) Reduction of food-borne diseases Sources: Annual reports of the health districts. Database of the Food Disease Surveillance System (WHO, Ministries). Specific studies on Collective Food toxins (TIAC). (b) Strengthening systems for monitoring zoonoses Sources: National reports on zoonoses monitoring (Ministry of Health and MIRAH). Project documents funded by technical and financial partners (WHO, FAO, OMSA). (C) TIAC management capacity Sources: Assessments of emergency plans and simulations carried out in the health districts. Training reports for TIAC managers. |  |  |
| Specific objective (of the project) | Food safety and veterinary hygiene systems are being improved | 1. Institutional and infrastructural capacity building •Indicator 1.1: Number of functional analytical laboratories compliant with international standards. Baseline: 7 functional laboratories in 2023 with ongoing compliance. Target: Increase the number of functional laboratories by 25 % by 2028. •Indicator 1.2: Proportion of officials of competent authorities trained in international health control standards. Baseline: 75 % of staff trained in 2023. Target: 90 % of staff trained by 2028. 2. Improved monitoring of health risks •Indicator 2.1: A functional notification system throughout the territory. • Baseline: 10 alerts from 8 out of 33 regions notified in 2023 (under notification) •Target: alert reports or confirming the absence of an alert from the 33 regions. •Indicator 2.2: Data from food businesses are available to the competent authorities. • Baseline: Not available. •Target: 100 % by 2028. 3. Reduction of food-borne diseases •Indicator 3.1: Incidence rate of ACTIs (Collective Food toxi-infections) per 100 000 inhabitants. • Baseline: NA not available •Target: 30 % reduction by 2028. •Indicator 3.2: Percentage of food samples not complying with microbiological standards. • Baseline: Not available. •Target: Reduction to less than 10 % by 2028. 4. Compliance of agri-food establishments •Indicator 4.1: Proportion of agri-food establishments complying with national and international health standards. • Baseline: 40 % of compliant establishments in 2023. •Target: 65 % by 2028. •Indicator 4.2: Proportion of food business operators who are aware of health and phyto health risks and monitoring arrangements • Baseline: Not available. •Target: 75 % by 2028. | Cross-cutting sources 1.national public institutions: • Technical Ministries (Health, Agriculture, Animal and Human Resources, Trade, etc.). • One-health platform. • Government platform (egouv.ci). 2.regional/international institutions: • UEMOA, ECOWAS, African Union, EU, FAO, WHO, OMSA. 3. public databases and sectoral studies: • Data from national censuses or specific surveys (agri-food, epidemiological). 4. stakeholder consultations: •• Meetings of technical committees, technical working group. •• Consultation workshops with actors in the food chain. | 1. Institutional and organisational risks •Lack of cross-sectoral coordination: Difficulty of collaboration between different stakeholders (ministries, technical services, private actors). •Low technical capacity: Insufficient number of staff trained to deal with complex issues. 2. Financial and budgetary risks •Insufficient financial resources: Limited budget for the purchase of equipment, training and infrastructure. 3. Technical risks •Inadequate infrastructure: Non-compliant laboratories, lack of modern equipment or frequent breakdowns. •Low technology uptake: Resistance to change or lack of digital literacy by actors. 4. Stakeholder risks •Non-compliance of economic operators: Resistance of food businesses to comply with health standards. •Lack of stakeholder engagement: Low involvement of local stakeholders (communities, consumers, producers). 5. Environmental and contextual risks •Health crises or pandemics: Emergence of new zoonotic or food diseases. •Climate change: Impact on food chains and health security (increase in pathogens, deterioration of conservation conditions). 6. Legal and regulatory risks •Regulatory inconsistencies: National standards not harmonised with international standards (Codex Alimentarius, OMSA). •Weak or uneven application of laws: Non-compliance by some actors due to impunity. 7. Socio-cultural risks •Lack of consumer awareness: Low awareness of food risks among the population. •Traditional or informal practices: Preference for informal channels or use of non-compliant artisanal production methods. | 1. Political and institutional assumptions •Political stability and government engagement: The project is based on continued political will and a stable environment to support the necessary reforms and investments. • Risk if not met: Instability slowing down decision-making processes or changing national priorities. •Cross-sectoral institutional support: Effective cooperation between ministries (Agriculture, Health, Trade, Environment, Animal Resources and Halieutics) and public agencies is ensured. • Risk if not met: Lack of coordination between actors, leading to overlaps or gaps in actions. 2. Financial and economic assumptions •Availability of funding: The necessary financial resources (national budgets and partners’ contributions) will be mobilised and allocated in time. • Risk if not met: Delay or cessation of activities due to lack of funds. •Economic stability: National economic stability allowing private actors to engage in compliance with health standards (e.g. through infrastructure investments). • Risk if not met: Contraction of economic activities and resilience of operators to adopt reforms. 3. Technical assumptions •Technical absorption capacity: Actors (controllers, economic operators, laboratories) can quickly integrate new technologies and approaches. • Risk if not met: Low uptake of innovations or slow implementation. •Access to modern infrastructure and equipment: The necessary infrastructure (laboratories, control equipment) and maintenance services will be available. • Risk if not met: Poor analytical performance and inability to identify risks. 4. Social and cultural assumptions •Acceptance by local stakeholders: People, producers and processors are ready to adopt modern health safety standards and practices. • Risk if not met: Cultural resistance or dependence on informal channels. •Active involvement of consumers: Consumers are showing growing demand for safe and standard-compliant products. • Risk if not met: Low market pressure to stimulate improvements in production standards. 5. Environmental assumptions •Favourable environmental conditions: The climatic conditions and natural resources needed for agriculture and livestock production remain stable. • Risk if not met: Climate change leading to new challenges (e.g.: increased pathogens, food insecurity). •Absence of major natural disasters: The project is not interrupted by natural events (droughts, floods) that could disrupt food systems. • Risk if not met: Significant delays in implementation. 6. Legal and regulatory assumptions •Legislative compliance with international standards: National laws and regulations will be harmonised with international frameworks (Codex Alimentarius, OMSA). • Risk if not met: Disconnection between international requirements and local practices, making it difficult to export. •Political will to enforce sanctions: Existing laws will be applied fairly and strictly. • Risk if not met: Perception of impunity among non-compliant operators. 7. Assumptions related to external partners •Continuous commitment of technical and financial partners: International partners (FAO, WHO, OIMSA, UEMOA, etc.) will continue their technical and financial support. • Risk if not met: Lack of funds or expertise for certain activities. •Availability of international expertise: The experts required for the transfer of know-how and technical assistance are available and accessible. • Risk if not met: Delays in the implementation of capacity building programmes. 8. Overall health assumptions •Absence of major health crises: There will be no pandemic or health emergency diverting the resources and priorities of the project. • Risk if not met: Reallocation of funds and human resources to other health priorities. |
| Mandatory results/outputs by components | R1: The update of the veterinary public health legislative and regulatory framework is effective | - Number of persons in the Directorate for Legal and Legal Affairs and the DSV who have received at least one capacity-building action (training, study visit, etc.) Nr (year): ND Target (end of project): tbd - Number of laws and regulations finalised and adopted (for decrees and decrees) or deposited in Parliament (for laws) Nr (year): ND Target (end of project): tbd | Activity reports | •Lack of cross-sectoral coordination •Low technical capacity • Lack of stakeholder engagement | •Cross-sectoral institutional support • Provision of human resources • Continuous stakeholder engagement |
|  | R2: The organisation of the competent authority and the internal functioning of the veterinary services are improved | - Number of staff of the Competent Authorities who have implemented the quality management system Nr (year): ND Target (end of project): tbd - Number of action plans developed and validated to improve the internal functioning of the services Nr (year): ND Target (end of project): tbd - Establishment of a coordination mechanism between SICOSAV and DSV Nr (year): ND Target (end of project): tbd - Number of operational veterinary public health information systems Nr (year): ND Target (end of project): tbd | Activity reports | •Lack of cross-sectoral coordination •Low technical capacity • Lack of stakeholder engagement |  |
|  | R3: Officials responsible for the official control and certification of animal and animal products have similar skills to their colleagues in European countries. | - Number of staff from competent authorities who have received minimum training Nr (year): ND Target (end of project): tbd - Number of procedures standardised and implemented by the Competent Authority Nr (year): ND Target (end of project): tbd - Number of control and supervision plans drawn up and monitored by the Competent Authority Nr (year): ND Target (end of project): tbd - Number of cases of animal diseases controlled Nr (year): ND Target (end of project): tbd | Activity reports | •Lack of cross-sectoral coordination •Low technical capacity • Lack of stakeholder engagement |  |
|  | R4: Stakeholders in the ESA sector are informed, made aware of and trained on good hygiene practices | - The communication strategy on animal health and welfare is revised Nr (year): ND Target (end of project): tbd - At least 3 awareness campaigns of operators, partners and stakeholders carried out Nr (year): ND Target (end of project): tbd - Number of persons from the Competent Authority who have completed the training Nr (year): ND Target (end of project): tbd | Activity reports | •Lack of cross-sectoral coordination •Low technical capacity • Lack of stakeholder engagement |  |
|  | R5: Operational capacities for health and regulatory monitoring are strengthened | - Number of epidemiological surveillance systems reinforced and monitored by the Competent Authority Nr (year): ND Target (end of project): tbd - Health and regulatory monitoring system put in place Nr (year): ND Target (end of project): tbd - Antimicrobial Resistance Monitoring Network set up Nr (year): ND Target (end of project): tbd | Activity reports | •Lack of cross-sectoral coordination •Low technical capacity • Lack of stakeholder engagement |  |
|  | R6: Operational capacities for biosecurity in livestock are strengthened | - Number of people trained in biosecurity Nr (year): ND Target (end of project): tbd - Number of specific biosecurity legislation adopted Nr (year): ND Target (end of project): tbd | Activity reports | •Lack of cross-sectoral coordination •Low technical capacity • Lack of stakeholder engagement |  |

GENERAL OBJECTIVE: indicate the global strategic objective which goes beyond the immediate scope of the project but to which the project can contribute. The overall objective should be linked to the general sector reform in the Beneficiary country, as agreed in the framework of the definition of cooperation with the EU.

These are the changes in the political, social, economic and environmental global context which will stem from interventions of all relevant actors and stakeholders in the project. These require the involvement of third parties that were not direct beneficiaries of the intervention. Hence, changes are indirectly influenced by EU Intervention.

Specific PROJECT OBJECTIVE (S): identify the specific objective (s) that shall be achieved through the implementation of the Twinning project. These are the effects on the political, social, economic and environmental areas targeted by EU intervention as well as changes in behaviour of Beneficiaries of EU intervention.

MANDATORY RESULTS/OUTPUTS: describe each of the results that shall be achieved by the project, as outlined in the Twinning Fiche. Each mandatory result/output should correspond to a “project component”. Please include one line per component.

INDICATORS: (with relevant baseline and target data): provide an indication of how the achievement of each component of the mandatory results (from sub results per component to outcomes (specific objectives) and to impact (overall objective) will be measured. Make sure that the indicators define the following, as appropriate: 1. Value of measurement (Quantity or Quality); 2. Baseline and target (values and times); 3. Actors in charge of data collection and reporting; 4. Target Group; 5. Deadline for reporting; 6. Location. Baseline and target data, as indicated in the Twinning Fiche, to be mentioned in brackets next to each indicator. Indicators may be revised if deemed appropriate when drafting the initial work plan.

SOURCES OF VERIFICATION: for every component, specify the sources of information from which evidence can be obtained that the targets have been achieved: e.g. independent reports, surveys, Official Journal, Commission reports, etc.

RISKS: mention external factors which can potentially hinder the successful implementation of the project, including any event beyond the control of the main actors involved.

ASSUMPTIONS: specify the external conditions and/or third parties initiatives which can influence the implementation of the project to the point that only their fulfilment can guarantee its success. These are the necessary and positive conditions that allow for a successful cause-and-effect relationship between different levels of results.